## Slide 1: Trivial Pursuits
G
What Chinese region is nicknamed The Roof of the World?
E
What names precede Yarrow, Stookey and Travers?
H
Who wrote the Star-Spangled Banner?
AL
Who compiled the first American dictionary?
SN
What’s the only place in Europe where monkeys live free?
SL
What do you get by mixing ginger ale, grenadine and a cherry?

## Slide 2: And the answers are …
G
What Chinese region is nicknamed The Roof of the World?
Tibet
E
What names precede Yarrow, Stookey and Travers?
Peter, Paul and Mary
H
Who wrote the Star-Spangled Banner?
Francis Scott Key
AL
Who compiled the first American dictionary?
Noah Webster
SN
What’s the only place in Europe where monkeys live free?
Gibraltar
SL
What do you get by mixing ginger ale, grenadine and a cherry?
A Shirley Temple

## Slide 3: Support & Enhancements
Chart: 
| YR:2011 | YE:2012 | YR:2013 | Today
 | 646 | 322 | 340 | 295

## Slide 4
September 18, 2014
2014 Year End Support Pack Project
IS&T
Kickoff

## Slide 5: Agenda
Background
Project Organization
Project wiki
Project Risks
Important Dates
Next Steps

## Slide 6: Background
Support Packs
  We all know what they are, periodic releases of system changes and corrections by SAP.
  Rather than apply these support packs when released we collect the Support Packs for a single installation at year end in an effort to minimize business interruption.
  The timing of our process is driven by SAP’s release of its year end support pack, typically in mid-October, which contains the base level necessary for the successful execution of SAP’s delivered year end tax reporting functionality (AP and Payroll) and stages the system for regulatory changes for the upcoming calendar year.

## Slide 7: Background
What are the benefits of applying Support Packs and the process itself?
  MIT will be able to successfully file its year end tax returns (W2s, 1099s, 1042s).
  MIT will be able to apply future regulatory changes with minimal interruption.
  It is an opportunity to keep all functional areas current.
  It adheres to SAP’s support recommendations.
  It provides a solid organizational exercise in testing.
  Ensures up to date test scripts for chosen transaction.

## Slide 8: Project Organization
Communication
Planning
Support Pack Technical Application
Testing
Go-live

## Slide 9: Project Organization
Communication
  Project Kickoff Meetings
    Steering Committee – 9/15/2014
    IS&T – Core Team & Extended Team – 09/18/2014
    SAPbiz – 09/22/2014
  Monthly Meetings
    Steering Committee
    SAPbiz
  Weekly Meetings
    Core Team
    Test Coordinators - Business & IS&T
  Email lists
  Project wiki
    https://wikis.mit.edu/confluence/display/sapscripts/2014+Year+End+SAP+Support+Pack+Project
    Contains project plans, test plans, general information, etc …; great source – use it!
    Don’t have access please contact Desiree Roberts (robertsd@mit.edu)

## Slide 10: Planning
Lets jump to the project wiki …
to look at the Team Roles & Responsibilities
to look at the Project Scope
to look at the Technical Landscape
to look at the Schedule
to look at the Project Transport Management Process
to look at the Project Testing Plan
    https://wikis.mit.edu/confluence/display/sapscripts/2014+Year+End+SAP+Support+Pack+Project

## Slide 11: Other Non-SP Projects
Other non-support pack project work (during SP project timeline)
  Atlas 4.0
    JV Suite
    Commuting Benefits
    Events Application Enhancements
    Atlas Maintenance
  Other activities
    …
    …

## Slide 12: Project Risks
Identified Risks
  Delay in SAP Releases
  QC Upgrade
    Application has been upgraded during the summer
    This will be the first time a lot of folks will have been in the upgraded system
  Two Phase Testing Approach
    Requires tight coordination and resource availability between the Business & IS&T
    But … we have four years experience with this approach
  Resource availability for the project (both Business & IS&T)
  Delay of implementation of pre-Support Pack Projects
    OE (scheduled for October)
  Impacts from other requested updates
    Atlas 4.0
    Potential others TBD …

## Slide 13: Important Dates
Now - October - Plan, convert/create/update test scripts in QC, move pending support & project work into production
10/9/2014 – SAP release of year end base level support pack
10/20/2014 - End of day production snapshot to be used to refresh test environments
10/20/2014 - Development Freeze begins
10/28/2014 - Last date to implement support & enhancement changes until freeze ends on 12/10/2014
10/24/2014 - 10/31/2014 Unit test
11/3/2014 - 11/26/2014 System Integration Test
12/5/2014 - 12/7/2014 Go-live weekend!
12/10/2014 - Development Freeze ends

## Slide 14: Next Steps
  Finish System changes currently in the pipeline
  Unit test Spreadsheet (google docs)
  Test Planning
  System preparation

## Slide 15
Where can I get Support Pack project information? Ah …

## Slide 16: Questions?
Any additional questions? Please contact:
Frank Quern Bart Dahlstrom
X2-4512 x3-9605
fquern@mit.edu bartd@mit.edu
OR
Your SAP testing team coordinator:
HR-Payroll: Mary Donovan
Financial-Logistics-EHS: Lee Collier