## Slide 1: Trivial Pursuits
G
What Chinese region is nicknamed The Roof of the World?
E
What names precede Yarrow, Stookey and Travers?
H
Who wrote the Star-Spangled Banner?
AL
Who compiled the first American dictionary?
SN
What’s the only place in Europe where monkeys live free?
SL
What do you get by mixing ginger ale, grenadine and a cherry?

## Slide 2: And the answers are …
G
What Chinese region is nicknamed The Roof of the World?
Tibet
E
What names precede Yarrow, Stookey and Travers?
Peter, Paul and Mary
H
Who wrote the Star-Spangled Banner?
Francis Scott Key
AL
Who compiled the first American dictionary?
Noah Webster
SN
What’s the only place in Europe where monkeys live free?
Gibraltar
SL
What do you get by mixing ginger ale, grenadine and a cherry?
A Shirley Temple

## Slide 3
September 22, 2014
2014 Year End Support Pack Project
SAPbiz
Kickoff

## Slide 4: Agenda
Background
Project Scope
Project Organization
High Level Time Line
Project Risks
Important Dates
Next Steps

## Slide 5: Background
What are Support Packs?
  On an on-going basis SAP releases system changes addressing defects and/or introducing new functionality across all functional areas through what they call OSS notes.
  Each month SAP compiles all these notes and releases them as a Support Pack.

## Slide 6: Background
Why does MIT then only apply Support Packs at this time?
  MIT does apply OSS notes to address specific functional defects or regulatory changes on an as needed basis throughout the year.
  MIT collects Support Packs for a single installation at year end in an effort to minimize business interruption.
  The timing is driven by SAP’s release of its year end support pack, typically in mid-October, which contains the base level necessary for the successful execution of SAP’s delivered year end tax reporting functionality (AP and Payroll) and stages the system for regulatory changes for the upcoming calendar year.

## Slide 7: Background
What are the benefits?
  Well there is the obvious, MIT will be able to successfully file its year end tax returns (W2s, 1099s, 1042s).
  MIT will be able to apply future regulatory changes with minimal interruption.
  It is an opportunity to keep all functional areas current.
  It adheres to SAP’s support recommendations.
  It provides a solid organizational exercise in testing.
  Ensures up to date test scripts for chosen transaction.

## Slide 8: Project Scope
What are we updating?
  SAP ERP: EHP7 for ERP 6.0 (w/SAP_HR 604 SP66 and EA-HR 607 SP17) to SAP ERP: EHP7 for ERP 6.0 (w/SAP_HR 604 SP79 and EA-HR 607 SP30)(the Support Packs)
  SAP Ancillary Systems
    ADS
    Portal
    GRC
  BSI
    System
    TUBs

## Slide 9: Project Organization
Communication
Planning
Support Pack Technical Application
Testing
Go-live

## Slide 10: Project Organization
Communication
  Project Kickoff Meetings
    Steering Committee – 9/15/2014
    IS&T – Core Team & Extended Team – 09/18/2014
    SAPbiz – 09/22/2014
  Monthly Meetings
    Steering Committee
    SAPbiz
  Weekly Meetings
    Core Team
    Test Coordinators - Business & IS&T
  Email lists
  Project wiki
    https://wikis.mit.edu/confluence/display/sapscripts/2014+Year+End+SAP+Support+Pack+Project
    Contains project plans, test plans, general information, etc …; great source – use it!
    Don’t have access please contact Desiree Roberts (robertsd@mit.edu)

## Slide 11: Project Organization
Roles & Responsibilities
Lets jump to the project wiki …
    https://wikis.mit.edu/confluence/display/sapscripts/2014+Year+End+SAP+Support+Pack+Project

## Slide 12: Project Organization
Support Pack Technical Application

## Slide 13: Project Organization
Testing

## Slide 14: Project Organization
Testing
  Two Phase Approach
    Unit Test - performed in SF2 by IS&T
    System Integration – performed in SH2 by IS&T and Business Testers as a combined pool
    We have successfully pursued this approach for the past four years
  Planning
    ALM/Quality Center (Central test case repository & tracking tool)
    Work with IS&T Testing Coordinators & QA
  Continuation of Automated Testing
    Automating testing tool - QTP
    Approximately 45% of last year’s test cases have been automated
  Link to ALM/QC …
  https://testcenter.mit.edu:8443/qcbin/start_a.jsp

## Slide 15: Important Dates
Now - October - Plan, convert/create/update test scripts in QC, move pending support & project work into production
10/9/2014 – SAP release of year end base level support pack
10/20/2014 - End of day production snapshot to be used to refresh test environments
10/20/2014 - Development Freeze begins
10/28/2014 - Last date to implement support & enhancement changes until freeze ends on 12/10/2014
10/24/2014 - 10/31/2014 Unit test
11/3/2014 - 11/26/2014 System Integration Test
12/5/2014 - 12/7/2014 Go-live weekend!
12/10/2014 - Development Freeze ends

## Slide 16: Project Risks
Identified Risks
  Delay in SAP Releases
  QC Upgrade
    Application has been upgraded during the summer
    This will be the first time a lot of folks will have been in the upgraded system
  Two Phase Testing Approach
    Requires tight coordination and resource availability between the Business & IS&T
    But … we have four years experience with this approach
  Resource availability for the project (both Business & IS&T)
  Delay of implementation of pre-Support Pack Projects
    OE (scheduled for October)
  Impacts from other requested updates
    Atlas 4.0
    Potential others TBD …

## Slide 17: Transport Management
  So what if we have an issue during the freeze period that needs immediate attention?
  Let’s jump back to the wiki …
  https://wikis.mit.edu/confluence/display/sapscripts/2014+Year+End+SAP+Support+Pack+Project

## Slide 18: Recap of Important Dates
Now - October - Plan, convert/create/update test scripts in QC, move pending support & project work into production
10/9/2014 – SAP release of year end base level support pack
10/20/2014 - End of day production snapshot to be used to refresh test environments
10/20/2014 - Development Freeze begins
10/28/2014 - Last date to implement support & enhancement changes until freeze ends on 12/10/2014
10/24/2014 - 10/31/2014 Unit test
11/3/2014 - 11/26/2014 System Integration Test
12/5/2014 - 12/7/2014 Go-live weekend!
12/10/2014 - Development Freeze ends

## Slide 19: Next Steps
  Your commitment to this plan
  Test Planning
  System preparation

## Slide 20: Not-soTrivial Pursuits
G
What environment will we be testing in?
E
What is ALM(QC)?
H
When will the last transports be moved to production before the freeze?
AL
Where can I find project related information?
SN
What are we updating?
SL
When is go-live weekend?

## Slide 21
Questions? Ah …

## Slide 22: Questions?
Any additional questions? Please contact:
Frank Quern Bart Dahlstrom
X2-4512 x3-9605
fquern@mit.edu bartd@mit.edu
OR
Your SAP testing team coordinator:
HR-Payroll: Mary Donovan
Financial-Logistics-EHS: Lee Collier