## Communication & Contacts
Communication
An IS&T telephone number (617-324-7468) will carry a message as to the status of the upgrade beginning at noon on Friday 12/5 through noon on Monday 12/8. The Project Manager will update this message as needed. A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 4:00pm on Sunday.
Voicemail With Status: 617-324-7468
Conference Call Line: Webex
Call-in toll number (US): 617-324-0000 Saturday Access code: 642 892 269 Sunday Access code: 644 048 233
Project wiki link: | https://wikis.mit.edu/confluence/display/sapscripts/2014+Year+End+SAP+Support+Pack+Project
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via voice message, email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
Contact Information
Area | Name – Location | Contact Telephone # | Email
A/P | Cathy Cherico – NE49 | Refer to online directory | CHERICO
VPF | Clarel Auguste – NE49 | 617-253-8488 | cauguste@mit.edu
VPF – Travel | Andrea Siegel - Off Campus | Contact PM | amsiegel@mit.edu
Dept. of Facilities | Bob Leonard – NE49 | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher – Off Campus | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix | Contact PM | lstcroix@mit.edu
EHS | Laurie Veal – Off Campus | Contact PM | veal@mit.edu
EHS | Joe MacLeod - Off Campus | Contact PM | jmacleod@mit.edu
HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu
HR/Benefits | Diane Johnston – Off Campus | Contact PM | djohnsto@mit.edu
HR/Benefits | Kathleen Flynn – Off Campus | Contact PM | kflynn@mit.edu
EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White – Off Campus | Contact PM | jwc@mit.edu
Procurement | Cindy Vye - NE49 | Contact PM | CI24314
Procurement | Cecilia Talamates – NE49 | Contact PM | cctala@mit.edu
Procurement | Jeff Rosa – Off Campus | Contact PM | jrosa@mit.edu
Procurement | Minerva Tirado -NE49 | Contact PM | MINERVA
Procurement | David Petricone - Off Campus | Contact PM | PETRICON
Procurement | Kimberly Harmon – Off Campus | Contact PM | kharmon@mit.edu
VPF – HR/Payroll | Leslie Wright – NE49 | 617-253-7715 | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Contact PM | darrenjs@mit.edu
VPF – HR/Payroll | Kristen McCormick | Contact PM | cassidyk@mit.edu
VPF – HR/Payroll | Nicole Valente | Contact PM | nferrant@mit.edu
VPF – HR/Payroll | Lilian Garcia | Contact PM | llg@mit.edu
VPF – HR/Payroll | Jen Quintero | Contact PM | jen_quin
VPF – HR/Payroll | Chris Durham – NE49 | Refer to online directory | cfdurham
IS&T – QA | Debra Wiley | Refer to online directory
IS&T - QA | Jack Kelliher | Contact PM | jackkell@mit.edu
IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu
IS&T - ERP System Manager | Bart Dahlstrom – W92 | Refer to online directory | bartd@mit.edu
IS&T - FI / EHS team lead | Siobhan Cunningham – W92 | Refer to online directory | snc@mit.edu
IS&T – Logistics | Adina Ion – W92 | Refer to online directory | aion@mit.edu
IS&T - FI Team | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu
IS&T - FI Team | Keyur Patel – W92 | Refer to online directory | keyurpb@mit.edu
IS&T - FI Team | Sandeep Nadendla - W92 | Contact PM | nadendla@mit.edu
IS&T – EHS/Parking | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu
IS&T – PM/VPIS Parking | Rita Zhovnirovsky – W92 | Refer to online directory | mzhovnir@mit.edu
IS&T – PM | Jim Fragala – W92 | Refer to online directory | ja17661@mit.edu
IS&T – Log/FIN/EHS Team Coordinator | Ken Levie – W92 | Refer to online directory | khann@mit.edu
IS&T – Ops | Kevin Mullins – Off Campus | Refer to online directory | kmullins@mit.edu
IS&T – Ops | Paul Cronin – Off Campus | Refer to online directory | croninp@mit.edu
IS&T – Tech Services | Wai-ming Li – W92 | Refer to online directory | waiming@mit.eu
IS&T – Ops | Olivia Wang – W91 | Refer to online directory | owang@mit.edu
IS&T - Data warehouse | Elena Zhitnikov – W92 | Refer to online directory | elena@mit.edu
IS&T - Data warehouse | Svetlana Lemeshov – W92 | Refer to online directory | lemeshov@mit.edu
IS&T - HR team lead | Frank Quern – W92 | Refer to online directory | fquern@mit.edu
IS&T – HR/Payroll Coordinator | Mary Donovan – W92 | Refer to online directory | donovan@mit.edu
IS&T – OIS | Matt Anctil | 617-909-7889 | manctil@mit.edu
IS&T - OIS | Patrick Whitney | (617) 253-5767 | pwhitney@mit.edu
IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu
IS&T - OIS | Server Operations | 617-775-3302 | Team Line
Project Manager | Frank Quern | 617-452-4512 | fquern@mit.edu
Assistant Project Manager | Desiree Roberts | Refer to online directory | robertsd@mit.edu
Monday Morning Coverage
Area | Name | Location | Time | Email
FLE | Lee Collier | W92 | 7:30am | lcollier@mit.edu
FLE | Jim Fragala | W92 | 7:30am | ja17661@mit.edu
HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu
HRP | Desiree Roberts | Off Campus | 7:30am | robertsd@mit.edu
R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu
Tech Services | Elda Prudden | W92 | 7:30am | eprudden@mit.edu
Tech Services | Mark Prudden | W92 | 7:30am | mprudden@mit.edu
Tech Services | Carolyn Fuller | Off Campus | 7:30am | fuller@mit.edu
SP Project | Frank Quern | W92 | 7:30am | fquern@mit.edu
FLE | Admin Systems Team | W92 | 8:00am + | administrative-systems@mit.edu
HRP | Admin Systems Team | W92 | 8:00am + | hrpay-sppt@mit.edu

## Task List
# | Date | Time | Action / Task | Person(s) Responsible | Status
Pre-Update Schedule and Processes:
1 | Tuesday 11/25/2014 | 2:00 PM- 3:30 PM | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team | Complete
2 | Wednesday 11/26/2014 | By EOD | Draft Cut-over Communication Plan/Submit to IS&T Communication Team for review. | Frank Quern | Complete
3 |  | By EOD | Submit Atlas Banner Message Request to Atlas Team for 12/2 | Frank Quern | Complete
4 |  | By EOD | Submit ECAT Outage Message Request to Procurement for 12/2 | Frank Quern | Complete
5 |  | By EOD | Submit Outage/Injury Report to EH&S for Review | Frank Quern | Complete
6 | Monday 12/1/14 | 12 pm - 2 pm | Cutover weekend planning meeting IS&T. | IS&T-SAP | Complete
7 | Tuesday 12/2/2014 | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | ops (Paul Cronin) | Complete
8 |  | 10:00 AM - 11:00 AM | Support Pack Transport Review Meeting. Final review all issues in RT project queue, transport list, and web components. | R3-Admin /Core Team/ABAP Team/Web-Tech/BSAs | Complete
9 |  | 12 noon | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee | Complete
10 |  | 4:00PM | Begin online upgrade piece of the application of Enhancement & Support Pack(s). Run time 2 days (complete by EOD 12/5). | R3-Admin (R. Parker) | Complete
11 |  | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker) | Complete
12 |  | By 5:00 PM | Post message on ECAT web site about upcoming SAP outage. | VPF – Cecilia Talamantes VPF – Scott Ball | Complete
13 |  | By 5:00 PM | Email Steering Committee Go/No-go decision to Team | Project Manager ( Frank Quern) | Complete
14 |  | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Project Manager ( Frank Quern) | Complete
15 | Wednesday 12/3/2014 | 2:00 PM- 3:30 PM | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | Project Manager ( Frank Quern) | Complete
16 |  | 16:00 | Email ops-help with list of web application deployment requests for Friday evening. (align with Atlas release) | Project Manager ( Frank Quern) | Complete
17 |  | By EOD | Final Copy of the Production Update Schedule (cutover plan)published and emailed. | Project Manager ( Frank Quern) | Complete
18 | Thursday 12/4/2014 | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be 12/8/2014). Notify R3-Admin (R. Parker) and PM (Frank Quern) when jobs have been scheduled. | VPF Finance (C. Auguste) | Complete
19 |  | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. | Admin Systems (M. Murray via Fire Fighter) | Complete
20 |  | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker) | Complete
21 | Friday 12/5/2014 | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM). | DW (E. Zhitnikov) | Complete
22 |  | By 2 PM | Print out/Download Facilities work order lists as back up for Monday Morning | Facilities (Bob Leonard) | Complete
23 |  | By 2 PM | Print out/Download Housing work order lists as back up for Monday Morning | Facilities (Bob Leonard) | Complete
24 |  | By 4:20 PM | Shift Concur outbound execution from 5:00 pm to 4:20pm | Tech Services (Wai-ming Li) | Complete
25 |  | By 4:30 PM | Suspend weekend MITSIS cron jobs for the BIO feed and the Grad Appointment Feed - On sky-app-1 under userid as_cron comment out weekend rprgapxt_new job - On sky-app-1 under the oasprod userid comment out the rprgabio_cron job. | Enterprise Appl. Admin (K. Mullins) | Complete
26 |  | By 5:00 PM | Workflow and JV Validation Reports (screen shots) · Workflow inbox report (Henry Leung) · JV Parked Documents Report (Henry Leung) · RFPs (Cathy Cherico) | VPF (Henry Leung) (Cathy Cherico) | Complete
27 |  | After 5 pm and before Sunday at 6 am | Update GUI XT on Facilities Department desktop machines | Facilities (M. Sherman) | scheduled to push to machines on Monday morning
System Isolation
28 |  | 4:35 PM (5 Minutes) | Stop EDI Production Jobs (5 Minutes) Will need access to logistics batch id ZZLOGISBAT01 (id needs to be converted to dialog thru the course of the implementation). o email sap-upgrade-core@mit.edu when complete | Tech Services (E. Wei) R3-Admin (G. Petrowsky) | Complete
29 |  | 5 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). · Run the push POs job · Shutdown the web server · Shutdown the application server · email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (O. Wang) | Complete
30 |  | 5 PM | Voice message update when system goes down (617-324-7468) o email sap-upgrade-core@mit.edu when complete | Project Manager ( Frank Quern) | Complete
31 |  | 5 PM | System Downtime Message (3 Down) o email sap-upgrade-core@mit.edu when complete | R3-Admin Project Manager (F. Quern) | Complete
32 |  | 5 PM | Bring down application servers. Production Environment becomes unavailable to users (including ECAT). o email sap-upgrade-core@mit.edu when complete | R3-Admin | Complete
33 |  | 5 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) o email sap-upgrade-core@mit.edu when complete | Ops ( Kevin Lyons / G. Gaudette) | Complete
34 |  | 5 PM (5 Minutes) | Suspend Drop-box processing. o email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li) | Complete
35 |  | 5 – 7 PM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Clarel Auguste via email cc fquern@mit.edu, nadendla@mit.edu that the reports are completed & downloaded. • VPF confirms the receipt of the Trial Balance Report. • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF (Clarel Auguste) | Complete
36 |  | 5 – 7 PM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • Save WT info to internal SAP table • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) (G. Petrowsky) | Complete
Support Pack Application and Processes:
37 |  | 7:00 PM – 4:00 AM | Backup PS1. • Shutdown SAP System (Ron) • Split off (disable) SRDF mirror (Matt) • Bring up SAP database • Generate full (level 0) SAP database RMAN backup (Matt) • Bring up SAP (Ron) • email sap-upgrade-core@mit.edu when complete (Ron) | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Resource: Patrick Whitney) | Complete
38 | Saturday (morning) 12/6/14 | 4:00 AM – 12:00 PM | SAP ERP: Execute support pack application. - Upgrade DOWN-TIME Phase - Upgrade Post Processing Phase - Upgrade SAP database • Email Notification to sap-upgrade-core@mit.edu from Ron Parker at the start of the support pack application • Email notifications to sap-upgrade-core@mit.edu by 11:59 pm on Friday (12/5) with status and by 7 am on Saturday (12/6) from Ron Parker upon completion. | R3-Admin (R. Parker) | Complete
39 |  | 9:00 | Deploy non-Atlas web apps (refer to deployment ticket request from Wednesday) • email sap-upgrade-core@mit.edu when complete | Ops (K. Mullins) | Complete
40 |  | 9:00 | Deploy Atlas web apps (refer to deployment ticket request from Wednesday) • email sap-upgrade-core@mit.edu when complete | Ops (K. Mullins) | Complete
41 |  | 12 PM - 5 PM | ADS Upgrade (DSP) o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Katkowski) | Complete
42 |  | 12:00 PM – 6:00 PM | Portal Upgrade (see portal task list on project wiki) o email sap-upgrade-core@mit.edu when complete | R3-Admin (Q. Kang) | Complete
43 |  | By 8:00 PM | BSI Upgrade (can occur any time after 5pm Friday) o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) | Complete
44 |  | 1 PM – 9:00 PM Concurrent w/ following Task 43 (BSI Upgrade) | Backup System (RMAN) o Generate full (level 0) SAP database RMAN backup (Matt) o email sap-upgrade-core@mit.edu when complete (Matt or Ron) | R3-Admin OIS/Enterprise Storage & Backup (Resource: Patrick Whitney) | Complete
45 |  | 1:00 PM – 9:00 PM | Execute concurrently: Generate DB Statistics (6 – 8 hours) ABAP Loads (5 hours) o email sap-upgrade-core@mit.edu when complete | R3-Admin | Complete
46 |  | 18:00 | IS&T Conference Call Check-in Core Team Check in at 6 pm on Saturday (use conference call webex line) | Project Manager (Frank Quern) | Complete
47 |  | 7:00 PM (15 mins) | Restore WT Table (once loads are done) o email sap-upgrade-core@mit.edu when complete | R3-Admin | Complete
48 |  | 9:00 PM – 11:00 PM | Transports Application – after the completion of the ABAP Loads • Email sap-upgrade-core@mit.edu before transport application • Email sap-upgrade-core@mit.edu after transport application is done Included in this year’s application DSM: Import the transports as part of the step above with unconditional mode 12468. Generate transport specific ABAP loads and DSM Object Classes. Run DSM Optimization Programs | R3-Admin | Complete
49 |  | 23:00 | Validation reports executed (trial balance reports) • R3-ADMIN notifies Clarel Auguste via email, cc to Frank Quern as soon as the trial balance is available for review • R3-ADMIN unlock CAUGUSTE id in PS1 • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF Finance (Clarel Auguste) | Complete
Post Upgrade Schedule and Processes:
50 | Sunday 12/7/14 | 12:00 AM – 8:00 AM | On Line back up of PS1 (RMAN). • Generate full (level 0) SAP database RMAN backup (Matt) • Resume hourly RMAN logfile backups (Matt) | R3-Admin OIS/Enterprise Storage & Backup (Recource: Patrick Whitney) | Complete
51 |  | 6:30 AM – 8:00 AM | R3-Admin Action Log Refer to R3 Action log posted on project wiki. Unique to this year’s activities: refer to the R3 Action Log for details o email sap-upgrade-core@mit.edu when complete | R3-Admin (All) | Complete
52 |  | 8 - 9 am | Admin Sys Post Upgrade Action Log - ADMIN SYS Action Log users unlocked - ADMIN SYS executes the PS1 Action Log / Validations and email steps completed to rest of the team (sap-action-log-team@mit.edu) - ADMIN SYS Extended Team reviews transport logs • email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Action Log (Frank Quern) | Complete
53 |  | 8 – 9 am | TB Validation reports validated • Clarel notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Clarel Auguste) (Sandeep) | Complete
54 |  | 8:00 | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (start EDI; but do not send or push any files yet) o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (Olivia Wang) | Complete
55 |  | 8:30 | EDI Step 2 Start EDI Jobs (start sending EDI files) o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (Olivia Wang) | Complete
56 |  | By 9 AM (5 Minutes) | EDI Step 3 (last step) Schedule EDI Job • Unlock ids (eprudden, ZZLOGISBAT01) • Schedule EDI Job • Monitor first job released (on the ½ hr) • email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Tech Services (E. Prudden) (ZZLOGISBAT01) | Complete
57 |  | By 9 AM | Email to ist-sap@mit.edu • List of transports applied and any related issues. • List of jobs shifted in PS1 during cutover | R3-Admin (Ron Parker) | Complete
58 |  | 8:30 | Atlas Project: Unlock Atlas Conversion Team members (upon completion of Post Upgrade Action Log activities) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) | Complete
59 |  | 9 - 9:30 am | Atlas Project: Parameter & Master Data setup o email sap-upgrade-core@mit.edu when complete | Atlas team | Complete
60 |  | 9:30 - 11:00 am | Atlas Project: Data Conversion o email sap-upgrade-core@mit.edu when complete | Atlas team | Complete
61 |  | 11:00 | Unlock Admin Sys Teams (BSAs, Tech Services) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) | complete
62 |  | 12:00 | Unlock validators (testers) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) | Complete
63 |  | By 12 PM | Update voice message whether or not Data Validation is on schedule. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | Project Manager (Frank Quern) | Complete
64 |  | 12 PM – 2 PM | PS1 Data Validations & Transaction processing listed in section 3 below performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs Admin Sys BAs | Complete
65 |  | By 2 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs Admin Sys BAs R3-Admin | Complete
66 |  | 16:00 | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, B. Dahlstrom, R. Parker, Wai-ming Li Admin Sys Team Leads) | Business Owners/ Test Coordinators Sponsor (B. Dahlstrom) Tech Services (W. Li) Admin Sys Team Leads IS&T Test Coordinators (M. Donovan), (L. Collier) | Complete
67 |  | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu,warehouse@mit.edu, Elena@mit.edu,) indicating decisions/results. | Project Manager (Frank Quern) | Complete
68 |  | 4:30 PM – 6:30 PM | Unlock users (Facilities, SMART) Unlock all users Switch the following batch ids to non-dialog: ZZLOGISBAT01 (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update Atlas message. | R3-Admin (G. Petrowsky) | Complete
69 |  | 6:30 PM Sunday (5 Minutes) | Enable Drop box o email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li) | Complete
70 |  | 18:30 | Reinstate weekend MITSIS Grad Appointment Feed o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (K. Mullins) | Complete
71 |  | By 6:30 PM | Execute ProCard from Bank of America Feed o email sap-upgrade-core@mit.edu when complete | Tech Services (Eping Wei) | Complete
72 |  | 8PM – 12AM | Data Warehouse Job Validation • Elena confirm job validation completion via email to sap-upgrade-core@mit.edu • Run extracts (10PM & 12AM) | R3-Admin
73 | Sunday / Monday morning | 1:30 | On Line back up of PS1 (RMAN). • Generate incremental SAP database RMAN backup (Matt) • Resume daily incremental and weekly full RMAN backup schedule (Matt) | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Resource: Patrick Whitney) | Complete
74 |  | By 6 AM | Update the 3-down web page & SAPgui message. o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) Project Manager (Frank Quern) | Complete
75 |  | By 6 AM | Remove SAP outage message on ECAT webpage. | VPF – Cecelia Talamantes VPF – Scott Ball
76 |  | By 6 AM | Remove Atlas and EHS messages. o email sap-upgrade-core@mit.edu when complete | Ops (K.Mullins) | Complete
77 |  | By 6 AM | Validate Atlas and EHS messages have been removed (verify in IE, Firefox, Chrome) | Admin Systems (Team) | Complete
78 |  | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | Project Manager (Frank Quern) | Complete
79 |  | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. o email sap-upgrade-core@mit.edu when complete | Admin System Desiree Roberts | Complete
80 | Tuesday 12/9/2014 | 17:00 | Reestablish SAP Production System SRDF replication between OC11 and E40 (Matt) | OIS/Enterprise Storage & Backup

## Escalation Path
Escalation Path
If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Bart will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday December 7th.
Functional Malfunction(s)
Clarel Auguste | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike Peretti | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Laurie Veal | Business Process Owner (EH&S) / Weekend Coordinator
Cathy Cherico | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Bart Dahlstrom | Project Sponsor IS&T / ADMIN SYS ERP Systems Manager
Steering Committee (+)
1. Bill VanSchalkwyk | Managing Director, EHS Programs
2. Scott Ball | Business Systems Manager, VPF
3. Lisa St. Croix | Business Systems Manager, Department of Facilities
4. Kathleen Flynn | HR Manager of Operations
5. Frank Quern | SP Project Manager
Escalation Support Team
Ron Parker | Basis / Technical Support
George Petrowsky | R3 Authorizations
Elena Zhitnikov | Data Warehouse Team
Frank Quern | Support Pack PM
Siobhan Cunningham | FIN/LOG/EH&S Team Lead
Kevin Mullins | Ops
Wai-ming Li | Tech Services
Lee Collier | FI/LOG/EHS Team Coordinator
Mary Donovan | HR/Payroll/EL Team Coordinator
Desiree Roberts | Assistant Project Manager

## Validation
Production Validation
Production Validation will occur in NE49, W92 and remotely. Validation is scheduled to start at 12:00 PM, however, please check the message line (617-324-7468) before coming into the office or starting to test remotely. The message will be updated by 11:30 AM if there are potential delays and by 12:00 PM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 8th. Frank will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/Clarel Auguste | Trial Balance Report validation occurs first. Ron Parker will email Clarel Auguste and Frank Quern when the reports have finished processing. Clarel will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following:Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log second. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu