## HR-Payroll
Task | Transaction tested | Tester | Backup | Complete* | Comments/Issues
Employee transactions | PA30 & PA40 |  |  |  |  | *S=Sunday & M=Monday
New hire |  | SC rep** | SC rep** | S
Termination |  | SC rep** | SC rep** | S
Supplement |  | SC rep** | SC rep** | S
Salary change |  | SC rep** | SC rep** | S
Promotion |  | SC rep** | SC rep** | S
Hourly Student transactions | SHA
ZHR_HSA_LOG |  | SC rep** | SC rep** | S | No longer receive requests on paper - can't validate zomchst
Grad Student transactions | PA30 & PA40
New appointment |  | SC rep** | SC rep** | S
Change appointment |  | SC rep** | SC rep** | S
Cancel appointment |  | SC rep** | SC rep** | S
Delimit appointment |  | SC rep** | SC rep** | S
APR - Appt Process Redesign | ZHRAP |  |  |  | DLC users on Monday morning too
Hire |  | SC rep** | SC rep** | S/M
Termination |  | SC rep** | SC rep** | S/M
Supplement |  | SC rep** | SC rep** | S/M
Leave |  | SC rep** | SC rep** | S/M
Change |  | SC rep** | SC rep** | S/M
ePaystub | Atlas Self Service | SC rep | SC rep | S | Email notification link
eW-2 | Atlas Self Service | SC rep | SC rep | S
direct deposit | PA30 & Atlas Self Service | SC rep | SC rep | S
tax withholding | PA30 & Atlas Self Service | SC rep | SC rep | S
deductions | ZPYDEDUCT | SC rep | SC rep | S
eSDS | Atlas Manage People
exempt |  | DLC user | DLC user | M
non-exempt; reg & premium |  | DLC user | DLC user | M
grad student RA; stipend & tuition |  | DLC user | DLC user | M
eDACCA | SAPweb
Search by each criteria |  | DLC user | DLC user | M
Certify Q1 20xx DACCA |  | DLC user | DLC user | M
Approve/Distribute Time Sheets | Atlas Manage People
Approve SC time sheets |  | Darren/Chris | Darren/Chris
SRS Vacation Tracker | Atlas Manage People | DLC user | DLC user | M
Appt Process Redesign | Gui - ZHRAP | SC rep | SC rep | S
Gross to Net | Off-cycle work bench or simulation
Exempt |  | Darren | Leslie | S
Non-exempt |  | Darren | Leslie | S
Additional Tax amounts-federal |  | Darren | Leslie | S
Additional Tax amounts -state |  | Darren | Leslie | S
401K max & catchup in Dec |  | Darren | Leslie | S
Time Evaluation | PT60 | Darren | ?? | S
CDU - exempt | ZPYCDU2
MAP |  | Darren | ?? | S
RA tuition |  | Darren | ?? | S
vacation credits |  | Darren | ?? | S
off campus |  | Darren | ?? | S
reduced EB |  | Darren | ?? | S
Tax Reporter | PU19
Print W2 form |  | SC rep** | SC rep** | S
Print 1099R form |  | SC rep** | SC rep** | S
Print W2C form |  | SC rep** | SC rep** | S
Reports
Missing IT9004 report | ZPYRMISSING9004 | Leslie | Darren | S
Vaca/Sick payout for ZW | S_AHR_61015611 | Leslie | Darren | S | Wage Type Statement
Sick cost out report | ZPYSCOR | Leslie | Darren | S
Appointment error messages | ZPYR_APPT_MESSAGES | Leslie | Darren | S
Glacier New Hire Report | zpy_nra_glac | Leslie |  | S | Need ZZPYBATCH001
Student bio feed log | zpy_mitsis_log | Leslie | Darren | S
Payroll Validation Audit | zpy_pay_val_rpt | Darren | Leslie | S
Leave accrual | PT50 | Darren | Leslie | S
Feeds
Lincoln Daily feed - manual | ZHRALE | Darren | ?? | S | see tab Lincoln feed for details
Contacts/Location
Leslie - on site NE49 3-7715
Who is secondary contact instead of Tricia?
Validators will be onsite:
Leslie | lesliem
Darren | darrenjs
Kristen | cassidyk
Nicole | nferrant
Lillian | llg
Jen Quintero | jen_quin
Chri s Durham | cfdurham

## HR
Type | Transaction | Assigned to | Backup | Backup
SAPGUI | Benefits Enrollment | Diane | Mike Peretti | Riley Hart
ESS | Benefits Enrollment | Diane | Mike Peretti | Riley Hart
ESS Personal Info | Home address | Diane | Mike Peretti | Riley Hart
| Ethnicity | Diane | Mike Peretti | Riley Hart
| Work Address | Diane | Mike Peretti | Riley Hart
| Emergency Contact | Diane | Mike Peretti | Riley Hart
| MITAlert (check links only) | Diane | Mike Peretti | Riley Hart
| Eduction History | Diane | Mike Peretti | Riley Hart
Learning Center | Register for training | Diane | Mike Peretti | Riley Hart
| Cancel registration | Diane | Mike Peretti | Riley Hart
Contacts/Location
Diane - at home 781-325-6591
Riley - at home 781-799-2945 (cell)
Michael Peretti at home 914-479-2334

## EL
Type | Transaction | Assigned to | Backup | Notes
Learner | Access the portal, both by certificate and username/password login | Jane White | Melissa Kavlakli | All portal transactions will be validated on PC and Macs, using various browsers.
| View My Profile | Jane White | Melissa Kavlakli
| View My Training | Jane White | Melissa Kavlakli
| Register for a course (verify auto email) | Jane White | Melissa Kavlakli
| Cancel a course (verify auto email) | Jane White | Melissa Kavlakli
| Prebook a course (verify auto email) | Jane White | Melissa Kavlakli
| Adding to a calendar for a classroom course | Jane White | Melissa Kavlakli
| Continue a previously started WBT (verify auto email) | Jane White | Melissa Kavlakli
| Book into new WBT (verify auto email) | Jane White | Melissa Kavlakli
| Cancel a WBT (verify auto email) | Jane White | Melissa Kavlakli
| Complete a WBT (verify auto email) | Jane White | Melissa Kavlakli
Instructor | Run Attendee list | Melissa Kavlakli | Jane White
Registrar | Create a course sessopn | Melissa Kavlakli | Jane White
| Book Jane into Course session | Melissa Kavlakli | Jane White
| Cancel Jane in course session | Melissa Kavlakli | Jane White
TNI Admin | Create a Requirement Set | Melissa Kavlakli | Jane White
| Create a Training Group | Melissa Kavlakli | Jane White
| Create an Activity | Melissa Kavlakli | Jane White
| Add Jane as member to Training group (Jane will verify entry via her profile) | Melissa Kavlakli | Jane White
| Run EHS training reports | Melissa Kavlakli | Jane White
| Test the completion uploader | Melissa Kavlakli | Jane White
| Profile administration | Melissa Kavlakli | Jane White
| Training Reconciliation | Melissa Kavlakli | Jane White
Contacts/Location
Jane - at home 978-475-5843
Melissa-at home 617-230-9458

## Lincoln Feed
Lincoln File Steps
Sunday December 7, 2014
Lincoln Files
1. Campus Service Center shuts down Lincoln job on Friday, December 5, any time before 5pm
2. Lincoln files are generated on a regular schedule, at 6pm, but are not loaded because the job is not active.
3. Wai-Ming shuts down SAP Dropbox on Friday, December 5 at 6pm
4. The Dropbox will be up and running at 6:30 Sunday, December 7
5. Larissa and Karen will validate the LL file is loaded and send an email out to the below email list if it was successful or if there are any issues.
Note:
Larissa talked with Eric, and he does not anticipate a big volume of changes to come on Friday; he also said that he will ask Lincoln Workforce center “to keep the volume light”, i.e. key only essential data on Friday. So hopefully we’ll have only one file on Friday, with not much data; just to make the validation easier/quicker
Email List
1. Larissa Kushkuley
2. Eric Ngo
3. Wai-ming Li
4. Leslie Wright
5. Karen Nolet
6. Scott Ball
7. Frank Quern
8. Desiree Roberts
Below email from Larissa to wsc re SP go-live:
Hi, As you know, we are going live with SAP support packs this coming weekend. SAP dropbox will be shut down at 5pm on Friday, and we will be loading Lincoln’s Friday files on Sunday. We would appreciate if you could keep Friday’s updates “light”, it will help us to get through Sunday’s validations faster! Thank you in advance, Larissa & the team | email to wsc@ll.mit.edu - sent on Thursday 12/5