## Overview and Assumptions
Timeframe for Test Execution
Comparison Test: 11/7/2011-11/28/2011 (3 holidays)
Integration Test: see comparision test
Assumptions:
Production snapshot as of midnight 10/21/2013
Test system will be available by start of day 11/4/2013
Comparison test consists of four payroll comparisons:
| Weekly Non-Exempt (payweek 43 (10/14/2013-10/20/2013)) | LL | 44/2013??
| Monthly Exempt (October 2013) | MC | 45/2013?? | Cycle 1 | Leslie will identify cost objects
Pension Payroll Lump Sum (October 31, 2013)
Pension Monthly Annuity Run (Nov 2013)
Overview of integration test strategy:
Generate payroll and run interfaces simulating the production payroll processes.
Compare test system SH1 results to PS1 Production results
Research discrepancies; resolve system issues
Execute select test scripts hiting key functionality not executed during pay run processes
Comparison Tools:
Create comparison reports using the EPIUSE variance monitor tool
Net pay comparisons in excel
Net pay comparison using EPIUSE variance monitor
Ultra Compare
Fox Pro
Overview of Script testing - majority of testing conducted by Business:
Test Scripts identified in Quality Center, both manual and automated:
in the HR domain space are the folder containing test scripts:
HR-Payroll/Manual_test_Suite
HR-Payroll/Automated_Test_Suite
Test lab folder: 2013_SupportPacks

## Comparision Run Schedule
Task # | Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Prep files ready? | Batch ID | Job Set # | Special Variant in PS1? | Update variant in sh2 | Notes | No. of files matched | PS1 | SH2 | Variances | Percent matched | Reasons for differences
P1 | Set up / Update SP Variants for all the feeds. |  |  | 2014-10-01 | 2014-10-03 | Mary D. Larissa Sharon | Complete |  |  |  | Yes - dates in variants will be changed in ps1
P2 | Execute ZM Payroll simulation in PS1 for 10.2014 |  |  | 2014-10-20 | 2014-10-20 | Gregg | Complete
P3 | Run HIRD report in PS1- do not send, retain file for comparison. use Firefighter role. |  |  | 2014-10-20 | 2014-10-20 | Desiree | Complete |  | ZZHRBENBTC01 |  | Yes |  | So we have a comparison
P4 | Run ZPY_PENSION_COMPENSATION - retain for comparison, Run in TEST mode - use Firefighter role. |  |  | 2014-10-20 | 2014-10-20 | Desiree | Complete |  | ZZHRBENBTC01
P5 | SF3 - After 9/22 snapshot applied and before support packs implemented, run ZM simulation for 09.2014; |  |  | 2014-10-03 | 2014-10-03 | Gregg | Complete | [5 empty] | Aliases in sf3?
P6 | SF3 - After support packs implemented, run ZM (PP09), ZP (PP10) & ZW actual for 39.2014 - use Greggs rem stmt variant |  |  | 2014-10-22 | 2014-10-22 | Gregg
P7 | SF3 - process ZM and ZW postings and CDU postings, let FI group know when finished. |  |  | 2014-10-22 | 2014-10-22 | Gregg /Mary
P8 | Compare BEFORE and AFTER results of 09.2014 ZM and ZP (10.2014), compare to the PS1 copy as well. |  |  | 2014-10-23 | 2014-10-23 | Gregg | [6 empty] | SF3 before v. after were identical. Each with 2 variances from PS1 due to IT0210 changes post simulation prior to copy. | 2
P9 | SF3 - Execute Business Owner validation steps - use last years steps. |  |  | 2014-10-22 | 2014-10-23 | HR Payroll Team
P10 | Capture production logs for the EL incoming feeds for 10/21/2012 - to be used for test comparisons. - see list of jobs in doc EL Feeds and EMAIL notifications.xls |  |  | 2014-10-21 | 2014-10-21 | Mary |  |  | Run under batch id ZZHRELBTCH01
P11 | Request new copies of all three payrolls checklists and documentation. |  |  | 2014-10-20 | 2014-10-29 | Mary | [6 empty] | Request to Laurie F - place copies in hr-istyearend shared folder.
SIT Environment Ready - Prep for testing
1 | Verify Feed Registry Archive Control Tables are correct for the environment - Need to change encryption flag for those files which are copied into test sapin directory. | SM30 | n/a | 2014-10-30 | 2014-10-30 | SD |  | n/a |  |  |  |  | Part of the action log. | n/a | n/a | n/a | n/a | n/a
2 | Repoint EDI test to current SP test environment |  |  | 2014-10-30 | 2014-10-30 | [7 empty] | 2013 - Ron needed to resave the port (needed in PS1?)
3 | Re-configure EDI Test Environment to accept files from SH2 |  | n/a | 2014-10-30 | 2014-10-30 | Ron, Larisa will remind him |  | n/a |  |  |  |  | Larissa points SP test env to EDI server | n/a | n/a | n/a | n/a | n/a
4 | Confirm w/ R3 that Lincoln configuration for EDI is active |  | n/a | 2014-10-30 | 2014-10-30 | Ron Parker |  | n/a |  |  |  |  | 2013: Per Larissa this needs to be done before the LL inbounds. Per Eric Ngo - 2012: The logical system is RC2CLNT400.(Ron should verify) | n/a | n/a | n/a | n/a | n/a
5 | Execute ZM, ZP Payroll simulation in SH2 for period 10.2014. Compare to PS1 simulation run on 10/20. |  |  | 2014-10-30 | 2014-10-30 | Gregg M. | [6 empty] | Compare to PS1 run. Use single line rem-statement. Log and report tie out. Don't need to wait for steps 1,,3 | 2
6 | Validate EL web connections functional |  |  | 2014-10-31 | 2014-10-31 | Mary
7 | Validate access to the authoring environment |  |  | 2014-10-31 | 2014-10-31 | Mary
8 | Validate APR web connections functional. |  |  | 2014-11-03 | 2014-11-03 | Emily
9 | Load ASR macros uploaded from the archive server to the proper server for each environment so that the ASR Faculty spreadsheet works correctly. |  |  | 2014-11-04 | 2014-11-04 | Emily | [6 empty] | Send email to Wai-ming
10 | DW extract of HR/Pay data | Multiple | n/a | 2014-11-03 | 2014-11-03 | Elena |  | n/a |  |  |  |  | Payrolls and feeds may be running
11 | Assign batch ids to testers - see sheet Batch IDs and aliases |  |  | 2014-11-03 | 2014-11-03 | George | [6 empty] | Send George list of ID's
12 | Validate Laurie19 aliases established |  |  | 2014-11-03 | 2014-11-03 | Mary & Gregg
Weekly and Pension Payrolls
13 | Outbound Run FSA Census outbound interface using Ultracompare compare file to Sunday production run (10/19). | PGM: ZPYI0170_FSA_CENSUS_DATA | py/fsa_census | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution
14 | Outbound Run FSA Enroll outbound interface (looks at the control record) using Ultracompare compare file to Sunday production run (10/19). | PGM: ZPYI0170_FSA_ENROLLMENT_DATA | py/fsa_enroll | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution
15 | Outbound LL non-exempt leave accruals (this is a daily interface) using ultracompare compare files to Tues production runs (10/21) | Trans: ZHR_LL_ACCRUALS_OUT PGM: ZPT_LL_ACCRUALS_OUTBOUND Check for errors on filezilla. | py/ll_leave | 2014-11-03 | 2014-11-03 | Karen |  |  | ZZHRLLFEED01 | 1 | SP |  | This was moved up from Job Set 3 - needs to run before ZW payroll,
16 | Weekly Payroll Processing (43/2014) Work week 10/13/2014-10/19/2014 (Execute with LAURIE19 alias) | Follow Non-exempt payroll checklist |  | 2014-11-03 | 2014-11-03 | MD |  | n/a | LAURIE19 alias |  |  |  | see comparisons results in step 22 below | - | - | - | - | -
17 | Pension Payroll - Lump Sum Run (10/31/2014) (includes loading PS1 copy of Pension Lump Sum file) (Execute with LAURIE19 alias) | Follow MIT Lump Sum checklist |  | 2014-11-03 | 2014-11-03 | GM |  |  | LAURIE19 alias |  |  |  | Where do files come from? encrypted file dumps decrypted file processes correctly
18 | Pension Payroll - Annuity Run (11/2014) (includes loading PS1 copy of Pension Annuity file) (Execute with LAURIE19 alias) | Follow MIT Annuity checklist |  | 2014-11-03 | 2014-11-03 | GM |  |  | LAURIE19 alias |  |  |  | Where do files come from? see comparisons results in step 23 below | - | - | - | - | -
19 | Notify DW ZW and ZP have been run and posted (including CDU) ZM TBD.
Job Set 1
20 | Outbound Run HR Fidelity outbound interface; using ultracompare compare file to Monday production run (10/20). Set parameter to process week before snapshot Mon-Sun | PGM: zhr_fidelity | hr/fid_hr | 2013-11-04 | 2013-11-04 | Desiree |  |  | ZZHRBENBTC01 | 1 | SPFID WKLY PS1 | yes | can run with DW extracts
21 | Outbound Benefits outbound: BCBS using ultracompare compare file to Sunday production run (10/19). Run for dates 10/19 - 100 days thru 10/19 + 45. In IDOC Cleanup allow retro 10 days-variant all set. | Two steps: rpuben52 & program ZHR_BENEFIT_IDOC_CLEANUP. | hr/bcbs | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | Use BLUE CROSS D when not in OE cycle for RPUBEN52 , else use SP BC OED/ SP BCBS PRD OE. Use BCBS PROD for ZHR_BENEFIT_IDOC_CLEANUP when not in OE cycle. |  | can run w/ DW extracts; comparison will be made to the production run (EDI)
22 | Outbound Benefits outbound: Delta using ultracompare compare file to Sunday production run (10/19). Run for dates 10/19 - 100 days thru 10/19 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: RPUBEN52, then program ZHR_BENEFIT_IDOC_CLEANUP | hr/delta | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | Use DELTA when not in OE cycle, else use SP DELTA OE for both RPUBEN52 and ZHR_BENEFIT_IDOC_CLEANUP. |  | can run w/ DW extracts; comparisons were made to production Differences were address changes, terminations, Campus Police (didn’t exclude them in SH1 run)
23 | Outbound Benefits outbound: Vision using ultracompare compare file to Sunday production run (10/19). Run for dates 10/19 - 100 days thru 10/19 + 45. There is currently no retro limit in IDOC Cleanup. | Two steps: RPUBEN52, then program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | Use VISION when not in OE cycle, else SP VISION OE for both RPUBEN52 and ZHR_BENEFIT_IDOC_CLEANUP. |  | can run w/ DW extracts comparison will be made to the production run (EDI)
24 | Outbound Run Express Scripts outbound; using ultracompare compare file to Sunday production run (10/19). | PGM: ZHR_ESI_FEED | hr/esi | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | Use SP FULLFILE outside OE cycle and SP FULLFILE OE during OE |  | can run w/ DW extracts
25 | Outbound Run Crosby Outbound terminations; using ultracompare compare files to Sunday production runs (10/19). *** follow all the way through to vendor *** | PGM: ZHRCSB02 | hr/crosby; | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | SPZHRCSB02_RPT |  | can run w/ DW extracts
26 | Outbound Run Crosby Outbound new entrants for the prior month (Sept); using ultracompare compare files to Sunday production runs (9/1). | PGM: ZHRCSB02 | hr/crosby_new | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | SP_ZHRCSB02_NH |  | can run w/ DW extracts
27 | Outbound Run Crosby Outbound dependents aging out; based on file created 10/1 for Nov ageoffs using ultracompare compare files to production runs (10/1). | PGM: ZHRCSB03 | hr/crosby_dep | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | SP_ZHRCSB03DEP |  | can run w/ DW extracts
28 | Outbound Run Metpay Census outbound interface; using ultracompare compare file to Sunday production run (10/19). | PGM: ZPY_METPAY_CENSUS_DATA | hr/metpcensus | 2014-11-03 | 2014-11-03 | Desiree |  |  | ZZHRBENBTC01 | 1 | SP PRODUCTION |  | can run w/ DW extracts
29 | Outbound Run Health Insurance Resposibility Disclosure (HIRD); outbound to Crosby | PGM: ZHR_OUTBOUND_HIRD_DATA | hr/hird | 2014-11-03 | 2014-11-03 | Desiree |  |  | Run Manually | 1 | SP HIRD Test |  | Compare to file generated in PS1 on 10/20 (step 4).
30 | Payroll Results Comparison (ZW) |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | pernrs | n/a
31 | Payroll Results Comparison (ZP) |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | pernrs | n/a
32 | Payroll Results Comparison (ZP)Lump Sum |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | pernrs | n/a
33 | FI POSTING COMPARISON (ZP) |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | lines in document | n/a
34 | FI POSTING COMPARISON (ZP)Lump Sum |  |  | 2014-11-05 | 2014-11-07 | Gregg M. | [6 empty] | accounts | n/a
35 | EDACCA TABLE COMPARISON |  |  | 2014-11-05 | 2014-11-07 | Gregg M. | [7 empty] | n/a
36 | FI POSTING COMPARISON (ZW) |  |  | 2014-11-05 | 2014-11-07 | Gregg M. | [6 empty] | lines in document | n/a
| (After Payroll Execution) Weekly Outbound Interfaces | [5 empty] | -
Job Set 2
37 | Outbound Timesheet file to MITSIS (combined w/ Grad Student Gross Pay) using ultracompare compare files to Tuesday's production runs (10/21) (This is part of the payroll checklist.) | Trans: ZPYIO_MITSIS_TIM PGM:ZPY_STUDENT_GROSS_PAY Dates From Wednesday to Wednesday | py/mitsis_tim | 2014-11-03 | 2014-11-03 | Mary ran with Laurie's ID, compares by Karen |  |  | laurie19 | 2 | ??? |  | Run after weekly payroll
38 | Outbound LL salary distribution weekly gross pay using ultracompare compare files to Wed production runs (10/22) File to be sent to Lincoln, coordinate with Eric. | PGM: ZPY_LL_SALARY_DISTRIBUTIONS | py/ll_sal_dst | 2014-11-03 | 2014-11-03 | Run by Gregg, compares by Karen |  |  | ZZPYBATCH001 | L2 | SP1ZW SP2ZW | Yes | Check for errors on filezilla
39 | Outbound Leave balance accruals for Facilities Service Staff (this is a weekly interface) | Trans: ZPTKRONOS_ACCRUL_OUT PGM: ZPTKRONOS_ACCRUALS_OUTBOUND | py/facil_leav | 2014-11-03 | 2014-11-03 | Run by Gregg, compares by Karen |  |  | ZZPYBATCH001 | 2 | no | n/a | internal test performed; additionally subsequent test performed with facilities
40 | Outbound FSA (Crosby). Compare results to production file using ultracompare compare files to Wed production runs (10/22) | Trans: ZPYIO_FSA_CONTRIB PGM: ZPYI0170_FSA_CONTRIB | py/fsa_dep | 2014-11-03 | 2014-11-03 | Run by Gregg, compares by Desiree |  |  | ZZPYBATCH001 | 2 | SP_WEEKLY | Yes
41 | Outbound Fidelity pension file (weekly 401 pension contributions) Use ZW Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS using ultracompare compare files to Wed production runs (10/22) | Trans: ZPYIO_FID_CNTRIB PGM: ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2014-11-03 | 2014-11-03 | Run by Gregg, compares by Mary |  |  | ZZPYBATCH001 | 2 | SP_ZWAUTOMATI | Yes
42 | Outbound LL Bank details (this is a daily extract) - compare feed from 10/21 | PGM: zpy_ll_bank_detail | py/ll_bank | 2014-11-03 | 2014-11-03 | Run by Gregg, compares by Gregg |  |  | ZZPYBATCH001 | L2 | No-run adhoc | n/a | Select a PS1 file which contains some changes and repeat test in sh2
| Inbound feeds to prep ZM payroll and next ZW payorll (before planned monthly run) | For 2012, change to include SHA feeds. Run 1 set of feeds for day after snapshot, then run Bio and Grad feeds up to exempt payroll process date. Execute LL daily feed up to date of next ZW payroll run.
43 | Inbound Student Bio Feed (MITSIS) (10/21) | Trans: ZMITSIS PGM: ZPY_LOAD_MITSIS_BIO_DATA | hr/mitsis_dem | 2014-11-04 | 2014-11-04 | Meaghan |  |  | ZZHRMITSIS01 | Execute these 5 feeds in order listed. | No | n/a | both old and new complete
44 | Inbound HSA Student Feed (10/21) Pre-req is the Student Bio feed above. Also need the previuos day's filr for comparison (10/20), Copy unencrypted file from the archive server and upload from workstation | Trans & PGM:ZHR_HSA_UPLOAD | py/sha_stdt Provider ccode=stud Feed code= has | 2014-11-04 | 2014-11-04 | Process by Lucia, compares by Cindy |  |  | ZZPHSABTC01 |  |  | n/a
45 | Inbound HSA UROP Feed (10/21) Copy unencrypted file from the archive server and upload from workstation | Trans & PGM: ZHR_UROP_UPLOAD | py/sha_urop Provider ccode=stud Feed code= uro | 2014-11-04 | 2014-11-04 | Process by Lucia, compares by Cindy |  |  | ZZPHSABTC01 |  |  | n/a
46 | Inbound Grad Appointment Inbound (this is a daily feed) (10/21) Copy PS1 file to local directory. | Trans: ZPY_LOAD_MITSIS_GRAD PGM: ZPY_LOAD_MITSIS_GRADAID | py/gradaid | 2014-11-04 | 2014-11-04 | Meaghan |  |  | ZZHRGRADAPT01 |  | No | n/a | both old and new complete
47 | Inbound LL daily feed (processed on 10/21). Feed files can be identified by running ZHRALELOG Need to copy unencrypted file to sh2/sapin directory. (8-12) | Trans: ZHRALE PGM: ZHRALE01 | hr/ll_hr_time Provider ccode=mith Feed code= hrm | 2014-11-04 | 2014-11-04 | Karen |  |  | ZZHRLLFEED01 |  | No | n/a | Check for errors on filezilla Validate using transaction ZHRALELOG TBD (may be that Eric will review)
48 | Inbound ZTN_MITSIS_ACADEMIC_TERMS (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_MITSIS_ACADEMIC_TERMS_IN | none - Provider ccode=dstud Feed code= trm | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 | Execute these 9 feeds in order | SP ACAD_TERMS | no update needed, no dates in variant | both old and new complete | [5 empty] | Compared to production processing logs for reasonableness.
49 | Inbound ZTN_MITSIS_ACADEMIC_SUBJECTS (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_MITSIS_ACAD_SUBJECTS_IN | none - Provider ccode=dstud Feed code= sub | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | SP ACAD_SUBJ | no update needed, no dates in variant | In PS1 program runs about 6AM - file may not be received until the afternoon, so the program is running the previous day's file. | [5 empty] | Compared to production processing logs for reasonableness.
50 | Inbound ZTN_MITSIS_SUBJECT_ENROLLMENT (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_MITSIS_ENROLLMENT_IN | none - Provider ccode=dstud Feed code= erl | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | SP ENROLLMENT | no update needed, no dates in variant | [6 empty] | Compared to production processing logs for reasonableness.
51 | Inbound ZTN_LINCOLN_PI_RECONCILER_FEED (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_LINCOLN_PI_RECONCILER_IN | none - Provider ccode=dllte Feed code=pir | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | SP PI_RECON | no update needed, no dates in variant | [6 empty] | Compared to production processing logs for reasonableness.
52 | Inbound ZTN_LINCOLN_PI_TRAINEE_IN (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_LINCOLN_PI_TRAINEE_IN | none - Provider ccode=dllte Feed code=pit | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | SP PI_TRAINEE | no update needed, no dates in variant | [6 empty] | Compared to production processing logs for reasonableness.
53 | Inbound ZTN_LINCOLN_COURSE_COMPLETIONS (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_LINCOLN_COURSE_COMPLETIONS | none - Provider ccode=dllte Feed code=crc | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | SP LL_COMPLS | no update needed, no dates in variant | [6 empty] | Compared to production processing logs for reasonableness.
54 | Inbound ZTN_REMEDY_INTERACTIVE_CONNECTOR (this is a daily feed) (10/21) Not yet running in PS1 need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_LINCOLN_COURSE_COMPLETIONS | none - Provider ccode=dehsw Feed code=ecc | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | SP EHS_ERGO | no update needed, no dates in variant | [6 empty] | Compared to production processing logs for reasonableness.
55 | Inbound LSO TNI DW ORG DLC MAPPING IN (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZTN_DW_ORG_DLC_MAPPING_IN | none - Provider ccode=dinfr Feed code=org | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | SP DLC_ORG_LD | no update needed, no dates in variant | [6 empty] | Compared to production processing logs for reasonableness.
56 | Inbound RCR QUALIFICATION LOAD (this is a daily feed) (10/21) need to have Waiming decrypt file from sapin folder and store on local drive | PGM: ZHRRCR_UPLOAD | none - Provider ccode=dciti Feed code=qlf | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | Select local file and add testers email address | n/a | Check for errors on filezilla | [5 empty] | Compared to production processing logs for reasonableness.
57 | Inbound Student Bio Feed (MITSIS) (10/22-10/27) (Run just up to the date of the exempt payroll execution, which is 10/27/2014). | Trans: ZMITSIS PGM: ZPY_LOAD_MITSIS_BIO_DATA | py/mitsis_dem | 2014-11-04 | 2014-11-04 | Meaghan |  |  | ZZHRMITSIS01 | IB1These 3 must run per day, one after the other | No | n/a | both old and new complete
58 | Inbound Grad Appointment Inbound (this is a daily feed) (10/22-10/27) (Run just up to thedate of the exempt payroll execution, which is 10/27/2014). | Trans: ZPY_LOAD_MITSIS_GRAD PGM: ZPY_LOAD_MITSIS_GRADAID | py/gradaid | 2014-11-04 | 2014-11-04 | Meaghan |  |  | ZZHRGRADAPT01 |  | No | n/a | both old and new complete
59 | Inbound LL daily feed (processed on 10/22-27). Feed files can be identified by running ZHRALELOG. Goal is to process all LL files before ZM processing. May not have files which ran on the 27th, check log. Need to copy unencrypted file to sh2/sapin directory. (8-12) Note: NOT NEEDED 2013 b/c no files were run on 23 LL daily feed (10/23) run thru Wed (before ZM processing) Will run Monday's files after the LL audit files are processed. (13-15) | Trans: ZHRALE PGM: ZHRALE01 | hr/ll_hr_time Provider ccode=mith Feed code= hrm | 2014-11-04 | 2014-11-04 | Karen |  |  | ZZHRLLFEED01 |  | No | n/a | Check for errors on filezilla Validate using transaction ZHRALELOG TBD (may be that Eric will review)
60 | Email: EL training reminder | PGM: ZTN_ACTSEL_NOTIF_TRAINING | N/A | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | No | n/a | Use zehcat entry: HY to not send email | [5 empty] | Verified emails were delivered
61 | Email: EL Expiring quals | PGM: ZTN_EMAIL_LRNR_EXPIRING_QUALS | N/A | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | No | n/a | Use zehcat entry: HY to not send email | [5 empty] | Verified emails were delivered
| Additional Payroll Interface Activities (before planned monthly run) For these interfaces, need to determine if the production snapshot included the input files, if no, process the files before the ZM processing. Otherwise execute ZM processing to test the input process. | Need to coordinate with above inbound run's |  |  |  |  | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
62 | Inbound Metpay Home/Auto inbound; compare reports to prod reports; spot-check the loaded data ( - need to determine for 2014) Copy PS1 file to local directory. Before for 2013 Need to determine if this should be processed before or after ZM payroll - depends on production snapshot date. | Trans: ZPY_METPAY_IN PGM: ZPY_METPAY_IN_BILLDED | py/metp-ded | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Cindy |  |  | ZZPYBATCH001 |  | no |  | 2013: Use PS1 inbound file then compare reports
63 | Monthly Payroll Processing - ZM | Follow Exempt Payroll Checklist |  | 2014-11-04 | 2014-11-04 | MD |  | n/a |  |  |  |  | see results below | n/a | n/a | n/a | n/a | n/a
Notifiy DW ZM has been run and posted, including CDU.
64 | Inbound Weekly Fidelity Percent Inbound; use Friday?? file (10/25); compare reports to prod reports; spot-check the loaded data Copy PS1 file to local directory. AFTER for 2013 Need to determine if this should be processed before or after ZM payroll - depends on production snapshot date. | Trans: ZPYII_FID_PCT PGM: ZPYI002_I_FID_PERLOAD | py/fid_pct | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Cindy |  |  | ZZPYBATCH001 |  | No |  | 2013: Use PS1 inbound file then compare reports Pre-2013: Trigger through drop box in Linux version.
65 | Inbound Weekly Tech Cash Inbound; use Friday?? file (10/25).; compare reports to prod reports; spot-check the loaded data Copy PS1 file to local directory. After for 2013 Need to determine if this should be processed before or after ZM payroll - depends on production snapshot date. | Trans: ZPYII_DED PGM: ZPYI001_I_DEDUCTIONS | py/tech_cash | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Cindy |  |  | ZZPYBATCH001 |  | No |  | 2013: Use PS1 inbound file then compare reports
66 | Payroll Results Comparison (ZM) |  |  | 2014-11-05 | 2014-11-05 | Gregg M. |  | - |  |  |  |  | pernrs
67 | EDACCA TABLE COMPARISON |  |  | 2014-11-05 | 2014-11-05 | Gregg M. |  | - |  |  |  |  | see detail notes tab
68 | FI POSTING COMPARISON |  |  | 2014-11-05 | 2014-11-05 | Gregg M. |  | - |  |  |  |  | lines in document
69 | After ZM 3-Party Processing - Test garnishments to A/P: Run F110 payment process; verify check format and Mass ACH file format. |  |  | 2014-11-05 | 2014-11-05 | Gregg M, Ken LeVie |  | n/a |  |  |  |  | ZM 3PR pp 03.2010 new vs. old are a match - 33 vendor payment line items in each = 100%
| (After Monthly Payroll Payroll Execution) Outbound Interfaces (Comparisons to production files) | [5 empty] | - | [5 empty] | Set up jobs Friday. | n/a | n/a | n/a | n/a | n/a
70 | Outbound Fidelity contributions outbound - monthly Use ZM Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS | PGM: ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Mary |  |  | ZZPYBATCH001 |  | SP_ZM_AUTOMATI | Yes
71 | Outbound FSA contributions outbound - monthly Use monthly variant, change start date/time to before payroll run, check test, enter handliing rule 001 | Trans: ZPYIO_FSA_CONTRIB PGM: ZPYI0170_FSA_CONTRIB | py/fsa_dep | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Emily |  |  | ZZPYBATCH001 |  | SP_Monthly | Yes
72 | Outbound Credit Union contributions Run for dates from PS1's last run email thru end of monthly payrun | Trans: ZPYIO_CU_UNION PGM: ZHRPY_CREDIT_UNION | py/cu | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Emily |  |  | ZZPYBATCH001 |  | SP_VAR_ZM_ZW | Yes
73 | Outbound John Hancock (long term care) contributions | Trans: ZPYIO_HANCOCK PGM: ZPYI006_O_JHK_LTCPRE | py/hancock | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Emily |  |  | ZZPYBATCH001 |  | SP_ZM_ZW | Yes
74 | Outbound TIAA-CREF (457B) contributions (10/27File) | Trans: ZPYIO_TIAA_CREF PGM: ZPY_457B_CONTRIB_OUT | py/tiaa_cref | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Emily |  |  | ZZPYBATCH001 |  | SP__ZMAUTOMATI | Yes
75 | Outbound LL Salary distribution monthly gross pay - send copy to Lincoln, coordinate with Eric. | PGM: ZPY_LL_SALARY_DISTRIBUTIONS | py/ll_sal_dst | 2014-11-04 | 2014-11-04 | Gregg |  |  | ZZPYBATCH001 |  | SP-ZM | Yes
76 | Outbound Pension outbound interface - Employment file (run before | Trans: ZPY_PENSION_EMPL PGM: ZPY_PENSION_EMPLOYMENT | py/pen_empl | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Cindy |  |  | ZZPYBATCH001 |  | no | n/a | Run Sept and Oct for comparisons for reasonability?
77 | Outbound Pension outbound interface -Personal file | Trans: ZPY_PENSION_PERS PGM: ZPY_PENSION_PERSONAL | py/pen_pers | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Cindy |  |  | ZZPYBATCH001 |  | no | n/a | Run Sept and Oct for comparisons for reasonability?
78 | Outbound Pension outbound interface -Compensation file | Trans: ZPY_PENSION_COMP PGM: ZPY_PENSION_COMPENSATION | py/pen_comp | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Cindy |  |  | ZZPYBATCH001 |  | SP Test (for SP2014, ran in PS1 on 10/20 for Sept. | Yes | Compare to PS1 extract run on 10/17 in step ???
79 | Outbound Pension outbound interface -Pay & Hours file | Trans: ZPY_PENSION_CONT PGM: ZPY_PENSION_PAY_HOURS | py/pen_cont | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Mary |  |  | ZZPYBATCH001 | 4 | SP TEST Run for ZM and one week of ZW - use dates 11/3/2014-11/6/2014 | Yes | Balance totals with recon report of 9C93
NEW HIRE Feeds and Reports
80 | Create a new hire employee eligible for work - indicate I9 Office has processed new hire. | PA30/PA40
81 | Inbound ZHR_DW_DEPT_ADMIN_IN (daily) | ZHR_DW_DEPT_ADMIN_IN | hr/mit_I9 | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 Variant DAILY
82 | Update / Outbound ZHR_NEWHIRE_NOTIFICATION (daily) - update - | ZHR_NEWHIRE_NOTIFICATION | not copied here | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 Varinats DAILY_ADD_NH
83 | ZHR_NEW_HIRE_FEED_FOR_ATLAS - outbound - run twice, two variants | ZHR_NEW_HIRE_FEED_FOR_ATLAS | hr/atlas_nh | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | atlas_server1 atlas_server2
84 | Outbound ZHR_NEWHIRE_NOTIFICATION (runs daily every 10 min) Run for 10/21/2014 | ZHR_NEWHIRE_NOTIFICATION | not copied here | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 Variant is EMAIL_I9
85 | Inbound ZHR_DW_TLO_SIGNATURES_IN (runs hourly - event driven). | ZHR_DW_TLO_SIGNATURES_IN | hr/mit_tlo | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 Variant DAILY W/O
86 | Inbound ZHR_DW_MITALERT_IN (daily) | ZHR_DW_MITALERT_IN | hr/mit_alert | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 Variant DAILY W/O
87 | Inbound ZHR_DW_MITIDCARD_IN (daily) | ZHR_DW_MITIDCARD_IN | hr/mit_card | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 Variant DAILY W/O
88 | Report ZUT_CHECK_FEED_PROC (daily) - run with 3 variants Varifies all necessary files receive dfrom DW | ZUT_CHECK_FEED_PROC |  | 2014-11-04 | 2014-11-04 | Run by Desiree with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 variants are: DW MIT ALERT DW MITID CARD DW TLO
Lincoln training history files:
89 | Inboiund ZTN_LINCOLN_TRAINING_HISTORY | ZTN_LINCOLN_TRAINING_HISTORY | use test file from unix directory. | 2014-11-04 | 2014-11-04 | Run by Mary with |  |  | ZZHRELBTCH01 |  |  |  | test for 1 pernr
90 | Outboiund ZTN_LINCOLN_TRAINING_HISTORY | ZTN_LINCOLN_TRAINING_HISTORY |  | 2014-11-04 | 2014-11-04 |  |  |  | ZZHRELBTCH01
| Inbound Interface Comparisons | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
91 | Load LL Daily feed (10/27-10/28) catchup on files after ZM run. - weekly IDOC file - need to copy to test system's sapin directory This is a separate set of files than th lincoln feed in step 40. (13-23) | Trans: ZHRALE PGM: ZHRALE01 | hr/ll_hr_time Provider ccode=mith Feed code= hrm | 2014-11-05 | 2014-11-06 | Karen as LL Batch ID |  |  | ZZHRLLFEED01 | IB3 |  |  | Validate using transaction ZHRALELOG TBD (may be that Eric will review)
92 | Run LL HR/Payroll audit files (10/28/2014) - weekly need to copy to test system's sapin directory - 3 separate files. Once files are in sapin and above step is processed, Lincoln person can execute audit report. | PGM: ZHRALF02 | py/ll_audt_py Provider code=dmith Feed code = paf | 2014-11-05 | 2014-11-06 | Eric |  | -- |  |  |  |  | Validated by Collen in the past
93 | Load LL Daily feed (10/27/2014-10/28/2014 upto ?? files) - weekly IDOC file - need to copy to test system's sapin directory This is a separate set of files than th lincoln feed in step 40. (24-29; and then process 000 as special) | Trans: ZHRALE PGM: ZHRALE01 | n/a | 2014-11-06 | 2014-11-07 | Karen as LL Batch ID |  |  |  | IB3 |  |  | TBD (may be that Eric will review)
94 | Run LL time audit (10/28/2014) - weekly need to copy to test system's sapin directory - 1 file. Once file is in sapin and above step is processed, Lincoln person can execute audit report. | Trans: ZPYII_LL_AUDT_TM PGM: ZHR_AUDIT_LINCOLN_TIME | py/ll_audt_tm Provider code=dmith Feed code = taf | 2014-11-06 | 2014-11-07 | Eric/Colleen Campbell | [6 empty] | TBD (may be that LL will review (ccassidy))
95 | Inbound Run Kronos Feed and compare IT2001/2002 records with change date of (date file was executed, changed by whomever ran the file) or time eval results. (10/28/2014) - weekly need to copy to test system's sapin directory. Warning - cannot repeat run unless first delete first update - will double data if run repeated. Execute by entering exact file name (cut and paste from seletion box) | Trans: ZHR_INBOUND_TIME PGM: ZPTKRONOS_TIME_INBOUND | py/facil_time Provider code=dkron Feed code =ktp | 2014-11-05 | 2014-11-05 | Run by Gregg, validation by Karen |  |  | ZZPYBATCH01 | IB4 |  |  | Can run by chosing decrypted file from local server. Make sure file is consistent with week to be processed - dates must line up!
96 | Inbound Parking Standard Internal deductions - monthly copy to test system's sapin directory (Use 10/17 file if available, change date in file to Nov) need to copy to test system's sapin directory | Trans: ZPYII_DED PGM: ZPYI001_I_DEDUCTIONS | py/parking Provider code=park Feed code = ded | 2014-11-06 | 2014-11-06 | Run by Gregg, validation by Mary |  |  | ZZPYBATCH01 | IB4 |  |  | loaded encrypted through drop box
97 | Inbound Tpass Standard Internal deductions - monthly; (use 10/16 file and change dates to 11/xx/2014) (pre Nov payrun) 4 files, imputed income file is blank. Process 2 file - Van pool and TPass. Will files be received by 11/16 - should we process Oct?? Can copy to local directory - need to change date in file to Nov. THIS Should be the last time to test for SP - new Atlas app replacing feed. | Trans: ZPYII_DED PGM: ZPYI001_I_DEDUCTIONS | py/t_pass Provider code=tark Feed code = ded | 2014-11-06 | 2014-11-06 | Run by Gregg, validation by Mary |  |  | ZZPYBATCH01 | IB4 |  |  | loaded locally
98 | Inbound Long Term Care (John Hancock) - monthly; (use 11/xx/2014 file) (pre Nov payrun) Will files be received by 11/16 - should we process Oct?? Can copy to local directory - need to change date in file to Dec. | PGM: zpyii _hancock | py/hancock Provider code=jhan Feed code = ltb | 2014-11-06 | 2014-11-06 | Run by Gregg, validation by Mary |  |  | ZZPYBATCH01 | IB4
99 | State Quarterly - outbound report - quarterly; Run Q3 2014 | pu19 sui wage reporting |  | 2014-11-07 | 2014-11-07 | Gregg |  | -- |  |  |  |  | count = lines in file
| Lincoln only payrun - testing the inbound LL feed files thru payroll. | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
100 | Run weekly payroll - limited (44/2014). Mary Note: This run will be for only LL run. Test cases after this run will be for week 45/2014. Run payroll for company code LCP1 only. | Follow Non-exempt payroll checklist |  | 2014-11-06 | 2014-11-06 | Gregg M. |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
101 | Run LL gross pay file for weekly outbound for payweek 44 Compare the output to pay week 44. File to be sent to Lincoln for comparison | PGM: ZPY_LL_SALARY_DISTRIBUTIONS | py/ll_sal_dst | 2014-11-06 | 2014-11-06 | Gregg |  | n/a | ZZPYBATCH01 | L5
| Additional payroll tests | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
102 | Update SH2 with any PS1 updates conducted after 10/20: * eW-2 parameters *eW-2 false positives *Update Payroll control records for earliest retro date |  |  | 2014-11-06 | 2014-11-06 | Mary , Gregg,
103 | Create and download 1042-S file Validate ACH File Testing printing: Payroll check DACCA W-2 1099R 1042-S |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
| Test LL files created in their Support Pack QA Environment 2014 - LL not upgrading until after Campus SP (keep in schedue as bookmark for next year). | [12 empty] | n/a | n/a | n/a | n/a | n/a
| Run LL HR/Payroll audit files (11/4/2013) - weekly | ZHRALF02 | py/ll_audt_py | 2013-11-12 | 2013-11-12 | Eric | N/A | -- |  |  |  |  | Start date dependent on progress of previous steps and if LL is ready to generate files. | n/a | n/a | n/a | n/a | n/a
| Load LL daily feed (11/5/2012) - these files will be generated by LL in their QA environment, to test their Support Packs upgrade. (This was not conducted fo SP2010, as LL did not upgrade Support Packs in 2010). | ZHRALE | n/a | 2011-11-14 | 2011-11-14 | Gregg | N/A | [5 empty] | Start date dependent on progress of previous steps and if LL is ready to generate files.
| Run LL time audit (11/5/2012) - weekly | ZPYII_LL_AUDT_TM | py/ll_audt_tm | 2011-11-14 | 2011-11-14 | Eric | N/A
| Open up testing for SIT test cases in ALM | [12 empty] | n/a | n/a | n/a | n/a | n/a
104 | Validate access to sh2 |  |  | 2014-11-04 | 2014-11-04 | All testers
Tests to conduct WHILE Payroll comparisons are executing (no dates prior to Nov 1, 2014)
105 | GRC testing |  |  | 2014-11-04 | 2014-11-07 | Emily Keyur
106 | E-Learning |  |  | 2014-11-04 | 2014-11-21 | Melissa/et al
107 | Exempt (No retro) |  |  | 2014-11-04 | 2014-11-10 | Leslie
108 | Non-Exempt (No retro) |  |  | 2014-11-04 | 2014-11-10 | Leslie
109 | Students (No retro) |  |  | 2014-11-04 | 2014-11-10 | Leslie
110 | ASR |  |  | 2014-11-04 | 2014-11-10 | Adrienne/Emily/Lisa
111 | APR View a transaction |  |  | 2014-11-04 | 2014-11-10 | Leslie
112 | Altas - About Me - Payroll |  |  | 2014-11-04 | 2014-11-10 | Leslie
113 | OM - Payroll |  |  | 2014-11-04 | 2014-11-10 | Leslie & Cindy
114 | OM - HR |  |  | 2014-11-04 | 2014-11-10 | Mike
115 | APR - Front end data entry (no SAP processing) |  |  | 2014-11-04 | 2014-11-10 | Leslie
116 | Altas - About Me -HR |  |  | 2014-11-04 | 2014-11-10 | Diane | N/A
117 | Benefits - Pending EOI, Total Comp |  |  | 2014-11-04 | 2014-11-10 | Mike
118 | Faculty Chair |  |  | 2014-11-04 | 2014-11-10 | Jean D
119 | Pension - date 12/1/2014 or later to execute week of 11/7. |  |  | 2014-11-04 | 2014-11-10 | Diane
120 | Atlas - HR - New Hire, Veterans. |  |  | 2014-11-04 | 2014-11-10 | Kathleen
121 | Atlas - Events |  |  | 2014-11-04 | 2014-11-10
122 | Year End Reporting (Mary,Gregg for support) |  |  | 2014-11-04 | 2014-11-10 | Leslie
| Tests to conduct AFTER Payroll comparisons completed - can contain dates prior to Nov 1, 2014 |  |  | 2014-11-12 | 2014-11-21
123 | Atlas - Payroll transactions - eDACCA, eSDS, time approvals |  |  | 2014-11-12 | 2014-11-21 | Leslie
124 | Exempt (Retros) |  |  | 2014-11-12 | 2014-11-21 | Leslie
125 | Non-Exempt (Retros) |  |  | 2014-11-12 | 2014-11-21 | Leslie
126 | Students (Retros) |  |  | 2014-11-12 | 2014-11-21 | Leslie
127 | APR - SAP backend processing |  |  | 2014-11-12 | 2014-11-21 | Leslie
128 | Execute Cycle 1 Payrolls |  |  | 2014-11-12 | 2014-11-21 | Leslie
129 | Miscellaneous (Gregg, support for garnishment tests) |  |  | 2014-11-12 | 2014-11-21 | Leslie Mary (NRA cases)
| Validations of all above transactions to be completed by 11/24/2014 |  |  |  |  | All
Legend:
Pay run execution
Section Heading
Lincoln Lab

## Pre-test Prep
3/24/2010 EDS In-bound Lump Sum File
3/24/2010 EDS In-bound Annuity File
[6 empty] | complete | 2010-03-08
Student Bio Feed (MITSIS)
Keep LL Audit files
Parking file
TPASS file
Grad Appointment feed
LL Feeds - have Wai-ming copy files to test environment's sapin directory
Archive Directory | Files Copied | # of Files | in/out | can be loaded locally? | task link
hr/bcbs |  |  | out
hr/crosby |  |  | out
hr/crosby_dep |  |  | out
hr/crosby_new |  |  | out
hr/delta |  |  | out
hr/fid_hr |  |  | out
hr/hird |  |  | out
hr/metpcensus |  |  | out
hr/mitsis_dem |  |  | out
hr/vision |  |  | out
py/cu |  |  | out
py/esi |  |  | out
py/facil_leav |  |  | out
py/facil_time |  | 1 | in | No | 82
py/fid_cntrib-weekly |  |  | out
py/fid_cntrib=monthly |  |  | out
py/fid_pct |  |  | in | Yes | 60
py/fsa_census |  |  | out
py/fsa_dep-weekly |  |  | out
py/fsa_dep-monthly |  |  | out
py/fsa_enroll |  |  | out
py/gradaid |  |  | in | Yes | 39
py/hancock |  |  | in | Yes | 77
py/hancock |  |  | out
py/ll_audt_py |  |  | Copy into SAPin to run reports.
py/ll_audt_tm |  |  | Copy into SAPin to run reports.
py/ll_bank |  |  | out
py/ll_leave |  |  | out
py/ll_sal_dst-weekly |  |  | out
py/ll_sal_dst-monthy |  |  | out
py/metp-ded |  | 1 | in | Yes | 50
py/mitsis_tim |  |  | out
py/parking |  | 1/1 | in | No | 75
py/t_pass |  | 1 | in | Yes | 76
py/tech_cash |  | 1 | in | Yes | 49
py/tiaa_cref |  |  | out
hr/mitsis_dem |  | 6/6 | in | Yes | 38
Pension Payroll EDS In-bound Annuity File |  | 1 | in | yes | 9
Pension Payroll EDS In-bound Lump Sum File |  | 1 | in | yes | 8
py/sha_stdt |  | 1 | in | no
py/sha_urop |  | 1 | in | no
dstud/trm |  | 1 | in | no
dstud/sub |  | 1 | in | no
dstud/erl |  | 1 | in | no
dllte/pir |  | 1 | in | no
dllte/pit |  | 1 | in | no
dllte/crc |  | 1 | in | no
deshw/ecc |  | 1 | in | no |  | not running in PS1 for 2012
dinfr/org |  | 1 | in | no
dciti/qlf |  | 1 | in | no
py/pen_empl |  | 1 | out
py/pen_pers |  | 1 | out
py/pen_comp |  | 1 | out
py/pen_cont |  | 1 | out
Lincoln inbound |  |  | in | No

## Suggestions from last Year
| Suggestions for next year (2014) | Action
1 | Test EL portals in SF3/SF2 for all browsers, Mac and Windows. Sanity check, make sure browsers launch, pages look reasonable. Launch a WBT. | Add to SF3 and SF2 checklist
2 | Request from laurie latest copies of all Payroll procedures and checklists. | Request sent, added to prep list
3 | Change SIT authorization for users like Shwn Spencer so they can update IT0105 themselves for ESS testing

## For Next Year
Suggestions for next year (2015)