## SF2 Not Released
Transport | Owner | Date | Time | Description | Team | Responsible Person | Final | Comment
SF2K955296 | LKUSHKUL | 2013-10-24 | 10:16 | HR : Obsolete, do not transport
SF2K956471 | LEVIE | 2013-11-21 | 10:16 | AP: Create 1099 Misc Correction PDF form
SF2K957165 | MZHOVNIR | 2014-03-24 | 10:14 | Creat a report for CSG using SQ01
SF2K954849 | GMCGRATH | 2014-04-07 | 0:12 | PY:**DO NOT TRANSPORT** Block SF2 Payroll Ctrl Record Checks
SF2K954905 | MPRUDDEN | 2014-04-07 | 0:12 | Utility Programs |  |  |  | In progress - Please leave it in SF2.
SF2K955211 | MPRUDDEN | 2014-04-07 | 0:12 | HR: Add "Care Of" to set of fields that reset bad addr flag |  |  |  | In progress - Please leave it in SF2.
SF2K955294 | ROBERTSD | 2014-04-07 | 0:12 | Add new family subtype 91 - RT2256057
SF2K955388 | JRTUTTLE | 2014-04-07 | 0:12 | VPF/SB RT 2344192 Sponsored Billing Cash Report (2) | FI | Keyur Patel |  | Extensive changes to first version: waiting on VPF
SF2K955708 | FULLER | 2014-04-07 | 0:12 | UT: RT#XXXXXXXX Bug fixes to ZUTALORS | Tech Serv | Carolyn Fuller |  | This ZUTALORS transport needs to move to PS1 before the next SF2 refresh
SF2K955756 | FULLER | 2014-04-07 | 0:12 | MM:RT#2489195 Fix download ZFCRS &ZWF_REQ_RELEASE_STRATEGIES | Logistics | Sumukhi Pyla |  | This should have gone to PS1 in Jan 2014 but no one using report in PS1
SF2K955994 | FULLER | 2014-04-07 | 0:12 | UT: Make changes for the 2013 Support Pack Transports | Tech Serv | Carolyn Fuller |  | This Transport Request Utility transport should move to PS1 before the next SF2 refresh
SF2K956242 | EPRUDDEN | 2014-04-07 | 0:12 | MM: Web Req Display (front end) |  |  |  | Work in progress
SF2K956244 | EPRUDDEN | 2014-04-07 | 0:12 | MM: Web Req Display (back end) |  |  |  | Work in progress
SF2K956366 | KNOLET | 2014-04-07 | 0:12 | EHS config A/A types by PSG - 01 custom
SF2K956406 | JHOSKEN | 2014-04-07 | 0:12 | PM: RT#2319899 Documentation | FLE - Faci | Jim Fragala |  | Wai-ming to determine
SF2K956420 | MPRUDDEN | 2014-04-07 | 0:12 | DNT: Changes to ZHR_EMAIL_PROC no longer create transports |  |  |  | In progress - Please leave it in SF2.
SF2K956485 | KNOLET | 2014-04-07 | 0:12 | PCGS_GRP profile add WBS Element
SF2K956609 | REP | 2014-04-07 | 0:12 | R3ADM* SuccessFactors Physical Path for Generated Files
SF2K956657 | FULLER | 2014-04-07 | 0:12 | UT: RT####### Tweaks to ZUT_SEARCH_ABAP | Tech Serv | Carolyn Fuller |  | This should move to PS1 before the next SF2 refresh
SF2K956692 | LEVIE | 2014-04-07 | 0:12 | AP: rt#2562948 setting change for output group
SF2K956716 | MZHOVNIR | 2014-04-07 | 0:12 | #2632421 - to eliminate user stat PICK
SF2K956753 | LEVIE | 2014-04-07 | 0:12 | AP:Enable amount split
SF2K956761 | LEVIE | 2014-04-07 | 0:12 | AP: Tax form fixes
SF2K956882 | EPRUDDEN | 2014-04-07 | 0:12 | CA: New fk mod for gen user info |  |  |  | Work in progress
SF2K956908 | ROTERO | 2014-04-07 | 0:12 | RT 2371338 CPOL Changes to 4/2 Schedule
SF2K956910 | DILIBERT | 2014-04-07 | 0:12 | PY Summer Session Changes
SF2K956962 | DILIBERT | 2014-04-07 | 0:12 | HR Success Factors | HR | Meaghan Murray
SF2K957012 | LKUSHKUL | 2014-04-07 | 0:12 | lk: do not transport
SF2K957108 | SSELIGMA | 2014-04-07 | 0:12 | test service to see if sso tokens can be retrieved from ITS
SF2K957224 | REP | 2014-04-07 | 0:12 | R3ADM* ME9F PO Archiving Output destination
SF2K957308 | MPRUDDEN | 2014-04-11 | 10:28 | DNT: Test of changes to custom HR email config |  |  |  | In progress - Please leave it in SF2.
SF2K957392 | DILIBERT | 2014-04-29 | 11:03 | APR RT2704002 Add position title to inbox | HR | Emily Cunningham
SF2K957355 | MAMURRAY | 2014-04-30 | 10:34 | HR-PA_2648940 New action Retire from LTD | HR-PY | Meaghan Murray |  | Move after support packs
SF2K956573 | MAMURRAY | 2014-04-30 | 10:36 | SFSF_2698751 initial img steps | HR-PY | Meaghan Murray |  | Project delayed - move after support packs
SF2K956970 | MAMURRAY | 2014-04-30 | 10:36 | SFSF_2698751 feature ENTRY; extraction variant | HR-PY | Meaghan Murray |  | Project delayed - move after support packs
SF2K957518 | KNOLET | 2014-05-14 | 11:20 | Remove Absence quota 01 and 02 for grp 02(ex) PSG 47_II
SF2K957553 | EPRUDDEN | 2014-05-16 | 8:07 | MM: RT#???????? RFC for Java Req Display
SF2K957335 | MZHOVNIR | 2014-05-27 | 11:47 | Not! 2680837:List of CLSD Notif/WOs with prv. usr st of CAN*
SF2K957509 | MZHOVNIR | 2014-05-27 | 11:48 | Not! 2680837-1: List of CLSD Notif with prev usr st of CAN*
SF2K957373 | EPRUDDEN | 2014-05-27 | 17:29 | PM: Report for Cancelled Requests |  |  |  | Work in progress
SF2K957665 | LEVIE | 2014-06-02 | 12:02 | AP: remove max dicount flag for CUR in payment config
SF2K957687 | FULLER | 2014-06-05 | 10:18 | RFP: RT#2857157 I/O Error with long text | Logistics | Ken LeVie |  | This is a rarely occurring bug that wipes out all long text when it occurs
SF2K957708 | QIANKANG | 2014-06-09 | 10:36 | R3 Admin DO NOT transport - modify port number EL content
SF2K957117 | SSELIGMA | 2014-06-09 | 15:46 | Utiliy service for generating mysapsso2 tokens
SF2K957943 | KNOLET | 2014-07-15 | 11:16 | 2855797_exclude L304,L305,L306 from Rule=081 count LWOP
SF2K957345 | JRTUTTLE | 2014-07-22 | 13:24 | EHS RT 1010990 Correct Room Rep Authorizations (Not yet!) | EHS | Nivedita Dhiman |  | Incomplete changes: changes commented out
SF2K958147 | MZHOVNIR | 2014-08-12 | 14:53 | Query Z_PM_WO_STLM_PER
SF2K958226 | LEVIE | 2014-08-28 | 9:08 | AP: 1042S DMEE File updates for 2014
SF2K958259 | JRTUTTLE | 2014-09-10 | 11:18 | AP RT 2944862 Add company code selection to AP SOD Report 10 | AP | Ken LeVie
SF2K958279 | LMA | 2014-09-11 | 12:51 | RT 1714388: MM-PO Close/Final Invoice Indicator | MM | Ken LeVie (Should be |  | Waiting for the new requirements and can wait after Support Pack
SF2K958293 | LMA | 2014-09-16 | 10:15 | RT 2928032: PM-Treat status CANC/CANF as CLSD | PM | Margarita Zhovnirovs |  | After Support Pack
SF2K958300 | MZHOVNIR | 2014-09-17 | 12:35 | test CAN for CANF & CACC
SF2K958315 | GEORGEP | 2014-09-22 | 8:17 | R3ADM* RT2982031 Pgms to Maintain ExtID type SA (GEORGEP
SF2K958352 | MPRUDDEN | 2014-09-26 | 10:23 | HR-BEN: OE 2014/15 Commenting |  |  |  | In progress - Please leave it in SF2.
SF2K958376 | DILIBERT | 2014-09-30 | 12:23 | HR Comp Extract for Mendix | HR | Cindy DeSimone/Emily
SF2K958437 | MPRUDDEN | 2014-10-07 | 9:07 | HR-PT: Change distribution relief pgm to include vaca payout |  |  |  | In progress - Please leave it in SF2.
SF2K958456 | EPRUDDEN | 2014-10-08 | 14:46 | dnt: back out |  |  |  | Work in progress - I'll be backing this out once I'm done with it.
SF2K958458 | FULLER | 2014-10-08 | 15:26 | MM: RT#XXXXXXXX Control Characters causing short dumps | Logistics | Adina Ion |  | Don't know if this effort to replace non-printable characters will be resurrected
SF2K958304 | FULLER | 2014-10-10 | 15:17 | JV: RT#2929468 Atlas 4 Workflow Report | Atlas | Larissa Kushkuley |  | This is new development for Atlas 4 but might not be used. Save code for possible enhancement later.
SF2K956888 | LMA | 2014-10-16 | 15:56 | DOF: ZDF00 report (Sync with PS1) | DoF | Keyur Patel |  | Removed all the changes and synchronized Production version
SF2K958510 | EDUTOIT | 2014-10-18 | 13:30 | Commuting benefits - RFC updates
SF2K958516 | REP | 2014-10-23 | 16:10 | R3ADM* Post-EHP7-SPS6 Orphaned Note Adjustments
SF2K958520 | EDUTOIT | 2014-10-24 | 10:52 | New Hire - Money matters fix
SF2K958522 | ELENA | 2014-10-24 | 11:28 | Alter to allow correct destination for extract files
SF2K958527 | GEORGEP | 2014-10-24 | 17:14 | R3ADM* RT2949139 Correct Exclude IDs option (GEORGEP
SF2K958529 | EDUTOIT | 2014-10-26 | 17:32 | Commuter Benefits - Configuration
SF2K958531 | JA17661 | 2014-10-27 | 9:03 | 3024977_LOG_PM_Turn off auto creation of notif for CREP CPM

## SF2 Released not in SH1
Transport | Owner | Date | Time | Description | Team | Responsible Person | Final | Comment
SF2K952496 | LMA | 2013-04-15 | 22:51 | RT 1714388/2171053: PO Close - Add Date check to ALL Items | EFL | Sumukhi Pyla |  | Business may decide to do this enhancement in 2014, keep it - Can be obsolete
SF2K954605 | LMA | 2013-04-15 | 22:51 | RT 2171053: SOD Changes to ZMMLIQPO_A | EFL | Sumukhi Pyla |  | Business may decide to do this enhancement in 2014, keep it - Can be obsolete
SF2K954723 | LMA | 2013-04-15 | 22:52 | RT 1714388: PO Close - output for background process | EFL | Sumukhi Pyla |  | Business may decide to do this enhancement in 2014, keep it - Can be obsolete
SF2K954727 | LMA | 2013-04-15 | 22:52 | RT 1714388: PO Close - output for background process 2 | EFL | Sumukhi Pyla |  | Business may decide to do this enhancement in 2014, keep it - Can be obsolete
SF2K954751 | LMA | 2013-04-15 | 22:53 | SF2 Refresh: synchronized Production version SF2K948248 | EFL | Sumukhi Pyla |  | Business may decide to do this enhancement in 2014, keep it - Can be obsolete
SF2K952267 | LCOLLIER | 2013-04-16 | 0:29 | EHS 1376921 SARA Reporting - Add MA State Tier II Info | EHS | Lee Collier |  | Please do NOT abandon
SF2K952518 | LCOLLIER | 2013-04-16 | 0:30 | EHS 1376921 - SARA Tier II Fields | EHS | Lee Collier |  | Please do NOT abandon
SF2K953621 | JRTUTTLE | 2013-04-16 | 0:32 | AP RT 2171035 AP SOD Issue 3 & 10 Report Fixes & Adjustments | Logistics | Ken LeVie |  | May go to production eventually
SF2K948151 | WAIMING | 2013-04-16 | 0:33 | Other obsolete programs | SF2K950615 | Waiming |  | we should move to SH2 and PS1
SF2K941434 | MPRUDDEN | 2013-04-16 | 0:33 | UPG: Mark old HR programs as obsolete | HRPY | Frank Quern |  | Should move to PS1 eventually, so please do not abandon.
SF2K955334 | JRTUTTLE | 2013-07-24 | 12:13 | VPF/SB RT#2344192 Sponsored Billing Cash Report | FI | Keyur Patel |  | First version; extensive changes (unreleased): waiting on VPF
SF2K956621 | GEORGEP | 2013-12-13 | 10:52 | R3ADM* RT2605442 Replace ' ' as CC 4 F_KNA1_BUK (MIRELLAV
SF2K956777 | RKATKOWS | 2014-01-17 | 8:07 | Role Z_DF_PREVENTIVEMAINT
SF2K956856 | MZHOVNIR | 2014-01-27 | 10:38 | 2622856: to allow SEMO services on leased buildings
SF2K956868 | REP | 2014-01-30 | 9:57 | R3ADM* Events Management Development Package (ZEM0)
SF2K956972 | GEORGEP | 2014-02-19 | 16:24 | R3ADM* RT2457273 ZHRLOGSUMM - View IT Chg Logs (MAMURRAY
SF2K957065 | GEORGEP | 2014-03-06 | 16:50 | R3ADM* RT2696521 Add ZSR1, ZSDAGE to role (MIRELLAV)
SF2K957143 | SQUIGLEY | 2014-03-19 | 16:22 | R3ADM* RT 2715277- Add MC44 to Z_FF_S_PLT_PLANT_SUPT
SF2K957167 | MZHOVNIR | 2014-03-27 | 12:49 | 2722773 - Create a CSG report
SF2K957178 | REP | 2014-04-02 | 14:58 | R3ADM* SAML Enablement
SF2K957237 | GEORGEP | 2014-04-03 | 10:31 | R3ADM* RT2586162 AuGr for pgm ZPY_TOTAL_COMP (DILIBERT
SF2K957280 | SQUIGLEY | 2014-04-08 | 16:03 | SAPADM* Add MC44 to Z_FF_S_PLT_PLANT_SUPT
SF2K957495 | GEORGEP | 2014-05-09 | 15:48 | R3ADM* RT2781302 Add ZUT_UNIX_LS_CMD to DEV FF Role (SNC
SF2K957669 | GEORGEP | 2014-06-02 | 15:45 | R3ADM* RT2787397 View Req&PO Attachments (AION,SC16196
SF2K957427 | GEORGEP | 2014-06-19 | 9:29 | R3ADM* RT2787473 Revert to ...503 (=PS1 version) (GEORGEP
SF2K957222 | GEORGEP | 2014-06-19 | 13:13 | R3ADM* RTxxxxxxx Revised R3Admin mail (GEORGEP
SF2K957811 | GEORGEP | 2014-06-25 | 7:43 | R3ADM* RT2676468 Au Grp ZEVTAUTH for EVENTS (LKUSHKUL
SF2K957860 | LKUSHKUL | 2014-06-26 | 17:23 | HR New Hire app: missing data type
SF2K957888 | LKUSHKUL | 2014-07-02 | 12:48 | Hr Events #38 - table of room links values
SF2K957904 | GEORGEP | 2014-07-07 | 17:14 | R3ADM* RT2890966 New AuGr for EqiFax Feed Pgm (FULLER
SF2K957964 | GEORGEP | 2014-07-15 | 15:44 | R3ADM* RT2852612 View Tables Role for FAC Analysts (MZHOVNIR
SF2K958323 | GEORGEP | 2014-09-22 | 17:21 | R3ADM* RT2983197 Set up for assign to BusHelp (KLYONS
SF2K958141 | GEORGEP | 2014-09-23 | 11:49 | R3ADM* RT2949139 NO TRANSPORT
SF2K958143 | GEORGEP | 2014-09-23 | 11:49 | R3ADM* RT2949139 NO TRANSPORT
SF2K957455 | GEORGEP | 2014-09-23 | 11:51 | R3ADM* RT2928812 New Tbl AuGr for Atlas Sec Opt out (EDUTOIT
SF2K954885 | GEORGEP | 2014-10-17 | 23:53 | R3ADM* Objects for George Utils | R3Admin | George Petrowsky |  | Released: Eventually will go to Prod before next SF2 Refresh
SF2K957090 | GEORGEP | 2014-10-17 | 23:54 | R3ADM* RTxxxxxxx New AuGr ZEV1 for EVENTS Tbls (LKUSHKUL)
SF2K956316 | GEORGEP | 2014-10-17 | 23:54 | R3ADM* Note: 1864062 - No Transport
SF2K956318 | GEORGEP | 2014-10-17 | 23:55 | R3ADM* Note: 1864062 - No Transport
SF2K956343 | GEORGEP | 2014-10-17 | 23:55 | R3ADM* RT2319899 New AuGr for FAC: ZPMTEMWK
SF2K956680 | GEORGEP | 2014-10-17 | 23:56 | R3ADM* RTxxxxxxx Structure for Profiles Input (GEORGEP
SF2K956912 | GEORGEP | 2014-10-18 | 0:14 | R3ADM* RT3016574 Updated Kerberos ID Load
SF2K956918 | GEORGEP | 2014-10-18 | 0:16 | DON'T TRANSPORT 3ADM* RTxxxxxxx Rev'd Vsn LOAD
SF2K956937 | GEORGEP | 2014-10-18 | 0:16 | R3ADM* RT2677661 New AuGr for HR Success Factors: ZHRSF001
SF2K957793 | GEORGEP | 2014-10-18 | 0:50 | R3ADM* RTxxxxxxx Copy SAPMSUU0_OLD (SU01_OLD) to Z Version
SF2K958514 | SQUIGLEY | 2014-10-21 | 16:12 | R3ADM* RT 3019743 Add 2 tcodes to Z_FF_S_HCM_PY role
SF2K958518 | REP | 2014-10-23 | 16:21 | R3ADM* Post-EHP7-SPS6 Orphaned Note RESETS
SF2K958524 | LKUSHKUL | 2014-10-24 | 15:12 | JV: RT#2951047 - Atlas Journal Vouchers (2)
SF2K958533 | GEORGEP | 2014-10-27 | 9:06 | R3ADM* RT3023070 Add IW21,22,23 w notif. ZC,ZE (JA17661

## SF2 Released in SH1 not in PS1
Transport | Owner | Date | Time | Description | Team | Responsible Person | Final | Comment
SF2K956655 | GEORGEP | 2014-03-03 | 12:20 | R3ADM* RT2616427 Add 2 S_WF_WI 16, NO_CLASS (LEVIE)
SF2K956682 | GEORGEP | 2014-03-03 | 12:23 | R3ADM* RT2614599 Add SCU3 to R3ADMIN Supprt Role (REP
SF2K956684 | JHOSKEN | 2014-03-03 | 12:24 | PM: RT#2616473 Suppress I Messages in BI
SF2K956714 | GEORGEP | 2014-03-03 | 12:26 | R3ADM* RT2365121 FS Doc Type (JV) Role 4 FAR (MIRELLAV)
SF2K956779 | RKATKOWS | 2014-03-03 | 12:30 | Role Z_DF_PREVENTIVEMAINT - Preventive Maintenance
SF2K956789 | RKATKOWS | 2014-03-03 | 12:31 | Role Z_DF_PREVENTIVEMAINT - Preventive Maintenance
SF2K956726 | DILIBERT | 2014-03-03 | 12:32 | TM CC Facil/Police/LL on leave w/out pay reductions RT245082 | payroll | Karen Nolet |  | going after support packs
SF2K957147 | SQUIGLEY | 2014-03-19 | 17:08 | R3ADM* RT 2715277 Add MC44 to Z_FF_S_PLT_PLANT_SUPT
SF2K957578 | LKUSHKUL | 2014-05-19 | 11:30 | HR Events: not for PS1!! Clean up program only
SF2K957595 | GMCGRATH | 2014-06-06 | 15:22 | PY:Correct union dues calc in OC adj runs (344182)
SF2K957862 | LKUSHKUL | 2014-06-26 | 17:47 | HR New Hire app: two new data elements to correct transport
SF2K957953 | GEORGEP | 2014-07-15 | 9:03 | R3ADM* RT2900543 Addt'l Auths Req'd for Function (MZHOVNIR
SF2K957980 | GEORGEP | 2014-07-18 | 8:22 | R3ADM* RT2880071 Add Maint Tbl ZCOOBJECT to role (MIRELLAV
SF2K958079 | EDUTOIT | 2014-07-30 | 12:09 | New Hire - Update text for MIT ID Card Tile
SF2K957896 | DILIBERT | 2014-08-01 | 13:46 | PY: RT#2881254 Equifax Employment Verification Service | payroll | Meaghan Murray |  | in production by 10/28
SF2K958090 | DILIBERT | 2014-08-01 | 15:38 | PY Equifax RT2881254 Part2 | payroll | Meaghan Murray |  | in production by 10/28
SF2K957714 | GMCGRATH | 2014-08-04 | 13:37 | PY:Correct union dues calc in OC adj runs (344182) #2
SF2K958092 | DILIBERT | 2014-08-05 | 10:40 | PY RT 2881254 Empl verify part 3 | payroll | Meaghan Murray |  | in production by 10/28
SF2K958111 | DILIBERT | 2014-08-06 | 8:02 | PY RT2881254 Equifax perfomance part 4 | payroll | Meaghan Murray |  | in production by 10/28
SF2K958163 | DILIBERT | 2014-08-18 | 13:25 | PY RT2881254 Equifax Emp Verify | payroll | Meaghan Murray |  | in production by 10/28
SF2K958178 | DILIBERT | 2014-08-19 | 8:51 | PY RT 2881254 Equifax | payroll | Meaghan Murray |  | in production by 10/28
SF2K958085 | GEORGEP | 2014-08-25 | 14:21 | R3ADM* RT 2949139 Add User Group adjustment to Pgm
SF2K958208 | GEORGEP | 2014-08-26 | 8:43 | R3ADM* RT2949139 Chg Tbl Maint Type (GEORGEP
SF2K958210 | GEORGEP | 2014-08-26 | 8:45 | R3ADM* RT2949139 Control Table Entries (GEORGEP
SF2K958216 | GEORGEP | 2014-08-27 | 14:55 | R3ADM* RT2949139 Small Adjustments (GEORGEP
SF2K958224 | GEORGEP | 2014-09-08 | 15:57 | R3ADM* RT2949139 Fix IS&T Determination
SF2K958249 | GEORGEP | 2014-09-09 | 15:59 | R3ADM* RT2949139 Reduce unnec processing (GEORGEP
SF2K957801 | DILIBERT | 2014-09-10 | 9:33 | TM time management report RT2671645 | payroll | Karen Nolet |  | going after support packs
SF2K958254 | GEORGEP | 2014-09-10 | 13:43 | R3ADM* RT2949139 Determine User Type / Group (GEORGEP
SF2K958269 | GEORGEP | 2014-09-10 | 17:25 | R3ADM* RT2949139 Fix output rept error, reduce msgs (GEORGEP
SF2K958271 | GEORGEP | 2014-09-12 | 16:02 | R3ADM* RT2949139 correct profile check (GEORGEP
SF2K958196 | DILIBERT | 2014-09-16 | 10:02 | PY RT2881254 Per end dates & hist program | payroll | Meaghan Murray |  | in production by 10/28
SF2K958291 | DILIBERT | 2014-09-16 | 13:16 | RT2881254 emp verify historical load | payroll | Meaghan Murray |  | in production by 10/28
SF2K958298 | DILIBERT | 2014-09-22 | 10:19 | PY RT2881254 Equifax fixes | payroll | Meaghan Murray |  | in production by 10/28
SF2K958027 | GEORGEP | 2014-09-23 | 11:52 | R3ADM* RT2949139 Remove User Group Maint (GEORGEP
SF2K958335 | DILIBERT | 2014-09-26 | 10:33 | py emp verify LTD hire dates RT2881254 | payroll | Meaghan Murray |  | in production by 10/28
SF2K958360 | DILIBERT | 2014-09-29 | 11:07 | PY Emp verify blank period end date | payroll | Meaghan Murray |  | in production by 10/28
SF2K958362 | DILIBERT | 2014-09-30 | 9:08 | py Equifax history RT2881254 | payroll | Meaghan Murray |  | in production by 10/28
SF2K958087 | WAIMING | 2014-10-01 | 15:21 | Infrastructure: SAP USER logon with SAP SSO ticket
SF2K958139 | WAIMING | 2014-10-01 | 15:23 | ASAPI RFC white list configuration
SF2K958348 | WAIMING | 2014-10-01 | 15:24 | SAP API: Whitelist for CSAIL Project
SF2K958404 | GEORGEP | 2014-10-01 | 15:37 | R3ADM* RT2985678 Role for CSAIL Purch Revw/Appr App (SBMIT
SF2K958337 | LMA | 2014-10-01 | 15:49 | RT 2985678: RFC-s for Mendix CSAIL project |  | Doug Walsh
SF2K958408 | LMA | 2014-10-01 | 16:22 | RT 2985678: RFC-s for Mendix CSAIL project - 2 |  | Doug Walsh
SF2K958102 | DILIBERT | 2014-10-06 | 15:41 | APR RT2904807 Dean WF issue | payroll | Cindy DeSimone |  | in production by 10/28
SF2K958422 | DILIBERT | 2014-10-06 | 16:06 | PY Pension Reverse Feed add trailer totals RT2972043 | payroll | Mary Donovan |  | in production by 10/28
SF2K958460 | GEORGEP | 2014-10-09 | 9:07 | R3ADM* RT2985678 New AuObj Z_CSAIL_PR (SBMIT,LMA
SF2K958468 | DILIBERT | 2014-10-10 | 13:20 | py RT 2881254 Excl Phased Rehab fix neg & sort | Rpayroll | Meaghan Murray |  | Going to production before support packs
SF2K958466 | EPRUDDEN | 2014-10-10 | 14:45 | MM: RT#3005104 Retrieve material group description |  |  |  | Now in SH1 and I believe will be moved to PS1 before freeze
SF2K958478 | GEORGEP | 2014-10-10 | 15:54 | R3ADM* RT2881254 Add Equifax feed Trans to role (MAMURRAY
SF2K958482 | GEORGEP | 2014-10-10 | 16:57 | R3ADM* RT2881254 Add Equifax Trans to Feed Role (MAMURRAY
SF2K957921 | REP | 2014-10-16 | 12:24 | R3ADM* DevClass/Package ZJV0 for Journal Voucher Development | Atlas |  |  | Atlas 4.0
SF2K957945 | JDUDLEYK | 2014-10-16 | 12:27 | JV: RT#2951047 - Atlas Journal Vouchers | Atlas |  |  | Atlas 4.0
SF2K957941 | JDUDLEYK | 2014-10-16 | 12:30 | JV: RT#2951047 - Atlas Journal Vouchers Customizing | Atlas |  |  | Atlas 4.0
SF2K958121 | FULLER | 2014-10-16 | 12:35 | JV: RT#2929468 Add eff dates to Z_CO_GET_COST_OBJECT_TYPE | Atlas | Kevin Lyons |  | Atlas 4.0
SF2K958174 | FULLER | 2014-10-16 | 12:36 | AP: RFP RT#2912452 URL for RFP changed to SearchSapDrillDown | Atlas/AP | Ken LeVie/K Lyons |  | Contains RFP & Atlas 4.0 JV code expected in PS1 with 2014 Support Pack
SF2K958462 | GEORGEP | 2014-10-16 | 12:38 | R3ADM* RT2945716 New Role for Atlas JV (LKUSHKUL, KLYONS | Atlas |  |  | Atlas 4.0
SF2K958470 | REP | 2014-10-16 | 12:39 | R3ADM* ATLAS/Community Global Document Types for JVs | Atlas |  |  | Atlas 4.0
SF2K958474 | REP | 2014-10-16 | 12:40 | R3ADM* ATLAS/Community ARCHIVELINK Object Links for JVs | Atlas |  |  | Atlas 4.0
SF2K958476 | GEORGEP | 2014-10-16 | 12:41 | R3ADM* RT2945716 New Atlas JV roles (SA & FY) (KEYURPB
SF2K958062 | EDUTOIT | 2014-10-16 | 12:46 | Commuting Benefits - Initial Development | Atlas |  |  | Atlas 4.0
SF2K958157 | EDUTOIT | 2014-10-16 | 12:47 | Commuting Benefits - Config data | Atlas |  |  | Atlas 4.0
SF2K958200 | GMCGRATH | 2014-10-16 | 12:48 | PY:Commuter Benefits Payroll Changes for Atlas | Atlas |  |  | Atlas 4.0
SF2K958496 | EDUTOIT | 2014-10-16 | 12:51 | Commuting Benefits - Program updates | Atlas |  |  | Atlas 4.0
SF2K958480 | GEORGEP | 2014-10-16 | 14:10 | R3ADM* RT2951057 Add ZHR_CBEN FuGr to ESS role (EDUTOIT | Atlas |  |  | Atlas 4.0
SF2K958498 | EDUTOIT | 2014-10-17 | 10:16 | Commuting Benefits - RFC updates
SF2K958500 | LKUSHKUL | 2014-10-17 | 12:14 | Atlas4-JV #2
SF2K958502 | LKUSHKUL | 2014-10-17 | 12:17 | Atlas-JV #3 customizing
SF2K957935 | LKUSHKUL | 2014-10-17 | 15:09 | HR New Hire: add more data validations
SF2K958504 | GEORGEP | 2014-10-17 | 15:59 | R3ADM* RT2951047 New Roles for JVs (Atlas) (KEYURPB
SF2K958508 | GEORGEP | 2014-10-20 | 6:55 | R3ADM* RT2949139 Comment out UserGroup Maint (GEORGEP
SF2K958506 | GEORGEP | 2014-10-20 | 13:35 | R3ADM* RT2951057 ESS T-Pass Access (KNOLET, MAMMURAY

## SF3 Mods in SF2 not in SH1
Transport | Owner | Date | Time | Description | Team | Responsible Person | Final | Comment
SF3K904121 | REP | 2014-03-14 | 13:20 | R3ADM* OSS 1981391 - Display of HRSFI tables in SE16
SF3K904134 | RKATKOWS | 2014-05-01 | 11:17 | R3ADM* OSS 1913828 - Short dump CX_SY_REF_IS_INITIAL.
SF3K904175 | REP | 2014-10-22 | 15:32 | R3ADM* OSS 1720495 SNOTE Invalid note deimplementations
SF3K904177 | REP | 2014-10-22 | 15:32 | R3ADM* OSS 1910464 -Processing SPDD-related note corrections
SF3K904179 | REP | 2014-10-22 | 15:33 | R3ADM* OSS 1279687 ERP6-EHP7-SPS6 Required PreUpdate Note
SF3K904181 | REP | 2014-10-22 | 15:34 | R3ADM* OSS 1941711 ERP6-EHP7-SPS6 Required PreUpdate Note
SF3K904183 | REP | 2014-10-22 | 15:34 | R3ADM* OSS 1994245 ERP6-EHP7-SPS6 Required PreUpdate Note
SF3K904185 | REP | 2014-10-22 | 15:37 | R3ADM* OSS 1861585 ERP6-EHP7-SPS6 Required PreUpdate Note
SF3K904187 | RKATKOWS | 2014-10-23 | 14:44 | R3ADM* OSS 1976932 - reimplemnet
SF3K904189 | RKATKOWS | 2014-10-23 | 14:45 | R3ADM* OSS 1995948 - reimplement after support packs
SF3K904191 | RKATKOWS | 2014-10-23 | 14:45 | R3ADM* OSS 454352 - reimplement after support packs
SF3K904193 | REP | 2014-10-23 | 15:01 | R3ADM* Post-EHP7-SPS6 Obsolete SAP Note Resets
SF3K904195 | REP | 2014-10-23 | 15:23 | R3ADM* Post-EHP7-SPS6 SAP Note 1976932 Reset
SF3K904207 | REP | 2014-10-23 | 15:23 | R3ADM* Post-EHP7-SPS6 VBRP~Z1 Index RESET to Original
SF3K904211 | REP | 2014-10-23 | 15:23 | R3ADM* Post-EHP7-SPS6 VBRP~Z1 Index Version Management
SF3K904215 | REP | 2014-10-23 | 15:23 | R3ADM* Post-EHP7-SPS6 2013-Y/E Tax Reporter Form Obj. RESETs
SF3K904217 | REP | 2014-10-23 | 15:23 | R3ADM* Post-EHP7-SPS6 SAP Note 1976932 SFPI.VET1+VETA Resets
SF3K904205 | FQUERN | 2014-10-23 | 15:23 | PP: RPCMASUT_USTAX_INDEP mod for 1099-R Processing
SF3K904209 | FQUERN | 2014-10-23 | 15:24 | PP: RPCMASUT_USTAX_CALC mod for suppl tax types multdistcode
SF3K904213 | LKUSHKUL | 2014-10-23 | 15:24 | HR-PY: SAP SP 2014 IT0000 mod
SF3K904225 | REP | 2014-10-23 | 15:49 | R3ADM* Local request SF3K904199(EPRUDDEN) Object Transport
SF3K904226 | REP | 2014-10-23 | 15:50 | R3ADM* Local request SF3K904201(EPRUDDEN) Object Transport
SF3K904227 | REP | 2014-10-23 | 15:51 | R3ADM* Local request SF3K904203(MPRUDDEN) Object Transport
SF3K904228 | REP | 2014-10-23 | 15:51 | R3ADM* Local request SF3K904197(FULLER) Object Transport
SF3K904229 | REP | 2014-10-23 | 15:52 | R3ADM* Local request SF3K904219(FULLER) Object Transport
SF3K904230 | REP | 2014-10-23 | 15:52 | R3ADM* Local request SF3K904221(FULLER) Object Transport
SF3K904231 | REP | 2014-10-23 | 15:53 | R3ADM* Local request SF3K904223(FULLER) Object Transport
SF3K904238 | REP | 2014-10-24 | 17:36 | R3ADM* OSS 1943974 -Payroll Short Dump after Note 1852687

## SF3 Mods in SF2 SH1 not in PS1
Transport | Owner | Date | Time | Description | Team | Responsible Person | Final | Comment