## Sheet1
R3-Administration Post HWR Action Log
Post SAP ERP migration ERP system actions
-- Check O/S environment
-- Obtain and install SAP license keys for SAP Central Instance and Central Instance failover servers
-- Apply adjustments to SAP Oracle Database and Application Server parameter/profile files
-- Start SAP ERP system components
-- Execute Oracle Dictionary, System, Table Statistics generations
-- Execute Table Histogram Statistics (for ESDS query)
-- Execute SE37 function Z_HR_RETRIEVE_MITID to test MITID connectivity
-- Execute SE38 RPUBTCU0 to test ERP to BSI/TaxFactory connectivity
-- Execute RTCCTOOL utility program
-- Test ssh handshaking with EDI production server
-- Test ssh handshaking with “sapdbmon” account
-- Test system to system RFC trusted connections
-- Test SAP system web (HTTPS and RFC) connectivity
-- Execute user maintenance report/program tests
------ Warehouse(MOIRA/Kerberos) data sync
------ Extid maintenance generation
-- Start ST01 Authorization trace on all PS1 servers first
Post SAP ERP migration SAP ADS R3-Admin Actions
-- Restart SAP ADS system DSP
-- Validate the ADS RFC connection from production to ADS server “DSP”
-- Execute ADS test reports in ERP
------ FP_CHECK_DESTINATION_SERVICE (Test Program for Destination Service of Templates)
------ FP_PDF_TEST_00 (Test Program: Version Information (for Analysis Only))
------ FP_TEST_00 (Form Processing: Central Test Program)
------ FP_TEST_03 (Flight Booking Example)
Post SAP ERP migration SAP Portal R3-Admin Actions
-- Restart SAP PORTAL system JP6
-- R3-admin validations (system related) to ensure all connections to ERP
-- Web-based course validation
Post SAP ERP migration SAP GRC Validations
-- Restart SAP GRC system ACP
-- Test running background jobs that connect to SAP ERP
-- Firefighter Validation
------ Execute GRAC_SPM Pass
------ Double click on the logon button for the appropriate FF test ID to log into it.
------ Execute sample transactions in PS1 with the Firefighter id.
------ Run Firefighter Log Synch job
------ After Controller returns Firefighter session log, click on link in email, enter requested comments. Pass
------ Click Return button to return the log to the Controller
-- Firefighter Controller Validation
------ Controller receives initial notification email, indicating tester has logged into the Firefighter ID
------ Controller receives a second email with link to Firefighter session log
------ Click on link to Firefighter log in second Controller email to view details of the Firefighter session
------ Under Other Actions, Select 'Additional Information'
------ Enter comments, such as 'Please include ticket number'
------ Click Return button to return the log to the Firefighter
------ After log is returned by the Firefighter with comments, click submit button to approve the log
-- Execute NWBC
------ Ensure NWBC can be accessed by clicking the link for GRC Production (ACP)
https://menkar.mit.edu:44375/nwbc/?sap-client=330&sap-language=EN&sap-nwbc-node=root Pass
------ On My Home tab, ensure you can double click on the Work Inbox link to view other pending Firefighter logs. Pass
------ Run Firefighter Log Summary Report on Reports and Analytics tab, on right side under Emergency Access Management Reports Pass
------ GRC Report Testing
-------- Risk Violations
-------- User Analysis
-------- User Level
-------- Role Level