## Communication & Contacts
Communication
An IS&T telephone number (617-324-7468) will carry a message as to the status of the upgrade beginning at noon on Friday 2/20 through noon on Monday 2/23. The Project Manager will update this message as needed. A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 2:30pm on Sunday.
Voicemail With Status: 617-324-7468
Conference Call Line: Webex
Call-in toll number (US): 617-324-0000 Saturday Access code: Sunday Access code:
Project wiki link: | https://wikis.mit.edu/confluence/display/sapscripts/2014+Year+End+SAP+Support+Pack+Project
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via voice message, email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
Contact Information
Area | Name – Location | Contact Telephone # | Email
A/P | Cathy Cherico – NE49 | Refer to online directory | CHERICO
VPF | Clarel Auguste – NE49 | 617-253-8488 | cauguste@mit.edu
VPF – Travel | Andrea Siegel - Off Campus | Contact PM | amsiegel@mit.edu
Dept. of Facilities | Bob Leonard – NE49 | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher – Off Campus | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix | Contact PM | lstcroix@mit.edu
EHS | Laurie Veal – Off Campus | Contact PM | veal@mit.edu
EHS | Joe MacLeod - Off Campus | Contact PM | jmacleod@mit.edu
HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu
HR/Benefits | Diane Johnston – Off Campus | Contact PM | djohnsto@mit.edu
HR/Benefits | Kathleen Flynn – Off Campus | Contact PM | kflynn@mit.edu
EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White – Off Campus | Contact PM | jwc@mit.edu
Procurement | Cindy Vye - NE49 | Contact PM | CI24314
Procurement | Cecilia Talamates – NE49 | Contact PM | cctala@mit.edu
Procurement | Jeff Rosa – Off Campus | Contact PM | jrosa@mit.edu
Procurement | Minerva Tirado -NE49 | Contact PM | MINERVA
Procurement | David Petricone - Off Campus | Contact PM | PETRICON
Procurement | Kimberly Harmon – Off Campus | Contact PM | kharmon@mit.edu
VPF – HR/Payroll | Leslie Wright – NE49 | 617-253-7715 | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Contact PM | darrenjs@mit.edu
VPF – HR/Payroll | Kristen McCormick | Contact PM | cassidyk@mit.edu
VPF – HR/Payroll | Nicole Valente | Contact PM | nferrant@mit.edu
VPF – HR/Payroll | Lilian Garcia | Contact PM | llg@mit.edu
VPF – HR/Payroll | Jen Quintero | Contact PM | jen_quin
VPF – HR/Payroll | Chris Durham – NE49 | Refer to online directory | cfdurham
IS&T – QA | Debra Wiley | Refer to online directory
IS&T - QA |  | Contact PM
IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu
IS&T - ERP System Manager | Bart Dahlstrom – W92 | Refer to online directory | bartd@mit.edu
IS&T - FI / EHS team lead | Siobhan Cunningham – W92 | Refer to online directory | snc@mit.edu
IS&T – Logistics | Adina Ion – W92 | Refer to online directory | aion@mit.edu
IS&T - FI Team | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu
IS&T - FI Team | Keyur Patel – W92 | Refer to online directory | keyurpb@mit.edu
IS&T - FI Team | Sandeep Nadendla - W92 | Contact PM | nadendla@mit.edu
IS&T – EHS/Parking | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu
IS&T – PM/VPIS Parking | Rita Zhovnirovsky – W92 | Refer to online directory | mzhovnir@mit.edu
IS&T – PM |  | Refer to online directory
IS&T – Log/FIN/EHS Team Coordinator | Ken Levie – W92 | Refer to online directory | khann@mit.edu
IS&T – Ops | Kevin Mullins – Off Campus | Refer to online directory | kmullins@mit.edu
IS&T – Ops | Paul Cronin – Off Campus | Refer to online directory | croninp@mit.edu
IS&T – Tech Services | Wai-ming Li – W92 | Refer to online directory | waiming@mit.eu
IS&T – Ops | Olivia Wang – W91 | Refer to online directory | owang@mit.edu
IS&T - Data warehouse | Elena Zhitnikov – W92 | Refer to online directory | elena@mit.edu
IS&T - Data warehouse | Svetlana Lemeshov – W92 | Refer to online directory | lemeshov@mit.edu
IS&T - HR team lead | Frank Quern – W92 | Refer to online directory | fquern@mit.edu
IS&T – HR/Payroll Coordinator | Mary Donovan – W92 | Refer to online directory | donovan@mit.edu
IS&T – OIS | Matt Anctil | 617-909-7889 | manctil@mit.edu
IS&T - OIS | Patrick Whitney | (617) 253-5767 | pwhitney@mit.edu
IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu
IS&T - OIS | Server Operations | 617-775-3302 | Team Line
Project Manager | Frank Quern | 617-452-4512 | fquern@mit.edu
Assistant Project Manager | Desiree Roberts | Refer to online directory | robertsd@mit.edu
Monday Morning Coverage
Area | Name | Location | Time | Email
FLE | Lee Collier | W92 | 7:30am | lcollier@mit.edu
FLE |  | W92
HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu
HRP | Desiree Roberts | Off Campus | 7:30am | robertsd@mit.edu
R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu
Tech Services | Elda Prudden | W92 | 7:30am | eprudden@mit.edu
Tech Services | Mark Prudden | W92 | 7:30am | mprudden@mit.edu
Tech Services | Carolyn Fuller | Off Campus | 7:30am | fuller@mit.edu
SP Project | Frank Quern | W92 | 7:30am | fquern@mit.edu
FLE | Admin Systems Team | W92 | 8:00am + | administrative-systems@mit.edu
HRP | Admin Systems Team | W92 | 8:00am + | hrpay-sppt@mit.edu

## Task List
---------------------> DRAFT<------------------
# | Date | Time | Action / Task | Person(s) Responsible | Status
Pre-Update Schedule and Processes:
1 | Thursday 2/12/2015 | 2:00 PM- 3:30 PM | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team | complete
2 | Thursday 2/12/2015 | By EOD | Draft Cut-over Communication Plan/Submit to IS&T Communication Team for review. | Frank Quern | complete
3 | Friday 2/13/2015 | By EOD | Submit Atlas Banner Message Request to Atlas Team for 2/21 | Frank Quern
4 |  | By EOD | Submit ECAT Outage Message Request to Procurement for 2/21 | Frank Quern
5 |  | By EOD | Submit Outage/Injury Report to EH&S for Review | Frank Quern
6 | Tuesday 2/17/2015 | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | ops (Paul Cronin)
7 | Tuesday 2/17/2015 | 1:30 pm - 2:30 pm | Cutover weekend planning meeting IS&T. | IS&T-SAP
8 |  | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker)
9 |  | By 5:00 PM | Post message on ECAT web site about upcoming SAP outage. | VPF – Cecilia Talamantes VPF – Scott Ball
10 |  | By 5:00 PM | Email Steering Committee Go/No-go decision to Team | Project Manager ( Frank Quern)
11 |  | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Project Manager ( Frank Quern)
12 | Wednesday 2/18/2015 | 11:00 | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee
13 |  | 14:30 | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | Project Manager ( Frank Quern)
14 |  | By EOD | Final Copy of the Production Update Schedule (cutover plan)published and emailed. | Project Manager ( Frank Quern)
15 | Thursday 2/19/2015 | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be 12/8/2014). Notify R3-Admin (R. Parker) and PM (Frank Quern) when jobs have been scheduled. | VPF Finance (C. Auguste)
16 |  | By EOD | Create New Hire notification variants for Saturday suspended run. | Admin Systems (M. Murray via Fire Fighter)
17 |  | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker)
18 | Friday 2/20/2015 | By 4:30 PM | Suspend weekend MITSIS cron jobs for the BIO feed and the Grad Appointment Feed - On sky-app-1 under userid as_cron comment out weekend rprgapxt_new job - On sky-app-1 under the oasprod userid comment out the rprgabio_cron job. | Enterprise Appl. Admin (K. Mullins)
19 |  | By 5:00 PM | Print out/Download Facilities work order lists as back up for Monday Morning | Facilities (Lisa St. Croix)
20 |  | By 5:00 PM | Print out/Download Housing work order lists as back up for Monday Morning | Facilities (Lisa St. Croix)
21 |  | By 5:00 PM | Workflow and JV Validation Reports (screen shots) · Workflow inbox report (Henry Leung) · JV Parked Documents Report (Henry Leung) · RFPs (Cathy Cherico) | VPF (Henry Leung) (Cathy Cherico)
22 | Saturday (morning) 2/21/15 | 1:30 AM – 6:00 AM | Backup System (RMAN) o Generate full (level 0) SAP database RMAN backup (Matt) o email sap-upgrade-core@mit.edu when complete (Matt or Ron) | R3-Admin OIS/Enterprise Storage & Backup (Resource: Patrick Whitney)
System Isolation
23 | Saturday (morning) 2/21/2015 | 6:30 AM (5 Minutes) | Stop EDI Production Jobs (5 Minutes) Will need access to logistics batch id ZZLOGISBAT01 (id needs to be converted to dialog thru the course of the implementation). o email sap-upgrade-core@mit.edu when complete | Tech Services (E. Wei) R3-Admin (G. Petrowsky)
24 |  | 7 AM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). · Run the push POs job · Shutdown the web server · Shutdown the application server · email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (O. Wang)
25 |  | 7 AM | Voice message update when system goes down (617-324-7468) o email sap-upgrade-core@mit.edu when complete | Project Manager ( Frank Quern)
26 |  | 7 AM | System Downtime Message (3 Down) o email sap-upgrade-core@mit.edu when complete | R3-Admin Project Manager (F. Quern)
27 |  | 7 AM | Bring down application servers. Production Environment becomes unavailable to users (including ECAT). o email sap-upgrade-core@mit.edu when complete | R3-Admin
28 |  | 7 AM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) o email sap-upgrade-core@mit.edu when complete | Ops ( Kevin Lyons / G. Gaudette)
29 |  | 7 AM (5 Minutes) | Suspend Drop-box processing. o email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li)
30 |  | 7 – 9 AM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday) • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) (G. Petrowsky) | unlock batch ids
31 |  | 7 – 9 AM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Clarel Auguste via email cc fquern@mit.edu, nadendla@mit.edu that the reports are completed & downloaded. • VPF confirms the receipt of the Trial Balance Report. • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF (Clarel Auguste)
32 |  | 9:00 | Split off SRDF mirror. • Shutdown SAP System (Ron) • Split off (disable) SRDF mirror (Matt) • email sap-upgrade-core@mit.edu when complete (Ron) | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Resource: TBD)
Hardware Renewal Migration and Processes:
33 | Saturday 2/21/15 | 9:00 AM – 6:00 PM | SAP ERP: Execute Hardware Migrations. • Email Notification to sap-upgrade-core@mit.edu from Ron Parker at the start of the hardware migration • Email notifications to sap-upgrade-core@mit.edu by noon on Saturday (2/21) with status and on Saturday (2/21) from Ron Parker upon completion. | R3-Admin (R. Parker)
34 |  | 18:00 | IS&T Conference Call Check-in Core Team Check in at 6 pm on Saturday (use conference call webex line) | Project Manager (Frank Quern)
35 |  | 6:00 PM – 8:00 PM | R3-Admin Action Log Refer to R3 Action log posted on project wiki. Unique to this year’s activities: refer to the R3 Action Log for details o email sap-upgrade-core@mit.edu when complete | R3-Admin (All)
36 |  | 20:00 | Validation reports executed (trial balance reports) • R3-ADMIN notifies Clarel Auguste via email, cc to Frank Quern as soon as the trial balance is available for review • R3-ADMIN unlock CAUGUSTE id in PS1 • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF Finance (Clarel Auguste) | need to confirm that we will be running TBs
Post Upgrade Schedule and Processes:
37 | Sunday 2/22/15 | 1:30 AM – 6:00 AM | On Line back up of PS1 (RMAN). • Generate full (level 0) SAP database RMAN backup (Matt) • Resume hourly RMAN logfile backups (Matt) | R3-Admin OIS/Enterprise Storage & Backup (Recource: Patrick Whitney)
38 |  | 8 - 9 am | Admin Sys Post Upgrade Action Log - ADMIN SYS Action Log users unlocked - ADMIN SYS executes the PS1 Action Log / Validations and email steps completed to rest of the team (sap-action-log-team@mit.edu) • email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Action Log (Frank Quern)
39 |  | 8 – 9 am | TB Validation reports validated • Clarel notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Clarel Auguste) (Sandeep)
40 |  | 8:00 | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (start EDI; but do not send or push any files yet) o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (Olivia Wang)
41 |  | 8:30 | EDI Step 2 Start EDI Jobs (start sending EDI files) o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (Olivia Wang)
42 |  | By 9 AM (5 Minutes) | EDI Step 3 (last step) Schedule EDI Job • Unlock ids (eprudden, ZZLOGISBAT01) • Schedule EDI Job • Monitor first job released (on the ½ hr) • email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Tech Services (E. Wei) (ZZLOGISBAT01)
43 |  | 11:00 | Unlock Admin Sys Teams (BSAs, Tech Services) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky)
44 |  | 12:00 | Unlock validators (testers) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky)
45 |  | By 12 PM | Update voice message whether or not Data Validation is on schedule. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | Project Manager (Frank Quern)
46 |  | 12 PM – 2 PM | PS1 Data Validations & Transaction processing listed in the Validation sheet in this workbook are performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs Admin Sys BAs
47 |  | By 2 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs Admin Sys BAs R3-Admin
48 |  | 14:30 | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, B. Dahlstrom, R. Parker, Wai-ming Li Admin Sys Team Leads) | Business Owners/ Test Coordinators Sponsor (B. Dahlstrom) Tech Services (W. Li) Admin Sys Team Leads IS&T Test Coordinators (M. Donovan), (L. Collier)
49 |  | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu,warehouse@mit.edu, Elena@mit.edu,) indicating decisions/results. | Project Manager (Frank Quern)
50 |  | 3:00 PM – 4:00 PM | Unlock users (Facilities, SMART) Unlock all users Switch the following batch ids to non-dialog: ZZLOGISBAT01 (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update Atlas message. | R3-Admin (G. Petrowsky)
51 |  | 4:00 PM Sunday (5 Minutes) | Enable Drop box o email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li)
52 |  | 16:30 | Reinstate weekend MITSIS Grad Appointment Feed o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (K. Mullins)
53 |  | By 4:30 PM | Execute ProCard from Bank of America Feed o email sap-upgrade-core@mit.edu when complete | Tech Services (Eping Wei)
54 | Sunday / Monday morning | 1:30 | On Line back up of PS1 (RMAN). • Generate incremental SAP database RMAN backup (Matt) • Resume daily incremental and weekly full RMAN backup schedule (Matt) | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Resource: Patrick Whitney)
55 |  | By 6 AM | Update the 3-down web page & SAPgui message. o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) Project Manager (Frank Quern)
56 |  | By 6 AM | Remove SAP outage message on ECAT webpage. | VPF – Cecelia Talamantes VPF – Scott Ball
57 |  | By 6 AM | Remove Atlas and EHS messages. o email sap-upgrade-core@mit.edu when complete | Ops (K.Mullins)
58 |  | By 6 AM | Validate Atlas and EHS messages have been removed (verify in IE, Firefox, Chrome) | Admin Systems (Team)
59 |  | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | Project Manager (Frank Quern)
60 |  | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. o email sap-upgrade-core@mit.edu when complete | Admin System Desiree Roberts
61 | Tuesday 2/24/2015 | 17:00 | Reestablish SAP Production System SRDF replication between OC11 and E40 (Matt) | OIS/Enterprise Storage & Backup

## Escalation Path
Escalation Path
If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Bart will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday December 7th.
Functional Malfunction(s)
Clarel Auguste | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike Peretti | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Laurie Veal | Business Process Owner (EH&S) / Weekend Coordinator
Cathy Cherico | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Bart Dahlstrom | Project Sponsor IS&T / ADMIN SYS ERP Systems Manager
Steering Committee (+)
1. Bill VanSchalkwyk | Managing Director, EHS Programs
2. Scott Ball | Business Systems Manager, VPF
3. Lisa St. Croix | Business Systems Manager, Department of Facilities
4. Kathleen Flynn | HR Manager of Operations
5. Frank Quern | SP Project Manager
Escalation Support Team
Ron Parker | Basis / Technical Support
George Petrowsky | R3 Authorizations
Elena Zhitnikov | Data Warehouse Team
Frank Quern | Support Pack PM
Siobhan Cunningham | FIN/LOG/EH&S Team Lead
Kevin Mullins | Ops
Garry Zacheiss | Ops
Wai-ming Li | Tech Services
Lee Collier | FI/LOG/EHS Team Coordinator
Mary Donovan | HR/Payroll/EL Team Coordinator
Desiree Roberts | Assistant Project Manager

## Validation
Production Validation
Production Validation will occur in NE49, W92 and remotely. Validation is scheduled to start at 12:00 PM, however, please check the message line (617-324-7468) before coming into the office or starting to test remotely. The message will be updated by 11:30 AM if there are potential delays and by 12:00 PM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday February 22nd. Frank will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/Clarel Auguste | Trial Balance Report validation occurs first. Ron Parker will email Clarel Auguste and Frank Quern when the reports have finished processing. Clarel will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following:Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log second. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu