## Timeline
 | time axis 2015-06-22 to 2016-12-19
Week | 2015-06-22: 0; 2015-06-29: 0; 2015-07-06: 1; 2015-07-13: 2; 2015-07-20: 3; 2015-07-27: 4; 2015-08-03: 5; 2015-08-10: 6; 2015-08-17: 7; 2015-08-24: 8; 2015-08-31: 9; 2015-09-07: 10; 2015-09-14: 11; 2015-09-21: 12; 2015-09-28: 13; 2015-10-05: 14; 2015-10-12: 15; 2015-10-19: 16; 2015-10-26: 17; 2015-11-02: 18; 2015-11-09: 19; 2015-11-16: 20; 2015-11-23: 21; 2015-11-30: 22; 2015-12-07: 23; 2015-12-14: 24; 2015-12-21: 25; 2015-12-28: 26; 2016-01-11: 27
Project Setup & Preparation | 2015-11-23: Thanksgiving
ABAP Code Remediation in SF2 (MIT)
Prep for System Copy (7/6 - MIT/HEC)
SAP Project Team Onboarding
Project Kick off
Cycle 1 (POC) - Test Migration (PS1 to SF3 copy & migrate to MIG-H) | bar: 2015-07-06 to 2015-09-21
SSO Design and Validation | bar: 2015-07-06 to 2015-07-20
Upgrade and Migrate to HANA with DMO (PS1 system copy) | bar: 2015-07-13 to 2015-07-27
BSI, Opentxt, file Storage Built by MIT Team | bar: 2015-07-20 to 2015-08-03
SSO Build and Testing | bar: 2015-07-27 to 2015-08-10
ABAP Code Validation | bar: 2015-08-03 to 2015-09-21
Functional Testing, New T-Code Testing, Regression Testing | bar: 2015-08-03 to 2015-09-21
Cycle 2 - Dev Test (SF2 copy to SF2, Migrate SF2 to SF2-H) | bar: 2015-08-03 to 2015-09-21
Upgrade and Migrate to HANA with DMO (SF2 to SF2-H) | bar: 2015-08-03
ABAP Code Validation | bar: 2015-08-10 to 2015-09-21
Functional Tests (code adjustment, functional, performance, ..) | bar: 2015-08-10 to 2015-09-21
Go - No - Go | bar: 2015-09-28
Cycle 3 - Development Cutover (SF2 to SF2-H) | bar: 2015-10-05 to 2015-10-12
Copy DEV & Switch PRD Support
Upgrade and Migrate to HANA with DMO (SF2-SF2-H)
Transport DV2 transports to SF2-H & Reconciliation
Development Unit Testing
Cycle 4 - QA Cutover (SH1 to SH1-H) | bar: 2015-10-12 to 2015-11-16
Upgrade and Migrate to HANA with DMO (SH1 to SH1-H) | bar: 2015-10-12
Regression / Performance / Integration Test | bar: 2015-10-19
Integration Test - 2 | bar: 2015-10-26 to 2015-11-16
Cycle 5 - Prod Mock 2 (SH1 to PS1) | bar: 2015-11-02 to 2015-11-16
System Copy (SH1 to PS1-H) | bar: 2015-11-02
Test HA, Backup Restore | bar: 2015-11-09 to 2015-11-16
Development Freeze (No Project or Production Support Changes) | bar: 2015-11-30 to 2015-12-07
Cycle 6 - HANA Migration Dress Rehearsal (PS1 to MIG-H) | bar: 2015-11-30
Upgrade and Migrate to HANA with DMO (PS1 system copy) | bar: 2015-11-30
Final verification Cutover plan and cookbook | bar: 2015-11-30
Cycle 7 - HANA Migration Go-Live Cutover (PS1 to PS1-H) | bar: 2015-12-07
Upgrade and Migrate to HANA with DMO (PS1 to PR-H) | bar: 2015-12-07
Post Go-Live (PS1 System powered by HANA) | bar: 2015-12-07 to 2015-12-14
Hypercare (operation, monitoring, optimization) | bar: 2015-12-07 to 2015-12-14