## Communication & Contacts
Communication
An IS&T telephone number (617-324-7468) will carry a message as to the status of the upgrade beginning at noon on Friday 12/11 through noon on Monday 12/14. The Project Manager or designee will update this message as needed. A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 6:00pm on Sunday.
Voicemail With Status: 617-324-7468
Conference Call Line: Webex
Call-in toll number (US): 617-324-0000 Saturday Access code: to be assigned Sunday Access code: to be assigned
Project wiki link: | https://wikis.mit.edu/confluence/pages/viewpage.action?pageId=109837297
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via voice message, email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
Contact Information
Area | Name – Location | Contact Telephone # | Email
A/P | Cathy Cherico – NE49 | Refer to online directory | CHERICO
VPF | Clarel Auguste – NE49 | 617-253-8488 | cauguste@mit.edu
VPF – Travel | Andrea Siegel - Off Campus | Contact PM | amsiegel@mit.edu
Dept. of Facilities | Bob Leonard – NE49 | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher – Off Campus | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix | Contact PM | lstcroix@mit.edu
EHS | Laurie Veal – Off Campus | Contact PM | veal@mit.edu
EHS | Joe MacLeod - Off Campus | Contact PM | jmacleod@mit.edu
HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu
HR/Benefits | Diane Johnston – Off Campus | Contact PM | djohnsto@mit.edu
HR/Benefits | Kathleen Flynn – Off Campus | Contact PM | kflynn@mit.edu
EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White – Off Campus | Contact PM | jwc@mit.edu
Procurement | Cindy Vye - NE49 | Contact PM | CI24314
Procurement | Cecilia Talamates – NE49 | Contact PM | cctala@mit.edu
Procurement | Jeff Rosa – Off Campus | Contact PM | jrosa@mit.edu
Procurement | Minerva Tirado -NE49 | Contact PM | MINERVA
Procurement | David Petricone - Off Campus | Contact PM | PETRICON
Procurement | Kimberly Harmon – Off Campus | Contact PM | kharmon@mit.edu
VPF – HR/Payroll | Leslie Wright – NE49 | 617-253-7715 | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Contact PM | darrenjs@mit.edu
VPF – HR/Payroll | Kristen McCormick | Contact PM | cassidyk@mit.edu
VPF – HR/Payroll | Nicole Valente | Contact PM | nferrant@mit.edu
VPF – HR/Payroll | Lilian Garcia | Contact PM | llg@mit.edu
VPF – HR/Payroll | Jen Quintero | Contact PM | jen_quin
VPF – HR/Payroll | Chris Durham – NE49 | Refer to online directory | cfdurham
IS&T – QA | Debra Wiley | Refer to online directory
IS&T - QA | Jack Kelliher | Contact PM | jackkell@mit.edu
IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu
IS&T - ERP System Manager |  | Refer to online directory
IS&T - Project Manager | Siobhan Cunningham – W92 | Refer to online directory | snc@mit.edu
IS&T – Logistics | Adina Ion – W92 | Refer to online directory | aion@mit.edu
IS&T - FLE Product Owner | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu
IS&T - FI Team | Keyur Patel – W92 | Refer to online directory | keyurpb@mit.edu
IS&T - FI Team | Sandeep Nadendla - W92 | Contact PM | nadendla@mit.edu
IS&T – EHS/Parking | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu
IS&T – PM/VPIS Parking | Rita Zhovnirovsky – W92 | Refer to online directory | mzhovnir@mit.edu
IS&T – PM | Jim Fragala – W92 | Refer to online directory | ja17661@mit.edu
IS&T – Log/FIN/EHS Team Coordinator | Ken Levie – W92 | Refer to online directory | khann@mit.edu
IS&T – Ops |  | Refer to online directory
IS&T – Ops | Paul Cronin – Off Campus | Refer to online directory | croninp@mit.edu
IS&T – Tech Services |  | Refer to online directory
IS&T – Ops |  | Refer to online directory
IS&T - Data warehouse | Elena Zhitnikov – W92 | Refer to online directory | elena@mit.edu
IS&T - Data warehouse |  | Refer to online directory
IS&T - HRP Product Owner | Frank Quern – W92 | Refer to online directory | fquern@mit.edu
IS&T – HRP Scrum Master | Meaghan Murray – W92 | Refer to online directory
IS&T – OIS | Matt Anctil | 617-909-7889 | manctil@mit.edu
IS&T - OIS | Patrick Whitney | (617) 253-5767 | pwhitney@mit.edu
IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu
IS&T - OIS | Server Operations | 617-775-3302 | Team Line
Monday Morning Coverage
Area | Name | Location | Time | Email
FLE | Lee Collier | W92 | 7:30am | lcollier@mit.edu
FLE | Jim Fragala | W92 | 7:30am | ja17661@mit.edu
HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu
HRP | Meaghan Murray | Off Campus | 7:30am
R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu
ABAP | Elda Prudden | W92 | 7:30am | eprudden@mit.edu
ABAP | Mark Prudden | W92 | 7:30am | mprudden@mit.edu
ABAP | Carolyn Fuller | Off Campus | 7:30am | fuller@mit.edu
SP Project | Frank Quern | W92 | 7:30am | fquern@mit.edu
FLE | IS&T SA Team | W92 | 8:00am + | administrative-systems@mit.edu
HRP | IS&T SA Team | W92 | 8:00am + | hrpay-sppt@mit.edu

## Task List
# | Date | Time | Action / Task | Person(s) Responsible | Status
Pre-Update Schedule and Processes:
| Wednesday 11/25/2015 | By EOD | Draft Cut-over Communication Plan/Submit to IS&T Communication Team for review. | Frank Quern
|  | By EOD | Submit Atlas Banner Message Request to Atlas Team for 12/7 | Frank Quern
|  | By EOD | Submit ECAT Outage Message Request to Procurement for 12/7 | Frank Quern
|  | By EOD | Submit Outage/Injury Report to EH&S for Review | Frank Quern
| Monday 12/7/2015 | 8:00 | Start DMO uptime phase | R3-Admin+
|  | 12 pm - 2 pm | Cutover weekend planning meeting IS&T. | IS&T-SAP
| Tuesday 12/8/2015 | By EOD | PS1 System transport lock (transports not allowed into production) | R3-Admin+
|  | 2:00 PM- 3:30 PM | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team
|  | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | ops (Paul Cronin)
|  | 10:00 AM - 11:00 AM | Support Pack Transport Review Meeting. Final review all issues in RT project queue, transport list, and web components. | R3-Admin /Core Team/ABAP Team/Web-Tech/BSAs
|  | 12 noon | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee
10 |  | 4:00PM | Begin online upgrade piece of the application of Enhancement & Support Pack(s). Run time 2 days (complete by EOD 12/5). | R3-Admin (R. Parker)
|  | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker)
|  | By 5:00 PM | Post message on ECAT web site about upcoming SAP outage. | VPF – Cecilia Talamantes VPF – Scott Ball
|  | By 5:00 PM | Email Steering Committee Go/No-go decision to Team | Project Manager ( Siobhan Cunningham)
|  | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Product Owner ( Frank Quern)
| Wednesday 12/9/2015 | 2:00 PM- 3:30 PM | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | POs ( Bob Casey, Frank Quern)
|  | 16:00 | Email ops-help with list of web application deployment requests for Friday evening. (align with Atlas release) | PO ( Frank Quern)
|  | By EOD | Final Copy of the Production Update Schedule (cutover plan)published and emailed. | PO ( Frank Quern)
| Thursday 12/10/2015 | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be 12/8/2014). Notify R3-Admin (R. Parker) and PM (Frank Quern) when jobs have been scheduled. | VPF Finance (C. Auguste)
|  | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. | Admin Systems (M. Murray via Fire Fighter)
|  | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker)
| Friday 12/11/2015 | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM). | DW (E. Zhitnikov)
|  | By 2 PM | Print out/Download Facilities work order lists as back up for Monday Morning | Facilities (Bob Leonard)
|  | By 2 PM | Print out/Download Housing work order lists as back up for Monday Morning | Facilities (Bob Leonard)
|  | By 3:20 PM | Shift Concur outbound execution from 5:00 pm to 3:20pm | R3-Admin
|  | By 3:30 PM | Suspend weekend MITSIS cron jobs for the BIO feed and the Grad Appointment Feed - On sky-app-1 under userid as_cron comment out weekend rprgapxt_new job - On sky-app-1 under the oasprod userid comment out the rprgabio_cron job. | Enterprise Appl. Admin (K. Mullins/opshelp)
|  | By 4:00 PM | Workflow and JV Validation Reports (screen shots) · Workflow inbox report (Henry Leung) · JV Parked Documents Report (Henry Leung) · RFPs (Cathy Cherico) | VPF (Henry Leung) (Cathy Cherico)
|  | After 4 pm and before Sunday at 6 am | Update GUI XT on Facilities Department desktop machines | Facilities (M. Sherman) | alternative: scheduled to push to machines on Monday morning
System Isolation
|  | 3:35 PM (5 Minutes) | Stop EDI Production Jobs (5 Minutes) Will need access to logistics batch id ZZLOGISBAT01 (id needs to be converted to dialog thru the course of the implementation). o email sap-upgrade-core@mit.edu when complete | Tech Services (E. Prudden) R3-Admin (G. Petrowsky)
|  | 4 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). · Run the push POs job · Shutdown the web server · Shutdown the application server · email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (O. Wang)
|  | 4 PM | Voice message update when system goes down (617-324-7468) o email sap-upgrade-core@mit.edu when complete | PO ( Frank Quern)
|  | 4 PM | System Downtime Message (3 Down) o email sap-upgrade-core@mit.edu when complete | R3-Admin PO (F. Quern)
|  | 4 PM | Bring down application servers. Production Environment becomes unavailable to users (including ECAT). o email sap-upgrade-core@mit.edu when complete | R3-Admin
|  | 4 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) o email sap-upgrade-core@mit.edu when complete | Ops ( Kevin Lyons / G. Gaudette)
|  | 4 PM (5 Minutes) | Suspend Drop-box processing. o email sap-upgrade-core@mit.edu when complete | R3 Admin
|  | 4 – 6 PM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Clarel Auguste via email cc fquern@mit.edu, nadendla@mit.edu that the reports are completed & downloaded. • VPF confirms the receipt of the Trial Balance Report. • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF (Clarel Auguste)
36 |  | 4 – 6 PM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • Save WT info to internal SAP table • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) (G. Petrowsky)
Support Pack Application/HANA Migration and Processes:
37 |  | 6 - 9 PM | Export PS1 ECC to SUM > Email Notification to sap-upgrade-core@mit.edu upon completion of step | R3-Admin
|  | 9 PM - 1 AM (4 hrs) | Transfer ECC export to HEC | R3-Admin
| Friday (night) - Saturday (morning) 12/12/2015 | 9 PM – 6 AM | Backup On-premise PS1. • Shutdown SAP System (Ron) • Split off (disable) SRDF mirror (Matt) • Bring up SAP database • Generate full (level 0) SAP database RMAN backup (Matt) • Bring up SAP (Ron) • email sap-upgrade-core@mit.edu when complete (Ron) | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Resource: Patrick Whitney) | If going w/ HANA should this just be the normal backup for on-prem PS1?
| Friday (night) - Saturday (morning) 12/12/2015 | 1 AM - 11 AM (10 hrs) | DMO Process (includes application of support packs) | HEC/R3-Admin
| Saturday 12/12/2015 | 11 - noon (1 hr) | PS1 (HEC) Backup - Snapshot/HA Replication | HEC
39 |  | noon - 2 PM (2hrs) | MIT Migration Post Processing | R3-Admin+
40 |  | 2 PM - 1:30 AM (13.5 hrs) | HEC Post Processing | HEC
|  | 18:00 | IS&T Conference Call Check-in Core Team Check in at 6 pm on Saturday (use conference call webex line) | Project Manager (Siobhan Cunningham)
43 |  | By 8:00 PM | BSI Upgrade (can occur any time after 5pm Friday) o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker)
41 |  | 1:30 AM - 6 AM (4.5 hrs) | MIT Technical Post Processing (Open Text, BSI, GRC, Printers, SOLMAN, SFTP, ADS) ABAP Loads Restore WT Table | R3-Admin+ | How long will this take? ABAP loads should occur during HEC Post Proc?
Post Upgrade Schedule and Processes:
|  | during the above window? | Validation reports executed (trial balance reports) • R3-ADMIN notifies Clarel Auguste via email, cc to Frank Quern as soon as the trial balance is available for review • R3-ADMIN unlock CAUGUSTE id in PS1 • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF Finance (Clarel Auguste)
| Sunday 12/13/2015 | 6 AM - 2 PM (8 hrs) | HA Failover - HEC Validation - MIT Validation HA Failback - HEC Validation | HA HEC MIT IS&T | (HEC Done at this point)
|  | 2 PM - 2:30 PM | MIT IS&T Post Upgrade Action Log Action Log team members unlocked | Action Log Team (R3, ABAP, SA)
|  | 14:00 | TB Validation reports validated • Clarel notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Clarel Auguste) (Sandeep)
63 |  | By 2 PM | Update voice message whether or not Data Validation is on schedule. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | PO (Frank Quern)
|  | 14:00 | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (start EDI; but do not send or push any files yet) o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (George Gaudette)
|  | 14:00 | EDI Step 2 Start EDI Jobs (start sending EDI files) o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (George Gaudette)
|  | By 2:30 PM (5 Minutes) | EDI Step 3 (last step) Schedule EDI Job • Unlock ids (eprudden, ZZLOGISBAT01) • Schedule EDI Job • Monitor first job released (on the ½ hr) • email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Tech Services (E. Prudden) (ZZLOGISBAT01)
|  | By 2:30 PM (5 Minutes) | Email to ist-sap@mit.edu • List of transports applied and any related issues. • List of jobs shifted in PS1 during cutover | R3-Admin (Ron Parker)
61 |  | 14:30 | Unlock IS&T Teams (ABAPs, BAs, SAs) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky)
|  | 2:30 PM - 4 PM | MIT IS&T Validations | All R3, ABAP, SA, BA
62 |  | 16:00 | Unlock validators (testers) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky)
64 |  | 4 PM – 6 PM | MIT Business Validation PS1 Data Validations & Transaction processing listed in section of the Validation tab performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs IS&T BAs & SAs
65 |  | By 6 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs IS&T BAs & SAs
66 |  | 18:00 | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, POs, Team Leads)
67 |  | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu,warehouse@mit.edu, Elena@mit.edu,) indicating decisions/results. | PO (Frank Quern)
68 |  | 6:30 PM – 7:30 PM | Unlock users (Facilities, SMART) Unlock all users Switch the following batch ids to non-dialog: ZZLOGISBAT01 (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update Atlas message. | R3-Admin (G. Petrowsky)
69 |  | 7:30 PM Sunday (5 Minutes) | Enable Drop box o email sap-upgrade-core@mit.edu when complete | R3 Admin (TBD)
70 |  | 18:30 | Reinstate weekend MITSIS Grad Appointment Feed o email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (TBD)
71 |  | By 7:30 PM | Execute ProCard from Bank of America Feed o email sap-upgrade-core@mit.edu when complete | ABAP Team (Eping Wei)
72 |  | 8PM – 12AM | Data Warehouse Job Validation • Elena confirm job validation completion via email to sap-upgrade-core@mit.edu • Run extracts (10PM & 12AM) | R3-Admin
73 | Sunday / Monday morning | 8PM - 6AM | HEC Processes (to be defined) | HEC
74 |  | By 6 AM | Update the 3-down web page & SAPgui message. o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) Project Manager (Frank Quern)
75 |  | By 6 AM | Remove SAP outage message on ECAT webpage. | VPF – Cecelia Talamantes VPF – Scott Ball
76 |  | By 6 AM | Remove Atlas and EHS messages. o email sap-upgrade-core@mit.edu when complete | Ops (TBD)
77 |  | By 6 AM | Validate Atlas and EHS messages have been removed (verify in IE, Firefox, Chrome) | SA (Team)
78 |  | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | PO (Frank Quern)
79 |  | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. o email sap-upgrade-core@mit.edu when complete | BA Meaghan Murray

## Escalation Path
Escalation Path
If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Siobhan will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday December 7th.
Functional Malfunction(s)
Clarel Auguste | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike Peretti | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Laurie Veal | Business Process Owner (EH&S) / Weekend Coordinator
Cathy Cherico | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Siobhan Cunningham | Project Manager
Steering Committee (+)
Chris Holness | SAP
Pat Casey | SAP
Stephen Koczur | SAP HEC
Fabiab Dias | SAP Basis
Deepak Kamath | SAP Basis
Escalation Support Team
Ron Parker | Basis PO
George Petrowsky | R3 Authorizations
Elena Zhitnikov | Data Warehouse Team
Frank Quern | HRP PO
Siobhan Cunningham | Project Manager
Bob Casey | FLE PO
Kevin Lyons | Atlas PO
Lee Collier | Scrum Master
Meaghan Murray | Scrum Master
Olympia Valentine | Scum Master
Qian Kang | Scrum Master

## Validation
Production Validation
Production Validation will occur in NE49, W92 and remotely. Validation is scheduled to start at 12:00 PM, however, please check the message line (617-324-7468) before coming into the office or starting to test remotely. The message will be updated by 11:30 AM if there are potential delays and by 12:00 PM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 8th. Frank will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/Clarel Auguste | Trial Balance Report validation occurs first. Ron Parker will email Clarel Auguste and Frank Quern when the reports have finished processing. Clarel will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following:Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log second. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu