## Communication & Contacts
Communication
An IS&T telephone number (617-324-7468) will carry a message as to the status of the upgrade beginning at noon on Friday 12/11 through noon on Monday 12/14. The Project Manager or designee will update this message as needed. A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 6:00pm on Sunday.
Voicemail With Status: 617-324-7468
Conference Call Line: Webex
Call-in toll number (US): 617-324-0000 Friday Access code (noon - 12 am): 640 512 339 Saturday Access code (midnight - 12 pm) : 648 318 887 Saturday Access code (noon - 12 am): 649 875 542 Sunday Access code (midnight - 12 pm): 642 810 428 Sunday Access code (noon - 12 am): 645 463 019
Project wiki link: | https://wikis.mit.edu/confluence/pages/viewpage.action?pageId=109837297
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via voice message, email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
SAP Conntact Information
Name | Phone | Email
Joe Caruso | 610 401-5587 | joseph.caruso@sap.com
Pat Casey | 513 332-7904 | pat.casey@sap.com
Fabian Dias | 650 283-6029 | fabian.dias@sap.com
Phil Ferenschak | 610 662-0526 | phillip.ferenschak@sap.com
Chris Holness | 404 825-0281 | christopher.holness@sap.com
Deepak Kamath | 412 953-0034 | deepak.kamath@sap.com
Steve Koczur | 610 745-6281 | stephen.koczur@sap.com
Kenton Pompey | 310.200.8979 | kenton.pompey@sap.com
Hassen Suleiman | 703 881-8020 | hassen.suleiman@sap.com
Annaji Vadlamani | 732 986-0032 | annaji.vadlamani@sap.com
David White | 864 494-2995 | david.white@sap.com
Contact Information
Area | Name – Location | Contact Telephone # | Email
A/P | John Larkin – NE49 | Refer to online directory | jlarkin@mit.edu
VPF | Stef Desmond – NE49 | Refer to online directory | sdesmond@mit.edu
VPF – Travel | Andrea Siegel - Off Campus | Contact PM | amsiegel@mit.edu
Dept. of Facilities | Bob Leonard – NE49 | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher – Off Campus | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix | Contact PM | lstcroix@mit.edu
EHS | Laurie Veal – Off Campus | Contact PM | veal@mit.edu
EHS | Jessica Van | Refer to online directory | jvan@mit.edu
EHS | Joe MacLeod - Off Campus | Contact PM | jmacleod@mit.edu
HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu
HR/Benefits | Diane Johnston – Off Campus | Contact PM | djohnsto@mit.edu
EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White – Off Campus | Contact PM | jwc@mit.edu
Procurement | Cindy Vye - NE49 | Contact PM | CI24314
Procurement | Cecilia Talamates – NE49 | Refer to online directory | cctala@mit.edu
Procurement | Jeff Rosa – Off Campus | Refer to online directory | jrosa@mit.edu
Procurement | Minerva Tirado -NE49 | Refer to online directory | MINERVA
Procurement | David Petricone - Off Campus | Contact PM | PETRICON
Procurement | Ben Simon | Refer to online directory | simonb2@mit.edu
Procurement | Paul Andersen | Refer to online directory | pander@mit.edu
Procurement | Kimberly Harmon – Off Campus | Contact PM | kharmon@mit.edu
VPF – HR/Payroll | Leslie Wright – NE49 | Refer to online directory | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Refer to online directory | darrenjs@mit.edu
VPF – HR/Payroll | Chris Durham – NE49 | Refer to online directory | cfdurham
IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu
IS&T - Project Manager | Siobhan Cunningham – W92 | Refer to online directory | snc@mit.edu
IS&T – Logistics | Adina Ion – W92 | Refer to online directory | aion@mit.edu
IS&T - FLE Product Owner | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu
IS&T - FI Team | Keyur Patel – W92 | Refer to online directory | keyurpb@mit.edu
IS&T - FI Team | Sandeep Nadendla - W92 | Contact PM | nadendla@mit.edu
IS&T – EHS/Parking - Scrum master | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu
IS&T – PM/VPIS Parking | Rita Zhovnirovsky – W92 | Refer to online directory | mzhovnir@mit.edu
IS&T – PM | Jim Fragala – W92 | Refer to online directory | ja17661@mit.edu
IS&T – Log/FIN/EHS Team Coordinator | Ken Levie – W92 | Refer to online directory | khann@mit.edu
IS&T – Ops | George Gaudette - W92 | Refer to online directory | gaudette@mit.edu
IS&T – Ops | Paul Cronin – Off Campus | Refer to online directory | croninp@mit.edu
IS&T - Data warehouse | Elena Zhitnikov – W92 | Refer to online directory | elena@mit.edu
IS&T - HRP Product Owner | Frank Quern – W92 | Refer to online directory | fquern@mit.edu
IS&T – HRP Scrum Master | Meaghan Murray – W92 | Refer to online directory | mamurray@mit.edu
IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu
IS&T - OIS | Server Operations | 617-775-3302 | Team Line
Monday Morning Coverage
Area | Name | Location | Time | Email
FLE | Lee Collier | W92 | 7:30am | lcollier@mit.edu
FLE | Jim Fragala | W92 | 7:30am | ja17661@mit.edu
HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu
HRP | Meaghan Murray | Off Campus | 7:30am
R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu
ABAP | Elda Prudden | W92 | 7:30am | eprudden@mit.edu
ABAP | Mark Prudden | W92 | 7:30am | mprudden@mit.edu
ABAP | Carolyn Fuller | Off Campus | 7:30am | fuller@mit.edu
FLE | IS&T SA Team | W92 | 8:00am + | administrative-systems@mit.edu
HRP | IS&T SA Team | W92 | 8:00am + | hrpay-sppt@mit.edu

## Cutover Task List
# | Date | Time (EST) | Action / Task | Person(s) Responsible | Status
Pre-Update Schedule and Processes:
1 | By Wednesday 12/2/2015 | By EOD | Execute MIT Web Deployments Task 0 Synch OC11 Atlas and Adminapps, EHSapps, Finsys with W92 versions (refer to MIT Web Deployments tab) | Ops George Gaudette | complete
2 | Wednesday 12/2/2015 | By EOD | Draft Cut-over Communication Plan/Submit to IS&T Communication Team for review. | Frank Quern | complete
3 |  | By EOD | Submit Atlas Banner Message Request to Atlas Team for 12/7 | Frank Quern | complete
4 |  | By EOD | Submit ECAT Outage Message Request to Procurement for 12/7 | Frank Quern | complete
5 |  | By EOD | Submit Outage/Injury Report to EH&S for Review | Frank Quern | complete
6 | Thursday 12/3/2015 | 12 noon | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee | complete
7 |  | By 5:00 PM | Email Steering Committee Go/No-go decision to Team | Project Manager ( Siobhan Cunningham) | complete
8 | 12/3 - 12/4/2015 | By EOD | Execute MIT web deployment tasks 1, 2 and 3 Update Atlas staging environment; deploy upgraded web applications (refer to MIT Web Deployments tab) | Ops George Gaudette | complete
9 | Monday 12/7/2015 | 8:00 | Start DMO uptime phase | R3-Admin+ | complete
10 |  | 9:30 - 11am | IS&T cutover weekend planning/review meeting. | IS&T-SAP | complete
11 |  | 1 - 2:30pm | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | POs ( Bob Casey, Frank Quern) | complete
12 | 12/7 - 12/9/2015 | By EOD | Execute MIT Web Deployments Task 4 Staging Validation - validation of Atlas and Tomcat apps (refer to MIT Web Deployments tab) | Globtrotters | complete
13 | Tuesday 12/8/2015 | By EOD | PS1 System transport lock (transports not allowed into production) | R3-Admin+ | complete
14 |  | 11am - noon | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team | complete
15 |  | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | ops (Kevin Lyons) | complete
16 |  | 1:30 - 3pm | Support Pack Transport Review Meeting. Final review all issues in RT project queue, transport list, and web components. | R3-Admin /Core Team/ABAP Team/Web-Tech/BSAs | complete
17 |  | By 5:00 PM | Post message on SAPgui indicating upcoming SAP gui expiration date | R3-Admin (R. Parker) | complete
18 |  | By 5:00 PM | Post message on ECAT web site about upcoming SAP outage. | VPF – Cecilia Talamantes VPF – Scott Ball | complete
19 |  | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | PO ( Frank Quern) | complete
20 | Wednesday 12/9/2015 | 16:00 | Email ops-help with list of web application deployment requests for Sunday morning. (refer to MIT Web Deplyment tab for details) | PO ( Frank Quern) | complete
21 |  | By EOD | Final Copy of the Production Update Schedule (cutover plan) published and emailed. | PO ( Frank Quern) | complete
22 | Thursday 12/10/2015 | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be 12/14/2015). Notify R3-Admin (R. Parker) and PO (Frank Quern) when jobs have been scheduled. | VPF Finance (S. Desmond/Keyur Patel) | complete
23 |  | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. | Admin Systems (M. Murray via Fire Fighter) | complete
24 |  | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker) | complete
25 | Friday 12/11/2015 | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM). | DW (E. Zhitnikov) | complete
26 |  | By 2 PM | Print out/Download Facilities work order lists as back up for Monday Morning | Facilities (Bob Leonard) | complete
27 |  | By 2 PM | Print out/Download Housing work order lists as back up for Monday Morning | Facilities (Bob Leonard/Lisa St. Croix) | complete
28 |  | By 3:20 PM | Shift Concur outbound execution from 5:00 pm to 3:20pm | R3-Admin | complete
29 |  | By 3:30 PM | Suspend weekend MITSIS cron jobs for the BIO feed and the Grad Appointment Feed - On sky-app-1 under userid as_cron comment out weekend rprgapxt_new job - On sky-app-5 under the as_cron userid comment out the /sis/mitsis/applications/scripts/GEN/triggerBatch.sh /sis/cron biofeedsJob job. | ops (Paul Cronin) | complete
30 |  | By 4:00 PM | Workflow and JV Validation Reports (screen shots) · Workflow inbox report (Henry Leung) · JV Parked Documents Report (Henry Leung) · RFPs (Cathy Cherico) | VPF (Henry Leung) (Cathy Cherico) | complete
31 |  | After 4 pm and before Sunday 6 am | Update GUI XT on Facilities Department desktop machines | Facilities (M. Sherman) | scheduled
System Isolation
32 |  | 3:35 PM (5 Minutes) | Stop EDI Production Jobs (5 Minutes) Will need access to logistics batch id ZZLOGISBAT01 (thru GRC). o email sap-upgrade-core@mit.edu when complete | Tech Services (E. Prudden) R3-Admin (G. Petrowsky) | complete
33 |  | 4 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). · Run the push POs job · Shutdown the web server · Shutdown the application server · email sap-upgrade-core@mit.edu when complete | ops (George Gaudette) | complete
34 |  | 4 PM | Voice message update when system goes down (617-324-7468) o email sap-upgrade-core@mit.edu when complete | PO ( Frank Quern) | complete
35 |  | 4 PM | System Downtime Message (3 Down) o email sap-upgrade-core@mit.edu when complete | R3-Admin PO (F. Quern) | complete
36 |  | 4 PM | Bring down application servers. Production Environment becomes unavailable to users (including ECAT). o email sap-upgrade-core@mit.edu when complete | R3-Admin | complete
37 |  | 4 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) o email sap-upgrade-core@mit.edu when complete | Ops ( Kevin Lyons) | complete
38 |  | 4 PM (5 Minutes) | Suspend Drop-box processing. o email sap-upgrade-core@mit.edu when complete | R3 Admin | complete
39 |  | 4 – 6 PM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Stef Desmond via email cc fquern@mit.edu, nadendla@mit.edu that the reports are completed & downloaded. • VPF confirms the receipt of the Trial Balance Report. • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF (Stef Desmond) | complete
40 |  | 4 – 6 PM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • Save WT info to internal SAP table • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) (G. Petrowsky) | complete
Support Pack Application/HANA Migration and Processes:
41 |  | 18:00 | Open Text Migration (deltas) | Ops George Gaudette | complete
42 |  | 18:00 | Shut down DR replication | HEC
43 |  | 18:15 | Shut down HA replication | HEC
44 |  | 6 - 9 PM (3 hrs) | Export PS1 ECC to SUM > Email Notification to sap-upgrade-core@mit.edu upon completion of step | R3-Admin+ | complete
45 |  | 8 PM - Midnight (4 hrs) | Transfer ECC export to HEC | R3-Admin+ | complete
46 | Friday (night) - Saturday (morning) 12/12/2015 | Midnight - 10 AM (10 hrs) | DMO Process (includes application of support packs) | HEC/R3-Admin+ | complete
47 | Saturday 12/12/2015 | 10am-noon (2 hr) | PS1 (HEC) Backup - Snapshot | HEC | in process
48 |  | noon - 12:15pm (15 mins) | MIT Migration Post Processing - kerberos - RSA keys - SNC - system verification | R3-Admin+
48a |  | noon-6pm (4 hr) | Commence HA data replication | HA (David White, SAP)
49 |  | 12:15pm - 8:15pm (8 hrs) | HEC Post Processing (refer to HEC Task List tab for details) | HEC
50 |  | 18:00 | IS&T Conference Call Check-in Core Team Check in at 6 pm on Saturday (use conference call webex line below) +1-617-324-0000 US Toll Number Access code: 646 193 031 | Project Manager (Siobhan Cunningham)
51 |  | By 8:00pm | BSI Upgrade - application of TUBs (can occur any time after 5pm Friday) o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) | complete
52 |  | 8:15pm - 1:30am (5hrs 15mins) | MIT Technical Post Processing (Open Text, BSI, GRC, Printers, SOLMAN, SFTP, ADS) Restore WT Table Many more details - transports, web deployments, redirects, central *ini file, … (refer to MIT Post Processing Task List tab for details) | R3-Admin+
Post Upgrade Schedule and Processes:
53 |  | during the above window | Validation reports executed (trial balance reports) • R3-ADMIN notifies Stef Desmond via email, cc to Frank Quern as soon as the trial balance is available for review • R3-ADMIN unlock sdesmond id in PS1 • email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF Finance (Stef Desmond)
54 |  | 1:30am - 2:00am | MIT IS&T Post Upgrade Action Log (Part 1) - action log team members unlocked - action log execution | Action Log Team (R3, ABAP, SA)
54a |  | 2:00am | PS1 (HEC) Timestamp | Deepak Karmath, SAP
55 | Sunday 12/13/2015 |  | DR Validation/ HA Failover/Failback
55b |  | 2:00am - 7:30am (5.25 hours) | Disaster Recovey Test (refer to the HA DR tab for details) | HA, HEC, MIT
55a |  | 7:30am - 11:00am (3.5 hours) | High Availability MIT Functional Test (refer to HA Task List tab for details) | HA, HEC, MIT | (HEC Done at this point)
56 |  | 11:00am - 12:30pm (1.5 hours) | MIT Post DR (90 min window) | R3-Admin
56a |  | 11:00am - noon (60 mins) | Update Roles DB Feeds 1. Update config file for ftpsapz and scptosap variables with new HEC production values 2. Update Roles to GRC web service call with new HEC urls | Identity and Access Management (Rob Campanella)
56b |  | 11-11:30 am | Switch Central saplogin.ini & validate | ops (Garry Zacheiss) SAs (TBD)
56c |  | 11:00am - 11:30am | Deploy staged asapis-prod-app-1/2 servers changes using the files ApplicationLocal.properties.HANA and GlobalResources.properties.HANA on the servers | ops (Paul Cronin)
57 |  | 11:00am - 12:00pm (1 hour) | Execute MIT Web Deployments tasks 5, 6 and 7 (refer to MIT Web Deployments tab) | Ops (George Gaudette)
57a |  | noon - 12:30pm | Execute MIT Web Deployments tasks 10 - 14 (refer to MIT Web Deployments tab) | Web Deployment Team (Dudley Kirpatrick, Larissa Kushkuley, Carolyn Fuller)
58 |  | 11am - noon (60 mins) | MIT IS&T Post Upgrade Action Log (Part 2) - action log team members unlocked - action log execution unique for 2015: - enter new EL number range: LSO_CRP (M. Donovan) | Action Log Team (R3, ABAP, SA)
59 |  | by 11:30am | TB Validation reports validated • Stef notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Stef Desmond) (Sandeep)
60 |  | By 12:00pm | Update voice message whether or not Data Validation is on schedule. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | PO (Frank Quern)
61 |  | 12:15 | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (start EDI; but do not send or push any files yet) o email sap-upgrade-core@mit.edu when complete | Ops (George Gaudette)
62 |  | 12:30 | EDI Step 2 Update TLE Paramenters - Application Server - SAP Password - Gateway server id - Gateway service - Hostname o email sap-upgrade-core@mit.edu when complete | Tech Services (E. Prudden)
63 |  | 12:45 | EDI Step 3 Start EDI Jobs (start sending EDI files) o email sap-upgrade-core@mit.edu when complete | Ops (George Gaudette)
64 |  | By 1 PM (5 Minutes) | EDI Step 4 (last step) Schedule EDI Job • Unlock ids (eprudden, ZZLOGISBAT01) • Schedule EDI Job • Monitor first job released (on the ½ hr) • email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) Tech Services (E. Prudden) (ZZLOGISBAT01)
65 |  | By 12:30 PM (5 Minutes) | Email to ist-sap@mit.edu • List of transports applied and any related issues. • List of jobs shifted in PS1 during cutover | R3-Admin (Ron Parker)
66 |  | 12:30 | Unlock IS&T Teams (ABAPs, BAs, SAs, DW, GRC ids) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky)
67 |  | 12:30 - 2pm | MIT IS&T Validations | All R3, ABAP, SA, BA, DW ids
68 |  | 2 - 2:30pm | Unlock validators (testers) o email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky)
69 |  | 2:30 - 4:30 PM (2 hours) | MIT Business Validation PS1 Data Validations & Transaction processing listed in section of the Validation tab performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs IS&T BAs & SAs
70 |  | By 4:30 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs IS&T BAs & SAs
71 |  | 17:00 | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, POs, Team Leads) +1-617-324-0000 US Toll Number Access code: 642 105 713 | PM (Siobhan Cunningham)
71a |  | 17:30 | Activate gui version detection/rejection for older SAP gui versions | R3-Admin (Ron Parker)
72 |  | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu,warehouse@mit.edu, Elena@mit.edu,) indicating decisions/results. | PO (Frank Quern)
73 |  | 5:30 PM – 6:30 PM | Unlock users (Facilities, SMART) Unlock all users (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update Atlas message. | R3-Admin (G. Petrowsky)
74 |  | 5:30 PM Sunday (5 Minutes) | Enable Drop box o email sap-upgrade-core@mit.edu when complete | R3 Admin (TBD)
75 |  | 17:30 | Reinstate weekend MITSIS Grad Appointment Feeds o email sap-upgrade-core@mit.edu when complete | ops (Paul Cronin)
76 |  | 8PM – 12AM | Data Warehouse Job Validation • Elena confirm job validation completion via email to sap-upgrade-core@mit.edu, warehouse-dev@mit.edu • Run extracts (10PM & 12AM) | R3-Admin
77 |  | By 6:30pm | Execute ProCard from Bank of America Feed o email sap-upgrade-core@mit.edu when complete | ABAP Team (Eping Wei)
78 | Sunday / Monday morning | By 6 AM | Update the 3-down web page & SAPgui message. o email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) Project Manager (Frank Quern)
79 |  | By 6 AM | Remove SAP outage message on ECAT webpage. | VPF – Cecelia Talamantes VPF – Scott Ball
80 |  | By 6 AM | Remove Atlas and EHS messages. o email sap-upgrade-core@mit.edu when complete | Ops (Kevin Lyons)
81 |  | By 6 AM | Post Atlas Banner Message with link to Know SAP Issues kb article o email sap-upgrade-core@mit.edu when complete | Ops (Kevin Lyons)
82 |  | By 6 AM | Validate Atlas and EHS outage messages have been removed (verify in IE, Firefox, Chrome) | SA (Kevin Lyons, Siobhan Cunningham)
83 |  | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | PO (Frank Quern)
84 |  | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. o email sap-upgrade-core@mit.edu when complete | BA Meaghan Murray

## HEC Task List
MIT ECC and GRC Production Cutover Post-Processing Activities
Step | Date | Duration (Hours) | Description | Resource Name(s) | Predecessor Step(s) | PS1 uptime needed | Hours | comments | actual time
|  | 30 mins | Ticket for FS/ DB backup
|  | 1 hour | FS/DB backup | Backup team
1 |  | 1 hour | Upgrade Kernel (took care of by migration) | Deepak |  |  | N/A | Migration
2 |  | 10mins | Import profiles using RZ10 | HEC CTC | 1 |  | N/A | Migration
3 |  | 1 hour | Update profiles including ICM server ports | HEC CTC | 2 |  | N/A | Migration
4 |  | 1.5 hours per server | Add additional dialog instances done | HEC CTC | 3 |  |  | Mock Only
5 |  | 3 hrs | Mounting the /usr/sap/trans done | HEC CTC | 4 |  | N/A | Prior to Mock
6 |  | 3 hrs | Installing the cups packages (only client portion is currently installed) Done | Deepak | 5 |  | N/A | Prior to Mock
7 |  | 4 hrs | Installing the ncftp package. Done | Deepak | 6 |  | N/A | Prior to Mock
8 |  | 30mins | Implement SAP License | HEC CTC | 7 | 0.5 | 0.5 | Can this be done prior ?
9 |  | 30mins | Create users - BATCH_USER, OMP_SOLMAN and SM_ADMIN_OMP | HEC CTC | 8 | 0.5 | 0.5
10 |  | 20mins | Import CMDB role and create/assign to CMDBSAP | HEC CTC | 9 | 0.25 | 0.25
11 |  | 20mins | Import ST-A/PI, RTCCTOLL Check done | HEC CTC | 10 |  | 0.25 | ST-PI and ST-API for monitoring setup
12 |  | 45mins | Import SISM transports and configure for update | HEC CTC | 11 | 0.75 | 0.75
13 |  | 2 hours | SLD connection | HEC CTC | 12 | 2 | 2
14 |  | 2 hours | Implement custom post processing activities | HEC CTC | 13 | 2 | 2
15 |  | 40mins | Import CAM transports | HEC CTC | 14 | 0.75 | 0.75
16 |  | 1 hour | RTCCTOOL configuration | HEC CTC | 15 | 1 | 1
17 |  | 30mins | Update passvault | HEC CTC | 16 |  | 0.5
18 |  | 30mins | Ticket for LMDB/MOPZ/EWA | HEC CTC | 17 |  | 0.5
19 |  | 2 hours | LMDB/MOPZ and Monitoring configuration | HEC Monitoring team | 18 |  | 2
20 |  | 30mins | SAM Setup | HEC CTC | 19 |  | 0.5 | SAM - Service Availability Manager
21 |  | 1 hour | Implement Standard Jobs | HEC CTC | 20 | 0.5 | 0.5
22 |  | 30mins | Implement BATCH_USER | HEC CTC | 21 | 0.5 | 0.5
23 |  | 5 hours | Validate confing and run SGEN | HEC CTC | 22 |  | N/A | Migration
24 |  | 2 hours | Quality checklist spreadsheet update | HEC CTC | 23 |  | 2
25 |  | 2 hours | Handover docs ready (DB backup took around 3 hours) | HEC CTC | 24 |  | 2
26 |  | creation tatsk 1 hr and follup | Interfaces mount points for SFTP fro deepak done | Server Team |  |  | N/A | Prior to Mock
[6 empty] | 8.75 | 16.5 | Total Hours

## MIT Web Deployments
SAP HANA web components for Dec 12-14, 2015 cutover
[Note: we will stage as much as possible (non SAP) in OC11 datacenter by Dec 4]
# | Task description | Request | Execute | When | Comment
0 | Synch OC11 Atlas and Adminapps, EHSapps, Finsys with W92 versions | Kevin | Ops-George G | By Dec 2 | synch staging environmenment in OC11 with current version in "live" W92 enviro.
1 | Atlas: Update servers.json in GitHub with ITS and Web Dynpro URLs, create new release Atlas config, request Ops to deploy in Prod all server, restart tomcat | Dudley | Ops | By Dec 4
2 | Deploy PersInfo WAR - atlas-personalinfo-457-111215115705, Deploy Atlas Config (link file) - atlas-configuration-r27-1117151438 (will change for step 1 above) PO (tomcat) po-po-s2-5-103015121335.war, SAP DOC ATTACH (tomcat) sap-doc-attach-sap-doc-attach-25-102015232100.war, insidemit repo | Dudley | Ops | By Dec 4 | Directory name fix for PersInfo, Add Cognos payroll reports to Reports page
3 | Steps for all 30 replicated application servers (See App Server list below for list of servers):
Tomcat - OC11 only
| a. switch SVN to GitHub for insidemit GitHub repository | Carolyn | Ops | By Dec 4
| b. since PS1-HEC instance number is different, update etc/services for sapmsps1 3601/tcp | Dudley | Ops | By Dec 4 | The instance number for message server changes from 10 to 01
| c. Update GlobalResources.properties with new PS1 connection details (SNC partners name, message server host, system number, logon group) | Dudley | Ops | By Dec 4
| d. restart all tomcat OC11 containers on each app server | Dudley | Ops | By Dec 4
4 | Staging Validation - validation of Atlas and Tomcat apps only by Globetrotters | Kevin | Globetrotters | Dec 4-9 | Confirm how long PS1-clone is up
5 | Steps for 4 remaining non-replicated application servers (See App Server tab for list of servers):
OAS app servers (sky-app-21, -22); tomcat ( asapis-prod-app-1, -2 )
| a. switch SVN to GitHub for insidemit GitHub repository | Carolyn | Ops | PS1 Down | George G has detailed document
| b. since PS1-HEC instance number is different, update etc/services for sapmsps1 3601/tcp | Dudley | Ops | PS1 Down | The instance number for message server changes from 10 to 01
| c. Update GlobalResources.properties with new PS1 connection details (SNC partners name, message server host, system number, logon group) | Dudley | Ops | PS1 Down | just waiting on final SNC name
| d. restart OAS and ASAPIS containers on each app server | Dudley | Ops | PS1 Down
6 | Redirect Production ITS URL: from ps1its.mit.edu to hecps1web01.mit.edu | R3-Admin | Ops | PS1 Down
7 | GTM networking update: point Atlas, AdminApps, AdminAppsts, to OC11 servers | Kevin | Ops-Garry | PS1 Down
8 | ITS: update point-to javascript files within SAP with new ITS and WDA URLs. | Mark | R3-Admin | PS1 Up | included In transport
9 | SAP ssh keys for New Hire feed to Atlas is in place on SAP-HEC (generate or copy, Ron? ) | Larissa | R3-Admin | PS1 Up | R3 action log?
10 | SAP-HEC trusts AdminApps, Insidemit, …. All application servers in W92 and OC11. If PS1 is copied, these should come over. | Dudley | R3-Admin | PS1 Up | Verify
11 | SSO2 trust set up for AdminApps (for touchstone enabled Atlas - if copy of PS1 it should be in place | Dudley | R3-Admin | PS1 Up | Verify in PS1-clone
12 | SAP config tables: |  |  | PS1 Up
| a. ZHR_SVR_LINK (check all ITS and WDA links, make sure using new URLs) |  | Larissa | PS1 Up
| b. ZHRX (check all ITS and WDA links, make sure using new URLs) |  | Larissa | PS1 Up
| c. ZNH_TILE_STEP (check all ITS and WDA links, make sure using new URLs) |  | Larissa | PS1 Up | benefits url
| d. ZHR_EMAIL_PROC (HRPA BENEFITS_C, BENEFITS_P change msg line link ) |  | Larissa | PS1 Up | benefits url
| e. ZEM_ROOM_LINKSID (verify url for photos included "ts" … https://adminappsts.mit.edu/events_content) |  | Larissa | PS1 Up | verify only
13 | Standard Texts (SO10): Update ITS URLs in these two texts: REQUISITIONAPPRB, REQCHANGEDB |  | Carolyn | PS1 Up
14 | Check that JCO MetaUser and Scorm users are unlocked in PS1: ZZJCOMETA000 (run any JCO app, e.g Disp PO) and ZZADMSCORM01 (open learning center course, e.g. event planning, chk table Z...) | Dudley | Carolyn | PS1 Up | Verify
NOTE: new ITS/WDA doman, use https://hecps1web01.mit.edu
| Server Name | Type
| atlas-w92-prod-app-1 | Atlas
| atlas-w92-prod-app-2 | Atlas
| atlas-w92-prod-app-3 | Atlas
| atlas-w92-prod-app-4 | Atlas
| atlas-oc11-4-prod-app-1 | Atlas
| atlas-oc11-4-prod-app-2 | Atlas
| atlas-oc11-4-prod-app-3 | Atlas
| atlas-oc11-4-prod-app-4 | Atlas
| admsys-w92-prod-app-1 | Application
| admsys-w92-prod-app-2 | Application
| admsys-w92-prod-app-3 | Application
| admsys-w92-prod-app-4 | Application
| admsys-w92-prod-app-5 | Application
| admsys-w92-prod-app-6 | Application
| admsys-oc11-4-prod-app-1 | Application
| admsys-oc11-4-prod-app-2 | Application
| admsys-oc11-4-prod-app-3 | Application
| admsys-oc11-4-prod-app-4 | Application
| admsys-oc11-4-prod-app-5 | Application
| admsys-oc11-4-prod-app-6 | Application
| ehssys-w92-prod-app-1 | Application
| ehssys-w92-prod-app-2 | Application
| ehssys-oc11-4-prod-app-1 | Application
| ehssys-oc11-4-prod-app-2 | Application
| finsys-w92-prod-app-1 | Application
| finsys-w92-prod-app-2 | Application
| finsys-oc11-4-prod-app-1 | Application
| finsys-oc11-4-prod-app-2 | Application
| sky-app-21 | Application | Not replicated
| sky-app-22 | Application | Not replicated
| asapis-prod-app-1 | Application | Not replicated
| asapis-prod-app-2 | Application | Not replicated

## MIT Post Processing Task List
Task # | Post-Update R3-Admin Actions (DRAFT) | Day | Start Time | End Time | Duration | Actual Duration | dependancies | Responsible | notes
1 | Update SAP Application Server Profiles | Saturday | 8:15pm | 8:30pm | 15 | 15 |  | Ron | validate
2 | Execute ABAP load generations |  | 8:30pm | 9:15pm | 60 | 45 | 1 | Ron/batch job | required for go live
3 | Transport Process |  |  |  | 120 | 180
| v---------Import post-update transports (define imort queue) |  | 8:30pm | 8:45pm |  |  | 1 | Rich
| v---------Import post-update transports (import) |  | 9:15pm | 11:15pm |  |  | 2 | Rich
4 | Restore pre-update customer wage types |  | 9:15pm | 10:00pm | 30 | 45 | 2 | Ron | required for go live
| v---------- Generate features in client 000 and 030 via report RPUMKG00 |  |  |  |  | 5
| v---------- Execute RGZZGLUX and RGBCFL00 Generations |  |  |  |  | 10
| v---------- Execute RSMODRES generations |  |  |  |  | 1
| v---------- Execute RTCCTOOL utility program |  |  |  |  | 5
| v---------- Execute transaction SIAC_PUBLISH_ALL_INT |  |  |  |  | 10
v---------- Validate Workflow Customizing Settings via transaction SWU3 and report RHSOBJCH
5 | Maintain/verify RFC destinations (i.e. SERVER_EXEC, BSI, IGS_RFC_DEST) |  | 9:15pm | 10:45pm | 60 | 90 | 2 | Ron | required for go live
v---------- Maintain/verify SNC ACL table
v---------- Connect to on-premise Gateways for MITID and FAX RFC servers
v---------- Trusted/Trusting Systems (GRC to ERP, ERP to itself)
6 | Maintain table HTTPURLLOC |  | 9:15pm | 10:00pm | 45 | 45 | 2 | Ron | required for go live
v---------- Execute STRUST and STRUSTSSO2 and update PSEs
v---------- Update SAML2 Touchstone/IDP Config
v---------- Update SAML2 STS Config for ASAPIS connectivity
v---------- Generate updated Web Service WSDL information
v---------- Update/Validate Web Service Call configs (if necessary)
7 | Enable Touchstone integration & Secure Token Service Integration (import, config, validate intergration for secure token service) |  | 10:00pm | 10:30pm | 90 | 30 | 6 | Ron | download completed in prepartion
8 | Execute report BTCTRNS2 to release batch jobs suspended by the update utility |  | 11:15pm | 11:30pm | 30 | 15 |  |  | required for go live
| v---------- Execute SE37 function Z_HR_RETRIEVE_MITID to test MITID connectivity | [5 empty] | 2 | Ron
| v---------- Deploy Mime updates via report WDG_MAINTAIN_UR_MIMES | [5 empty] | 3 | Ron
| v---------- Activate Business Functions (if required) | [5 empty] | 3 | Ron
| v---------- BSI sync | [5 empty] | 3 | Ron
| v---------- Execute RPUBTCU0 to Verify BSI 10 connectivity | [5 empty] | 2 | Ron
9 | Execute SPAD (Printer config, TEMSE Administration) |  | TBD |  | 30 | 30 | ? | Deepak | required for go live
10 | Restart SAP servers (make sure everthing gets copied over) |  | 11:30pm | 11:50pm |  | 20 | 8 | Deepak | required for go live (need OS access)
11 | Execute Post-Update Trial Balance reports |  | 11:15pm | 11:45pm | 45 | 30 | 3 | Ron | required for go live
12 | Configure OpenText connectivity |  | 10:00pm | 10:45pm | 60 | 45 | 6 | Ron | required for go live
V---------- Update Content Repositories
v---------- Enable ERP to OpenText Archive handshaking
v---------- Update OpenText Java Viewer Attributes
13 | General Action Log steps (per FQUERN) |  | 9:15pm | 9:30pm | 15 | 15 | 2 | R3-Admin | required for go live
14 | Enable ERP PDF rendering via ADS |  | 11:15pm | 11:30pm | 30 | 15 | 3 | Rich | portion is pre-configured
v---------- Define/enable ADS to ERP RFC connection
v---------- Execute ADS test reports in ERP
v---------- FP_CHECK_DESTINATION_SERVICE (Test Program for Destination Service of Templates)
v---------- FP_PDF_TEST_00 (Test Program: Version Information (for Analysis Only))
v---------- FP_TEST_00 (Form Processing: Central Test Program)
v---------- FP_TEST_03 (Flight Booking Example)
15 | Enable Dropbox/Interfaces Connectivity | Sunday | 11:30am |  | 75 | 75 | during/after business validations | REP, Qian, Rich, Garry | required for go live
| v---------- Deactivate on-premise cron jobs | Saturday | TBD |  |  |  | shut down process
| v---------- Activate cron jobs in HEC | Sunday |  |  |  |  | Sunday morning window
| v---------- Validate FTP connectivity to external partners | Sunday |  |  |  |  | Sunday morning window
| v---------- Update SFTP server scripts and connections (pre) | TBD |  |  |  |  | between now & go live
| v---------- Verify SFTP server scripts and connections (post) | Sunday |  |  |  |  | Sunday morning window
16 | Validate User Maintenance processes | Sunday |  |  | 60 | 60 | 2 | George | required for go live | Sunday morning window
v---------- Test the User Administration programs in Test (non-update) mode
v---------- Execute User Maintenance update with Friday updates
v---------- Start ST01 authorization trace on all PS1 servers
v---------- Unlock IDs at appointed times
17 | Validate GRC | Sunday |  |  | 90 | 90 | 5 | Sarah | required for go live | Sunday morning window
v---------- Dashboard Reports: Access Rule Library
v------------- Mitigating Control Library
v------------- Risk Violations
v------------- User Analysis
v------------- Role Analysis
v------------- Violations Comparisons
v---------- User Level RA Report for for VPF and IS&T custom groups
v---------- User Level simulation, adding a role to a user
v---------- Role level simulation, adding a transaction to a role
v---------- Firefighter log reports
v---------- Repository Object Sync job
v---------- Firefighter test - Log into ACP--> PS1, run several transactions
v---------- Run Firefighter log sync job
v---------- Firefighter Controller - Return Firefighter log to Firefighter for additional information
v---------- Firefighter returns log with additional information requested
v---------- Approve log
v---------- Roles Database user simulation test with GRC
876
14.6
OpenText Data Transfers

## HA DR
Action Checklist
# | Procedure Step | Executed by | Applicability to test | Planned Start time | Planned Completion time | Date | Completed | Actual Start time | Actual Completion time | Notes
Pre-Test Activities
Both | Notify users of scheduled downtime |  |  |  |  | 2015-12-11
Both | Verify VPN tunnel is operational in Santa Clara | MIT |  | 12:00 | 12:00 | 2015-12-11
Both | Set systems to planned downtime - 12/13/15 10:30 AM - 12/13/15 4 PM ), IT Event Calendar | SAP |  | 12:00 | 12:00 | 2015-12-11
| Send invite for test day Conference Bridge | Phil Ferenschak |  | 14:00 | 14:00 | 2015-12-11
| Test Activities |  |  |  |  | 2015-12-13
Both | Open Conference Bridge -- | Phil Ferenschak |  | 1:30 | at conclusion | 2015-12-13
Both | Stop or reschedule all batch jobs | Ron Parker | Not Applicable for this Test | 8:00 | 8:30 | 2015-12-13
Both | Shutdown interfaces | Ron Parker | Not Applicable for this Test | 8:00 | 8:30 | 2015-12-13
Both | Clear alI Message Queues | Ron Parker | Not Applicable for this Test | 8:00 | 8:30 | 2015-12-13
Both | Notify of Completion batch / interface job completion | Ron Parker | Not Applicable for this Test | 8:30 | 8:30 | 2015-12-13
| Change IP address for Load Balancer to Santa Clara IP address | MIT Network Team |  | 2:00 | 2:15 | 2015-12-13 |  |  |  | 15
| MIT makes transactions in PS1 sterling | MIT |  | 2:15 | 2:45 | 2015-12-13 |  |  |  | 30
| MIT communicates readiness for Test | Ron Parker |  | 2:45 | 2:45 | 2015-12-13
| Wait for transaction replication RTO | Phil Ferenschak |  | 2:45 | 3:15 | 2015-12-13 |  |  |  | 30
Both | Declare Disaster (test) | SAP |  | 3:15 | 3:15 | 2015-12-13
| Notify DR Site (Santa Clara) of disaster event | HEC / MIT | Not Applicable for Test
Both | Activate Call Tree Notification | SAP HEC | Not Applicable for Test
Both | Initiate MIT notification to users | SAP HEC | Not Applicable for Test
Both | Establish DR call | MIT | Not Applicable for Test
| Stop HANA replication/shut down applications @ Sterling | SAP Team |  | 3:15 | 3:30 | 2015-12-13 |  |  |  | 15
Both | Stop BSP in Sterling | Ron Parker |  | 3:15 | 3:30 | 2015-12-13
| Failover to Santa Clara | SAP Team |  | 3:30 | 3:45 | 2015-12-13 |  |  |  | 15
Both | Startup applications @ SAC | SAP Team |  | 3:45 | 4:30 | 2015-12-13 |  |  |  | 45
10-24 | Phil Ferenschak to notify Frank Quern, Ron Parker & Bob Casey when systems are up in Santa Clara | Phil Ferenschak |  | 4:30 | 4:30 | 2015-12-13
| Start BSP in Santa Clara ; Ron Parker Notifies Frank Quern and Bob Casey when complete & they can begin transaction processing | Ron Parker |  | 3:45 | 4:00 | 2015-12-13
| MIT confirms transactions entered in Sterling are found in Santa Clara | MIT |  | 4:30 | 4:45 | 2015-12-13 |  |  |  | 15
Both | MIT enter test data into Santa Clara Server to confirm systems operational | MIT |  | 4:45 | 5:30 | 2015-12-13 |  |  |  | 45
| Frank Quern informs Ron Parker & Phil Ferenschak of test completion | Frank Quern |  | 5:30 | 5:30 | 2015-12-13
Both | Stop BSP in Santa Clara | Ron Parker |  | 5:30 | 5:45 | 2015-12-13
| shut down applications @ Santa Clara | SAP Team |  | 5:30 | 6:15 | 2015-12-13 |  |  |  | 45
| Failback to Sterling | SAP Team |  | 6:15 | 6:30 | 2015-12-13 |  |  |  | 15
| Startup applications -STL | SAP Team |  | 6:30 | 6:45 | 2015-12-13 |  |  |  | 15
| Phil Ferenschak to notify Ron Parker, Frank Quern & Bob Casey when systems are up in Sterling | Phil Ferenschak |  | 6:45 | 6:45 | 2015-12-13
| Start BSP in Sterling | MIT |  | 6:30 | 6:45 | 2015-12-13
| Change IP address for Load Balancer to Sterling IP address | MIT Network Team |  | 6:45 | 7:00 | 2015-12-13 |  |  |  | 15
| Verify monitoring and management tools functioning | SAP Team |  | 6:45 | 6:55 | 2015-12-13
| Ron Parker performs testing on PS1 to confirm connectivity and operation | Ron Parker |  | 6:45 | 7:15 | 2015-12-13 |  |  |  | 15
| SAP regenerates Replication to Santa Clara | SAP Team |  | 6:55 | 7:10 | 2015-12-13
315
5.25

## HA Task List
# |  | Time | Duration | Action / Task | Person(s) Responsible | Status | Acutal Duration
High Availability MIT Functional Test
1 | Sunday 12/13/2015 | 7:30 AM - 11:00 AM (Eastern Standard Time) | 60 mins | MIT performs transactions on Site 1 |  |  | 60
2 |  |  | 1 mins | MIT notifies Phil Ferenschak of Data completion |  |  | 1
3 |  |  | 5 mins | Take Screen shots of Site 1 machine |  |  | 5
4 |  |  | 10 mins | Shut down Primary Site 1 HANA |  |  | 10
5 |  |  | 10 mins | Failover from Primary (Site 1 ) HANA to Site 2 HANA |  |  | 10
6 |  |  | 5 mins | Start up Alternate (Site 2) HANA |  |  | 5
7 |  |  | 10 mins | Establish replication between Site 2 HANA to Primary site 1 HANA |  |  | 10
8 |  |  | 1 mins | Phil Ferenschak notifies MIT that Alternate site is operational |  |  | 1
9 |  |  | 60 mins | MIT performs transactions on Site 2 |  |  | 60
10 |  |  | 1 mins | MIT notifies Phil Ferenschak of Data completion |  |  | 1
11 |  |  | 5 mins | Take Screen shots of Alternate machine |  |  | 5
12 |  |  | 5 mins | Shut down Alternate (Site 2) HANA |  |  | 5
13 |  |  | 5 mins | Failover from Site 2 to Primary site 1 |  |  | 5
14 |  |  | 5 mins | Start up Primary (Site 1) HANA |  |  | 5
15 |  |  | 20 mins | Re-establish replication between Primary Site HANA to Site 2 HANA |  |  | 20
16 |  |  | 1 mins | Phil Ferenschak notifies MIT that Primary site is operational |  |  | 2
17 |  |  | 5 hrs | Re-establish replication between Site 2 and DR site 3 |  |  |  | executed in parallel with subsequent steps
205
3.4167

## Escalation Path
Escalation Path
If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Siobhan Cunningham will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday December 7th.
Functional Malfunction(s)
Stef Desmond | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike Peretti | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Laurie Veal | Business Process Owner (EH&S) / Weekend Coordinator
Cathy Cherico | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Siobhan Cunningham | Project Manager
Mark Silis | Associate Vice President, IS&T
Chris Holness | SAP
Pat Casey | SAP
Stephen Koczur | SAP HEC
Fabiab Dias | SAP Basis
Deepak Kamath | SAP Basis
Escalation Support Team
Ron Parker | Basis PO
George Petrowsky | R3 Authorizations
Elena Zhitnikov | Data Warehouse Team
Frank Quern | HRP PO
Siobhan Cunningham | Project Manager
Bob Casey | FLE PO
Kevin Lyons | Atlas PO
Lee Collier | Scrum Master
Meaghan Murray | Scrum Master
Olympia Valentine | Scum Master
Qian Kang | Scrum Master

## Validation
Production Validation
Production Validation will occur in NE49, W92 and remotely. Validation is scheduled to start at 12:00 PM, however, please check the message line (617-324-7468) before coming into the office or starting to test remotely. The message will be updated by 11:30 AM if there are potential delays and by 12:00 PM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 8th. Frank will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/Stef desmond | Trial Balance Report validation occurs first. Ron Parker will email Stef Desmond, Siobhan Cunningham and Frank Quern when the reports have finished processing. Stef will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following:Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log second. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu