## Overview and Assumptions
Timeframe for Test Execution
Comparison Test: 11/7/2011-11/28/2011 (3 holidays)
Integration Test: see comparision test
Assumptions:
Production snapshot as of midnight 10/21/2013
Test system will be available by start of day 11/4/2013
Comparison test consists of four payroll comparisons:
| Weekly Non-Exempt (payweek 43 (10/14/2013-10/20/2013)) | LL | 44/2013??
| Monthly Exempt (October 2013) | MC | 45/2013?? | Cycle 1 | Leslie will identify cost objects
Pension Payroll Lump Sum (October 31, 2013)
Pension Monthly Annuity Run (Nov 2013)
Overview of integration test strategy:
Generate payroll and run interfaces simulating the production payroll processes.
Compare test system SH1 results to PS1 Production results
Research discrepancies; resolve system issues
Execute select test scripts hiting key functionality not executed during pay run processes
Comparison Tools:
Create comparison reports using the EPIUSE variance monitor tool
Net pay comparisons in excel
Net pay comparison using EPIUSE variance monitor
Ultra Compare
Fox Pro
Overview of Script testing - majority of testing conducted by Business:
Test Scripts identified in Quality Center, both manual and automated:
in the HR domain space are the folder containing test scripts:
HR-Payroll/Manual_test_Suite
HR-Payroll/Automated_Test_Suite
Test lab folder: 2013_SupportPacks

## Comparision Run Schedule
Task # | Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Prep files ready? | Batch ID | Job Set # | Special Variant in PS1? | Update variant in sh2 | Notes | No. of files matched | SF3 | SF3-H | Variances | Percent matched | Reasons for differences
SF3 Environment Ready - Prep for testing
1 | Verify Feed Registry Archive Control Tables are correct for the environment - Need to change encryption flag for those files which are copied into test sapin directory. | SM30 | n/a | 2014-10-30 | 2014-10-30 | SD |  | n/a |  |  |  |  | Part of the action log. | n/a | n/a | n/a | n/a | n/a
2 | Setup EDI test in SF3-H - ( Benefits ) |  |  | 2014-10-30 | 2014-10-30 | Larissa | [6 empty] | 2013 - Ron needed to resave the port (needed in PS1?)
Repoint EDI test in SF3-H - ( Benefits )
3 | Re-configure EDI Test Environment to accept files from SF3-H - EDI for Lincoln |  | n/a | 2014-10-30 | 2014-10-30 | Ron, Larissa will remind him |  | n/a |  |  |  |  | Larissa points SP test env to EDI server | n/a | n/a | n/a | n/a | n/a
4 | Confirm w/ R3 that Lincoln configuration for EDI is active in SF3-H and SF3 |  | n/a | 2014-10-30 | 2014-10-30 | Larissa |  | n/a |  |  |  |  | 2013: Per Larissa this needs to be done before the LL inbounds. Per Eric Ngo - 2012: The logical system is RC2CLNT400.(Ron should verify) | n/a | n/a | n/a | n/a | n/a
5 | Notify R3 Admin with list of files to be placed in sapin directory Lincoln inbound and MIT Alert |  |  |  |  | Larissa
6 | Request Pension upload files from Laurie - file for August payrolls |  |  |  |  | Gregg
7 | Copy MITSIS Bio feed file to DATA files folder for testing copy file from 7/7 |  |  |  |  | Mary | Complete | Yes
8 | Execute ZM, ZP Payroll simulation in SF3 & SF3-H for period 07.2015 (ZM) and 08.2015 (ZP). Compare data between two environments. |  |  | 2014-10-30 | 2014-10-30 | Gregg M. | [6 empty] | Compare to PS1 run. Use single line rem-statement. Log and report tie out. Don't need to wait for steps 1,,3
9 | Validate APR web connections functional to SF3-H. |  |  | 2014-11-03 | 2014-11-03 | Emily
10 | Load ASR macros uploaded from the archive server to the proper server for each environment - SF3 & SF3-H - so that the ASR Faculty spreadsheet works correctly. |  |  | 2014-11-04 | 2014-11-04 | Emily | [6 empty] | Send email to Wai-ming
11 | DW extract of HR/Pay data | Multiple | n/a | 2014-11-03 | 2014-11-03 | Elena |  | n/a |  |  |  |  | Payrolls and feeds may be running
12 | Assign batch ids to testers - see sheet Batch IDs and aliases |  |  | 2014-11-03 | 2014-11-03 | George | [6 empty] | Send George list of ID's
13 | Validate Laurie19 aliases established |  |  | 2014-11-03 | 2014-11-03 | Mary & Gregg
Feeds testing Set 1
14 | Outbound Run FSA Census outbound interface - SF3 & SF3-H Compare files - mimic variant from Sunday's 7/5. | PGM: ZPYI0170_FSA_CENSUS_DATA | py/fsa_census | 2014-11-03 | 2014-11-03 | Karen |  | Yes | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution |  |  |  | 3
Weekly and Pension Payrolls
15 | Weekly Payroll Processing (28/2015) - SF3 & SF3-H Work week 06/29/2015-07/05/2015 (Execute with LAURIE19 alias) | Follow Non-exempt payroll checklist |  | 2014-11-03 | 2014-11-03 | MD |  | n/a | LAURIE19 alias |  |  |  | see comparisons results in step 22 below | - | - | - | - | -
16 | Pension Payroll - Lump Sum Run (7/31/2015) SF3 & SF3-H (includes loading PS1 copy of Pension Lump Sum file) (Execute with LAURIE19 alias) | Follow MIT Lump Sum checklist |  | 2014-11-03 | 2014-11-03 | GM |  |  | LAURIE19 alias |  |  |  | Where do files come from? encrypted file dumps decrypted file processes correctly
17 | Pension Payroll - Annuity Run (08/2015) SF3 & SF3-H (includes loading PS1 copy of Pension Annuity file) (Execute with LAURIE19 alias) | Follow MIT Annuity checklist |  | 2014-11-03 | 2014-11-03 | GM |  |  | LAURIE19 alias |  |  |  | Where do files come from? see comparisons results in step 23 below | - | - | - | - | -
18 | Notify DW ZW and ZP have been run and posted (including CDU) ZM TBD. |  |  |  |  | Mary
Feeds testing Set 2
19 | Outbound Benefits outbound: BCBS SF3 & SF3-H Compare files - mimic variant from Sunday's 7/5. Run for dates 10/19 - 100 days thru 10/19 + 45. In IDOC Cleanup allow retro 10 days-variant all set. | Two steps: rpuben52 & program ZHR_BENEFIT_IDOC_CLEANUP. | hr/bcbs | 2014-11-03 | 2014-11-03 | Karen |  | Yes | ZZHRBENBTC01 | 1 | Use BLUE CROSS D when not in OE cycle for RPUBEN52 , else use SP BC OED/ SP BCBS PRD OE. Use BCBS PROD for ZHR_BENEFIT_IDOC_CLEANUP when not in OE cycle. |  | can run w/ DW extracts; comparison will be made to the production run (EDI)
20 | Outbound Run Crosby Outbound terminations; SF3 & SF3-H Compare files - mimic variant from Sunday's 7/5. | PGM: ZHRCSB02 | hr/crosby; | 2014-11-03 | 2014-11-03 | Karen |  | Yes | ZZHRBENBTC01 | 1 | SPZHRCSB02_RPT |  | can run w/ DW extracts
Data comparison tasks 1 - compare SF3 to SF3-H
21 | Payroll Results Comparison (ZW) |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | pernrs | n/a
22 | Payroll Results Comparison (ZP) |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | pernrs | n/a
23 | Payroll Results Comparison (ZP)Lump Sum |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | pernrs | n/a
24 | FI POSTING COMPARISON (ZP) |  |  | 2014-11-04 | 2014-11-06 | Gregg M. | [6 empty] | lines in document | n/a
25 | FI POSTING COMPARISON (ZP)Lump Sum |  |  | 2014-11-05 | 2014-11-07 | Gregg M. | [6 empty] | accounts | n/a
26 | EDACCA TABLE COMPARISON |  |  | 2014-11-05 | 2014-11-07 | Gregg M. | [7 empty] | n/a
27 | FI POSTING COMPARISON (ZW) |  |  | 2014-11-05 | 2014-11-07 | Gregg M. | [6 empty] | lines in document | n/a
Feeds testing Set 3
28 | Inbound Student Bio Feed (MITSIS) (7/7) - local Process in SF3 & SF3-H - compare output reports and spot check results. | Trans: ZMITSIS PGM: ZPY_LOAD_MITSIS_BIO_DATA | py/mitsis_dem | 2014-11-04 | 2014-11-04 | Meaghan |  | Yes | ZZHRMITSIS01 | Execute these 5 feeds in order listed. | No | n/a | both old and new complete
29 | Inbound LL daily feed (TBD). Feed files can be identified by running ZHRALELOG File Seq# XXX Process in SF3 & SF3-H - compare output reports and spot check results. Need to copy unencrypted file to sh2/sapin directory. | Trans: ZHRALE PGM: ZHRALE01 | hr/ll_hr_time Provider ccode=mith Feed code= hrm | 2014-11-04 | 2014-11-04 | Karen |  | Yes | ZZHRLLFEED01 |  | No | n/a | Check for errors on filezilla Validate using transaction ZHRALELOG TBD (may be that Eric will review)
30 | Email: EL training reminder | PGM: ZTN_ACTSEL_NOTIF_TRAINING | N/A | 2014-11-04 | 2014-11-04 | Mary |  |  | ZZHRELBTCH01 |  | No | n/a | Use zehcat entry: HY to not send email
Monthly Payroll Processing - ZM
31 | Monthly Payroll Processing - ZM - 07.2015 | Follow Exempt Payroll Checklist |  | 2014-11-04 | 2014-11-04 | MD |  | n/a |  |  |  |  | see results below | n/a | n/a | n/a | n/a | n/a
32 | Notifiy DW ZM has been run and posted, including CDU. |  |  |  |  | Mary
Data comparison tasks 2 - compare SF3 to SF3-H
33 | Payroll Results Comparison (ZM) |  |  | 2014-11-05 | 2014-11-05 | Gregg M. |  | - |  |  |  |  | pernrs
34 | EDACCA TABLE COMPARISON |  |  | 2014-11-05 | 2014-11-05 | Gregg M. |  | - |  |  |  |  | see detail notes tab
35 | FI POSTING COMPARISON |  |  | 2014-11-05 | 2014-11-05 | Gregg M. |  | - |  |  |  |  | lines in document
36 | After ZM 3-Party Processing - Test garnishments to A/P: Run F110 payment process; verify check format and Mass ACH file format. |  |  | 2014-11-05 | 2014-11-05 | Gregg M, Ken LeVie |  | n/a |  |  |  |  | ZM 3PR pp 03.2010 new vs. old are a match - 33 vendor payment line items in each = 100%
| Feeds testing Set 4 Outbound Interfaces (Comparisons to production files) | [11 empty] | Set up jobs Friday. | n/a | n/a | n/a | n/a | n/a
37 | Outbound Pension outbound interface - Employment file Process in SF3 & SF3-H | Trans: ZPY_PENSION_EMPL PGM: ZPY_PENSION_EMPLOYMENT | py/pen_empl | 2014-11-04 | 2014-11-04 | Run by Gregg, compares by Cindy |  | Yes | ZZPYBATCH001 |  | no | n/a | Run Sept and Oct for comparisons for reasonability?
NEW HIRE Feeds and Reports
38 | Create a new hire employee eligible for work - indicate I9 Office has processed new hire. - SF3 & SF3-H | PA30/PA40 |  |  |  | Meaghan
39 | Update / Outbound ZHR_NEWHIRE_NOTIFICATION (daily) - update - | ZHR_NEWHIRE_NOTIFICATION | not copied here | 2014-11-04 | 2014-11-04 | Run by Karen with Meaghan |  | n/a | ZZHRBENBTC01 |  | PS1 Varinats DAILY_ADD_NH | Yes | Processed as of 10/21/14 (for new hires added in production 10/20/14)
40 | ZHR_NEW_HIRE_FEED_FOR_ATLAS - outbound - run twice, two variants | ZHR_NEW_HIRE_FEED_FOR_ATLAS | hr/atlas_nh | 2014-11-04 | 2014-11-04 | Run by Karen with Meaghan |  |  | ZZHRBENBTC01 |  | atlas_server1 atlas_server2 | No | Added entry in zutarchivecrtl for atls and feed code nh1
41 | Inbound ZHR_DW_MITALERT_IN (daily) | ZHR_DW_MITALERT_IN | hr/mit_alert | 2014-11-04 | 2014-11-04 | Run by Karen with Meaghan |  |  | ZZHRBENBTC01 |  | PS1 Variant DAILY W/O | No | Processed 3 files from 10/22/14
| Additional payroll tests | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
42 | Update SH2 with any PS1 updates conducted after 7/6 * eW-2 parameters *eW-2 false positives *Update Payroll control records for earliest retro date |  |  | 2014-11-06 | 2014-11-06 | Mary , Gregg,
43 | Create and download 1042-S file |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
44 | Validate ACH File |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
45 | Testing printing (send test request to ops-help@mit.edu): Payroll check |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
46 | Testing printing (send test request to ops-help@mit.edu): Payroll advices |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
47 | Testing printing (send test request to ops-help@mit.edu): DACCA |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
48 | Testing printing (send test request to ops-help@mit.edu): W-2 |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
49 | Testing printing (send test request to ops-help@mit.edu): 1099R |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
50 | Testing printing (send test request to ops-help@mit.edu): 1042-S |  |  | 2014-11-07 | 2014-11-07 | Mary , Gregg, | [6 empty] | Frank keep MICR formatting card in his signature and bank file
51 | Remediation Program to test: APR Terminations - requires approval, R1 initiator - process all the way thru to the backend. | LZHR_APPOINTMENT_PROCESSU31 |  |  |  | Emily | [6 empty] | Frank keep MICR formatting card in his signature and bank file
52 | Remediation Program to test: SHA Inbox | LZHR_HSA_INBOXF01 |  |  |  | Cindy | [6 empty] | Frank keep MICR formatting card in his signature and bank file
Once all above are complete, continue testing on spreadsheet Transaction Testing
Legend:
Pay run execution
Section Heading
Lincoln Lab

## Userids and Aliases
Tester | Userid | Date to allow access | Assign batch id | Create alias | Additional authorizations
Frank Quern | fquern
Mary Donovan | donovan |  | zzhrelbtch01 | laurie19
Larissa Kushkuley | lkushkul
Sharon Diliberto | dilibert
Gregg McGrath | gmcgrath |  | ZZPYBATCH001 | laurie19
Emily Cunningham | ecunning |  |  | amccosh R3EDUI10
Karen Nolet | knolet |  | ZZHRBENBTC01 ZZHRLLFEED01
Meaghan Murray | mamurray |  | ZZHRMITSIS01
Cindy DeSimone | cindyo
Mark Prudden | mprudden

## Transaction Testing
Test Count | TransactionReportName | Transaction (T) Report (R) | 2014 Count | 2013 Count | Title | Indicate NEW if new for 2014 | MIT custom? Y/N | Team Responsible (HR/Payroll; Fin; EHS; Logistics; ABAP; Basis) | Test during 2013 Unit test? Y/N/TBD | Test for 2014? | Tested by | Unit test results Pass/Fail | Notes
1 | ZHR_HSA_BACKEND | R | 66778671 | 2101666 | HR: HSA monitors appointment requests that have been submitted to SAP |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone |  | Test Manual update in SF2
2 | ZHR_APR_AUTHORIZATIONS | R | 46909 | 947 | HR APR authorizations report |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone
3 | ZHRDWLIMITACCESS | R | 63717 | 14969 | Add entries to Data Warehouse access table ZHRDWLIMITACCESS |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone |  | Duplicate - to transaction
4 | ZHROM_AUDIT2 | R | 3755 | 61 | HR-OM: Job Description List Report |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone
5 | ZHRPRINTERS | T | 0 | 84 | Valid Printers Pers Action Forms |  |  | HR/Payroll | Yes | Yes | Cindy DeSimone
6 | ZPYR_MAP_RECONCILE | T | 78 | 66 | MAP Reconcilliation Report |  |  | HR/Payroll | Yes | Yes | Cindy DeSimone
7 | PP02 | T | 135708108 | 8458040 | Maintain Plan Data (Open) |  | No | HR/Payroll | Yes | Yes | cindy DeSimone |  | 0
8 | ZHR_HOURLY_GRAD | T | 30198 | 24786 | Hourly Paid Graduate Student Setup |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone |  | os note applied, reran successfully 2010; 2011 ran okay
9 | ZHRMITID | T | 88152 | 5699 | Search Assign MITIDs |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
10 | ZOMCGST | T | 215989 | 27345 | HR - process OM transactions |  | Yes | HR/Payroll | Yes | Yes | cindy DeSimone
11 | ZOMCHSTL | T | 1653 | 814 | HR - process Lincoln OM transactions |  | Yes | HR/Payroll | Yes | Yes | cindy DeSimone
12 | PA40 | T | 4881285 | 431678 | Personnel Actions |  | No | HR/Payroll | Yes | Yes | Cindy DeSimone |  | To insure the 9003 post processing is working, test a non-exempt, an exempt RGE1 and MNT1 9month duration. SPOT too
13 | PA41 | T | 161168 | 5747 | Change Entry/Leaving Date |  | No | HR/Payroll | Yes | yes | Cindy DeSimone |  | 0
14 | PO03 | T | 854168 | 40829 | Maintain Job |  | No | HR/Payroll | Yes | yes | Cindy DeSimone |  | 0
15 | PO10 | T | 213574 | 7508 | Maintain Organizational Unit |  | No | HR/Payroll | Yes | yes | Cindy DeSimone |  | 0
16 | PO13 | T | 1608302 | 156370 | Maintain Position |  | No | HR/Payroll | Yes | yes | Cindy DeSimone |  | 0
17 | PO13D | T | 64805 | 985 | Display Position |  | No | HR/Payroll | Yes | yes | Cindy DeSimone |  | 0
18 | PP01 | T | 920177 | 63224 | Maintain Plan Data (Menu-Guided) |  | No | HR/Payroll | Yes | yes | Cindy DeSimone |  | 0
19 | PP01_DISP | T | 15190 | 1355 | Display Plan Data (Menu Guided) |  | No | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
20 | PPOM | T | 209681 | 13250 | Maintain Organizational Plan |  | No | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
21 | PPOS_OLD | T | 52127 | 4729 | Display Organizational Plan |  | No | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
22 | RE_RHBEGDA0 | T | 23305 | 6905 | Change start date |  | No | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
23 | S_AHR_61016380 | T | 408996 | 33337 | Logged Changes in Infotype Data |  | No | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
24 | ZHR_CDAT | T | 91042 | 4077 | HR: Convert pay date to/fm earn date |  | Yes | HR/Payroll | yes | Yes | Cindy DeSimone |  | 0
25 | ZHR_IT9033_AUDIT_RPT | T | 87741 | 2523 | HR/PY: IT9033 AUDIT REPORT |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone
26 | ZHR_JOB+POS_DESC | T | 44247 | 3781 | Complete Job/Position Description |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
27 | ZHRCONFIDENTIAL | T | 0 | 78 | Maintain HR/Payroll Confidential |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone
28 | ZHRLTD_ASSIGN | T | 23828 | 1593 | Transfer an Active Employee to LTD |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone
29 | ZHRPAYROLL_INTERFACE | T | 29765 | 44816 | Run HR Payroll Interface Report |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone |  | 0
30 | ZOMC | T | 3986445 | 209091 | HR - process OM transactions |  | Yes | HR/Payroll | Yes | Yes | Cindy DeSimone |  | Suite test (create, delimit)
31 | ZOMCHST | T | 40939 | 103772 | HR - process OM transactions |  | Yes | HR/Payroll | Yes | yes | Cindy DeSimone |  | 0
32 | ZPY_PENSION_COMP | T | 0 | 69 | Pension compensation for TW |  | Yes | HR/Payroll | Yes | yes | Cindy Desimone
33 | ZPY_PENSION_EMPL | T | 0 | 174 | Pension employment data for TW |  | Yes | HR/Payroll | Yes | yes | Cindy Desimone
34 | ZPYR_APPT_MESSAGES | T | 41285 | 1824 | Appointments Messages Report |  | Yes | HR/Payroll | Yes | yes | Cindy Desimone |  | 0
35 | ZHRX | T | 5001 | 6 | HR: Modify Generic parameter table |  | Yes | HR/Payroll | Yes | yes | Cindy DeSimone
36 | ZHR_HSA_LOG | T | 356483 | 33938 | HR Hourly Students Log |  | Yes | HR/Payroll | Yes | yes | Cindy DeSimone |  | Test Web dynpro front end IE, Firefox, Chome
37 | ZHR_APR_AUTH | T | 46909 | 917 | Display HR APR Authorizations |  |  | HR/Payroll | Yes | Yes | Cindy DeSimone
38 | ZHR_UROP | T | 43627 | 119 | Maintain table ZHR_UROP |  |  | HR/Payroll | Yes | Yes | Cindy DeSimone
39 | RHBUCH00_LSO | R | 47250 | 1935 | Bookings per Participant |  | No | EL | Yes | Yes | Emily Cunningham |  | LSO_RHXBUCH0
40 | RHPEQCAT | R | 101487 | 5531 | Change/Display Qualifications Catalog |  | No | EL | Yes | Yes | Emily Cunningham
41 | RHQALIF0 | R | 2443 | 1066 | Attendee's Qualifications |  | No | EL | Yes | Yes | Emily Cunningham
42 | OOER | T | 0 | 81 | Create External Instructor |  |  | HR/Payroll | Yes | Yes | Emily Cunningham
43 | PV02 | T | 0 | 1 | Prebook Attendance |  |  | HR/Payroll | Yes | Yes | Emily Cunningham
44 | PVH0 | T | 0 | 28 | Create/Change External Instructor |  |  | HR/Payroll | Yes | Yes | Emily Cunningham
45 | LSO_PP40 | T | 3699 | 850 | Manual Output |  |  | EL | Yes | Yes | Emily Cunningham
46 | ZASR | T | 2000015 | 80098 | Annual Salary Review |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham |  | Include Promo and Tenure; Export and Import of Spreadsheet; full cycle through activation
47 | ZASR_FAC_SUPPL_LOAD | T | 351 | 31 | ASR: Load Faculty Supplements Table |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham |  | 0
48 | ZASRREJECTS | T | 51189 | 1842 | HR: ASR Rejects Report |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham |  | 0
49 | ZASRSUMRPT | T | 530817 | 13949 | Annual Salary Review - Summary Rpt |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham |  | 0
50 | ZASRTBL | T | 25449 | 2884 | ASR: Table Maintenance |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham |  | 0
51 | ZHRAP | T | 3956940 | 187113 | APR backend processing |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham
52 | ZHRAP_USER | T | 9374 | 634 | APR backend processing: regular user |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham
53 | ZHR_APR_AUDIT | T | 1649 | 418 | APR Audit Reconciliation |  | Yes | HR/Payroll | Yes | Yes | Emily Cunningham
54 | PU00 | T | 0 | 66 | Delete Personnel Data |  |  | HR/Payroll | Yes | Yes | Emily Cunningham
55 | ZHR_APR_OPEN_REQS | T | 0 | 12 | Open APR requests |  |  | HR/Payroll | Yes | Yes | Emily Cunningham
56 | ZHRSPECIAL_DATES | T | 0 | 237 | Special dates table |  |  | HR/Payroll | Yes | Yes | Emily Cunningham
57 | APR - Hire | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
58 | APR - Supplement | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
59 | APR - Termination | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
60 | APR - Leaves | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
61 | APR - Changes | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
62 | APR - Copy | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
63 | APR - Edit | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
64 | APR - Attachments | [6 empty] | HR/Payroll |  |  | Emily Cunningham/ Cindy DeSimone
65 | PE00 | T | 15 | 76 | Starts Transactions PE01, PE02, PE03 |  | No | HR/Payroll | No | No | Gregg McGrath
66 | RPCTRDU0 | Report | 630 |  | PCL4 -DISPLAY/DELETE (U1) | New |  | HR/Payroll |  | No | Gregg McGrath |  | Duplicate
67 | RPCSC000 | R | 93110 | 5742 | Scheduler for parallel accounting |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
68 | ZQADTAXREP | R | 0 | 108 | W2 Comparison Report |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath
69 | RPLWCOU0 | R | 984 | 720 | US Workers' Compensation Report |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
70 | ZPY_LOADTBL_W2_W25C | R | 1932 | 45 | Towers Watson Pension Plan W-2 box 13 |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath
71 | ZPY_LOAD_ZPYTEMPCODES | R | 3825 | 117 | HRPR: Load Payroll Table ZPYTEMPCODES |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath
72 | RPUSCC00 | R | 0 | 10 | Compare Schemas |  |  | HR/Payroll | Yes | Yes | Gregg McGrath
73 | RPUTRBK0 | R | 0 | 91 | Transfer old payroll results: Update Payroll Status (Infotype 0003) |  |  | HR/Payroll | Yes | Yes | Gregg McGrath
74 | S_AHR_61015611 | T | 68208 | 5506 | Wage Type Statement |  |  | HR/Payroll | Yes | Yes | Gregg McGrath
75 | PA70 | T | 0 | 1115 | Fast Entry |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
76 | PAUX | T | 749445 | 65622 | Adjustment Workbench |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
77 | PAUY | T | 77219 | 12102 | Adjustment Workbench (retro proc.) |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
78 | PC00_M10_CALC_SIMU | T | 1194732 | 71595 | Simulation payroll accounting 10 |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
79 | PC00_M10_CEDT | T | 76846 | 7482 | Payroll Remuneration Statement - 10 |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
80 | PC00_M10_CLAIMS | T | 206146 | 19481 | Claims processing |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
81 | PC00_M10_CLJN | T | 44693 | 238 | Payroll Journal |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
82 | PC00_M10_CLSTR | T | 85935 | 27703 | Tools - Payroll Results - 10 |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
83 | PC00_M10_FFOC | T | 76487 | 6780 | Payroll Transfer - Check Printing 10 |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath |  | RFFOUS_C
84 | PC00_M10_FFOT | T | 58098 | 4193 | Create Payroll Transfer DTA 10 |  | No | HR/Payroll | Yes | Yes | Gregg McGrath |  | RFFOUS_T
85 | PC00_M10_REC | T | 432749 | 44212 | Payroll reconciliation report |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
86 | PC00_M10_RFFOAVIS | T | 51995 | 3237 | Print zero net advices |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
87 | PC00_M10_U500 | T | 41058 | 2584 | 3PR Prepare evaluation run (US) |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
88 | PC00_M99_CIPC | T | 2221 | 1209 | Check Completeness of Posting |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
89 | PC00_M99_CIPC_PNP | T | 16690 | 10563 | Check Completeness of Posting |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
90 | PC00_M99_CWTR | T | 842 | 532 | Wage type reporter |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
91 | PC00_M99_PA03_CORR | T | 55085 | 3047 | Corrections |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
92 | PC00_M99_PA03_END | T | 60779 | 2983 | Exit payroll |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
93 | PC00_M99_PA03_RELEA | T | 103304 | 6597 | Release payroll |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
94 | PC00_M99_URMD | T | 0 | 51 | 3PR Undo remittance runs |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
95 | PC00_M99_URMP | T | 41391 | 3649 | 3PR Create posting run (US) |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
96 | PC00_M99_URMU | T | 40145 | 2683 | 3PR Store evaluation run |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
97 | PCP0 | T | 383691 | 114517 | Edit posting runs |  | No | HR/Payroll | Yes | Yes | Gregg McGrath |  | Test end to end - display, create, release, post to FI, deleting, reversing
98 | PU19 | T | 1423813 | 78748 | Tax Reporter |  | No | HR/Payroll | Yes | Yes | Gregg McGrath |  | Test full cycle, W-2 and 1099R, W-2C and 1099RC (2011 note 1644528 to be applied to correct W2 name format issue)
99 | PUOC_10 | T | 17828052 | 1255435 | Off-Cycle Workbench USA |  | No | HR/Payroll | Yes | Yes | Gregg McGrath |  | Full cycle testing - no replacement payment-can not generate PREDME
100 | PUOCBA | T | 858320 | 68809 | Off-Cycle-Batch: Subsequent Activity |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
101 | PUOCLG | T | 18210 | 2380 | OC-Batch: Batch Table List |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
102 | PUOCLL | T | 0 | 153 | OC: List of Replacements/Reversals |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
103 | PUST | T | 2309 | 550 | HR Process Workbench |  | No | HR/Payroll | Yes | Yes | Gregg McGrath
104 | Z_CREATE_FI_POSTING | T | 299345 | 38557 | MIT Create FI Posting - RPCIPE00_OLD |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath
105 | ZPREDME | T | 64399 | 5380 | HR: Pension Payroll Pre-Dme Trans |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath
106 | ZPY_CHKREC | T | 54406 | 1396 | Payroll Check Reconciliation |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath
107 | ZPYDEDUCT | T | 1924451 | 33560 | Deductions - Internal Provider |  | Yes | HR/Payroll | Yes | Yes | Gregg McGrath
108 | PC00_M19_CIPC_PNP | Transaction | 390 |  | Check Completeness of Posting | New |  | HR/Payroll |  | Yes | Gregg McGrath
109 | PA20 | T | 56473103 | 3069221 | Display HR Master Data |  | No | HR/Payroll | Yes | Yes | HR/Pay Team |  | 0
110 | PA30 | T | 79316842 | 12824435 | Maintain HR Master Data |  | No | HR/Payroll | Yes | Yes | HR/Pay Team |  | 0
111 | ZHRBENCP0167CSTSH | Transaction | 325 |  | Infotype Copy 0167 cost sharing | New |  | HR/Payroll |  | Yes | Karen Nolet
112 | ZHR_MONITOR_B2_NOTIF | R | 67245 | 4 | Time Monitor and Notification Report |  |  | HR/Payroll | N/A | N/A | Karen Nolet |  | Dupe same as ZTMR_B2NOTIFY_0128
113 | ZHR_UPDATE_9035 | R | 358299 | 6559 | HR: Logic for Retirement Date |  |  | HR/Payroll | N/A | N/A | Karen Nolet |  | processed via user exit during retirement action. Ran Action created 9035 automatically
114 | ZHRPY_TIMESHEET_APPROVAL_REPT | R | 1785 | 2026 | Time Sheet Approval Report |  |  | HR/Payroll | N/A | N/A | Karen Nolet |  | Dupe same as ZHR_TSH_APPR_RPT
115 | ZHRALF | T | 76268 | 8964 | HR: Audit Lincoln Labs feed |  | Yes | HR/Payroll | N/A | N/A | Karen Nolet |  | duplicate with Transaction-ZHRALF02 (should be Report)
116 | ZHR_INBOUND_TIME | T | 36519 | 5198 | Kronos inbound time load (Test Mode) |  | Yes | HR/Payroll | N/A | N/A | Karen Nolet |  | Dupe - same as ZPTKRONOS_TIME_IN for Kronos
117 | ZPTKRONOS_TIME_IN | T | 49815 | 5529 | Kronos inbound time load (Update) |  | Yes | HR/Payroll | N/A | N/A | Karen Nolet |  | Dupe same as ZHR_INBOUND_TIME for Kronos
118 | ZHRALE01 | R | 1148063 | 55482 | HR: Lincoln Lab MD interface pre-processor |  | Yes | HR/Payroll | Yes | No | Karen Nolet |  | duplicate with Transaction-ZHRALE
119 | ZHRALELOG | R | 1412403 | 87849 | HR ALE feed log report |  | Yes | HR/Payroll | Yes | No | Karen Nolet |  | duplicae with transaction - ZHRALELOG
120 | RPTERR00 | R | 64493 | 4147 | Time Management: Error Handling |  | No | HR/Payroll | No | No | Karen Nolet
121 | RPTBAL00 | Report | 86470 |  | Cumulated Time Evaluation Results: Time Balances/Wage Types | New |  | HR/Payroll |  | No | Karen Nolet |  | Duplicate with transaction PT_BAL00
122 | ZHR_EVENTS_AUTHORIZATIONS | Report | 70122 |  | HR Events authorizations report | New |  | HR/Payroll |  | No | Karen Nolet |  | Duplicate with transaction ZHR_IEVENTS_AUTH - this is the program name vs the transaction code
123 | ZHR_AUDIT_LINCOLN_TIME | R | 35387 | 4166 | Audit Lincoln Time feed |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet |  | File dmithtaf.409.20140127131554.txt
124 | ZHRCHECK_LINCOLN_FEED | R | 99301 | 6511 | HR: Check Lincoln feed |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
125 | ZPY_LL_BANK_DETAIL | R | 235096 | 15415 | Outbound Interface: Bank Details Data File to Lincoln |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
126 | CATSSHOW | R | 1065104 | 98251 | Display Time Sheet Data |  | No | HR/Payroll | Yes | Yes | Karen Nolet
127 | RPTERL00 | R | 464032 | 29842 | Time Evaluation Messages Display |  | No | HR/Payroll | Yes | Yes | Karen Nolet
128 | ZPT_LL_ACCRUALS_OUTBOUND | R | 235736 | 15339 | Outbound leave accrual balances to Lincoln Lab |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
129 | ZPTKRONOS_TIME_INBOUND | R | 117190 | 13014 | Kronos inbound time interface |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
130 | ZHRPT_UPDT_PDC_RECALC_DATE2 | R | 70825 | 799 | PDC Recalc update |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
131 | ZHR_BALANCES_EXEMPTS | R | 231863 | 1526 | Automatically zero out vacation balances for all exempts |  |  | HR/Payroll | Yes | Yes | Karen Nolet
132 | Y0300014 | R | 1273 | 1127 | Approved Student time w/o time eval on IT0007 |  |  | HR/Payroll | Yes | Yes | Karen Nolet
133 | ZPYR_HRSTUD_AUDIT | T | 0 | 356 | Hourly Paid Student Audit Report |  |  | HR/Payroll | Yes | Yes | Karen Nolet
134 | CAT2 | T | 4285728 | 166945 | Time Sheet: Maintain Times |  | No | HR/Payroll | Yes | Yes | Karen Nolet
135 | CAT3 | T | 96284 | 1987 | Time Sheet: Display Times |  | No | HR/Payroll | Yes | Yes | Karen Nolet
136 | CAT6 | T | 149826 | 8197 | Transfer External -> Time Management |  | No | HR/Payroll | Yes | Yes | Karen Nolet
137 | CAT7 | T | 23479 | 2257 | CATS: Transfer Data to CO |  | No | HR/Payroll | Yes | Yes | Karen Nolet |  | Used for facilities timesheets
138 | PT50 | T | 580970 | 74980 | Quota Overview |  | No | HR/Payroll | Yes | Yes | Karen Nolet
139 | PT60 | T | 570358 | 68183 | Time Evaluation |  | No | HR/Payroll | Yes | Yes | Karen Nolet
140 | PT66 | T | 95561 | 3329 | Display Cluster B2 |  | No | HR/Payroll | Yes | Yes | Karen Nolet
141 | ZPTKRONOS_ACCRUL_OUT | T | 36390 | 2363 | Kronos outbound accruals (Prod) |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
142 | ZPYR_UNAPPR_TIME | T | 70189 | 8184 | Unapproved Time Entries Report |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
143 | ZTSO | T | 43235 | 2770 | Time Approval Scheduled Outage |  | Yes | HR/Payroll | Yes | Yes | Karen Nolet
144 | ZHR_TSH_APPR_RPT | T | 1785 | 2035 | Time Sheet Approval Report |  |  | HR/Payroll | Yes | Yes | Karen Nolet
145 | ZPYIO_LL_SAL_DST | T | 0 | 66 | Lincoln Lab salary distribution int |  |  | HR/Payroll | Yes | Yes | Karen Nolet
146 | ZPYR_TIMEGROUP | T | 0 | 78 | Time group report |  |  | HR/Payroll | Yes | Yes | Karen Nolet
147 | ZTMR_B2NOTIFY_0128 | T | 32570 | 2 | Time Results Notification Report |  |  | HR/Payroll | Yes | Yes | Karen Nolet
148 | RPTLEA40 | Report | 1128 |  | Overview Graphic of Attendances/Absences | New |  | HR/Payroll |  | Yes | Karen Nolet
149 | PT_BAL00 | Transaction | 83713 |  | Cumulated Time Evaluation Results | New |  | HR/Payroll |  | Yes | Karen Nolet
150 | ZHR_EVENTS_AUTH | Transaction | 68847 |  | Display Events authorizations | New |  | HR/Payroll |  | Yes | Karen Nolet
151 | ZHR_EVETNS_AUTH | Transaction | [8 empty] | Karen Nolet
152 | ZPMELOG | Transaction |  |  | logs all emails generated w/n SAP for events | [5 empty] | Karen Nolet
153 | ZHRALE01 |  |  |  | Larissa: Lincoln file load |  |  | HR-Payroll |  |  | Larissa Kushkuley
154 | ZASR faculty/DHD |  |  |  | Larissa: ASR spreadsheet download/upload |  |  | HR-Payroll |  |  | Larissa Kushkuley
155 | Benefits EDI feed |  |  |  | Larissa: Benefits EDI feed |  |  | HR-Payroll |  |  | Larissa Kushkuley
156 | ZHR_UPDT_DEP_DOCS_REQD | R | 739220 | 4807 | Maintain Dep Docs Reqd flag on IT0021 when IT0167 changes |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | tested via plan enrollment with dependent (not online report)
157 | ZHRPZ40 | T | 8111416 | 403387 | FSA Claims (Clone from PZ40) |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | ESS app: Tuition Assistance - Mark has contacted SAP regarding ITS apps which may fix this issue
158 | ZHR_SET_WEB_OE_WINDOW | R | 1061 | 295 | Set the Dates and Times that OE is Available on the Web |  |  | HR/Payroll | Yes | Yes | Mark Prudden
159 | ZHRBEN_ESS_WIZARD | R | 5456682 | 823404 | ESS Benefits wizard control program |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the program run by zhri_fsa_only, zhri_nh_benefits and zhri_oe_benefits
160 | ZHRI_FSA_ONLY | T | 22928 | 60987 | ZHRI_FSA_ONLY |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden
161 | ZHRI_NH_BENEFITS | T | 4809782 | 204473 | ZHRI_NH_BENEFITS |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | Transaction brings up "Maintain electronic W-2 Sign Up Info"
162 | ZHRI_OE_BENEFITS | T | 625336 | 557944 | ZHRI_OE_BENEFITS |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden
163 | ZHRI_DIR_HME | T | 2809749 | 315103 | HR ITS - Home Address |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | 0
164 | ZHRI_DIR_EDU | T | 747690 | 129757 | HR ITS - Education Attainment |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | Education History' link on the ESS 'Personal Information' tab.
165 | ZHRI_DIR_EMG | T | 782247 | 133869 | HR ITS - Emergency Contact Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | Emergency Contact' link on the ESS 'Personal Information' tab.
166 | ZHRI_DIR_ETH | T | 348164 | 87428 | HR ITS - Ethnic/Gender/Military Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | Ethnicity/Race/Gender/Veteran Status' link on the ESS 'Personal Information' tab.
167 | ZHRI_DIR_WIZ | T | 106010 | 307871 | HR ITS - Start pt of Dir Info Wizard |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | Personal Info' link on the ESS 'Personal Information' tab.
168 | ZHRI_DIR_WRK | T | 2134494 | 239972 | HR ITS - Work Contact Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | Work Address and Phone' link on the ESS 'Personal Information' tab.
169 | ZHRI_ESDSV | T | 38753962 | 2148543 | ESDS - View-Only |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | 'Salary Distribution System (eSDS)' link on the SAPweb 'Employees' tab.
170 | ZHRI_OE_CONTACT | T | 643112 | 932984 | Open Enrollment Contact Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Name and Address' screen accessed via the 'Benefits Enrollment' link on the ESS 'Benefits' tab.
171 | ZHRI_TEM_USER_CHECK | T | 0 | 514325 | Check if user is set for TEM access |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden
172 | ZHRI_TIMESHEET | T | 152386285 | 9305677 | HR ESS - Timesheet Entry |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | Time Sheets' link on the ESS 'Time' tab.
173 | ZHRI_TS_ADMIN | T | 47846208 | 3181919 | HR ITS - Timesheet Administration |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | 'Approve/Distribute Time Sheets' link on the SAPweb 'Employees' tab.
174 | ZHRI_TS_HIST | T | 15653827 | 884823 | HR ESS - View Timesheet History |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | View Time Sheets' link on the ESS 'Time' tab.
175 | ZHRI_TS_HISTADMIN | T | 1958353 | 205965 | HR ITS - Timesheet History for Admin |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | 'View Time Sheets' link on the SAPweb 'Employees' tab.
176 | ZHRI_UPI | T | 1730521 | 181887 | HR ITS - Update Personal Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | 'Update Personal Information' link on the SAPweb 'Employees' tab.
177 | ZHRI_UPI_EDU | T | 93994 | 13883 | HR ITS - Education Attainment |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Education History ' screen accessed via the 'Update Personal Info' link on the SAPweb 'Employees' tab.
178 | ZHRI_UPI_EMG | T | 187882 | 21673 | HR ITS - Emergency Contact Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Emergency Contact' screen accessed via the 'Update Personal Info' link on the SAPweb 'Employees' tab.
179 | ZHRI_UPI_ETH | T | 86637 | 15078 | HR ITS - Ethnic/Military Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Ethnicity, Race, Gender & Veteran Status' screen accessed via the 'Update Personal Info' link on the SAPweb 'Employees' tab.
180 | ZHRI_UPI_HME | T | 1186343 | 89467 | HR ITS - Home Address |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Name and Home Address' screen accessed via the 'Update Personal Info' link on the SAPweb 'Employees' tab.
181 | ZHRI_UPI_WRK | T | 912923 | 132637 | HR ITS - Work Contact Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Work Address & Phone' screen accessed via the 'Update Personal Info' link on the SAPweb 'Employees' tab.
182 | ZHRI_WIZ_EDU | T | 56787 | 180084 | HR ITS - Education Attainment |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Education History' screen accessed via the 'Personal Info' link on the ESS 'Personal Information' tab.
183 | ZHRI_WIZ_EMG | T | 61343 | 198204 | HR ITS - Emergency Contact Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Emergency Contact' screen accessed via the 'Personal Info' link on the ESS 'Personal Information' tab.
184 | ZHRI_WIZ_ETH | T | 74667 | 234293 | HR ITS - Ethnic/Gender/Military Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Ethnicity/Race/Gender/Veteran Status' screen accessed via the 'Personal Info' link on the ESS 'Personal Information' tab.
185 | ZHRI_WIZ_HME | T | 2884 | 8177 | HR ITS - Home Address |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Name and Home Address' screen accessed via the 'Personal Info' link on the ESS 'Personal Information' tab.
186 | ZHRI_WIZ_WRK | T | 68822 | 215342 | HR ITS - Work Contact Info |  | Yes | HR/Payroll | Yes | Yes | Mark Prudden |  | This is the 'Work Address and Phone' screen accessed via the 'Personal Info' link on the ESS 'Personal Information' tab.
187 | HSA Create Student Appointment |  |  |  | Create Student Appt (custom web dynpro app) |  |  | HR/Payroll |  |  | Mark Prudden
188 | View Your Benefits |  |  |  | Custom ITS app and custom Adobe form |  |  | HR/Payroll |  |  | Mark Prudden
189 | Online W2 |  |  |  | Java web app and SAP-delivered Adobe form |  |  | HR/Payroll |  |  | Mark Prudden
190 | ZHRRCR_UPLOAD | R | 234343 | 6699 | HR: RCR UPLOAD |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | Need production file on the SF2 unix directory
191 | ZPE_TRIGGER_CREATE_USER | R | 67136 | 1185 | Trigger Creation of HR Records for New TEM User |  | Yes | EL | No | Yes | Mary Donovan
192 | PSV8 | T | 0 | 28 | Create Attendee |  |  | HR/Payroll | Yes | Yes | Mary Donovan
193 | ZLS_CORR_QUAL_COMPL | T | 62395 | 2883 | Correct ZLS_QUAL_COMPL table |  |  | HR/Payroll | Yes | Yes | Mary Donovan |  | Duplicate (ZLS_CORRECT_QUAL_COMPL_TABLE)
194 | ZLS_MANUAL_EMAIL | T | 13963 | 2737 | Editable Manual Email Correspondence |  | Yes | EL | Yes | Yes | Mary Donovan
195 | ZPE_RHXTEILN | T | 29280 | 2467 | Attendee List |  | Yes | EL | Yes | Yes | Mary Donovan |  | 0
196 | ZPECLASS_ATTENDEES | T | 180484 | 27136 | Instructor Class Attendee Report |  | Yes | EL | Yes | Yes | Mary Donovan |  | 0
197 | ZPEI_ATTENDEE_LIST | T | 0 | 19742 | Web Version of Class Attendee List |  | Yes | EL | Yes | Yes | Mary Donovan |  | Test via atlas
198 | LSO_RHXTHIST | T | 111760 | 6338 | Participant's Training History |  | No | EL | Yes | Yes | Mary Donovan
199 | ZHR_CITI_LOOKUP | Transaction | 7453 |  | HR: Update CITI Course Lookup table | New |  | HR/Payroll |  | Yes | Mary Donovan
200 | EL Web: My Training Needs | [6 empty] | HR-Payroll |  |  | Mary Donovan
201 | EL Web: My Courses | [6 empty] | HR-Payroll |  |  | Mary Donovan
202 | EL Web: Course Catalog | [6 empty] | HR-Payroll |  |  | Mary Donovan
203 | EL Web: My Profile | [6 empty] | HR-Payroll |  |  | Mary Donovan
204 | Training Admin: Print Attendee List | [6 empty] | HR-Payroll |  |  | Mary Donovan
205 | Training Admin: Training Group Members | [6 empty] | HR-Payroll |  |  | Mary Donovan
206 | Training Admin: Record Course Completion | [6 empty] | HR-Payroll |  |  | Mary Donovan
207 | Training Rule Admin: Create Training Group | [6 empty] | HR-Payroll |  |  | Mary Donovan
208 | Training Rule Admin: Change Training Group | [6 empty] | HR-Payroll |  |  | Mary Donovan
209 | Training Rule Admin: Display Training Group | [6 empty] | HR-Payroll |  |  | Mary Donovan
210 | Training Rule Admin: Create EHS Activity | [6 empty] | HR-Payroll |  |  | Mary Donovan
211 | Training Rule Admin: Change EHS Activity | [6 empty] | HR-Payroll |  |  | Mary Donovan
212 | Training Rule Admin: Display EHS Activity | [6 empty] | HR-Payroll |  |  | Mary Donovan
213 | Training Rule Admin: Create Requirement Set | [6 empty] | HR-Payroll |  |  | Mary Donovan
214 | Training Rule Admin: Change Requirement Set | [6 empty] | HR-Payroll |  |  | Mary Donovan
215 | Training Rule Admin: Display Requirement Set | [6 empty] | HR-Payroll |  |  | Mary Donovan
216 | Training Rule Admin: Learner Profile Administration | [6 empty] | HR-Payroll |  |  | Mary Donovan
217 | Training Rule Admin:Course Evaluation Results | [6 empty] | HR-Payroll |  |  | Mary Donovan
218 | Training Rule Admin:Send Manual Email | [6 empty] | HR-Payroll |  |  | Mary Donovan
219 | Course Publisher | [6 empty] | HR-Payroll |  |  | Mary Donovan
220 | EHS Training:Report 1-4 | [6 empty] | HR-Payroll |  |  | Mary Donovan
221 | EHS Training:DLC Assessment Report | [6 empty] | HR-Payroll |  |  | Mary Donovan
222 | EHS Training:Training Reconciliation | [6 empty] | HR-Payroll |  |  | Mary Donovan
223 | EHS Training: Training Group Members | [6 empty] | HR-Payroll |  |  | Mary Donovan
224 | EHS Training: Record Course Completion | [6 empty] | HR-Payroll |  |  | Mary Donovan
225 | Money Matters: Paystubs | [6 empty] | HR-Payroll |  |  | Mary Donovan
226 | Money Matters: W2 | [6 empty] | HR-Payroll |  |  | Mary Donovan
227 | Money Matters: Tax Withholding | [6 empty] | HR-Payroll |  |  | Mary Donovan
228 | Money Matters: Direct Deposit | [6 empty] | HR-Payroll |  |  | Mary Donovan
229 | Salary Distribution: eSDS | [6 empty] | HR-Payroll |  |  | Mary Donovan
230 | Salary Distribution: eDACCA | [6 empty] | HR-Payroll |  |  | Mary Donovan
231 | /USE/PDS3_ADM_GOCL | R | 136 | 38 | EPI-USE: Generate Object Classes |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | 0Assume part of DSM
232 | /USE/PDS3_OPTIMIZE | R | 34201 | 2157 | EPI-USE: Optimization per Object Types |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0Assume part of DSM
233 | /USE/PDS3_RUNTIME | R | 346491 | 12773 | EPI-USE: Runtime |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | Assume part of DSM
234 | H99_DISPLAY_PAYRESULT | R | 282381 | 58922 |  |  | No | HR/Payroll | Yes | Yes | Mary Donovan
235 | RPCIPDEL | R | 71148 | 10430 | Deletion of Posting Runs |  | No | HR/Payroll | Yes | Yes | Mary Donovan
236 | RPCPL2U0 | R | 153 | 238 | Listing of Customizing Tables |  | No | HR/Payroll | Yes | Yes | Mary Donovan
237 | ZHR_VACATION_COST_OUT_RPT | R | 2883 | 566 | Vacation cost out report |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
238 | ZPY_DIST_CO_UPDATE | R | 231866 | 14927 | Distribution Cost Object Update |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
239 | ZPY_LOAD_ZHR_EDACCA_PRN | R | 232832 | 14992 | EDCCA: LOAD ROLES / SAP R/3 ZHR_EDACCA_PRN FEED |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | DACCA Auth roles - Lucia loads file, then I validate
240 | ZPY_PAYROLL_COMPARE_AUDIT | R | 18578 | 1270 | Payroll Validation Report |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
241 | ZPYRMISSING9004 | R | 372543 | 27761 | HR/PY: Report Missing IT9004s |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan
242 | RHTHIST0_LSO | R | 198164 | 9855 | Training History |  | No | EL | Yes | Yes | Mary Donovan
243 | ZTN_POPULATE_REQDB | R | 232027 | 7266 | Program ZTN_POPULATE_REQDB |  | Yes | EL | Yes | Yes | Mary Donovan
244 | ZLSO_UPDATE_BROWSER_LIST | R | 2382 | 4 | Update the list of browsers not supported by LSO |  |  | HR/Payroll | Yes | Yes | Mary Donovan
245 | ZPY_EPAYSTUB_EMAIL | R | 231863 | 3702 | HR/PAYROLL: ePaystub Email Notification |  |  | HR/Payroll | Yes | Yes | Mary Donovan
246 | ZPY_MAP_RECONCILIATION_REPORT | R | 78 | 66 | Modified Annual Plan (MAP) Reconciliation Report |  |  | HR/Payroll | Yes | Yes | Mary Donovan
247 | RHKURS20_LSO | R | 34318 | 6251 | Participation statistics |  |  | HR/Payroll | Yes | Yes | Mary Donovan
248 | RHSEMI60 | R | 0 | 36 | Business Event Information |  |  | HR/Payroll | Yes | Yes | Mary Donovan
249 | ZPYR_J1_VISA | T | 253 | 24 | J-1 Visa Report |  |  | HR/Payroll | Yes | Yes | Mary Donovan
250 | ZHR_IT0128 | T | 0 | 135 | HR: Create/Delete Infotype 0128 |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
251 | ZHR_IT0655 | T | 231880 | 64 | HR: Create/delete Infotype 0655 |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
252 | /USE/DSM3 | T | 397399 | 19049 | DSM Object Sync |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | DSM must be upgraded
253 | /USE/DSM3_CREATE | T | 71940 | 2103 | DSM Object Sync: Create Sync |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | DSM must be upgraded
254 | /USE/DSM3_MON | T | 345472 | 12538 | DSM Object Sync: Monitor Desk |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | DSM must be upgraded
255 | PA03 | T | 424742 | 25381 | Maintain Personnel Control Record |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
256 | PE02 | T | 2460 | 363 | HR: Maintain Calculation Rules |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
257 | PE04 | T | 0 | 16 | Creates Functions and Operations |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
258 | PU01 | T | 2838 | 186 | Delete current payroll result |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
259 | PU03 | T | 0 | 91 | Change Payroll Status |  | No | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
260 | ZHRI_W2_SIGNUP | T | 648064 | 619049 | Electronic W2 Sign-Up |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | Test via Atlas
261 | ZPT_DIST_RELIEF | T | 67732 | 2085 | SRS Distribution Relief |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
262 | ZPY_PENSION_CONT | T | 7390 | 24 | TW Pay and Hours Contibutions |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan
263 | ZPY_REVERSE_PENSION | T | 6622 | 3 | Reverse Pension Feed to TW |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan
264 | ZPYCDDIS_S2 | T | 101780 | 9236 | CDU: Analyze Distribution |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
265 | ZPYCDMCE | T | 465 | 381 | Maintain edacca certifcation table |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
266 | ZPYCDMCO | T | 1723 | 338 | Maintain edacca control table |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
267 | ZPYCDMPR | T | 5864 | 1891 | Maintain print edacca control table |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
268 | ZPYCDMSC | T | 13879 | 800 | Maintain sus obj determination table |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
269 | ZPYCDPRN_O2 | T | 150423 | 6748 | CDU:manual print of edacca(Override) |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
270 | ZPYCDPRN2 | T | 74282 | 1158 | CDU:manual print of edacca ver. II |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
271 | ZPYCDRPT2 | T | 221201 | 8713 | CDU: Display EDACCA Entries |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
272 | ZPYII_DED | T | 29777 | 2643 | Deductions |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | 0
273 | ZPYNRA0210 | T | 35236 | 3059 | HR: Updating HR InfoTypes 0210 |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan |  | Oct 31 2011 - RT#1785565 - resolved transport # SF2K951292
274 | LSO_SCORM_REPORT | T | 4518 | 121 | Report of SCORM Data |  | No | EL | Yes | Yes | Mary Donovan
275 | LSO_TAC_TRAIN_RESULT | T | 0 | 234 | Results Overview: Course |  | No | EL | Yes | Yes | Mary Donovan
276 | PV06 | T | 0 | 21 | Prebook List: Attendees |  | No | EL | Yes | Yes | Mary Donovan
277 | ZPYR_NONRES | T | 0 | 36 | Non resident federal tax allowance |  | Yes | HR/Payroll | Yes | Yes | Mary Donovan
278 | ZTN_TRAINING_REPORT | T | 20373 | 684 | Assigned Training of a Learner |  | Yes | EL | Yes | Yes | Mary Donovan
279 | LSO_PUBLISHER | T | 0 | 6 | Display Publisher Database |  |  | HR/Payroll | Yes | Yes | Mary Donovan
280 | LSO_RHXKVOR0 | T | 1712 | 15 | Participation Prerequisites |  |  | HR/Payroll | Yes | Yes | Mary Donovan
281 | Y0300015 | R | 1 | 96 | PY:NRAs who are Resident Aliens |  |  | HR/Payroll | Yes | Yes | Mary Donovan
282 | Y0300016 | R | 1257 | 215 | PY:Community Giving |  |  | HR/Payroll | Yes | Yes | Mary Donovan
283 | LSO_TAC_PART_RESULT | Transaction | 1830 |  | Results Overview: Participant | New |  | HR/Payroll |  | Yes | Mary Donovan
284 | LSO_RHXUMBU0 | Transaction | 1540 |  | Participants for Rebooking | New |  | HR/Payroll |  | Yes | Mary Donovan
285 | Z_PY_SSO_APPT_UPDATE | Report |  |  | Summer Session appts |  |  | HR/Payroll |  | Yes | Mary Donovan |  | execute via SE37
286 | Z_PY_SSO_DIST_UPDATE | Report |  |  | Summer Session distribution |  |  | HR/Payroll |  | Yes | Mary Donovan |  | execute via SE37
287 | HRBEN0071 | T | 351 | 144 | Eligible Employees |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
288 | HRBEN0078 | T | 0 | 30 | FSA Contributions |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
289 | LSO_PSV1 | T | 643308 | 27565 | Dynamic Participation Menu |  |  | EL | Yes | Yes | Meaghan Murray |  | will test book, prebook, rebook, and cancel through this transaction
290 | LSO_PSV2 | T | 1212982 | 34398 | Dynamic Course Menu |  |  | EL | Yes | Yes | Meaghan Murray |  | 0
291 | LSO_PSV3 | T | 58235 | 3007 | Dynamic Information Menu |  |  | EL | Yes | Yes | Meaghan Murray
292 | LSO_PVCT | T | 300516 | 10641 | Master Data Catalog |  |  | EL | Yes | Yes | Meaghan Murray |  | 0
293 | RHXSTOR0_LSO | Report | 4161 |  | Participant Cancellations per Course | New |  | HR/Payroll |  | Yes | Meaghan Murray
294 | ZHR_MARK_OE_PCP | R | 0 | 66 | HR: mark PCPs entered during Open Enrollment |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
295 | ZHRPP_LIFE_INS_PREM_RPT | R | 16285 | 1137 | Pension Annuitant Life Insurance Premium Report |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
296 | ZHRBENTERM | T | 466015 | 6083 | Terminate Ineligible Benefits |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
297 | ZHRCLAIMS | T | 505946 | 25438 | Tuition Assistance Course Monitor |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
298 | ZHR_CLEAR_VAL_ATT | Transaction |  |  | Clear attempts to enter Atlas values | [5 empty] | Meaghan Murray
299 | ZCB_EMAIL_REMINDER | Transaction |  |  | Commuting Benefits: Bike reminder pr | [5 empty] | Meaghan Murray
300 | ZHR_CG_MAN_DONATIONS | Transaction |  |  | Manage Community Giving Donations | [5 empty] | Meaghan Murray
301 | ZHR_CG_REPORTS | Transaction |  |  | Community Giving Reports | [5 empty] | Meaghan Murray
302 | ZHR_CG_ADD_DONATION | Transaction |  |  | Add Donation | [5 empty] | Meaghan Murray
303 | ZHR_CG_MAN_CHARITIES | Transaction |  |  | Community Giving Manage Charities | [5 empty] | Meaghan Murray
304 | ZHR_CBEN_ADMINS | Transaction |  |  | Manage Commuter Benefits Admins | [5 empty] | Meaghan Murray
305 | ZHR_CBEN_TPASS_CANC | Transaction |  |  | T-Pass Cancel Account | [5 empty] | Meaghan Murray
306 | ZHR_CBEN_TPASS_DISP | Transaction |  |  | T-Pass Display Status | [5 empty] | Meaghan Murray
307 | ZHR_CBEN_TPASS_ELIG | Transaction |  |  | T-Pass Eligibility Changes | [5 empty] | Meaghan Murray
308 | ZHR_CBEN_TPASS_SUSP | Transaction |  |  | T-Pass Account Suspension | [5 empty] | Meaghan Murray
309 | ZHR_CBEN_TPASS_DELIV | Transaction |  |  | T-Pass Change Delivery Method | [5 empty] | Meaghan Murray
310 | ZHR_CBEN_TPASS_ZONE | Transaction |  |  | T-Pass Change Zone ID | [5 empty] | Meaghan Murray
311 | ZHR_CBEN_ACAD_TERMS | Transaction |  |  | T-Pass Academic Terms | [5 empty] | Meaghan Murray
312 | ZHR_CBEN_OVERRIDE | Transaction |  |  | Commuter Benefits Override Table | [5 empty] | Meaghan Murray
313 | ZHR_CBEN_PARKING | Transaction |  |  | Commuter Benefits Parking Table | [5 empty] | Meaghan Murray
314 | ZHR_CBEN_PARTNERS | Transaction |  |  | Commuter Benefits Partners | [5 empty] | Meaghan Murray
315 | ZHR_CBEN_PART_DISC | Transaction |  |  | Commuter Benefits Partner Discounts | [5 empty] | Meaghan Murray
316 | ZHR_CBEN_TPASS_MAIL | Transaction |  |  | T-Pass Mailing Address | [5 empty] | Meaghan Murray
317 | ZHR_CBEN_YEARS | Transaction |  |  | Commuter Benefits Years | [5 empty] | Meaghan Murray
318 | ZHR_CBEN_ZONE_FEES | Transaction |  |  | T-Pass Zone Fees | [5 empty] | Meaghan Murray
319 | ZHR_TPASS_STUD_EDIT | Transaction |  |  | Edit Student's T-pass | [5 empty] | Meaghan Murray
320 | ZHR_CBEN_TPASS_PYREC | Transaction |  |  | T-PASS: Pre-payroll reconcillation | [5 empty] | Meaghan Murray
321 | ZCB_TPASS_ADJUST_DED | Transaction |  |  | Adjust T-Pass Deductions When Rates | [5 empty] | Meaghan Murray
322 | ZCB_VANPOOL_ADMIN | Transaction |  |  | Monthly VanPool Approvals | [5 empty] | Meaghan Murray
323 | ZHR_CBEN_MBTA_EXT | Transaction |  |  | MBTA Extract for T-Pass Signups | [5 empty] | Meaghan Murray
324 | ZHR_CBEN_BURSAR_EXT | Transaction |  |  | Bursar Office Extract for T-Pass | [5 empty] | Meaghan Murray
325 | ZHR_CBEN_TPASS_DELTA | Transaction |  |  | T-Pass Sign-up Changes Report | [5 empty] | Meaghan Murray
326 | ZHR_CBEN_TPASS_EXCEP | Transaction |  |  | T-Pass Student/Employees Exceptions | [5 empty] | Meaghan Murray
327 | ZPY_LOAD_MITSIS_BIO_DATA | R | 166159 | 10697 | Load Student's Biographic data from MITSIS feed |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
328 | ZHR_DW_DEPT_ADMIN_IN | R | 231742 | 70 | Process Data Warehouse Feed of Department Administrators to SAP |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
329 | ZHR_DW_MITALERT_IN | R | 3020603 | 823 | Process Data Warehouse Feed of MITALERT changes to SAP |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
330 | ZHR_DW_MITIDCARD_IN | R | 3017951 | 826 | Process Data Warehouse Feed of MITID Card changes to SAP |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
331 | ZHR_DW_TLO_SIGNATURES_IN | R | 3015540 | 823 | Process Data Warehouse Feed of TLO data to SAP |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
332 | ZHR_NEWHIRE_NOTIFICATION | R | 33488158 | 132 | HR New Hires Notification |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
333 | /USE/PQM3_D001 | R | 1 | 150 | Headcount Report: Active and Inactive Employees |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
334 | /USE/PQM3_D003 | R | 0 | 78 | Employee Age by Category |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
335 | /USE/PQM3_D016 | R | 0 | 247 | Employee Data Report |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
336 | /USE/PQM3_D407 | R | 0 | 78 | Position information with attached EE info |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
337 | /USE/PQM3_D408 | R | 55 | 99 | Position assigned roles by Employee |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
338 | /USE/PQM3_D410 | R | 0 | 21 | Org Structure Naming Conventions |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
339 | /USE/PQM3_D701 | R | 0 | 91 | Audit Detail Report: Personnel Admin |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
340 | S_AHR_61015471 | T | 4315 | 148 | Infotype Overview for Employee |  | No | HR/Payroll | Yes | Yes | Meaghan Murray |  | RT#2561150 - retest successful in SF2 10/30/13
341 | ZPY_GRADAID_LOG | T | 189354 | 20205 | Graduate Appointment Interface Log |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
342 | ZPY_LOAD_MITSIS_GRAD | T | 0 | 138 | Load MITSIS Grad appts file |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
343 | ZPY_MITSIS_LOG | T | 344832 | 17865 | MITSIS error log report |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
344 | ZPYIO_MITSIS_TIM | T | 32697 | 2285 | Stident Gross Pay File to MITSIS |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
345 | ZPY_METPAY_IN | T | 0 | 66 | zpy_metpay_in_billded |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
346 | ZPY_NRA_GLAC | T | 8925 | 9 | Glacier Feed |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
347 | ZPYIO_FSA_CONTRIB | T | 0 | 66 | FSA Contribution Data File to Crosby |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
348 | ZUT_CHECK_FEED_PROC | Report | 697710 |  | Check Feed Runs | New | Yes | HR/Payroll |  | Yes | Meaghan Murray
349 | ZHR_NEW_HIRE_FEED_FOR_ATLAS | Report | 413293 |  | New Hire Feed for Atlas | New | Yes | HR/Payroll |  | Yes | Meaghan Murray
350 | ZHR_ATLAS_SEC_OPTOUT | Transaction | 9777 |  | Atlas Security Step Opt Out | New | Yes | HR/Payroll |  | Yes | Meaghan Murray
351 | HRBEN0081 | Transaction | 351 |  | Employee Demographics | New | No | HR/Payroll |  | Yes | Meaghan Murray
352 | ZHREDU_FOSC | Transaction | 136 |  | Maintain Categ. Codes for Education | New | Yes | HR/Payroll |  | Yes | Meaghan Murray
353 | ZHREDU_FOSF | Transaction | 21 |  | Maintain 4-Digit Codes for Education | New | Yes | HR/Payroll |  | Yes | Meaghan Murray
354 | ZHR_COPY_PCP | R | 34692 | 2162 | HR: the program copies PCP data from IT0106-0 to IT0376(used by feeds) |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray |  | tested as part of WEEKLY SUNDAY CARRIER FEEDS OE
355 | HRBEN0001 | T | 644698 | 140133 | Enrollment |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
356 | HRBEN0006 | T | 468492 | 18912 | Benefits Participation Overview |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
357 | HRBEN0012 | T | 0 | 9549 | Automatic Plan Enrollment |  | No | HR/Payroll | Yes | Yes | Meaghan Murray |  | Replaced with transaction zhrben0012 don't need to test for 2014
358 | HRBEN0014 | T | 581406 | 32174 | Termination of Participation |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
359 | HRBEN0015 | T | 62535 | 5120 | Confirmation Form |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray |  | RT# 3023687 - retest successful in SF2 10/27/2014
360 | ZHRBEN0012 | T | 0 | 189 | HR:MIT Version Benefits Auto-Enroll |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
361 | ZHREDU_INST | T | 7462343 | 982 | Maintain educational Instituations |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
362 | ZPYDEPLIFERPT | T | 8991 | 835 | Dependent Life Report ZHRPY_ACTIVE_DEPLIFE_PREM_RPT |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
363 | ZPYLIFEINSRPT | T | 20268 | 3581 | HR/PY:ZHRPY_ACTIVE_LIFE_INS_PREM_RPT |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
364 | HRBEN0009 | T | 0 | 91 | Benefits - Plan Overview |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
365 | HRBEN0055 | T | 2853 | 468 | Overview Adjustment Permissions |  | No | HR/Payroll | Yes | Yes | Meaghan Murray
366 | HRBEN0085 | T | 0 | 91 | Costs/Contributions for Misc. Plans |  | No | HR/Payroll | Yes | Yes | Meaghan Murray |  | RT# 3023687 - retest successful in SF2 10/27/2014
367 | ZHR_TERM_ACTIONS | T | 0 | 168 | Maintain Termination Actions |  | Yes | HR/Payroll | Yes | Yes | Meaghan Murray
368 | HRBEN0005 | T | 17049 | 9572 | Enrollment Form |  | No | HR/Payroll | Yes | Yes | Meaghan Murray |  | will be obsolete with 2015 oe
369 | ZHRBEN_END_DATE_LIFE | R | 1081 | 96 | HR/Benefits: End date IT0168 Life Insurance (LIFB / LIFS) |  | Yes | HR/Payroll | Yes | Yes | Sharon Diliberto
370 | ZHRRETIRE_ANNUITY | T | 151255 | 7037 | Create Retiree in RDBP |  | Yes | HR/Payroll | Yes | Yes | Sharon Diliberto |  | 0
371 | SWI1 | Transaction |  |  | Workflow |  | No | ABAP |  |  | Sharon Diliberto
372 | SMW0 | Transaction |  |  | Web Repository |  | No | ABAP |  |  | Sharon Diliberto

## Files Prep
3/24/2010 EDS In-bound Lump Sum File
3/24/2010 EDS In-bound Annuity File
[7 empty] | complete | 2010-03-08
Student Bio Feed (MITSIS)
Keep LL Audit files
Parking file
TPASS file
Grad Appointment feed
LL Feeds - have Wai-ming copy files to test environment's sapin directory
Archive Directory | Assigned to | Comment | Files Copied | # of Files | in/out | can be loaded locally?
hr/bcbs | Karen | outbound, no copies | n/a |  | out
hr/crosby | Karen | outbound, no copies | n/a |  | out
hr/ll_hr_time | Karen | R3 Admin request to place in dropbox |  |  | in
hr/mit_alert | Meaghan | R3 Admin request to place in dropbox |  |  | in
ZHR_NEWHIRE_NOTIFICATION | Meaghan | outbound, no copies | n/a |  | out
hr/atlas_nh | Meaghan | outbound, no copies | n/a |  | out
py/fsa_census | Karen | outbound, no copies | n/a |  | out
hr/mitsis_dem | Meaghan | Retrieve from archive server, run local | dstudsbi.956.20150707020033 |  | in | Yes
Pension Payroll EDS In-bound Annuity File | Gregg | Obtain August files from Laurie |  |  | in | yes
Pension Payroll EDS In-bound Lump Sum File | Gregg | Obtain August files from Laurie |  |  | in | yes
py/pen_empl | Cindy | outbound, no copies | n/a |  | out