## Sheet1
Done? | Who? | No. (in SAP's doc) | Object Name | Line No. | Native SQL
Hana-compatible | Larissa | 1 | LZHR_APPOINTMENT_PROCESSU31 | 62 | EXEC SQL.
Hana-compatible | Larissa | 2 | LZHR_HSA_INBOXF01 | 218 | EXEC SQL PERFORMING add_username.
Pooled or cluster table(s)…without ORDER BY
Yes | Lucia | 1 | LZCO_SAFOF01 | 1856 | BSEG
Yes | Carolyn | 2 | LZFIJVU05 | 253 | BSEG
Yes | Larissa | 3 | LZHR_HRPSC_DATAF00 | 31, 164, 234 | T527X | No changes required (select of unique org unit text by org unit no)
Yes | Mark | 4 | LZHR_PERSONAL_INFOU11 | 77, 84 | T517A
Yes | Carolyn | 5 | LZHR_SEARCHU02 | 124 | T588B
Yes | Larissa | 6 | LZJV_ATLASU05 | 120 | BSEG | SF2K959877 in RT 3243705 JV Phase 2, going to production in July
| Lucia | 7 | ZAPPT008 | 271 | BSEG | Old Travel System
| Lucia | 8 | ZAPPT027 | 237 | BSEG | Old Travel System
| Lucia | 9 | ZAPPT029B | 3827 | BSEG | Old Travel System
| Lucia | 10 | ZAPPT041 | 269 | BSEG | Old Travel System
Yes | Carolyn | 11 | ZARI0040 | 169 | BSEG
Yes | Lucia | 12 | ZBILL09A | 1738 | BSEG
Yes | Elda | 13 | ZBP002 | 256 642 | T009B BSEG
Yes | Elda | 14 | ZBP002B | 192 | T517A
yes | Lucia | 15 | ZFCCFE01B | 2837, 2859 | T588B
Yes | Carolyn | 16 | ZGLAUDIT_DETAIL | 936, 942 | BSEG
Yes | Mark | 17 | ZPYPOPEDACCA | 396 | BSEG
Yes | Elena | 18 | ZWHACCGR | 136 | BSEG
Yes | Elena | 19 | ZWHDOCTY | 118 | BSEG
Yes | Elena | 20 | ZWHPAYROLL_PERIODS | 132 | BSEG
Yes | Elena | 21 | ZWHRELEASE_INDICATOR | 132 | T161S
Yes | Elena | 22 | ZWHRFDOC | 140 | BSEG
Yes | Elena | 23 | ZWHVCGRP | 124, 146 | T077Y
Problematic Statements…without ORDER BY/SORT
Yes | Lucia | 1 | MZCO1F01 | 2853 | READ TABLE… BINARY SEARCH
Open transport | Lucia | 2 | ZCOSTF01 | 219 | DELETE ADJACENT DUPLICATES | SF2K959648, RT 3192503: Change ZSTM for PM work orders
Open transport | Lucia | 3 | ZBILL08A | 1514 | READ TABLE… BINARY SEARCH | SF2K959648, RT 3192503: Change ZSTM for PM work orders
Yes | Elda | 4 | LZWF1U05 | 287 | READ TABLE… BINARY SEARCH
Yes | Elda | 5 | ZCL_IHREP_ORDER_OPERATION_LISTCM00K | 304 | READ TABLE… BINARY SEARCH
Yes | Elda | 6 | ZCL_NOTIF_WO_RPT==============CM00K | 304 | READ TABLE… BINARY SEARCH
Yes | John | 7 | ZCL_TN_ASSIST_ACAD_SUBJECTS===CM002 | 144, 156 | READ TABLE… BINARY SEARCH
Yes | John | 8 | LZEHSU06 | 388 | READ TABLE… BINARY SEARCH
Yes | Lucia | 9 | ZGL46B | 968, 1621, 1357 | READ TABLE… BINARY SEARCH
Yes | Lucia | 10 | LZKS1F01 | 1078, 1653 | READ TABLE… BINARY SEARCH
Yes | Elda | 11 | ZMMR002_F01 | 570, 593 | READ TABLE… BINARY SEARCH
Yes | Lucia | 12 | ZPPR001 | 1256, 1775, 1779 1802 | READ TABLE… BINARY SEARCH DELETE ADJACENT DUPLICATES
Yes | Mark | 13 | MP900400F01 | 4802 | PROVIDE… ENDPROVIDE
Yes | Mark | 14 | MP901800F01 | 2200 | PROVIDE… ENDPROVIDE
Yes (no change req'd) | Mark | 15 | MZHR_ESS_USER_CHECKF01 | 271 | LOOP… AT FIRST… ENDAT
Yes | Elda | 16 | MZREQSF01 | 1266 | DELETE ADJACENT DUPLICATES
Awaiting R3-Admin | Mark | 17 | Z_ROLE_SET_MASTERLANG | 55 | READ TABLE… BINARY SEARCH
Obsolete | Lucia | 18 | ZCSCHKRP | 272 293 | LOOP… AT NEW… ENDAT LOOP… AT NEW… ENDAT | .Searching for: ZCSCHKRP | Found 0 occurrence(s) in 46 file(s)
Yes | Carolyn | 19 | ZFIPPV00 | 582 | READ TABLE… INDEX 2
Yes | Larissa | 20 | LZHR_EMSU19 | 93 | DELETE ADJACENT DUPLICATES | SF2K959594 in RT 3133070 Events support, going to production in July
SF2K959536 | Sharon | 21 | ZHR_FIDELITY | 6028 | DELETE ADJACENT DUPLICATES
Yes | Mark | 22 | LZHR_HSA_VALIDATIONSU10 | 125 | PROVIDE… ENDPROVIDE
Yes | Lucia | 23 | ZHR_IT0128 | 331, 350 | DELETE ADJACENT DUPLICATES
Yes | Lucia | 24 | ZHR_IT0655 | 333, 352 | DELETE ADJACENT DUPLICATES
Yes | Larissa | 25 | LZHR_NEW_HIREU41 | 209 | DELETE… FROM 1 TO i | SF2K959770, Atlas New Hire, going to production in July
yes, not tested | Sharon | 26 | LZHR_VACATION_TRACKINGF01 | 90, 99, 110, 119 | DELETE ADJACENT DUPLICATES
Yes | Mark | 27 | LZHREDACCAU10 | 208 | LOOP… AT NEW… ENDAT
Yes | Elda | 28 | ZMM_PO_CREATE_INCL | 863 874 | LOOP… AT NEW… ENDAT LOOP… AT END OF… ENDAT
Yes | Carolyn | 29 | ZPCFCRS | 186 | DELETE ADJACENT DUPLICATES
| Sharon | 30 | ZPTKRONOS_TIME_INBOUND | 1318 | DELETE ADJACENT DUPLICATES
Yes (no change req'd) | Mark | 31 | LZPY_CD_BTEF01 | 448 | READ TABLE… BINARY SEARCH
Yes | Carolyn | 32 | ZPY_LOAD_MITSIS_BIO_DATA | 8245, 8474, 8794, 8854, 8913, 8998 | PROVIDE… ENDPROVIDE
| obsolete | 33 | ZPY_LOAD_MITSIS_BIO_DATA_MAT | 6822, 7061, 7393, 7458, 7522, 7612 | PROVIDE… ENDPROVIDE
| obsolete | 34 | ZPY_LOAD_MITSIS_BIO_DATA_NEW | 8105, 8344, 8676, 8741, 8805, 8895 | PROVIDE… ENDPROVIDE
Yes | Larissa | 35 | ZPY_MIETAX | 614 | READ TABLE… BINARY SEARCH
SF2K959636 | Sharon | 36 | ZPY_PENSION_COMPENSATION | 2550, 2564, 2593, 2607 | READ TABLE… INDEX 1
Obsolte | Lucia | 37 | ZREQ006 | 305 | LOOP… AT FIRST… ENDAT | Searching for: ZREQ006 | Found 0 occurrence(s) in 48 file(s)
Open transport | Lucia | 38 | ZCOSTF01 | 219 | DELETE ADJACENT DUPLICATES | SF2K959648, RT 3192503: Change ZSTM for PM work orders
Yes | Lucia | 39 | ZSB_BUDGET_REPORT | 1453, 1463 219, 1317 | READ TABLE… BINARY SEARCH DELETE ADJACENT DUPLICATES
Yes | Lucia | 40 | ZSB_PROJECTION_REPORT | 899, 930 | LOOP… AT NEW… ENDAT
Yes | Carolyn | 41 | ZSDADSHD | 542 | DELETE ADJACENT DUPLICATES
Open transport | Lucia | 42 | ZCOSTF01 | 219 | DELETE ADJACENT DUPLICATES | SF2K959648, RT 3192503: Change ZSTM for PM work orders
Yes but not tested | Carolyn | 43 | ZSLOAN17 | 353, 376, 400 | READ TABLE… BINARY SEARCH
Yes | John | 44 | LZTN_AUTHF01 | 52, 66 | LOOP… AT NEW… ENDAT LOOP… AT END OF… ENDAT
Yes | John | 45 | LZZ_EHS_AUTHF02 | 59, 78 | LOOP… AT NEW… ENDAT LOOP… AT END OF… ENDAT
Yes | Carolyn |  | Z_AP_SINGLE_RFP_GET |  | Larissa had questions about this earlier in the year…the 'order by' has been commented out