## Communication & Contacts
Communication
An IS&T telephone number (617-324-7468) will carry a message as to the status of the upgrade beginning at noon on Friday 12/2 through noon on Monday 12/5. The Project Manager or designee will update this message as needed. A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 6:00pm on Sunday.
Voicemail With Status: 617-324-7468
Conference Call Line: Webex
Call-in toll number (US): 617-324-0000 Friday Access code (7pm - 7 am): 640 464 567 Saturday Access code (7am - 7 pm) : 645 662 482 Sunday Access code (7am - 7 pm):646 155 333
Project wiki link: | https://wikis.mit.edu/confluence/display/sapscripts/2016+Year+End+SAP+Support+Pack+Project
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via voice message, email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
SAP Conntact Information
Name | Phone | Email
Steve Koczur | 610 745-6281 | stephen.koczur@sap.com
Phil Ferenschak | 610 662-0526 | phillip.ferenschak@sap.com
Santiago Lopez | T +528120885726 M +5218116003655 | santiago.lopez01@sap.com
Chris Holness | 404-825-0281 | christopher.holness@sap.com
Contact Information
Area | Name – Location | Contact Telephone # | Email
A/P | John Larkin – NE49 | Refer to online directory | jlarkin@mit.edu
Parking Office for Commuting Benefits applications | Robynn Cruz | Refer to online directory | Refer to online directory
Charitable Giving Office | Anthony Farrell | Refer to online directory | Refer to online directory
VPF | Stef Desmond – NE49 | Refer to online directory | sdesmond@mit.edu
VPF | Steve Hoover | Refer to online directory | Refer to online directory
VPF – Travel | Andrea Siegel - Off Campus | Contact PM | amsiegel@mit.edu
Dept. of Facilities | Bob Leonard – Off Campus | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher – On Campus (10-063) | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix | Contact PM | lstcroix@mit.edu
EHS | Laurie Veal – Off Campus | Contact PM | veal@mit.edu
EHS | Jessica Van | Refer to online directory | jvan@mit.edu
EHS | Joe MacLeod - Off Campus | Contact PM | jmacleod@mit.edu
HR Coordinator | Mike MacDonald | Refer to online directory | mikemacd@mit.edu
HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu
HR/Benefits | Diane Johnston – Off Campus | Contact PM | djohnsto@mit.edu
EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White – Off Campus | Contact PM | jwc@mit.edu
Procurement | Cindy Vye - NE49 | Contact PM | CI24314
Procurement | Cecilia Talamantes | Refer to online directory | Refer to online directory
Procurement | Ben Simon | Refer to online directory | Refer to online directory
Procurement | Jeff Rosa | Refer to online directory | Refer to online directory
Procurement | Jordan Lewis | Contact PM | Refer to online directory
Procurement | Scott Ball | Refer to online directory | Refer to online directory
Procurement | Tammy Doyle | Refer to online directory | Refer to online directory
Procurement | Dan DiPasquale | Refer to online directory | Refer to online directory
Procurement | Paul Anderson | Refer to online directory | Refer to online directory
Procurement | Andrea Siegel | Refer to online directory | Refer to online directory
Procurement | Kathy McGrath | Refer to online directory | Refer to online directory
Procurement | Joanne Reynolds | Refer to online directory | Refer to online directory
VPF – HR/Payroll | Leslie Wright – NE49 | Refer to online directory | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Refer to online directory | darrenjs@mit.edu
VPF – HR/Payroll | Chris Durham – NE49 | Refer to online directory | cfdurham
IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu
IS&T - Project Manager | Frank Quern – W92 | Refer to online directory | fquern@mit.edu
IS&T - FLE Product Owner | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu
IS&T - FI Team | Keyur Patel – W92 | Refer to online directory | keyurpb@mit.edu
IS&T – EHS/Parking - Scrum master | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu
IS&T – Facilities PO | Jim Fragala – W92 | Refer to online directory | jfragala@mit.edu
IS&T – Logistics | Ken Levie – W92 | Refer to online directory | levie@mit.edu
IS&T – Log/FIN/EHS Team Coordinator | Adina Ion – W92 | Refer to online directory | aion@mit.edu
IS&T – Ops | George Gaudette - W92 | Refer to online directory | gaudette@mit.edu
IS&T – Ops | Paul Cronin – Off Campus | Refer to online directory | croninp@mit.edu
IS&T - Data warehouse | Warehouse support team | Refer to online directory | warehouse-dev@mit.edu
IS&T – HRP Scrum Master | Meaghan Murray – W92 | Refer to online directory | mamurray@mit.edu
IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu
IS&T - OIS | Server Operations | 617-775-3302 | Team Line
Monday Morning Coverage
Area | Name | Location | Time | Email
Help Desk | Team | W91 | 6:00am
FLE | Lee Collier | W92 | 7:30am | lcollier@mit.edu
FLE | Jim Fragala | W92 | 7:30am | ja17661@mit.edu
HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu
HRP | Meaghan Murray | Off Campus | 7:30am | mamurray@mit.edu
R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu
ABAP | Elda Prudden | Off Campus | 7:30am | eprudden@mit.edu
ABAP | Mark Prudden | Off Campus | 7:30am | mprudden@mit.edu
FLE | IS&T SA Team | W92 | 8:00am + | administrative-systems@mit.edu
HRP | IS&T SA Team | W92 | 8:00am + | hrpay-sppt@mit.edu

## Cutover Task List
# | Date | Time (EST) | Action / Task | Person(s) Responsible | Status | Upon completion send email to: | Comments
Pre-Update Schedule and Processes:
1 | By Tuesday 11/15/2016 | By EOD | Schedule review meetings: - IS&T Transport Review - IS&T Cutover Review - IS&T Action Log Review - SAPbiz Cutover Review | Frank Quern | complete | n/a
2 | Tuesday 11/22/2016 | 13:00 | Transport Review Meeting Final review all issues in RT project queue, transport list, and web components. | IS&T-SAP | complete | n/a
3 | Wednesday 11/23/2016 | By EOD | Draft Cut-over Communication Plan/Submit to IS&T Communication Team for review. | Frank Quern | complete | n/a
4 | Monday 11/28/16 | 13:00 | IS&T cutover weekend planning/review meeting. | IS&T-SAP | complete | n/a
5 | Tuesday 11/29/2016 | By EOD | Submit Atlas Banner Message Request to Atlas Team for 12/2 | Frank Quern | complete | n/a
6 |  | By EOD | Submit ECAT Outage Message Request to Procurement for 12/2 | Frank Quern | complete | n/a
7 |  | By EOD | Submit Outage/Injury Report to EH&S for Review | Frank Quern | complete | n/a
8 |  | 3:30-4:30 PM | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | POs (Bob Casey, Frank Quern) | complete | n/a
9 |  | 17:00 | Start Enh 8 Preprocessing (uptime) phase | HEC/R3-Admin | complete | fquern@mit.edu
10 |  | By EOD | PS1 System transport lock (transports not allowed into production) | HEC/R3-Admin | complete | fquern@mit.edu
11 | Wednesday 11/30/2016 | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | Frank Quern | complete | fquern@mit.edu
12 |  | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker) | complete | fquern@mit.edu
13 |  | By 5:00 PM | Post message on ECAT web site about upcoming SAP outage. | VPF (Cecilia Talamantes) (Scott Ball) | complete | n/a
14 |  | 11:00 | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team | complete | n/a
15 |  | 14:00 | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee | complete | n/a
16 |  | 16:00 | Email ops-help with list of web application deployment requests for Sunday morning. (refer to MIT Web Deplyment tab for details) | PM ( Frank Quern) |  | fquern@mit.edu
17 |  | By EOD | Email Steering Committee Go/No-go decision to Team | Frank Quern | complete | n/a
18 |  | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Frank Quern | complete | fquern@mit.edu
19 |  | By EOD | Final Copy of the Production Update Schedule (cutover plan) published and emailed. | Frank Quern | complete | fquern@mit.edu
20 | Thursday 12/1/2016 | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be 12/14/2015). Notify R3-Admin (R. Parker) and PO (Frank Quern) when jobs have been scheduled. | VPF Finance (S. Desmond) FIN BSA (Keyur Patel) | complete | fquern@mit.edu | submitted on 11/21
21 |  | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. | Admin Systems (M. Murray via Fire Fighter) |  | n/a
22 |  | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker) |  | n/a
23 | Friday 12/2/2016 | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM Monday). | ABAP Team (Eping Lucia Wei) |  | fquern@mit.edu
24 |  | By 2 PM | Download Facilities work order lists as back up for Monday Morning | Facilities (Bob Leonard) |  | fquern@mit.edu
25 |  | By 2 PM | Download Housing work order lists as back up for Monday Morning | Facilities (Mike Sherman/Bob Leonard/Lisa St. Croix) |  | fquern@mit.edu
26 |  | By 3:20 PM | Shift Concur outbound execution from 5:00 pm to 3:20pm | R3-Admin |  | fquern@mit.edu
27 |  | By 3:30 PM | Suspend weekend MITSIS cron jobs for the BIO feed and the Grad Appointment Feed - On sky-app-1 under userid as_cron comment out weekend rprgapxt_new job - On sky-app-5 under the as_cron userid comment out the /sis/mitsis/applications/scripts/GEN/triggerBatch.sh /sis/cron biofeedsJob job. | ops (G. Gaudette) |  | fquern@mit.edu
28 |  | By 4:00 PM | Workflow and JV Validation Reports · Workflow inbox report (Steve Hoover) · JV Parked Documents Report (Steve Hoover) · RFPs (Cathy Cherico) | VPF (Steve Hoover) (Cathy Cherico) |  | fquern@mit.edu
System Isolation
29 | Friday 12/2/2016 | 15:30 | MIT Handoff SAP Mobile Platform (SMP_ to HEC for Upgrade Processing | R3-Admin |  | fquern@mit.edu
30 |  | 16:30 | SAP Mobile Platform shutdown | HEC |  | fquern@mit.edu
31 |  | 4:30 PM (4 hours) | SAP Mobile Platform Upgrade (Refer to the SAP Mobile (SMP) Upgrade TAB) | HEC |  | fquern@mit.edu
32 |  | 4:30 PM (5 Minutes) | Suspend Drop-box processing. | R3 Admin (Qian Kang) |  | sap-upgrade-core@mit.edu
33 |  | 4:35 PM (5 Minutes) | Stop EDI Production Jobs (5 Minutes) Will need access to logistics batch id ZZLOGISBAT01 (thru GRC). | Tech Services (Elda Prudden) R3-Admin (George Petrowsky) |  | sap-upgrade-core@mit.edu
34 |  | 5 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). · Run the push POs job · Shutdown the web server · Shutdown the application server | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
34a |  | 16:45 | Disable COUPA Integration - In the following order disable: (1) requisitions integration, (2) POs, (3) invoices - Leave buytopay-req-auto-approval enabled | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
35 |  | 5 PM | Voice message update when system goes down (617-324-7468) | PM ( Frank Quern) |  | sap-upgrade-core@mit.edu
36 |  | 5 PM | System Downtime Message (3 Down) | R3-Admin PM (Frank Quern) |  | sap-upgrade-core@mit.edu
37 |  | 5 PM | Bring down application servers. Production Environment becomes unavailable to users (including ECAT). | HEC/R3-Admin |  | sap-upgrade-core@mit.edu
38 |  | 5 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) | Frank Quern |  | sap-upgrade-core@mit.edu
39 |  | 5 – 7 PM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Stef Desmond via email cc fquern@mit.edu, keyurpb@mit.edu that the reports are completed & downloaded. • VPF confirms the receipt of the Trial Balance Report. | R3-Admin (R. Parker) VPF (Stef Desmond) |  | sap-upgrade-core@mit.edu
40 |  | 5 – 7 PM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday) • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • Save WT info to internal SAP table | R3-Admin (R. Parker) (G. Petrowsky) |  | sap-upgrade-core@mit.edu
Support Pack Application/HANA Upgrade and Processes:
41 | Friday 12/2/2016 | By 7:30 PM | MIT Handoff to HEC for PS1, ACP, & OTP Upgrade Processing | R3-Admin |  | sap-upgrade-core@mit.edu
42 |  | 7:30 PM (12 hrs) | PS1 Enhancement Pack 8 upgrade/support pack application (Refer to the ERP (PS1) Upgrade TAB) | HEC |  | sap-upgrade-core@mit.edu
43 |  | 7:30 PM (4 hrs) | GRC ACP System Upgrade (Refer to GRC (ACP) Upgrade TAB) | HEC |  | sap-upgrade-core@mit.edu
44 |  | 5:15 PM (4 hrs) | OpenText HANA Upgrade (Refer to OpenText (OTP) Upgrade TAB) | HEC |  | sap-upgrade-core@mit.edu
45 |  | 6:30 PM (30 mins) | OpenText application HANA Client (Refer to OpenText (OTP) Upgrade TAB) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
46 |  | 7:30 PM (4 hrs) | BSI Upgrade - application of TUBs (can occur any time after 5pm Friday) | R3-Admin (Ron Parker) |  | sap-update-core@mit.edu
Post Upgrade Schedule and Processes:
47 | Saturday 12/3/2016 | 7:30 AM (10 hrs) | MIT Technical Post Upgrade Processing (Open Text, BSI, GRC, SOLMAN, SFTP, ADS, SAP Mobile, Printers) - Restore WT Table - Many more ... (Refer to MIT Post Processing Task List tab for details) | R3-Admin |  | sap-upgrade-core@mit.edu
48 |  | By noon | Execute MIT Web Deployments tasks (refer to MIT Web Deployments tab) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu | Friday evening/Saturday morning
49 |  | during the above 10 hour window | Validation reports executed (trial balance reports) • R3-ADMIN notifies Stef Desmond via email, cc to Frank Quern as soon as the trial balance is available for review • R3-ADMIN unlock sdesmond id in PS1 | R3-Admin (R. Parker) VPF Finance (Stef Desmond) |  | sap-upgrade-core@mit.edu | after transports & generations
50 |  | 16:00 | IS&T Conference Call Check-in Core Team Check in at 4 pm on Saturday (use conference call webex line below) +1-617-324-0000 US Toll Number Access code: 644 196 523 | Project Manager (Frank Quern) |  | sap-upgrade-core@mit.edu
51 |  | 5:30 PM - 6:30 PM | MIT IS&T Post Upgrade Action Log - action log team members unlocked - action log execution unique for 2016: - Add Jurisdiction configuration for EDI in SAP - Ken Levie - more … | Action Log Team (R3, ABAP, SA) |  | sap-upgrade-core@mit.edu
52 | Sunday 12/4/2016 | By 7:30 AM | Update voice message. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | PO (Frank Quern) |  | sap-upgrade-core@mit.edu
53 |  | 8:15 | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (start EDI; but do not send or push any files yet) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
54 |  | 8:30 | EDI Step 2 Update TLE Paramenters - Change version in Tle from 740 to 750 | Tech Services (E. Prudden) |  | sap-upgrade-core@mit.edu
55 |  | 8:45 | EDI Step 3 Start EDI Jobs (start sending EDI files) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
56 |  | By 9 AM (5 Minutes) | EDI Step 4 (last step) Schedule EDI Job • Unlock ids (eprudden, ZZLOGISBAT01) • Schedule EDI Job • Monitor first job released (on the ½ hr) | R3-Admin (G. Petrowsky) Tech Services (E. Prudden) (ZZLOGISBAT01) |  | sap-upgrade-core@mit.edu
57 |  | By 8:30 AM (5 Minutes) | Email to ist-sap@mit.edu • List of transports applied and any related issues. • List of jobs shifted in PS1 during cutover | R3-Admin (Ron Parker) |  | sap-upgrade-core@mit.edu
58 |  | 9:00 | Unlock IS&T Teams (ABAPs, BAs, SAs, DW, GRC ids) | R3-Admin (G. Petrowsky) |  | sap-upgrade-core@mit.edu
59 |  | 9:00 AM - 10:30 AM | IST SAP Team Validations | All R3, ABAP, BSA, DW ids |  | sap-upgrade-core@mit.edu
60 |  | by 10:30am | TB Validation reports validated • Stef notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Stef Desmond) (Keyur) |  | sap-upgrade-core@mit.edu
61 |  | by 10:30am | Update voice message. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | PO (Frank Quern) |  | sap-upgrade-core@mit.edu
61a |  | 10:30 | Enable COUPA Integration in the following order: (1) requisitions integration (2) Pos (3) invoices | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
62 |  | 10:30 | Unlock validators (testers) | R3-Admin (G. Petrowsky) |  | sap-upgrade-core@mit.edu
63 |  | 10:30 AM - 12:30 PM (2 hours) | MIT Business Validation PS1 Data Validations & Transaction processing listed in section of the Validation tab performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs IS&T BSAs |  | sap-upgrade-core@mit.edu
64 |  | By 12:30 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs IS&T BAs & SAs |  | sap-upgrade-core@mit.edu
65 |  | 13:00 | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, POs, Team Leads) +1-617-324-0000 US Toll Number Access code: 644 852 387 | PM (Frank Quern) |  | sap-upgrade-core@mit.edu
Go Live
66 | Sunday 12/4/2016 | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu, warehouse@mit.edu) indicating decisions/results. | PM (Frank Quern) |  | sapbiz@mit.edu sap-upgrade-core@mit.edu ist-sap@mit.edu warehouse@mit.edu
67 |  | 1:30 PM – 2:30 PM | Unlock users (Facilities, SMART) Unlock all users (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update Atlas message. | R3-Admin (George Petrowsky) |  | sap-upgrade-core@mit.edu
68 |  | 2:30 PM Sunday (5 Minutes) | Enable Drop box | R3 Admin (Qian Kang) |  | sap-upgrade-core@mit.edu
69 |  | 14:30 | Reinstate weekend MITSIS Grad Appointment Feeds | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
70 |  | 8PM – 12AM | Data Warehouse Job Validation • Eping (Lucia) Wei confirm job validation completion via email to sap-upgrade-core@mit.edu, warehouse-dev@mit.edu • Run extracts (10PM & 12AM) | R3-Admin |  | sap-upgrade-core@mit.edu
71 |  | By 6:30pm | Execute ProCard from Bank of America Feed | ABAP Team (Eping Lucia Wei) |  | sap-upgrade-core@mit.edu
72 | Monday morning 12/5/2016 | By 6 AM | Update the 3-down web page & SAPgui message. | R3-Admin (R. Parker) Project Manager (Frank Quern) |  | sap-upgrade-core@mit.edu
73 |  | By 6 AM | Remove SAP outage message on ECAT webpage. | VPF (Cecelia Talamantes) (Scott Ball) |  | sap-upgrade-core@mit.edu
74 |  | By 6 AM | Remove Atlas and EHS messages. | Frank Quern |  | sap-upgrade-core@mit.edu
75 |  | By 6 AM | Post Atlas Banner Message with link to Known SAP Issues kb article | Frank Quern |  | sap-upgrade-core@mit.edu | if needed
76 |  | By 6 AM | Validate Atlas and EHS outage messages have been removed (verify in IE, Firefox, Chrome) | HRP BSA (Meaghan Murray) |  | sap-upgrade-core@mit.edu
77 |  | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | PM (Frank Quern) |  | sap-upgrade-core@mit.edu
78 |  | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. o email sap-upgrade-core@mit.edu when complete | HRP BSA (Meaghan Murray) |  | sap-upgrade-core@mit.edu
| 2017-01-01 | 17:30 | Activate gui version detection/rejection for older SAP gui versions | R3-Admin (Ron Parker) | on hold | n/a | will we be doing this this fiscal year?

## MIT Web Deployments
SAP web components for Dec 2-4, 2016 cutover
[Note: we will stage as much as possible (non SAP) in OC11 datacenter by Dec 2]
# | Task description | Request | Execute | When | Comment
| Mulesoft - Anypoint Proxy Deployment |  | complete
| Mulesoft - Anypoint I-9 APIs (Fragomen) |  | requested
Java deployments for:
| The New Hire app tag: emp-newhire-175-081816111017 |  | pending | 12/2/2016: 5:30 PM | deploy anytime after 5:30 PM still under review
| The Atlas Config tag: atlas-configuration-r41-1012161519 (contains I-9 link only) Tag atlas-configuration-r42-1013161026 (contains both I9 and Diversity links) |  | pending | 12/2/2016: 5:30 PM | need to assess which version we will be going live with
| Diversity App tag: enriching-diversity-build-master-20161115-118 Diversity App tag: enriching-diversity-build-master-20161126-119 |  |  | 12/2/2016: 5:30 PM | deploy anytime after 5:30 PM
| Ops request:Tag: atlas-1497-102816112114 War File: /home/www/release/atlas-atlas-1497-102816112114.war | RT # 4061177 |  |  | SAP 2016 - BN - Initial Benefits Enrollment: MIT Benefits Office link on terms of use does not open
| Ops request:Tag: atlas-1497-102816112114War File: /home/www/release/atlas-atlas-1497-102816112114.war |  |  | 12/2/2016: 5:30 PM | deploy anytime after 5:30 PM
| (1) /home/www/release/po-po-s2-14-091616162208.war |  | hold to post | 12/2/2016: 5:30 PM | deploy anytime after 5:30 PM
| (2) The static file project, insidemit, needs to be propagated to our tomcat & OAS servers from GitHub. The repos can be found: git@github.mit.edu:AdminSystems/insidemit.git |  | hold to post | 12/2/2016: 5:30 PM | deploy anytime after 5:30 PM
| (3) atlas-configuration: 1 javascript file needed to be modified changing SH1 WDA/ITS entries on premise URLs to HEC URLs |  | N/A | 12/2/2016: 5:30 PM | part of atlas deploys for diversity project
NOTE: new ITS/WDA doman, use https://hecps1web01.mit.edu
| Server Name | Type
| atlas-w92-prod-app-1 | Atlas
| atlas-w92-prod-app-2 | Atlas
| atlas-w92-prod-app-3 | Atlas
| atlas-w92-prod-app-4 | Atlas
| atlas-oc11-4-prod-app-1 | Atlas
| atlas-oc11-4-prod-app-2 | Atlas
| atlas-oc11-4-prod-app-3 | Atlas
| atlas-oc11-4-prod-app-4 | Atlas
| admsys-w92-prod-app-1 | Application
| admsys-w92-prod-app-2 | Application
| admsys-w92-prod-app-3 | Application
| admsys-w92-prod-app-4 | Application
| admsys-w92-prod-app-5 | Application
| admsys-w92-prod-app-6 | Application
| admsys-oc11-4-prod-app-1 | Application
| admsys-oc11-4-prod-app-2 | Application
| admsys-oc11-4-prod-app-3 | Application
| admsys-oc11-4-prod-app-4 | Application
| admsys-oc11-4-prod-app-5 | Application
| admsys-oc11-4-prod-app-6 | Application
| ehssys-w92-prod-app-1 | Application
| ehssys-w92-prod-app-2 | Application
| ehssys-oc11-4-prod-app-1 | Application
| ehssys-oc11-4-prod-app-2 | Application
| finsys-w92-prod-app-1 | Application
| finsys-w92-prod-app-2 | Application
| finsys-oc11-4-prod-app-1 | Application
| finsys-oc11-4-prod-app-2 | Application
| sky-app-21 | Application | Not replicated
| sky-app-22 | Application | Not replicated
| asapis-prod-app-1 | Application | Not replicated
| asapis-prod-app-2 | Application | Not replicated

## R3 Post Upgrade Tasks
Task ID |  | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
Thursday
| PS1 | 2016-12-01 | by 5 PM | 2016-12-01 | by 5 PM | N/A | Ron Parker | Save Wage type table (after system is locked)
| PS1 | 2016-12-01 | by 5 PM | 2016-12-01 | by 5 PM | N/A | Ron Parker | Snapshoft of Profiles (8 profiles)
Friday
| SMP | 2016-12-02 | 15:30 | 2016-12-02 | 15:30 | N/A | Ron Parker | MIT Handoff SAP Mobile Platform (SMP_ to HEC for Upgrade Processing
| PS1 |  | 17:00 |  | 17:00 | N/A | Ron Parker | Request SAP bring down application systems
| PS1 |  | 17:00 |  | 17:30 | 30 minutes | George Petrowsky | Lock Users
| PS1 |  | 5:00 PM EDT |  | 17:30 | 30 minutes | George Petrowsky | Disabling Logon groups
| PS1 |  | 17:00 |  | 17:30 | 30 minutes | Ron Parker | Run TB Reports
| GRC - ACP | 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 7:30 PM EDT | 2 hours | MIT (R3-Admin) | Update System Security Environment (Touchstone)
| GRC - ACP | 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 7:30 PM EDT | 30 minutes | MIT (R3-Admin) | Validate SAML Touchstone connectivity
Saturday
| PS1 | 2016-12-03 | 7:30 PM EDT | 2016-12-03 | 12:30 PM EDT | 5 hours | Rich Katkowski | Load Tranport buffer and Transport
| GRC - ACP | 2016-12-03 | 12:30 PM EDT | 2016-12-03 | 1:00 PM EDT | 0.5 hours | Rich Katkowski | Import GRC Transports
|  |  | 7:30 PM EDT |  | 5:30 PM EDT | 10 hours | R3 | R3-Admin action log
| PS1 | 2016-12-03 | [5 empty] | Generate features in client 0 for select transports
| PS1 | 2016-12-03 | [5 empty] | Generate features in client 30 for select transports
| PS1 | 2016-12-03 | [5 empty] | Restore Wage Types
| PS1 | 2016-12-03 | [5 empty] | Unified rendering
| PS1 | 2016-12-03 | [5 empty] | Run TB Reports
| PS1 | 2016-12-03 | [5 empty] | User validations
| PS1 | 2016-12-03 | [5 empty] | Roles feed file process
| PS1 | 2016-12-03 | [5 empty] | BSI Test Connection
| PS1 | 2016-12-03 | [5 empty] | Check/Test Open Text Connectivity
| All | 2016-12-03 | [5 empty] | Test of infrastucture
| PS1 | 2016-12-03 | [5 empty] | rendering
| PS1 | 2016-12-03 | [5 empty] | user maintienance
| PS1 | 2016-12-03 | [5 empty] | trusted links validations
| PS1 | 2016-12-03 | [5 empty] | drop box
| ASAPI | 2016-12-03 | [5 empty] | Restart ASAPI servers (production tier)
| Menix | 2016-12-03 | [5 empty] | Restart CSAIL and Comp Analysis in Mendix
| PS1 | 2016-12-03 | [5 empty] | Shift back to weekend those jobs that normally occur on weekend
| GRC - ACP | 2016-12-03 | 14:00 | 2016-12-03 | 2016-12-03 | 30 minutes | Sarah Quigley | Turn on PS1 sync job
| GRC - ACP | 2016-12-03 | 14:00 |  | 16:00 | 2 hours | Sarah Quigley | GRC Validations
Check that JCO MetaUser and Scorm users are unlocked in PS1: ZZJCOMETA000 (run any JCO app, e.g Disp PO) and ZZADMSCORM01 (open learning center course, e.g. event planning, chk table Z...)

## SAP Tickets
PS1 | 434584 / 2016 Execute PS1 Support and Enhancement Package upgrade to ERP 6.0 w/EHP8 | In Processing by SAP
ACP - ACPMIT | 434725 / 2016 SUSE Linux patching SCN-2016-1398 [Linux-High] for ACP | Sent to SAP
ACP - ACPMIT | 434810 / 2016 Sybase Upgrade to 15.7 SP136 HF1 for system ACP
We have scheduled the ASE Upgrade activity on 03rd Dec 2016 between 8:00 AM IST to 7:00 PM IST (02/12 9:30 PM to 03/12 8:30 AM EST)
The maintenance window of 09:30PM on Friday, December 02 2016 EST, through 08:30AM on Saturday 03 2016 EST, is available for the upgrade of the ACP system's Sybase database to version 15.7 SP-Level 136 HF1 (the maintenance window can be shifted to immediately follow the ACP system Linux patching requested in incident 434725). This database upgrade will be accompanied/followed by an update of the ACP system's ABAP and Application Server kernel components.
ACP - ACPMIT | 434840 / 2016 Update NetWeaver GRC system ACP | Sent to SAP
OTP | 426924 / 2016 SUSE Linux patching SCN-2016-1398 [Linux-High] for OTP
This incident is an approval to apply high priority Linux patch SCN-2016-1398 to the HEC-managed OTP HANA database environment (server vhmitotpdb01). The maintenance window of Friday, December 02 2016, from 05:15PM to 08:15PM EST, can be used to perform this maintenance.
| 426935 / 2016 Upgrade OpenText system HANA database from SP 9 to SP 12 for OTP | Sent to SAP
SMP | 427030 / 2016 Allocate additional memory to SAP Mobile JVMs for SMP
Per SAP recommendation, the memory allocations for the JVMs of the MIT Mobile Application Servers need to be increased from their default settings in order to take advantage of memory made available on its up-scaled servers. The maintenance window of Friday, December 02 2016, from 3:30PM to 4:30PM EST can be used to perform this maintenance for the SMP SAP Mobile system (servers vhmitsmpci, vhmitsmpai01 and vhmitsmpai02). My understanding is that the SMP application server JVMs will get the same JVM memory increases as those evaluated in the SAP Mobile test tier system, SMQ.
SMP | 426955 / 2016 Upgrade the SAP Mobile Database to SAP ASE 16 SP02 PL04 HF1 for SMP
The databases of the MIT SAP Mobile tiers need to be upgraded to ASE version 16 SP02 PL04 HF1, in order to address a vulnerability to denial of service attacks. The maintenance window of Friday, December 02 2016, from 4:30:00PM to 8:30 EST can be used to perform this Sybase database upgrade against the SMP ASE database on vhmitsmpdb01.
NOTE:
The vhmitsmpdb01 (hec03v004968) database server is being scaled up to accommodate the ASE 16.x upgrade before the specified DB upgrade window (as described in incident 422452).

## ERP (PS1) Upgrade
PS1 System upgrade between 12/2 starting at 7:30 PM EDT and 12/3 7:30 AM EDT
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
a | 11/23/2016 | By EOD | 11/23/2016 | By EOD | N/A | MIT (R3-Admin) | Create Ticket for ehp8 Upgrade no later than 11/23 | complete
b | 11/23/2016 | 8:00 AM EDT | 11/25/2016 | 8:00 AM EDT |  | MIT (R3-Admin) | To confirm in the ticket that preparation steps have been completed in OSS note ( some tasks includes Import OSS notes, backup tables related to HR, etc) | complete
Extraction, Configuration and Check Phases
1 | 11/25/2016 | 12:00 PM EDT | 2016-11-28 | 5:00 PM EDT | 2 days | HEC | Extraction, Configuration, Check phases from Software Update Manager Tool, we will wait to Tuesday 29th afternoon in order to start with Preprocessing phase ( system lock) | complete
2 | [6 empty] | During Extraction Phase, PS1 XML file is provided, it was created by HEC at the same week that SH2 XML was created | complete
3 | [6 empty] | During Extraction Phase Import SPAM version 63 REV 740 is mandatory | complete
4 | [6 empty] | During configuration phase to configure to use the Standard mode ( Shadow Instance)/Define the parallel Process to be used in the Shadow Instance | complete
5 | [6 empty] | During Configuration Phase (PREP_INTEGRATION/ADJUSTPRP) to provide Transport request provided by MIT (example: SF3K904745 was used in SH2); will be indicated in the service request ticket. | complete
6 | [6 empty] | HEC To confirm/validate the target version of each ABAP component | complete
Preprocessing Phase
7 | 2016-11-29 | By 5:00 PM EDT | 2016-11-29 | By 5:00 PM EDT | N/A | MIT (R3-Admin) | To confirm with an update in the ticket that HEC can proceed with Preprocessing phase ( lock development environment for any change) - MIT will update in ticket
8 | 2016-11-29 | 5:00 PM EDT | 2016-12-01 | 5:00 PM EDT | 2 days | HEC | Preprocessing phase to be executed from Nov 29th, to December 1st, 2016
| 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 5:00 PM EDT | N/A | HEC | Stop the PS1 Application Servers
| 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 5:00 PM EDT | N/A | MIT (R3-Admin) | Redirect ADS from DSP to DST
9 | 2016-12-02 | 7:30 PM EDT | 2016-12-02 | 9:30 PM EDT | 2 hours | HEC | End_steps_Preprocessing_phase ( requires about 2 hrs.)
10 | [6 empty] | Isolate Central Instances ( stop AI1 to AI7)
11 | [6 empty] | Suspend batch jobs
12 | [6 empty] | Logoff all users from Central Instance
13 | [6 empty] | Create full backup of intallation directory /usr/sap/PS1/ including SUM directory
14 | [6 empty] | Create Full Backup of HANA database
15 | [6 empty] | Change HANA log_mode from normal to overwrite
16 | [6 empty] | Stop HANA replication to HA node and DR site (Request through Software Update Manager Tool)
Execution and Post Processing Phase
17 | 2016-12-02 | 9:30 PM EDT | 2016-12-03 | 4:30 AM EDT | 7 hours | HEC | Execution Phase ( to run for about 7 hrs.)
18 | [6 empty] | At the end of Execution Phase, SUM tool request to change HANA log_mode to normal again ( HANA database restart is required)
19 | [6 empty] | after above step is completed, Execute a new HANA full backup ( 1 hr.)
20 | 2016-12-03 | 4:30 AM EDT | 2016-12-03 | 5:30 AM EDT | 1 hour | HEC | Post-Processing phase ( 1 hr.)
22 | [6 empty] | Also during post-processing phase, manual task request to Start Suspended Jobs, we will not perform it, as agreed MIT will take care of this task later on
23 | [6 empty] | HANA Replication will be re-enable during Post-processing phase
24 | 2016-12-03 | 5:30 AM EDT | 2016-12-03 | 7:30 AM EDT | 2 hours | HEC | Additonal Manual task after SUM process
Update SAP Kernel from 745 SP200 to SAP Kernel 745 311/Update SAPCrypto 8.5.5/
25 | [6 empty] | Update SAPcrypto related parameters to overcome issue reported after SAPCrypto update (client-ciphersuite) - MIT will note in ticket
26 | [6 empty] | Restart All Application servers
System Handover
27 | 2016-12-03 | 7:30 AM EDT | 2016-12-03 | 7:30 AM EDT | N/A | HEC | Handover PS1 Upgraded System to MIT at 7:30 AM EDT
28 | 2016-12-03 | 7:30 AM EDT | 2016-12-03 | 5:30 PM EDT | 10 hours | MIT (R3-Admin) | Perform Post-Upgrade tasks in PS1
29 | 2016-12-03 | TBD | 2016-12-03 | TBD | ? | MIT (R3-Admin) | Start Suspended Jobs
Special note: For Central Instance and Application intances in the DR site, no further action is needed due to the fact we have snap-mirror in place for the installation directory

## GRC (ACP) Upgrade
GRC System ACP upgrade between 12/2 starting at 7:30 PM EDT and 12/3 7:30 AM EDT
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
1 | 2016-11-23 | By EOD | 2016-11-23 | By EOD | N/A | MIT | Create ticket for Sybase Update to 15.7 SP136 HF1 at Friday 12/2 from 7:30 PM EDT to 10:30 PM EDT | complete
2 | 2016-11-23 | By EOD | 2016-11-23 | By EOD | N/A | MIT | Create ticket for ACP Support package update/SAP kernel update downtime window 12/02 from 10:30 PM EDT to 12/03 7:30 AM EDT | complete
3 | 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 7:30 PM EDT | 2 hours | MIT (R3-Admin) | Update System Security Environment (Touchstone)
4 | 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 7:30 PM EDT | 30 mins | MIT (R3-Admin) | Validate SAML Touchstone connectivity
| 2016-12-02 | 7:30 PM EDT | 2016-12-03 | 7:30 AM EDT | 12 hours | HEC | ACP Upgrade (12 Hour Window)
5 | 2016-12-02 | 7:30 PM EDT | 2016-12-02 | 8:30 PM EDT | 1 hour | HEC | System Backup (local)
6 | 2016-12-02 | 8:30 PM EDT | 2016-12-02 | 10:30 PM EDT | 3 hours | HEC | To perform Sybase update from current version 15.7 SP135 to 15.7 SP136 in both DR and Primary site
7 | 2016-12-02 | 10:30 PM EDT | 2016-12-03 | 7:30 PM EDT | 8 hours | HEC | To perform Support Package update/SAP Kernel Update to the same target version that we did in non-production systems

## OpenText (OTP) Upgrade
OTP System Upgrade
Task ID | Date | Time | Duration | Responsible | Task description | Status | comments
1 | 2016-11-23 | By EOD | N/A | MIT (Ron Parker) | Create the ticket with above information into XX-HST-OPR component at least 1 week in advance of the downtime window 12/02 at 7:30 PM EDT | complete
2 | 2016-12-01 | 4:00 PM EDT | 3 hours | DR Site Team | HANA database to be upgraded in DR Site 1 day in advance, on December 1st at 4PM EDT |  | monitor outage - ignore alerts between 4-7pm
3 | 2016-12-02 | 5:15 PM EDT | 1 hour | HEC | HANA database backup
3a | 2016-12-02 | 6:15 PM EDT | 1 hour | HEC | SUSE Linux patching SCN-2016-1398 [Linux-High] for OTP
4 | 2016-12-02 | 8:30 PM EDT | 3 hours | HEC | HANA database upgrade from REV 97 to REV 122.03 ( SP12)
5 | 2016-12-02 | 8:30 PM EDT | 30 minutes | MIT (George Gaudette) | Upgrade OpenText application HANA Client (this is an IaaS server hosted by HEC managed by MIT) upgrade both the primary site and the DR site
6 | 2016-12-02 | 11:30 PM EDT | 15 minutes | MIT (George Gaudette) | Verify Connectivity to DB
7 | 2016-12-03 | 8:00 EDT AM + | 15 minutes | MIT (R3-Admin) | Verify Connectivity through SAP ERP - including SSL (post transports)

## SAP Mobile (SMP) Upgrade
Task ID | Date | Time | Duration | Responsible | Description | Status
1 | 2016-11-28 | 6:00 PM EDT | 2.5 hours | HEC | 422452 / 2016 Scale-up VM vhmitsmpdb01 (hec03v004968) from 32 GB to 64 GB for system SMP
This is a request to scale up our SAP production Mobile system's database server VM, vhmitsmpdb01.hec.mit.edu (hec03v004968), from 32 GB to 64 GB with 16 virtual CPUs
The increased DB server memory is a prerequisite to upgrading the SMP system database from SAP ASE 15.7 SP 135 to SAP ASE 16 SP02 PL04 HF1.
The maintenance window of Monday, November 28 2016, between 6:00PM and 8:30PM EST is approved as the SMP maintenance downtime window for this activity.
2 | 2016-12-02 | 4:30 PM EDT | 3 hours | HEC | SAP Mobile Platform Database Upgrade from SAP ASE 15.7 SP 135 to SAP ASE 16 SP02 PL04 HF1
3 | 2016-12-02 | 7:30 PM EDT | 1 hour | HEC | JVM parameter increase from defaults

## SAP Mobile Cutover Steps
Step | Date | Description | Point of Contact
1 | FRI (or earlier) | Validate that mobile rollout for CSG 3rd shift and R&M Corrective have been deferred | Completed - Jim Fragala
2 | FRI (or earlier) | Communicate to the mobile community what is happening. | Lisa St. Croix/Nicole Smith
3 | Friday | upgrade to iOS 10 also, collect devices on Friday, upgrade to iOS 10 | M. Sherman, with help on manual steps from Jack Smith and Nicole Smith
4 | Friday | Verify no weekend work for current iPad users (Electricians), Mobile users down by 3:00 PM | Nicole Smith
5 | FRI (or earlier) | Identify personnel on call (e.g. Evora IT, LSI) | Jim Fragala
6 | SAT (during shutdown) | Use CASPER to push new Agentry files to mobile users (add specific steps here) | M. Sherman
7 | SAT | Validate that SMP mobile server is up | R3 admin
8 | When r3 admin done with ECC upgrade | Restart the SMP Cluster nodes after the ECC upgrade is complete | R3 admin
9 | When r3 admin done with ECC upgrade | Make sure that the switch framework switches for the mobile enhancements are still on after the upgrade | R3 admin
10 | SUN | Mobile validations in production by business Validate steps needed on iPad (re-enter iTunes password?, reboot iPad?) | R Leonard, M Sherman, Nicole Smith, Jack Smith
11 | SUN | Notify Electrical Supervisor/Planner of successful (or need for backup plan) | Nicole Smith/ Lisa St. Croix
12 | MON | Backup plan for mobile if cutover fails - Shop Papers | Nicole Smith
13 | MON | 6:45 am @ WW15 Electrical Shop - WO Receipt Support Paper as a backup. Validate all iPads | Jack Smith and Nicole Smith and Bob Leonard
14 | MON | 2 pm @ WW15 Electrical Shop - WO Closeout Support | Jack Smith and Nicole Smith and Bob Leonard

## BSI Upgrade Tasks
Task ID | Date | Time | Duration | Responsible | Task description | Status | comments
| 2016-12-02 | 17:00 | 4 hours | R3- Admin - Ronald Parker | Upgrade BSI

## Escalation Path
Escalation Path
If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Garry Zacheiss will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday December 4th.
Functional Malfunction(s)
Stef Desmond | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike MacDonald | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Laurie Veal | Business Process Owner (EH&S) / Weekend Coordinator
Cathy Cherico | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Frank Quern | Project Manager
Mark Silis | Associate Vice President, IS&T
Garry Zacheiss | Director, IS&T
Ron Parker | Manager, R3 Admin
Stephen Koczur | SAP HEC
Santiago Lopez | SAP Basis
Escalation Support Team
Adina Ion | Scrum Master
Bob Casey | FLE PO
Frank Quern | HRP PO
Frank Quern | Project Manager
George Petrowsky | R3 Authorizations
George Petrowsky | Scrum Master
Jim Fragala | Facilities PO
Kevin Lyons | Atlas PO
Lisa Robinson | Scum Master
Meaghan Murray | Scrum Master
Ron Parker | Basis PO
Faith Hill | Data Warehouse Team
Suhail Amroze | Data Warehouse Team

## Validation
Production Validation
Production Validation will occur in NE49, W92 and remotely. Validation is scheduled to start at 12:00 PM, however, please check the message line (617-324-7468) before coming into the office or starting to test remotely. The message will be updated by 11:30 AM if there are potential delays and by 12:00 PM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 8th. Frank will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/Stef desmond | Trial Balance Report validation. Ron Parker will email Stef Desmond, Bob Casey and Frank Quern when the reports have finished processing. Stef will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following:Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/Atlas ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu