## Sheet1
SAP - Consolidated Action Log
This document is used by IS&T and Business Process Owners as a guide to validate SAP systems after a database copy, infrastructure update and version upgrade. | [8 empty] | Performed in Environment? | [25 empty] | Dependencies or Timing Issues | Notes
Task # | User/Resp | Area | Dev/ Config / Trx. | DB Copy | Infra Update | Upgrade | R3 Auth | Description | SF3 Refresh |  | SF3 Post SP Application |  | SF8 Refresh |  | SF6 Refresh |  | SF2 Post SP |  | SF2 Refresh |  | SE1 Refresh |  | SH2 Refresh |  | SH2 Post SP Application |  | PS1 Post SP Application |  | SH1 Refresh |  | SH3 |  | SF8 Refresh
[9 empty] | Required Task | Task Status | Required Task | Task Status | Required Task |  | Required Task | Task Status | Required Task | a | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status
1 | Ron Parker | Email Notification | SE38 | Yes | Yes | Yes |  | Program ZBRSMAIL provides a mechanism to modify, replace, append, or write to tables Zemctrl and Zehcat. It is also possible to delete all of the rows of either of the two tables. These tables are used in the email redirection/distribution process. (Download values in ZEHCAT and ZEMCTRL tables) | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
2 | Ron Parker | Email Notification |  | Yes | Yes | Yes |  | Reset table settings for Z_SENDMAIL : 1. delete all entries from ZEMCTRL. 2. replace the contents of ZEHCAT with two rows: HNCAT=<space><space>, CMODE=X, ACTION=X, All other fields=<space>; HNCAT=++, CMODE=X, ACTION=X, All other fields=<space> | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
3 | Ron Parker | Email Notification | Config | Yes | Yes | Yes |  | Redirect e-mail notifications. Transaction SE30 Call View Maintenance. Table: ZEHCAT E-mail control table - handling categories. Action: Redirect Emailto: user@mit.edu or Action: Cancel. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
4 | Ron Parker | ITS | SICF |  |  |  |  | Activate /default_host/sap/public/bc/its/mimes | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate
5 | Ron Parker | ITS | SICF |  |  |  |  | 1. SICF 2. /default_host/sap/public/bc/icons 3. Menu >> Service/Host 4. Activate Object S_ICF_ADM Object class AAAB Activity 07 ICF: Name of Virtual Host ' ' ICF: GUID of ICF Service/Alias 000000000000000000000000 ICF: Service/Host/Alias NODE | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate
6 | Karen Nolet | HR | SE38 | Yes | N/A | N/A |  | Scramble HR data before system is open to others for validation | No | n/a | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | Yes |  |  | Do not scramble any environment without confirmation from SP PM
7 | Lucia Ma | MM | OMJ3 | Yes | Yes | Yes | Z_OMJ3 | Ensure Inventory printers are not directed to the production environment. Go to IMG: Materials management -> Inventory management and physical inventory -> Output determination -> Printer determination -> Printer determination by plant/storage location. (T_code: OMJ3) Change printers to MRP5. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
8 | Lucia Ma | MM | SPRO or SM30 (V_024_N) | Yes | Yes | Yes |  | Ensure Purchasing Group printers are not directed to the production environment. Go to IMG: Materials management -> Purchasing -> Messages ->Assign Output Devices to Purchasing Group. Change printers to MRP5. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
9 | Lucia Ma | MM | SM30 | Yes | Yes | Yes |  | Ensure ISP printouts are not directed to the production environment. Transaction SM30. Table: ZISPREQ Hit maintain and change printers to MRP5. Also modify USERID, USERPWD and PRINTER in table ZCAPARM. Check the values in ZV_MT_BROAD and ZV_MT_LOFTWARE do not have production values. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
10 | Lucia Ma | Classification | CT04 |  |  |  | Z#GL:CT04 | Change Facilities IO printer classification characteristic to print to spool MRP5, not a production printer. Looking for "DISTRIBUTION" | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
11 | Lucia Ma | Cross App | SE38 | Yes | Yes | Yes |  | Run Program ZCOC020 | No | n/a | No | n/a | No | n/a | Yes |  | No | n/a | Yes |  | No | n/a | Yes | issue | No | n/a | No | n/a | Yes | issue | Yes |  | No | n/a
12 | Lucia Ma | Workflow | SEWTYPV |  |  |  | Z#AA:WKFLADM | Reactivate all workflow event linkages. (Tcode: SWETYPV) | validate | complete | validate | complete | validate | complete | Yes |  | validate | complete | validate |  | validate | complete | Yes | complete | validate | complete | validate |  | Yes | complete | Yes |  | Yes
13 | Lucia Ma | Email Notification | SM30 |  |  |  | Z#EM:02_ZEM0 | Update ZEHCAT table to allow e-mail messages to be sent for commitment posting errors (first time entry into ZEHCAT) also make sure "FA" ~ "FZ" are redirected. Also check EL email redirection (ZHR_EMAIL_AREA, ZHR_EMAIL_PROC which email area 'LSO') | validate | complete | No | n/a | validate | complete | Yes |  | No | n/a | validate |  | validate | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | No | n/a
14 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | DoF validation: Enter program GBT30FIF and search (do Find in program) for GLL. (There should be none, only GAL.) If GLL is found, then regenerate validation rules from step above. NOTE: the "30" in the program name is based on the client in which the program is run, i.e. change to "25" if the client is 025, etc. Also looking for TEMP_STRUCT-SGTXT in GBT30COJ. | validate | complete | validate | complete | validate | complete | Yes |  | Yes | complete | validate |  | validate | complete | Yes | complete | validate | complete | validate |  | Yes | complete | Yes |  | Yes
15 | Ron Parker | FI/CO | SE38 | Yes | Yes | Yes |  | Generate validations/substitutions and sets. Run program RGUGBR00 with params: *,*,xxxxxx NOTE: This step should be completed only after all transports have been applied to the system, because transports containing validation rules will overwrite and require regeneration. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
16 | Lucia Ma | FI | SE38 | Yes | Yes | Yes |  | Regenerate FBV1 JV fast entry template: Run RFFAKP01 with parameters program = SAPLF040, application = PRPOS | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
17 | Lucia Ma | CO user exits | CMOD | Yes | Yes | Yes |  | Enter projects COOPA003, COOMKS01, WBSENHA, CATS0002 select "components" with "change" mode, make sure all exits are activated (green dots). If any component is not noted with a green dot, then return to CMOD screen, and deactivate, then reactivate the project, and confirm the project is activated./If deactivated, all users with CMOD need to check theirs as a follow up. | validate | complete | validate | complete | validate | complete | Yes |  | validate | complete | validate |  | validate | complete | Yes | complete | validate | complete | validate |  | Yes | complete | Yes |  | Yes
18 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | Run programs RK811XST to convert transaction groups for CO allocations (incl. Business cycles). No parameters necessary. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
19 | E. Prudden | IXOS | OAC3 | Yes | Yes | Yes | Z_OAC3 | IXOS Archive Link Setting. Transaction OAC3 Change View "Links for Content Repositories": Overview. (ALSO NEED FOR SPONSORED BILL ARCHIVE KL-10/30/03) If Ron doesn't put a value in there, don't have to modify it (look at the Cont.Rep.ID field and using the pulldown, make sure that the production values are not being referenced). | validate | complete | validate | complete | validate | complete | Yes |  | validate | complete | validate |  | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate |  | Yes
20 | E. Prudden | LO-EDI & HR-EDI | WE20 | Yes | Yes | Yes |  | Change the Receiver Port for Outbound Parameters. Transaction WE20 (Partner Profiles). Double click on "Partner Number" then dobule click on "Outbound Parmtrs". New screen come up. Change the "Receiver Port" under "Outbound Options". To confirm, check table EDP13 (field RCVPOR). | Yes | complete | validate | complete | Yes | complete | Yes |  | validate | complete | Yes |  | Yes | complete | Yes | complete | validate | complete | No | n/a | Yes | complete | Yes |  | Yes
21 | G. McGrath | HR | SM30 |  |  |  |  | Validate entries in table ZHRRETIREE_PLANS | No | n/a | No | n/a | No | n/a | No |  | validate | complete | validate |  | validate | complete | No | N/A | Yes | complete | validate |  | No | N/A | No | N/A | No | n/a
22 | G. McGrath / R3-Admin | Payroll | Dev |  |  |  |  | Update signature on check: "Void V Void" in all testing environments via transport. SHOULD NEVER GO TO PS1. Verify by transaction SE78, table Z_TTBT (SF2K927761 HRPP: Void Signiture File) | Yes | complete | validate | complete | Yes | complete | Yes |  | validate | complete | validate |  | validate | complete | Yes | complete | validate | complete | validate |  | Yes | complete | Yes |  | Yes
23 | E. Prudden | EHS / TEM | SM37 |  |  |  | IDs: ZZEHSBTCH001 ZZHRTEMBTC01 ZZHRELBTCH01 | Set up job to create users. Program, ZPE_CREATE_USER, under the ID, ZZHRTEMBTC01 , and is triggered by event, Z_TEM_SETUP (Check it first, if not exist, need to create one) NOTE: start after event "Z_TEM_SETUP" and it's a periodic job. Also create 2 additional batch jobs ZTN_LINCOLN_PI_TRAINEE_FEED under user ZZHRELBTCH01 & ZEHS_ROLESDB_WA_RELATS under user ZZEHSBATCH01. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | validate |  | Yes | complete | Yes |  | Yes
24 | G. McGrath | Payroll | Config |  |  |  |  | If refreshing a test environment determine if the control record should be checked during payrun processing if so comment out check from schema ZINO. This setting should never be commented out in a production environment. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete | No | n/a | Yes | complete | Yes |  | Yes
25 | Keyur Patel | FI | OB52 or ZFICLOSE |  |  |  | Z_CA_ZFICLOSE_POST_PER_OPN_CLO or Z#GL:OB52 or ID: ZZCAZFICLOSE | Open current FI posting period. Execute the following jobs: - OPEN NEW MONTH FOR MIT COA (USER ZZGLCLOSE001) - PCARD POSTING DATE ROLLOVER (USER ZZPRBATCH001) - SCHEDULE MANAGER VARIANT CUR (USER ZZFISCHDPC01) - RRPPERIOD FLIP (USER ZZAPBATCH001) - FLIP PERIOD ON PARKED SAJV'S (USER ZZGLCLOSE001) | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | validate |  | Yes | complete | Yes |  | Yes |  | Timing Issue in PS1
26 | R3-ADMIN | All | [5 empty] | Dropbox pointed to new test environment | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | validate |  | No | n/a | Yes | as needed | No | n/a | No | n/a | Yes | pending | No | N/A | No | n/a | as needed
27 | G. McGrath | Payroll | SE38 |  |  |  |  | Test BSI 10.0 connection. Execute program RPUBTCU0, select BSI Version 10.0 and execute. Test OC transaction (select a pernr) and verify BSI tax calculation is generated. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete | validate |  | Yes | complete | Yes |  | Yes
28 | G. McGrath | Payroll | PU19 |  |  |  |  | Test ADS connection. Execute Test Run of Tax Forms for individual pernrs via transaction PU19. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | pending | Yes |  | Yes | complete | Yes | complete | Yes | error | validate |  | Yes | complete | Yes |  | Yes
29 | G. McGrath | HR | SM30 |  |  |  |  | Compare Wage Type table: V_512W_O | No | n/a | Yes | complete | No | n/a | No |  | Yes | complete | Yes |  | No | n/a | No | N/A | Yes | complete | Yes |  | No | N/A | No | N/A | No | n/a
30 | Sharon DiLiberto | HR/Feed | [5 empty] | Check and verify/set ZUTARCHIVECRTL table | Yes | complete | validate | complete | Yes | complete | Yes |  | No | n/a | No | n/a | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
31 | G. McGrath | Payroll | SM30 |  |  |  |  | Check HR Payroll constant table: V_T511P, V_T511K | No | n/a | Yes | pending | No | n/a | No |  | Yes | complete | Yes |  | No | n/a | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes |  |  | a transport may be needed to correct the value of NNRCT in table V_T511K
32 | G. McGrath | Payroll | SPRO |  |  |  |  | Check PDF Validity Date for the tax form: V_T5UX7 Forms: HR_F_W2, HR_F_W2C, HR_F_1099R, HR_F_1099RC | No | n/a | Yes | complete | No | n/a | No |  | Yes | complete | Yes |  | No | n/a | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
33 | R3-ADMIN | Infra-structure | [5 empty] | Turn on the FAX Gateway | Yes | complete | validate | complete | Yes | complete | Yes |  | validate | complete | Yes |  | Yes | complete | Yes | complete | validate | complete | validate |  | Yes | complete | Yes |  | Yes
34 | R3-ADMIN | Infra-structure | [5 empty] | Establish target systems Operation Mode (work process distributions) | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
35 | BASIS | HR | PA40 |  |  |  |  | The features generation program, RPUMKG00, to activate generated programs related to HR features. | No | n/a | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | No | n/a | No | N/A | Yes | complete | Yes |  | No | N/A | No | N/A | No | n/a
36 | E. Prudden | TLE EDI | SAP Instance Info |  |  |  |  | In TLE, change the "Application Server" name, the "Gateway Server Name" and the "Host Name" (this action log item is only required for the hardware renewal project) | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | No | n/a |  | SP Proj: see cut-over plan Is this relevant for 2014? No.
37 | G. McGrath | Portal | ESS/Training |  |  |  |  | Test Portal Connection | No | n/a | No | n/a | Yes | complete | Yes | hold | No | n/a | Yes |  | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | Yes | hold
38 | Keyur Patel | FIN |  | Yes | Yes | Yes |  | Execute Trial Balance | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | No | n/a
39 | E. Prudden | ECAT Pointers | [5 empty] | Switch ECAT Pointers 1) In the edi subsystem (TLE), for every one of the 50+ vendors, change 2 settings (i.e. in TLE terms, the "interchange reference" and the "application"). 2) The web team needs to change the pointer on their end for the ECAT app | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | Yes | as needed | No | n/a | No | n/a | Yes | pending | No | N/A | No | n/a | as needed | make the switch when we switch to the test environment
40 | L. Collier | NRL Notifications | [5 empty] | 1. Transaction IL02 • Select all functional locations in NRL Hierarchy. • For each Functional location go to Partner screen (by clicking on partner icon) • Remove existing Partners. • Back • Save. 2. Transaction IE02 • Select all equipment assigned to functional locations in NRL hierarchy • For each equipment item go to partner screen • Remove existing partners • Back • Save 3. Check data • Transaction IE07 • Use Functional location structure selection option for equipment, multiple selection option • Select all nodes of NRL functional locations • List will reflect all equipment in NRL functional locs • In selection screen also make sure that object check box for partners is selected • Run transaction • List display will show all partners assigned to equipment assigned to NRL functional locations • Review and make sure that no one who gets emails in production will get confusion email from QA system (unless necessary for specific test) | Yes | complete | No | n/a | Yes | complete | Yes | hold | No | n/a | Yes |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
41 | E. Prudden | Stock Room | OXK1 | N |  | Y |  | Check if screen 9101, 9102, 9103, 9104, 9105, 9106, 9107, 9110, 9111, and 9112 exist in Function Group KACB (ABAP program SAPLKACB). If theses screens are missing, using transaction OXK1 (or report RBKNT001) to generate the screen. To generate screen: from OXK1, go to the menu option Subscreen -> Generate All. To generate the transport request: from OXK1, go to menu option Subscreen -> Transport (pick up the 9xxx screen one by one). | validate | new | Yes | new | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | N/A | No | n/a | validate |  | No | N/A | No | N/A | No | n/a
42 | FLE Team (Bob Casey) | FI | OB52 or ZFICLOSE |  |  |  | ID: ZZCAZFICLOSE | Schedule period end closing jobs – ZFICLOSE Controlling Area SING Variant Controlling Area MIT Variant | No | n/a | No | n/a | No | n/a |  |  | No | n/a | No | n/a | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | No | n/a
43 | L. Kushkuley | [6 empty] | Validate/Update entries in the ZHR_SRV_LINK table | validate | complete | validate | complete | validate | complete |  |  | No | n/a | validate |  | validate | complete | validate | complete | No | n/a | No | n/a | validate | complete | validate |  | validate
44 | G. Petrowsky/R3-Admin | Infra-structure | [5 empty] | Validate daily id sync is operational ID: ZZROLESFEED Jobs: ZR3_DAILY_MOIRA_&_SAP_ID_SYNC_2 ZR3_EXTID_MAINT | Yes | complete | Yes | complete | Yes | complete |  |  | Yes | complete | Yes |  | No | n/a | Yes | complete | No | na | Yes |  | Yes |  | Yes |  | Yes |  |  | ensure operational when SF2 is ever refreshed
45 | Karen Nolet | HR | PA30 |  |  |  |  | Reconnect APR test IDs, R3EDUI01- R3EDUI09, to PERNRs after refresh of test systems SH1, SH2, SH3. Map infotype 0105 SYSID & EMAIL. Change Infotype 0002 name. | No | n/a | No | n/a | No | n/a |  |  | No | n/a | No |  | No | n/a | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | No | n/a |  | Assignments: 00000852 R3EDUI01 00001034 R3EDUI03 00001155 R3EDUI09 00001294 R3EDUI02 00001568 R3EDUI06 00003725 R3EDUI08 00003812 R3EDUI04 00005572 R3EDUI05 00003825 R3EDUI07 00008057 R3EDUI10
46 | Lucia Ma | EL | SM30 |  |  |  |  | Check email redirection for LSO: two tables (ZHR_EMAIL_PROC with LSO and ZEHCAT with HW) | Yes | complete | validate | complete | Yes | complete |  |  | validate | complete | validate |  | Yes | complete | Yes | complete | validate | complete | No | n/a | Yes | complete | Yes |  | Yes
47 | L. Kushkuley | HR | [5 empty] | Confirm utility (ZHR_CLEAR_NH_TILES ) associated with transports: "SF2K956088 - New hire:clear tiles; NOT FOR PS1!!" and "SF2K956162 - HR Clear tiles program: recognize not a new hire" are in refreshed environment. SF2K960935 HANA replacement for SF2K956088 SF2K960936 HANA replacement for SF2K956162 | No | n/a | No | n/a | Yes | complete |  |  | No | n/a | validate |  | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | Yes |  | Yes |  |  | Transport should never go to production. (task should not be needed going forward 2/2/16) This step can be eliminated going forward.
48 | Mary Donovan | HRP | [5 empty] | For 2015 SP only - update EL number range: LSO_CRP | No | n/a | No | n/a | No | n/a |  |  | No | n/a | No |  | No | n/a | No | n/a | No | n/a | No | n/a | No | N/A | No | N/A | N/A | n/a
49 | L. Kushkuley | HR | [5 empty] | Replace the production URLS with the ‘test’ environment URLS in the following two tables: ZHR_NH_TILE_STEP ZHR_EMAIL_PROC New Hire table ZHR_NH_TILE_STEP Verify application URLs are correct, e.g. Benefits Enrollment | Yes | complete | validate | complete | Yes | complete |  |  | validate | complete |  |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
50 | R3-ADMIN | DW | SM30 |  |  |  |  | Execute only in a non-production environment. Update the following entries in table ZV_MT_WAREHOUSE: FTP value must be set to be identical to FTP_TEST PP value must be set to be identical to PP_TEST | Yes | complete | validate | complete | Yes | complete |  |  | validate | complete |  |  | Yes | complete | Yes | complete | No | n/a | No | n/a | Yes | complete |  |  | Yes
51 | Gregg McGrath | PY | SE38 | N |  | Y |  | Display the source code of RPCGET00_FUP0009 using SE38 and validate that the “PROVIDE” after option 3 is the one that is active as shown below. * Modification as of note 454352. * 1) use all records between period begin and end (SAP standard) * PROVIDE * FROM p0009 BETWEEN aper-begda AND aper-endda. * 2) use only records valid on period end * PROVIDE * FROM p0009 BETWEEN aper-endda AND aper-endda. * 3) use only records valid on payment date PROVIDE * FROM p0009 BETWEEN aper-chkdt AND aper-chkdt. | No | n/a | validate | complete | No | n/a |  |  | validate | complete |  |  | No | n/a | No | N/A | No | n/a | validate |  | No | N/A | No | n/a | No | n/a |  | a transport will be required to re-apply a mod to RPCGET00_FUP0009
52 | Cindy DeSimone | All | SE16 | N |  | Y |  | Re-generate program for HRP Tables PA0001, PA0009, PA2001 | No | n/a | No | n/a | No | n/a |  |  | No | n/a |  |  | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | [5 empty] | 2014 SP Only
53 | Ken LeVie | AP | SM30 | Yes |  | Y |  | ZCAPARM Proj Group Seq Description Value From: APPYT IP 1 IP ADDRESS ftp.paymode.com To: APPYT IP 1 IP ADDRESS testftp.paymode.com | Yes | complete | No | n/a |  |  |  |  | No | n/a |  |  | Yes | complete | Yes | complete | No | n/a | validate |  | Yes | complete
54 | Ken LeVie | AP | SM30 | Yes |  | Y |  | ZV_MT_AP Value: elink-http4.bankofamerica.com SD3YTHS5 TSTAH9SI | Yes | complete | No | n/a |  |  |  |  | No | n/a |  |  | Yes | complete | Yes | complete | No | n/a | validate |  | Yes | complete
55 | Keyur Patel | SP | [5 empty] | RT # 4057900 SAP 2016_SF2_FIN_Property_ Cutomized reports are not working Manual step required in each environment. See ticket details for instructions. Keyur will perform the task in PS1 directly under FFID. | [12 empty] | No: Yes
56 | Mark Prudden | SP | [5 empty] | RT # 4059211 SAP 2016: BN: P0106-FININ field label changed Manual fix (needs to be applied to each environment) Restore our custom field label texts by running transaction CMOD and selecting: Goto -> Text Enhancements -> Keywords -> Restore Customer Version | [12 empty] | No: Yes
57 | Larissa | SP | [5 empty] | RT # 4066115 SAP 2016 - HR Payroll - EDI field EXPLENG sizing Manually execute SEGREP to modify one record in the table EDISDEF for segment E1BEN07, correcting the segment length (to include one additional custom field. Will need to be executed in PS1 as part of the cutover. | [12 empty] | No: Yes