## Communication & Contacts
Communication
Cutover status messages will be sent to the project team and business validators and posted on the project cutover wiki page beginning at noon on Friday 12/8 through noon on Monday 12/11. The Project Manager or designee will update/send these messages as needed. A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 6:00pm on Sunday.
Conference Call Line: Webex
Call-in toll number (US): 617-324-0000 Friday Access code (24 hrs): 317 950 157 Saturday Access code (24 hrs) : 311 224 867 Sunday Access code (24 hrs): 315 045 860
Project wiki link: | https://wikis.mit.edu/confluence/display/sapscripts/2017+Year+End+SAP+Support+Pack+Project
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via voice message, email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
sapgui-updates@mit.edu | Used to notify specific users who need to upgrade their gui version
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
SAP Conntact Information
Name | Phone | Email
Steve Koczur | 610 745-6281 | stephen.koczur@sap.com
Phil Ferenschak | 610 662-0526 | phillip.ferenschak@sap.com
Michel Cervantes |  | m.cervantes@sap.com
Contact Information
Area | Name – Location | Contact Telephone # | Email
A/P | John Larkin – NE49 | Refer to online directory | jlarkin@mit.edu
Parking Office for Commuting Benefits applications | Robynn Cruz | Refer to online directory | Refer to online directory
Charitable Giving Office | Traci Swartz | Refer to online directory | Refer to online directory
VPF | Joe Siniscalchi | Refer to online directory | Refer to online directory
VPF | Steve Hoover | Refer to online directory | Refer to online directory
VPF – Travel | Kathy McGrath - Off Campus | Contact PM | Refer to online directory
Dept. of Facilities | Bob Leonard – Off Campus | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher – On Campus (10-063) | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix | Contact PM | lstcroix@mit.edu
EHS | Laurie Veal | Contact PM | veal@mit.edu
EHS | Jessica Van | Refer to online directory | jvan@mit.edu
EHS | Joe MacLeod - Off Campus | Contact PM | jmacleod@mit.edu
HR Coordinator | Mike MacDonald | Refer to online directory | mikemacd@mit.edu
HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu
HR/Benefits | Diane Sullivan – Off Campus | Contact PM | djohnsto@mit.edu
EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White – Off Campus | Contact PM | jwc@mit.edu
Procurement | Cindy Vye - NE49 | Contact PM | CI24314
Procurement | Scott Ball | Refer to online directory | Refer to online directory
VPF – HR/Payroll | Leslie Wright – NE49 | Refer to online directory | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Refer to online directory | darrenjs@mit.edu
VPF – HR/Payroll | Chris Durham – NE49 | Refer to online directory | cfdurham
IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu
IS&T - Project Manager | Frank Quern – W92 | Refer to online directory | fquern@mit.edu
IS&T - FLE Product Owner | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu
IS&T - FI Team | Keyur Patel – W92 | Refer to online directory | keyurpb@mit.edu
IS&T – EHS/Parking - Scrum master | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu
IS&T – Facilities PO | Jim Fragala – W92 | Refer to online directory | jfragala@mit.edu
IS&T – Logistics | Ken Levie – W92 | Refer to online directory | levie@mit.edu
IS&T – Log/FIN/EHS Team Coordinator | Adina Ion – W92 | Refer to online directory | aion@mit.edu
IS&T – Ops | George Gaudette - W92 | Refer to online directory | gaudette@mit.edu
IS&T – Ops | Paul Cronin – Off Campus | Refer to online directory | croninp@mit.edu
IS&T - Data warehouse | Warehouse support team | Refer to online directory | warehouse-dev@mit.edu
IS&T – HRP Scrum Master | Gregg McGrath – W92 | Refer to online directory | gmcgrath@mit.edu
IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu
IS&T - OIS | Server Operations | 617-775-3302 | Team Line
Monday Morning Coverage
Area | Name | Location | Time | Email
Help Desk | Team | W91 | 6:00am
FAC | Lee Collier | W92 | 7:30am | lcollier@mit.edu
FAC | Jim Fragala | W92 | 7:30am | ja17661@mit.edu
HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu
R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu
ABAP | Elda Prudden | Off Campus | 7:30am | eprudden@mit.edu
ABAP | Mark Prudden | Off Campus | 7:30am | mprudden@mit.edu
FLE | IS&T SA Team | W92 | 8:00am + | administrative-systems@mit.edu
HRP | IS&T SA Team | W92 | 8:00am + | hrpay-sppt@mit.edu

## Cutover Task List
# | Date | Time (EST) | Action / Task | Person(s) Responsible | Status | Upon completion send email to: | Comments
Pre-Update Schedule and Processes: [complete]
1 | By Tuesday 11/22/2017 | By EOD | Schedule review meetings: - R3 Cutover Planning - IS&T Transport Review - IS&T Cutover Review - IS&T Action Log Review - SAPbiz Cutover Review - Steering Committee Review | Frank Quern | complete | n/a | 11/28 12/5 11/29 12/5 12/6 12/4
2 | Wednesday 11/29/2017 | 10:30 | IS&T cutover weekend planning/review meeting. | IS&T-SAP | complete | n/a
3 | Thursday 11/30/2017 | By EOD | Draft Cut-over Communication Plan/Submit to IS&T Communication Team for review. | Frank Quern | complete | n/a
4 | Monday 12/4/2017 | 16:00 | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee | complete | n/a
5 |  | By EOD | Email Steering Committee Go/No-go decision to Team | Frank Quern | complete | n/a
6 | Tuesday 12/5/2017 | 13:00 | Transport Review Meeting Final review all issues in RT project queue, transport list, and web components. | IS&T-SAP | complete | n/a
7 |  | 16:00 | Email ops-help with list of web application deployment requests for Sunday morning. (refer to MIT Web Deplyment tab for details) | PM ( Frank Quern) | complete | fquern@mit.edu
8 |  | By EOD | Submit Atlas Banner Message Request to Atlas Team for 12/8 | Frank Quern | complete | n/a
9 |  | By EOD | Submit Coupa Outage Message Request to Procurement for 12/8 | Frank Quern | complete | n/a
10 |  | By EOD | Submit Outage/Injury Message to EH&S for Review | Frank Quern | complete | n/a
11 |  | By EOD | Submit Outage Banner Message Request to GAP support | Frank Quern | complete | n/a
12 |  | 14:00 | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team | complete | n/a
13 |  | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Frank Quern | complete | fquern@mit.edu
14 | Wednesday 12/6/2017 | 13:00 | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | POs (Bob Casey, Frank Quern) | complete | n/a
15 |  | 17:00 | Start Support Pack Preprocessing (uptime) phase | HEC/R3-Admin | complete | fquern@mit.edu
16 |  | Noon | PS1 System transport lock (transports not allowed into production) | HEC/R3-Admin | complete | fquern@mit.edu
17 |  | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | Frank Quern | complete | fquern@mit.edu
18 |  | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker) | complete | fquern@mit.edu
19 |  | By 5:00 PM | Post message on Coupa web site about upcoming SAP outage. | VPF (Cecilia Talamantes) (Scott Ball) | complete | n/a
20 |  | By EOD | Final Copy of the Production Update Schedule (cutover plan) published and emailed. | Frank Quern | complete | fquern@mit.edu
21 | Thursday 12/7/2017 | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be in the future). Notify R3-Admin (R. Parker) and PO (Frank Quern) when jobs have been scheduled. | VPF Finance (Joe Siniscalchi) FIN BSA (Keyur Patel) | complete | fquern@mit.edu
22 |  | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. | Admin Systems (L. Kushkuley via Fire Fighter) | complete | n/a
23 |  | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker) | complete | n/a
24 |  | By EOD | AIMS – Send an email to tomasz@aimsparking.com requesting that the AIMS job that runs M-F at 6 PM and posts JVs for Visitor parking reservations be disabled on Friday, Dec 8th. | Nivedita Dhiman | complete | fquern@mit.edu
25 |  | By EOD | Set up job for GAP posting program ZGAPOST to run Monday after go-live. See instructions in doc ‘Set up GAP posting catchup job’, located in Spartans’ (HR-Payroll) Support Packs Test Plans dropbox folder. | Mary Donovan | complete | fquern@mit.edu
26 | Friday 12/8/2017 | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM Monday). | ABAP Team (Eping Lucia Wei) | complete | fquern@mit.edu
27 |  | By 2 PM | Download Facilities work order lists as back up for Monday Morning | Facilities (Bob Leonard) | complete | fquern@mit.edu
28 |  | By 2 PM | Download Housing work order lists as back up for Monday Morning | Facilities (Mike Sherman/Bob Leonard/Lisa St. Croix) | complete | fquern@mit.edu
29 |  | By 3:20 PM | Shift Concur outbound execution from 5:00 pm to 3:20pm | R3-Admin | complete | fquern@mit.edu | see R3 Upgrade Tasks spreadsheet
30 |  | By 3:30 PM | Suspend weekend MITSIS cron job for the BIO feed: On sky-app-5 under the userid as_cron comment out the /sis/mitsis/applications/scripts/GEN/triggerBatch.sh /sis/cron biofeedsJob job. | ops (G. Gaudette) | complete | fquern@mit.edu
31 |  | By 4:00 PM | Workflow and JV Validation Reports · Workflow inbox report (Steve Hoover) · JV Parked Documents Report (Steve Hoover) · RFPs (Cathy Cherico) | VPF (Steve Hoover) (Cathy Cherico) | complete | fquern@mit.edu
System Isolation: [pending]
32 | Friday 12/8/2017 | 15:30 | MIT Handoff SAP Mobile Platform (SMP_ to HEC for Upgrade Processing | R3-Admin | complete | fquern@mit.edu
33 |  | 16:30 | SAP Mobile Platform shutdown | HEC | complete | fquern@mit.edu
34 |  | 4:30 PM (10 hours) | SAP Mobile Platform Upgrade (Refer to the SAP Mobile (SMP) Upgrade worksheet) | HEC | in process | fquern@mit.edu
35 |  | 4:30 PM (5 Minutes) | Suspend Drop-box processing. | R3 Admin (Qian Kang) | complete | sap-upgrade-core@mit.edu | see R3 Upgrade spreadsheet
36 |  | 16:45 | Disable COUPA Integration - In the following order disable: (1) requisitions integration, (2) POs, (3) invoices - Leave buytopay-req-auto-approval enabled | ops (George Gaudette) | complete | sap-upgrade-core@mit.edu
37 |  | 5 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). · Shutdown the web server · Shutdown the application server | ops (George Gaudette) | complete | sap-upgrade-core@mit.edu
38 |  | 17:00 | Disable/shut down/stop the following mulesoft applications: mit-compass - emailStatisticsDaily - pollSendDataToTerraDotta mit-ebuilder - ebuilder_poll_InvoicePayments - warningMessageEmail Pol mit-hr - createBadgeCache mit-student-appointments - awardPushPoll - out-of-balance-cron mit-surveys - work-order-rating-polling-job | ops (G. Gaudette) | complete | sap-upgrade-core@mit.edu
39 |  | 5 PM | Post status when system goes down on project wiki | PM ( Frank Quern) | complete | sap-upgrade-core@mit.edu
40 |  | 5 PM | System Downtime Message (3 Down) | R3-Admin PM (Frank Quern) | complete | sap-upgrade-core@mit.edu
41 |  | 5 PM | Bring down application servers. Production Environment becomes unavailable to users. | HEC/R3-Admin | complete | sap-upgrade-core@mit.edu
42 |  | 5 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) | Frank Quern | complete | sap-upgrade-core@mit.edu
43 |  | 5 – 7:30 PM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Joe Siniscalchi via email cc fquern@mit.edu, keyurpb@mit.edu that the reports are completed & downloaded. • VPF confirms the receipt of the Trial Balance Report. | R3-Admin (R. Parker) VPF (Joe Siniscalchi) | in process | sap-upgrade-core@mit.edu
44 |  | 5 – 7:30 PM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday) • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • Save WT info to internal SAP table | R3-Admin (R. Parker) (G. Petrowsky) | in process | sap-upgrade-core@mit.edu
Support Pack Application/HANA Upgrade and Processes: [pending]
45 | Friday 12/8/2017 | By 7:30 PM | MIT Handoff to HEC for PS1, ACP Upgrade Processing | R3-Admin |  | sap-upgrade-core@mit.edu
46 |  | 7:30 PM (12 hrs) | PS1 Enhancement Pack 8 support pack application (Refer to the ERP (PS1) Upgrade TAB) | HEC |  | sap-upgrade-core@mit.edu
47 |  | 7:30 PM (4 hrs) | GRC ACP System Upgrade (Refer to GRC (ACP) Upgrade TAB) | HEC |  | sap-upgrade-core@mit.edu
Post Upgrade Schedule and Processes: [pending]
48 | Saturday 12/9/2017 | 7:30 AM (10 hrs) | MIT Technical Post Upgrade Processing - Restore WT Table - Many more ... (Refer to MIT Post Processing Task List tab for details) | R3-Admin |  | sap-upgrade-core@mit.edu | GRC steps need to finish (last steps for this task)
49 |  | By noon | Execute MIT Web Deployments tasks (refer to MIT Web Deployments worksheet) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu | Friday evening/Saturday morning
50 |  | during the above 10 hour window | Validation reports executed (trial balance reports) • R3-ADMIN notifies Joe Siniscalchi via email, cc to Frank Quern as soon as the trial balance is available for review • R3-ADMIN unlock jsinisca id in PS1 9 (as needed) | R3-Admin (R. Parker) VPF Finance (Joe Siniscalchi) |  | sap-upgrade-core@mit.edu | after transports & generations
51 |  | 16:00 | IS&T Conference Call Check-in Core Team Check in at 4 pm on Saturday (use conference call webex line below) +1-617-324-0000 US Toll Number Access code: 311 224 867 | Project Manager (Frank Quern) |  | sap-upgrade-core@mit.edu
52 |  | 5:30 PM - 6:30 PM | MIT IS&T Post Upgrade Action Log - action log team members unlocked - action log execution unique for 2017: - refer to action log task list workbook | Action Log Team (R3, ABAP, SA) |  | sap-upgrade-core@mit.edu
53 | Sunday 12/10/2017 | By 7:30 AM | Post status message on cutover wiki page. Email to sap-validation-team@mit.edu that the validation is to start on schedule | PM (Frank Quern) |  | sap-upgrade-core@mit.edu
54 |  | 8:15 | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (start EDI; but do not send or push any files yet) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
55 |  | 8:30 | EDI Step 2 Update TLE Paramenters - Change version in Tle from 750 to (TBD) | Tech Services (E. Prudden) | N/A | sap-upgrade-core@mit.edu | No change for 2017
56 |  | 8:45 | EDI Step 3 Start EDI Jobs (start sending EDI files) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
57 |  | By 8:30 AM (5 Minutes) | Email to ist-sap@mit.edu • List of transports applied and any related issues. • List of jobs shifted in PS1 during cutover | R3-Admin (Ron Parker) |  | sap-upgrade-core@mit.edu
58 |  | 9:00 | Unlock IS&T Teams (ABAPs, BAs, SAs, DW, GRC ids) | R3-Admin (G. Petrowsky) |  | sap-upgrade-core@mit.edu
59 |  | 9:00 AM - 10:30 AM | IST SAP Team Validations | All R3, ABAP, BSA, DW ids |  | sap-upgrade-core@mit.edu
60 |  | by 10:30am | TB Validation reports validated • Joe notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Joe Siniscalchi) (Keyur Patel) |  | sap-upgrade-core@mit.edu
61 |  | by 10:30am | Post status message on cutover wiki page. Email to sap-validation-team@mit.edu that the validation is to start on schedule | PO (Frank Quern) |  | sap-upgrade-core@mit.edu
62 |  | 10:30 | Enable COUPA Integration in the following order: (1) requisitions integration (2) Pos (3) invoices | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
63 |  | 10:30 | Enable/start the following mulesoft applications: mit-compass - emailStatisticsDaily - pollSendDataToTerraDotta mit-ebuilder - ebuilder_poll_InvoicePayments mit-hr - createBadgeCache mit-student-appointments - awardPushPoll - out-of-balance-cron mit-surveys - work-order-rating-polling-job | ops (G. Gaudette) |  | fquern@mit.edu
64 |  | 10:30 | Unlock validators (testers) | R3-Admin (G. Petrowsky) |  | sap-upgrade-core@mit.edu
65 |  | 10:30 AM - 12:30 PM (2 hours) | MIT Business Validation PS1 Data Validations & Transaction processing listed in section of the Validation spreadsheet performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs IS&T BSAs |  | sap-upgrade-core@mit.edu
66 |  | By 12:30 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs IS&T BAs & SAs |  | sap-upgrade-core@mit.edu
67 |  | 13:00 | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, POs, Team Leads) +1-617-324-0000 US Toll Number Access code: | PM (Frank Quern) |  | sap-upgrade-core@mit.edu
Go Live
68 | Sunday 12/10/2017 | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu, warehouse@mit.edu) indicating decisions/results. | PM (Frank Quern) |  | sapbiz@mit.edu sap-upgrade-core@mit.edu ist-sap@mit.edu warehouse@mit.edu
69 |  | 1:30 PM – 2:30 PM | Unlock users (Facilities, SMART) Unlock all users (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update Atlas message. | R3-Admin (George Petrowsky) |  | sap-upgrade-core@mit.edu
70 |  | 2:30 PM Sunday (5 Minutes) | Enable Drop box | R3 Admin (Qian Kang) |  | sap-upgrade-core@mit.edu
71 |  | 14:30 | Reinstate weekend MITSIS Bio Feed | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
72 |  | 8PM – 12AM | Data Warehouse Job Validation • Eping (Lucia) Wei confirm job validation completion via email to sap-upgrade-core@mit.edu, warehouse-dev@mit.edu • Run extracts (10PM & 12AM) | R3-Admin |  | sap-upgrade-core@mit.edu
73 |  | By 6:30pm | Execute ProCard from Bank of America Feed | ABAP Team (Eping Lucia Wei) |  | sap-upgrade-core@mit.edu
74 | Monday morning 12/10/2017 | By 6 AM | Update the 3-down web page & SAPgui message. | R3-Admin (R. Parker) Project Manager (Frank Quern) |  | sap-upgrade-core@mit.edu
75 |  | By 6 AM | Remove SAP outage message on Coupa webpage. | VPF (Cecelia Talamantes) (Scott Ball) |  | sap-upgrade-core@mit.edu
76 |  | By 6 AM | Remove Atlas and EHS messages. | Frank Quern |  | sap-upgrade-core@mit.edu
77 |  | By 6 AM | Post Atlas Banner Message with link to Known SAP Issues kb article | Frank Quern |  | sap-upgrade-core@mit.edu | if needed
78 |  | By 6 AM | Remove GAP Banner message | Deepa Salman |  | sap-upgrade-core@mit.edu
79 |  | By 6 AM | Validate Atlas and EHS outage messages have been removed (verify in IE, Firefox, Chrome) | HRP BSA (Meaghan Murray) |  | sap-upgrade-core@mit.edu
80 |  | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | PM (Frank Quern) |  | sap-upgrade-core@mit.edu
81 |  | By 10 AM | AIMS – Send an email to tomasz@aimsparking.com requesting that the AIMS job that runs M-F at 6 PM and posts JVs for Visitor parking reservations be enabled. | Nivedita Dhiman |  | sap-upgrade-core@mit.edu
82 |  | By EOD | Review Qualtrics responses not captured during the outage. | Nivedita Dhiman |  | sap-upgrade-core@mit.edu
83 |  | By EOD | eBuider expense catch up | Nivedita Dhiman |  | sap-upgrade-core@mit.edu
84 |  | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. o email sap-upgrade-core@mit.edu when complete | HRP BSA (L. Kushkuley) |  | sap-upgrade-core@mit.edu
85 | 2017-12-31 | 17:30 | Activate gui version detection/rejection for older SAP gui versions | R3-Admin (Ron Parker) |  | n/a

## MIT Web Deployments
SAP web components for Dec 8-10, 2017 cutover
[Note: we will stage as much as possible (non SAP) in OC11 datacenter by Dec 8]
# | Task description | Request | Execute | When | Comment
Mulesoft deployments:
Java deployments for:
| Please update atlas config to: atlas-configuration-r71-1109171505 | 4417427 |  | 12/8/2017 after 5pm | Atlas Configuration for VPFForms and JVSuite
| Please setup and deploy vpfforms. a. The nexus war file is: vpfforms-0.0.1-20171115.015808-4.war b. The property file is in /root/vpfforms_properties/prod of admsys-dev-app-4 | 4413254 |  | by 12/8/2017 7:30pm | Late Salary Change Request web server change
| Please setup and deploy jvsuite a. The nexus war file is: jvsuite-2.0.1-20171106.150900-11.war b. The property file van be copied from test (/var/local/etc/jvsuite/ApplicationLocal.properties) but the value for r3default needs to be modified to PS1 | 4401012 |  | by 12/8/2017 7:30pm | SAP 2017 LOG PCard updates AKA jvsuite *
* On Saturday Larissa will use PS1 Firefighter role:
Use transaction SM30 to update one record (with the key JV_DISPL) in the table ZHR_SRV_LINK.
Production link = https://adminappsts.mit.edu/jvsuite/CreditCardReport.action?sapSystemId=PS1
NOTE: new ITS/WDA doman, use https://hecps1web01.mit.edu
| Server Name | Type
| atlas-ca-prod-app-1 | Atlas
| atlas-ca-prod-app-2 | Atlas
| atlas-ca-prod-app-3 | Atlas
| atlas-ca-prod-app-4 | Atlas
| atlas-oc11-4-prod-app-1 | Atlas
| atlas-oc11-4-prod-app-2 | Atlas
| atlas-oc11-4-prod-app-3 | Atlas
| atlas-oc11-4-prod-app-4 | Atlas
| atlas-ca-prod-db-1 | Database
| atlas-prod-db-1 | Database
| admsys-ca-prod-app-1 | Application
| admsys-ca-prod-app-2 | Application
| admsys-ca-prod-app-3 | Application
| admsys-ca-prod-app-4 | Application
| admsys-ca-prod-app-5 | Application
| admsys-ca-prod-app-6 | Application
| admsys-ca-prod-app-7 | Application
| admsys-ca-prod-app-8 | Application
| admsys-oc11-4-prod-app-1 | Application
| admsys-oc11-4-prod-app-2 | Application
| admsys-oc11-4-prod-app-3 | Application
| admsys-oc11-4-prod-app-4 | Application
| admsys-oc11-4-prod-app-5 | Application
| admsys-oc11-4-prod-app-6 | Application
| admsys-oc11-4-prod-app-7 | Application
| admsys-oc11-4-prod-app-8 | Application
| aprsys-ca-prod-app-1 | Application
| aprsys-ca-prod-app-2 | Application
| aprsys-oc11-4-prod-app-1 | Application
| aprsys-oc11-4-prod-app-2 | Application
| ehssys-ca-prod-app-1 | Application
| ehssys-ca-prod-app-2 | Application
| ehssys-oc11-4-prod-app-1 | Application
| ehssys-oc11-4-prod-app-2 | Application
| finsys-ca-prod-app-1 | Application
| finsys-ca-prod-app-2 | Application
| finsys-oc11-4-prod-app-1 | Application
| finsys-oc11-4-prod-app-2 | Application
| scorm-ca-prod-app-1 | Application
| scorm-ca-prod-app-2 | Application
| scorm-oc11-4-prod-app-1 | Application
| scorm-oc11-4-prod-app-2 | Application
| scorm-ca-prod-db-1 | Database
| scorm-ca-prod-db-2 | Database
| asapis-prod-app-1 | Application | Not replicated
| asapis-prod-app-2 | Application | Not replicated

## R3 Upgrade Tasks
Task ID |  | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
Thursday |  | 2017-11-30 | 17:00 | 2017-11-30 |  | 30 mins | Rich Katkowski | Pre-upgrade Transports | complete
Thursday
| PS1 | 2017-12-07 | by 5 PM | 2017-12-07 | by 5 PM | N/A | Ron Parker | Save Wage type table (after system is locked)
| PS1 | 2017-12-07 | by 5 PM | 2017-12-07 | by 5 PM | N/A | Ron Parker | Snapshoft of Profiles (8 profiles)
Friday
| PS1 | 2017-12-08 | by 3 PM | 2017-12-08 | by 3 PM | 30 mins | Qian Kang | Shift concur outbound execution from 5 to 3:20 Comment out the following on axplor 00 17 * * 1-5 su - sapdbmon -c "/export/home/sapdbmon/bin/rldb_tra_extract.pl /export/home/sapdbmon/script_config/tra_extract2prd.cfg" >>/export/home/sapdbmon/logs/log.travel_extracts_prd 2>&1 Run this, 20 15 * * 1-5 su - sapdbmon -c "/export/home/sapdbmon/bin/rldb_tra_extract.pl /export/home/sapdbmon/script_config/tra_extract2prd.cfg" >>/export/home/sapdbmon/logs/log.travel_extracts_prd 2>&1 |  | on main cutover task list
| SMP | 2017-12-08 | 15:30 | 2017-12-08 | 15:30 | N/A | Ron Parker | MIT Handoff SAP Mobile Platform (SMP_ to HEC for Upgrade Processing
| PS1 | 2017-12-08 | 5:00 PM EDT | 2017-12-08 | 17:00 | N/A | Qian Kang | Suspend dropbox Comment out pull script on sftp02 Comment out pull 1file scripts on sftp02 Suspend this job on axplor 00 22 * * * su - sapdbmon -c "/home/sapdbmon/bin/citi_download.pl /home/sapdbmon/script_config/citi_download.cfg" >>/home/sapdbmon/logs/log.citi_download_prd 2>&1 Suspend this job on axplor 0 07 * * * su - infrp -c "/usr/bridges/prod/infrp/get_warehouse_extracts" >>/usr/bridges/prod/infrp/log.get_warehouse_extracts 2>&1 |  | on main cutover task list
| PS1 |  | 17:00 |  | 17:00 | N/A | Ron Parker | Request SAP bring down application systems
| PS1 |  | 17:00 |  | 17:30 | 30 minutes | George Petrowsky | Lock Users
| PS1 |  | 5:00 PM EDT |  | 17:30 | 30 minutes | Ron Parker | Disabling Logon groups
| PS1 |  | 17:00 |  | 17:30 | 30 minutes | Ron Parker | Run TB Reports
| PS1 |  | 15:00 |  | 19:30 |  | George Petrowsky | Shift all non-DW jobs to start after 6am on Monday
| F5 | [5 empty] | ops | Adjust F5 hecps1web01.mit.edu port 553,55300 to point to port 55300 on PS1 application servers
| GRC - ACP | 2017-12-08 | 5:00 PM EDT | 2017-12-08 | 7:30 PM EDT | 2 hours | MIT (R3-Admin) | Update System Security Environment (Touchstone) | N/A
| GRC - ACP | 2017-12-08 | 5:00 PM EDT | 2017-12-08 | 7:30 PM EDT | 30 minutes | MIT (R3-Admin) | Validate SAML Touchstone connectivity | N/A
Saturday
|  |  | 7:30 PM EDT |  | 5:30 PM EDT | 10 hours | R3 | R3-Admin action log
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute SGEN Load Generations - Objects for all PS1 components - Regernerate already existing invalid loads - BSP Applications - Web Dynpros
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Restore Wage Types
| PS1 | 2017-12-09 | 7:30 PM EDT | 2017-12-09 | 12:30 PM EDT | 5 hours | Rich Katkowski | Load Tranport buffer and Transport
| GRC - ACP | 2017-12-09 |  |  |  |  | Ron Parker | Execute SGEN Load Generations - Objects for all ACP components - Regernerate already existing invalid loads - BSP Applications - Web Dynpros
| GRC - ACP | 2017-12-09 | 12:30 PM EDT | 2017-12-09 | 1:00 PM EDT | 0.5 hours | Rich Katkowski | Import GRC Transports
| GRC - ACP | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | a) Deploy MIMEs (program WDG_MAINTAIN_UR_MIMES) b) Execute restore of GUI Interface Changes, Activation Flag for Function Exits (program RSMODRES) c) Execute transaction SIAC_PUBLISH_ALL_INT (publish services) d) Execute transaction SWU3 (verify Workflow Customizing) e) Execute TCC Servicetools Update (program RTCCTOOL)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Generate features in client 0 for select transports
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Generate features in client 30 for select transports
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Deploy MIMEs (program WDG_MAINTAIN_UR_MIMES)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute FI-SL XPRA: Generation GLU1, GLU2, FI-SL Programs (program RGZZGLUX)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute update of FI-SL Programs (program RGBCFL00)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute generation of ABAP code for validations/substitutions/rules (program RGUGBR00)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute restore of GUI Interface Changes, Activation Flag for Function Exits (program RSMODRES)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute transaction SIAC_PUBLISH_ALL_INT (publish services)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute transaction SWU3 (verify Workflow Customizing)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Execute TCC Servicetools Update (program RTCCTOOL)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Activate UI Core Services (default_host/sap/public/bc/uics/whitelist per note 2389051)
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Enable port 55300 on PS1 application servers for certificate authentication
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Disable certificate verification for port 44300 on application servers ai06 and ai07
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Verify SAP Kernel post-update adjustment via Z_SENDMAIL test
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | N/A | Unified rendering | N/A
| PS1 | 2017-12-09 |  | 2017-12-09 |  | 1 hour | Ron Parker | Run TB Reports -- Batch environment adjustment -- Trial Balance Batch Executions -- Trial Balance Report Extracts and Email notifications
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | George Petrowsky | User validations
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | George Petrowsky | Roles feed file process
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | BSI Test Connection
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Check/Test Open Text Connectivity
| All | 2017-12-09 |  | 2017-12-09 |  |  | All | Test of infrastucture
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | Rich Katkowski | Validate Adobe form rendering - run fp_check_destination_service - run fp_pdf_test_00 - run fp_test_00 - run fp_test_003 - display W2 form - display W2 form instructions
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | R3 | user maintienance
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | R3 | trusted links validations
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | R3 | drop box
| ASAPI | 2017-12-09 |  | 2017-12-09 |  |  | Ron Parker | Restart ASAPI servers (production tier)
| Menix | 2017-12-09 |  | 2017-12-09 |  |  | Qian Kang | Restart CSAIL and Comp Analysis in Mendix
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | George Petrowsky | Shift back to weekend those jobs that normally occur on weekend
| GRC - ACP | 2017-12-09 | 14:00 | 2017-12-09 | 2017-12-09 | 30 minutes | Sarah Quigley | Turn on PS1 sync job
| GRC - ACP | 2017-12-09 | 14:00 | 2017-12-09 | 16:00 | 1.50 hours | Sarah Quigley | GRC Validations
| PS1 | 2017-12-09 |  | 2017-12-09 |  | 15 min | Rich Katkowski | Point DST to Production
| PS1 | 2017-12-09 |  | 2017-12-09 |  |  | George Petrowsky | Check that JCO MetaUser and Scorm users are unlocked in PS1: ZZJCOMETA000 (run any JCO app, e.g Disp PO) and ZZADMSCORM01 (open learning center course, e.g. event planning, chk table Z...)
Sunday | PS1 | 2017-12-10 |  | 2017-12-10 |  |  |  | Enable drop box |  | on main cutover task list

## SAP Tickets
System ID | Description |  | Status
PS1 | 598812 / 2017 HECSR_STD PS1MIT Update Software Version of Application (12/3/2017-12/9/2017) | Sent to SAP
-- ERP Support Package Updates
ACP - ACPMIT | 568868 / 2017 HECSR_STD ACPMIT Update database software version (12/1/2017) | Sent to SAP | complete
ACP - ACPMIT | 599690 / 2017 HECSR_EMS ACPMIT Upgrade Software Version of Application (12/6/2017-12/9/2017) | Sent to SAP
-- GRC Support Package Updates
SMP | 573607 / 2017 HECSR_STD SMPMIT Update database software version (12/8/2017) | Sent to SAP | complete
SMP | 603790 / 2017 HECSR_STD SMPMIT Perform other HEC Standard Service (12/8/2017-12/9/2017) | Sent to SAP
-- SAP Mobile Platform Runtime 3.0 and JVM 7.1 Support Package Updates
NOTE:
none at this time

## ERP (PS1) Upgrade 2017
PS1 System upgrade between 12/8 starting at 7:30 PM EDT and 12/9 7:30 AM EST | [5 empty] | Timezone: US Eastern
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
a | 11/29/2017 |  | 11/29/2017 |  |  | MIT (R3-Admin) | Create Ticket EHP8 for ERP 6.0 SPS 08 (Incident 598812 / 2017 / HECSR_STD PS1MIT Update Software Version of Application) | complete
b | 11/29/2017 |  | 11/29/2017 |  |  | MIT (R3-Admin) | To confirm in the ticket that preparation steps have been completed in OSS note ( some tasks includes Import OSS notes, backup tables related to HR, etc) | complete
Extraction, Configuration and Check Phases
1 | 2017-12-03 | 9:00 | 2017-12-06 | 11:59 | 3 days | HEC | Extraction, Configuration, Check phases from Software Update Manager Tool, we will wait to Tuesday 29th afternoon in order to start with Preprocessing phase ( system lock) | complete
2 | [6 empty] | During Extraction Phase, PS1 XML file is provided, it was created by HEC at the same week that SH2 XML was created | complete
3 | [6 empty] | During Extraction Phase Import SPAM version 66 750 is mandatory | complete
4 | [6 empty] | During configuration phase to configure to use the Standard mode ( Shadow Instance)/Define the parallel Process to be used in the Shadow Instance | complete
5 | [6 empty] | During Configuration Phase (PREP_INTEGRATION/ADJUSTPRP) to provide Transport request provided by MIT SF3K905023 will be indicated in the service request ticket. | pending
6 | [6 empty] | HEC To confirm/validate the target version of each ABAP component | pending
Preprocessing Phase
7 | 2017-12-07 | 11:59 | 2017-12-08 | 11:59 | N/A | MIT (R3-Admin) | To confirm with an update in the ticket that HEC can proceed with Preprocessing phase ( lock development environment for any change) - MIT will update in ticket | pending
8 | [5 empty] | HEC | Continue with preprocessing | pending
[6 empty] | HEC | Stop the PS1 Application Servers | pending
[6 empty] | MIT (R3-Admin) | Redirect ADS from DSP to DST | pending
9 | [5 empty] | HEC | End_steps_Preprocessing_phase ( requires about 2 hrs.) | pending
10 | [6 empty] | Isolate Central Instances ( stop AI1 to AI7) | pending
11 | [6 empty] | Suspend batch jobs | pending
12 | [6 empty] | Logoff all users from Central Instance | pending
13 | [6 empty] | Create full backup of intallation directory /usr/sap/PS1/ including SUM directory | pending
14 | [6 empty] | Create Full Backup of HANA database | pending
15 | [6 empty] | Change HANA log_mode from normal to overwrite | pending
16 | [6 empty] | Stop HANA replication to HA node and DR site (Request through Software Update Manager Tool) | pending
Execution and Post Processing Phase
17 | 2017-12-08 | 19:30 | 2017-12-09 | 7:30 | 12 hours | HEC | Execution Phase ( to run for about 7 hrs.) | pending
18 | [6 empty] | At the end of Execution Phase, SUM tool request to change HANA log_mode to normal again ( HANA database restart is required) | pending
19 | [6 empty] | after above step is completed, Execute a new HANA full backup ( 1 hr.) | pending
20 | [5 empty] | HEC | Post-Processing phase ( 1 hr.) | pending
22 | [6 empty] | Also during post-processing phase, manual task request to Start Suspended Jobs, we will not perform it, as agreed MIT will take care of this task later on | pending
23 | [6 empty] | HANA Replication will be re-enable during Post-processing phase | pending
24 | [5 empty] | HEC | Additonal Manual task after SUM process | pending
[7 empty] | copy RFC libs from previous SAP Kernel version | pending
25 | [6 empty] | CUST1 user creation and share credentials | pending
26 | [6 empty] | HEC system health checks(monitoring tools, integration tools, PS1 system health) | pending
System Handover
27 | 2017-12-09 | 7:30 | 2017-12-09 | 7:30 |  | HEC | Handover PS1 Upgraded System to MIT at 7:30 AM EDT | pending
28 | [5 empty] | MIT (R3-Admin) | Perform Post-Upgrade tasks in PS1 | pending
29 | [5 empty] | MIT (R3-Admin) | Start Suspended Jobs | pending
Special note: For Central Instance and Application intances in the DR site, no further action is needed due to the fact we have snap-mirror in place for the installation directory

## ERP (PS1) Upgrade 2016
PS1 System upgrade between 12/2 starting at 7:30 PM EDT and 12/3 7:30 AM EDT
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
a | 11/23/2016 | By EOD | 11/23/2016 | By EOD | N/A | MIT (R3-Admin) | Create Ticket for ehp8 Upgrade no later than 11/23 | complete
b | 11/23/2016 | 8:00 AM EDT | 11/25/2016 | 8:00 AM EDT |  | MIT (R3-Admin) | To confirm in the ticket that preparation steps have been completed in OSS note ( some tasks includes Import OSS notes, backup tables related to HR, etc) | complete
Extraction, Configuration and Check Phases
1 | 11/25/2016 | 12:00 PM EDT | 2016-11-28 | 5:00 PM EDT | 2 days | HEC | Extraction, Configuration, Check phases from Software Update Manager Tool, we will wait to Tuesday 29th afternoon in order to start with Preprocessing phase ( system lock) | complete
2 | [6 empty] | During Extraction Phase, PS1 XML file is provided, it was created by HEC at the same week that SH2 XML was created | complete
3 | [6 empty] | During Extraction Phase Import SPAM version 63 REV 740 is mandatory | complete
4 | [6 empty] | During configuration phase to configure to use the Standard mode ( Shadow Instance)/Define the parallel Process to be used in the Shadow Instance | complete
5 | [6 empty] | During Configuration Phase (PREP_INTEGRATION/ADJUSTPRP) to provide Transport request provided by MIT (example: SF3K904745 was used in SH2); will be indicated in the service request ticket. | complete
6 | [6 empty] | HEC To confirm/validate the target version of each ABAP component | complete
Preprocessing Phase
7 | 2016-11-29 | By 5:00 PM EDT | 2016-11-29 | By 5:00 PM EDT | N/A | MIT (R3-Admin) | To confirm with an update in the ticket that HEC can proceed with Preprocessing phase ( lock development environment for any change) - MIT will update in ticket | complete
8 | 2016-11-29 | 5:00 PM EDT | 2016-12-01 | 5:00 PM EDT | 2 days | HEC | Preprocessing phase to be executed from Nov 29th, to December 1st, 2016 | complete
| 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 5:00 PM EDT | N/A | HEC | Stop the PS1 Application Servers | complete
| 2016-12-02 | 5:00 PM EDT | 2016-12-02 | 5:00 PM EDT | N/A | MIT (R3-Admin) | Redirect ADS from DSP to DST | complete
9 | 2016-12-02 | 7:30 PM EDT | 2016-12-02 | 9:30 PM EDT | 2 hours | HEC | End_steps_Preprocessing_phase ( requires about 2 hrs.) - spread out between 12/2 and 12/3
10 | [6 empty] | Isolate Central Instances ( stop AI1 to AI7) | complete
11 | [6 empty] | Suspend batch jobs | complete
12 | [6 empty] | Logoff all users from Central Instance | complete
13 | [6 empty] | Create full backup of intallation directory /usr/sap/PS1/ including SUM directory | complete
14 | [6 empty] | Create Full Backup of HANA database | complete
15 | [6 empty] | Change HANA log_mode from normal to overwrite | complete
16 | [6 empty] | Stop HANA replication to HA node and DR site (Request through Software Update Manager Tool) | complete
Execution and Post Processing Phase
17 | 2016-12-02 | 9:30 PM EDT | 2016-12-03 | 4:30 AM EDT | 7 hours | HEC | Execution Phase ( to run for about 7 hrs.)
18 | [6 empty] | At the end of Execution Phase, SUM tool request to change HANA log_mode to normal again ( HANA database restart is required) | complete
19 | [6 empty] | after above step is completed, Execute a new HANA full backup ( 1 hr.) | complete
20 | 2016-12-03 | 4:30 AM EDT | 2016-12-03 | 5:30 AM EDT | 1 hour | HEC | Post-Processing phase ( 1 hr.) | complete
22 | [6 empty] | Also during post-processing phase, manual task request to Start Suspended Jobs, we will not perform it, as agreed MIT will take care of this task later on | complete
23 | [6 empty] | HANA Replication will be re-enable during Post-processing phase | complete
24 | 2016-12-03 | 5:30 AM EDT | 2016-12-03 | 7:30 AM EDT | 2 hours | HEC | Additonal Manual task after SUM process
[7 empty] | Update SAP Kernel from 745 SP200 to SAP Kernel 745 311/Update SAPCrypto 8.5.5/ | complete
25 | [6 empty] | Update SAPcrypto related parameters to overcome issue reported after SAPCrypto update (client-ciphersuite) - MIT will note in ticket | complete
26 | [6 empty] | Restart All Application servers | complete
System Handover
27 | 2016-12-03 | 7:30 AM EDT | 2016-12-03 | 7:30 AM EDT | N/A | HEC | Handover PS1 Upgraded System to MIT at 7:30 AM EDT (actual 8:30 AM)
28 | 2016-12-03 | 7:30 AM EDT | 2016-12-03 | 5:30 PM EDT | 10 hours | MIT (R3-Admin) | Perform Post-Upgrade tasks in PS1
29 | 2016-12-03 | TBD | 2016-12-03 | TBD | ? | MIT (R3-Admin) | Start Suspended Jobs
Special note: For Central Instance and Application intances in the DR site, no further action is needed due to the fact we have snap-mirror in place for the installation directory

## GRC (ACP) Upgrade
ACP System upgrade between 12/6 starting at 11:59 AM and 12/9 7:30 AM | [5 empty] | Timezone: US Eastern
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
1 | 11/29/17 | By EOD | 11/29/17 | By EOD | N/A | MIT | Create ticket for ACP Upgrade downtime window 12/6 starting at 11:59 AM and 12/9 7:30 AM TICKET:Incident 599690 / 2017 / [HEC-EMS]HECSR_EMS ACPMIT Upgrade Software Version | completed
2 | 11/29/17 |  | 11/29/17 |  |  | MIT (R3-Admin) | Update System Security Environment (Touchstone) | pending
3 | 11/29/17 |  | 11/29/17 |  |  | MIT (R3-Admin) | Validate SAML Touchstone connectivity | pending
| 2017-12-08 | 19:30 | 2017-09-12 | 7:30 | 12 hours | HEC | ACP Upgrade (12 Hour Window) | pending
4 | 2017-12-08 | 19:30 | 2017-08-12 | 21:30 | 2 hours | HEC | Execution phase preparations | pending
5 | 2017-12-08 | 21:30 | 2017-09-12 | 5:30 | 8 hours | HEC | Execution & post processing phases | pending
6 | 2017-12-09 | 5:30 | 2017-09-12 | 7:30 | 2 hours | HEC | HEC system health checks(monitoring tools, integration tools, ACP system health) | pending

## OpenText (OTP) Upgrade
OTP System Upgrade
Task ID | Date | Time | Duration | Responsible | Task description | Status | comments
1 | 2016-11-23 | By EOD | N/A | MIT (Ron Parker) | Create the ticket with above information into XX-HST-OPR component at least 1 week in advance of the downtime window 12/02 at 7:30 PM EDT | complete
2 | 2016-12-01 | 4:00 PM EDT | 3 hours | DR Site Team | HANA database to be upgraded in DR Site 1 day in advance, on December 1st at 4PM EDT |  | monitor outage - ignore alerts between 4-7pm
3 | 2016-12-02 | 5:15 PM EDT | 1 hour | HEC | HANA database backup | complete
3a | 2016-12-02 | 6:15 PM EDT | 1 hour | HEC | SUSE Linux patching SCN-2016-1398 [Linux-High] for OTP | complete
4 | 2016-12-02 | 8:30 PM EDT | 3 hours | HEC | HANA database upgrade from REV 97 to REV 122.03 ( SP12) | complete
5 | 2016-12-02 | 8:30 PM EDT | 30 minutes | MIT (George Gaudette) | Upgrade OpenText application HANA Client (this is an IaaS server hosted by HEC managed by MIT) upgrade both the primary site and the DR site | complete
6 | 2016-12-02 | 11:30 PM EDT | 15 minutes | MIT (George Gaudette) | Verify Connectivity to DB | complete
7 | 2016-12-03 | 8:00 EDT AM + | 15 minutes | MIT (R3-Admin) | Verify Connectivity through SAP ERP - including SSL (post transports)

## SAP Mobile (SMP) Upgrade
Task ID | Start Date | Start Time | End Date | End Time | Duration | Responsible | Description | Status
1 | 2017-12-08 | 4:00 PM EDT | 2017-12-08 | 9:00 PM EDT | TBD | HEC | 573607 / 2017 HECSR_STD SMPMIT Update database software version (12/8/2017)
[7 empty] | SAP Mobile Platform Database Upgrade from SAP ASE 16 SP02 PL04 HF15 to SAP ASE 16 SP02 PL06 HF1 + EBF 27583 | in process
2 | [6 empty] | 603790 / 2017 HECSR_STD SMPMIT Perform other HEC Standard Service (12/8/2017-12/9/2017)
| 2017-12-08 | 9:00 PM EDT | 2017-12-09 | 7:30 AM EDT | 7 hours | HEC | Upgrade SAP Mobile Platform Runtime 3.0 from SP11 PL03 to SP13 PL03 | pending
| 2017-12-09 | 4:00 AM EDT | 2017-12-09 | 6:00 AM EDT | 2 hours | HEC | Upgrade JVM 7.1 to SP52 | pending
| 2017-12-09 | 6:00 AM EDT | 2017-12-09 | 7:00 AM EDT | 1 hour | HEC | HEC system health checks(monitoring tools, integration tools, SMP system health) | pending

## SAP Mobile Cutover Steps
Step | Date | Description | Point of Contact
1 | FRI (or earlier) | Save all Facilities and Housing work orders | Bob Leonard
2 | FRI (Earlier) | Identify personnel on call (e.g. Evora IT, LSI) | Lee Collier
3 | FRI (Earlier) | upgrade to iOS 11 | Mike Sherman
4 | FRI (or earlier) | Communicate to the mobile community what is happening. Include documentation on reset steps by Lee C | Lisa St. Croix
5 | Friday | Verify no weekend work for current iPad users, Mobile users down at 3:30 PM official, GUI users down at 5:00 pm. Coordinate with the Operations Center. | Lisa St. Croix
6 | SAT (during shutdown) | Use CASPER to push new Agentry files to mobile users (Agentry reset not required) | Mike Sherman
7 | SAT | Validate that SMP mobile server is up | R3 admin
8 | When r3 admin done with SAP Support Packs Upgrade | Restart the SMP Cluster nodes after the SAP Support Packs upgrade is complete - notify cosmos2030@mit.edu that restart is successful | R3 admin
9 | SUN | Mobile validations in production by business Validate steps needed on iPad (re-enter iTunes password?, reboot iPad?) | Bob Leonard, Mike Sherman
10 | SUN | Notify community successful (or need for backup plan) | Bob Leonard
11 | MON | Backup plan for mobile if cutover fails - Shop Papers | Lisa St. Croix
12 | MON | 6:45 am @ E19 | Lee Collier Bob Leonard
13 | MON | 6:45 am @ 32 (CSG) | Bob Ketchum, Jack Smith
14 | MON | 6:45 am @ WW15 | Nivedita Dhiman

## BSI Upgrade Tasks
Task ID | Date | Time | Duration | Responsible | Task description | Status | comments
Upgrade completed before cutover weekend

## Escalation Path
Escalation Path
If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Garry Zacheiss will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday December 4th.
Functional Malfunction(s)
Joe Siniscalchi | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike MacDonald | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Laurie Veal | Business Process Owner (EH&S) / Weekend Coordinator
John Larkin | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Frank Quern | Project Manager
Mark Silis | Associate Vice President, IS&T
Garry Zacheiss | Director, IS&T
Ron Parker | Manager, R3 Admin
Stephen Koczur | SAP HEC
Michel Cervantes | SAP Basis
Project Steering Committee
Escalation Support Team
Adina Ion | BSA FLE Support
Bob Casey | FLE PO
Frank Quern | HRP PO
Frank Quern | Project Manager
George Petrowsky | R3 Authorizations
George Petrowsky | Scrum Master
Jim Fragala | Facilities PO
Kevin Lyons | Atlas PO
Lisa Robinson | Scum Master
Gregg McGrath | Scrum Master
Ron Parker | Basis PO
Faith Hill | Data Warehouse Team
Brandin Tumeinski | Data Warehouse Team

## Validation
Production Validation
Production Validation will occur in NE49, W92, N52 and remotely. Validation is scheduled to start at 10:30 AM, however, please check the your email or the cutover page for the status of the cutover before coming into the office or starting to test remotely. The message will be updated by 9:30 AM if there are potential delays and by 10:30 AM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 8th. Frank will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/Joe Siniscalchi | Trial Balance Report validation. Ron Parker will email Joe Siniscalchi, Bob Casey, Keyur Patel and Frank Quern when the reports have finished processing. Joe will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following:Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/Atlas ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu