## Slide 1
November 27, 2018
2018 Year End Support Pack Project
Steering Committee Update
(cutover)

## Slide 2: Agenda
High Level Time Line (& where are we now?)
Testing
Issues
Cutover Plan
Next Steps

## Slide 3: High Level Timeline

## Slide 4: Where are we now? Project Landscape

## Slide 5: Testing Status
SH2: System Integration/User Acceptance Testing:
    Collaborative Business and IS&T integration and regression testing of Support Packs
Testing Results:

## Slide 6: Issues
Is it worth it?
Well, yes …
  We can jump to RT for details: https://help.mit.edu/
Phases Issues were identified in … |  |  |  | 
(as of 11/28/17) |  |  |  | 
Issue type | Unit | SIT |  | Open
Required an SAP fix | 6 | 2 |  | 
Required an MIT fix | 5 | 6 |  | 
Infrastructure Related | 3 | 1 |  | 
User/Data Error |  | 8 |  | 
Duplicate |  |  |  | 
Production Issue - to be addressed after SP | 1 | 3 |  | 
Totals | 15 | 20 | 35 | 2

## Slide 7: Issues (cont.)
How does it compare to prior years?
 | 2011 | 2012 | 2013 | 2014 | 2015* | 2016 | 2017 | 2018
Issues | 41 | 54 | 86 | 58 | 135 | 73 | 54 | 35
SAP fix required | 8 | 9 | 23 | 22 | 16 | 9 | 11 | 8
MIT fix required | 17 | 17 | 19 | 21 | 25 | 33 | 10 | 11
Total fixes required | 25 | 26 | 42 | 43 | 41 * HEC | 42 | 21 | 19

## Slide 8: Next Steps
11/29/2018 SAPbiz
12/05/2018 Community notification
12/07/2018 (5:00pm) - 12/10/2018 Go-live weekend!
Meaning … we’ll have to execute a cutover plan!!

## Slide 9: Cutover
Preparation work
System Isolation
Support Pack Application
Post Upgrade Processes (conversions, validations)
Go-live
  Let’s jump to the project wiki’s Cutover Plan page and take a look at the plan …

## Slide 10: Questions?
Please contact:
Contact | Email | Phone extension
Bob Casey | rcasey@mit.edu | x3-1844
Jim Fragala | jfragala@mit.edu | x4-6250
Lisa Robinson | lmrobin@mit.edu | x8-0492
Ron Parker | rep@mit.edu | x3-1339
Frank Quern | fquern@mit.edu | x2-4512

## Slide 11: Support Packs are Coming! Support Packs are Coming!
We’re ready (are you?)