## Communication & Contacts
Communication
Cutover status messages will be sent to the project team and business validators and posted on the project cutover wiki page beginning at noon on Friday 12/7 through noon on Monday 12/10. The Project Manager or designee will update/send these messages as needed. A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 1:00pm on Sunday.
Conference Call Line: Webex
Call-in toll number (US): 617-324-0000 Friday Access code (24 hrs): 643 397 639 Saturday Access code (24 hrs) : 641 869 587 Sunday Access code (24 hrs): 642 538 749
Project wiki link: | https://wikis.mit.edu/confluence/display/sapscripts/2018+Year+End+SAP+Support+Pack+Project
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
sapgui-updates@mit.edu | Used to notify specific users who need to upgrade their gui version
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
SAP Conntact Information
Name | Phone | Email
Steve Koczur | 610 745-6281 | stephen.koczur@sap.com
Phil Ferenschak | 610 662-0526 | phillip.ferenschak@sap.com
Gia Dinh |  | gia.dinh@sap.com
Contact Information
Area | Name | Location | Contact Telephone # | Email
A/P | John Larkin | NE49 | Refer to online directory | jlarkin@mit.edu
Parking Office for Commuting Benefits applications | Robynn Cruz |  | Refer to online directory | Refer to online directory
Charitable Giving Office | Traci Swartz |  | Refer to online directory | Refer to online directory
VPF | Joe Siniscalchi |  | Refer to online directory | Refer to online directory
VPF | Steve Hoover |  | Refer to online directory | Refer to online directory
VPF | Ross Monaghan |  | Contact PM | rmonagha@mit.edu
VPF – Travel | Kathy McGrath | Off Campus | Contact PM | Refer to online directory
Dept. of Facilities | Bob Leonard | Off Campus | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher | On Campus (10-063) | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix |  | Contact PM | lstcroix@mit.edu
EHS | Laurie Veal |  | Contact PM | veal@mit.edu
EHS | Jessica Van |  | Refer to online directory | jvan@mit.edu
EHS | Suzanne Adams | Off Campus | Contact PM | sma@mit.edu
HR Coordinator | Mike MacDonald | Off Campus | Refer to online directory | mikemacd@mit.edu
HR/Benefits | Diane Sullivan | Off Campus | Contact PM | djohnsto@mit.edu
EL | Melissa Kavlakli | Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White | Off Campus | Contact PM | jwc@mit.edu
EL | Mae Jones | Off Campus | Contact PM | maejones@mit.edu
Procurement | Cindy Vye | NE49 | Contact PM | CI24314
Procurement | Scott Ball | NE49 | Refer to online directory | Refer to online directory
VPF – HR/Payroll | Leslie Wright | NE49 | Refer to online directory | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Off Campus | Refer to online directory | darrenjs@mit.edu
VPF – HR/Payroll | Chris Durham | NE49 | Refer to online directory | cfdurham
IS&T - R3-Admin | George Petrowsky |  | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker | W92 | Refer to online directory | rep@mit.edu
IS&T - Project Manager | Frank Quern | W92 | Refer to online directory | fquern@mit.edu
IS&T - FLE Product Owner | Bob Casey | W92 | Refer to online directory | rcasey@mit.edu
IS&T - FI Team | Sandeep Nadendla | W92 | Refer to online directory | nadendla@mit.edu
IS&T – EHS/Parking - Scrum master | Lee Collier | W92 | Refer to online directory | lcollier@mit.edu
IS&T – Facilities PO | Jim Fragala | W92 | Refer to online directory | jfragala@mit.edu
IS&T – Logistics | Ken Levie | W92 | Refer to online directory | levie@mit.edu
IS&T – Log/FIN/EHS Team Coordinator | Adina Ion | W92 | Refer to online directory | aion@mit.edu
IS&T – Ops | George Gaudette | W92 | Refer to online directory | gaudette@mit.edu
IS&T – Ops | Paul Cronin | Off Campus | Refer to online directory | croninp@mit.edu
IS&T - Data warehouse | Warehouse support team | W92 | Refer to online directory | warehouse-dev@mit.edu
IS&T – HRP Scrum Master | Gregg McGrath | W92 | Refer to online directory | gmcgrath@mit.edu
IS&T – OIS | Garry Zacheiss | W92 | 617-216-1541 | zacheiss@mit.edu
IS&T - OIS | Server Operations | W92 | 617-775-3302 | Team Line
Monday Morning Coverage
Area | Name | Location | Time | Email
Help Desk | Team | W91 | 6:00am
FAC | Lee Collier | W92 | 7:30am | lcollier@mit.edu
FAC | Jim Fragala | W92 | 7:30am | ja17661@mit.edu
HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu
R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu
ABAP | Elda Prudden | Off Campus | 7:30am | eprudden@mit.edu
ABAP | Mark Prudden | Off Campus | 7:30am | mprudden@mit.edu
FLE | IS&T SA Team | W92 | 8:00am + | administrative-systems@mit.edu
HRP | IS&T SA Team | W92 | 8:00am + | hrpay-sppt@mit.edu

## Cutover Task List
# | Date | Time (EST) | Action / Task | Person(s) Responsible | Status | Upon completion send email to: | Comments
Pre-Update Schedule and Processes: [complete]
1 | By Wednesday 11/21/2018 | By EOD | Schedule review meetings: - R3 Cutover Planning - IS&T Transport Review - IS&T Cutover Review - IS&T Action Log Review - SAPbiz Cutover Review - Steering Committee Review - CRB | Lori Singer |  | n/a | 11/29 12/3 11/28 11/27 11/29 11/27 11/30
2 | Week of 11/11/2019 | TBD | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team
3 | Tuesday 11/27/2018 | 13:00 | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee |  | n/a
4 |  | By EOD | Email Steering Committee Go/No-go decision to Team | Lori Singer |  | n/a
5 | Thursday 11/1/2019 | 14:00 | IS&T cutover weekend planning/review meeting. | IS&T-SAP |  | n/a
6 | Thursday 11/29/2018 | 13:00 | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | POs (Bob Casey, Frank Quern, Andrew Barnaby, Lori Singer) |  | n/a
7 |  | By EOD | Draft Cut-over Communication Plan/Submit to IS&T Communication Team for review. | Lori Singer |  | n/a
8 | Monday 11/18/2019 | 13:00 | Transport Review Meeting Final review all issues in RT project queue, transport list, and web components. | IS&T-SAP |  | n/a
9 | Tuesday 12/4/2018 | 16:00 | Email ops-help with list of web application deployment requests for Sunday morning. (refer to MIT Web Deplyment tab for details) | PM ( Lori Singer) |  | lsinger@mit.edu
10 |  | By EOD | Submit Atlas Banner Message Request to Atlas Team for 12/7 | Lori Singer |  | n/a
11 |  | By EOD | Submit Coupa Outage Message Request to Procurement for 12/7 | Lori Singer |  | n/a
12 |  | By EOD | Submit Outage/Injury Message to EH&S for Review | Lori Singer |  | n/a
13 |  | By EOD | Submit Outage Banner Message Request to GAP support | Lori Singer |  | n/a
14 |  | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Lori Singer |  | lsinger@mit.edu
15 | Monday 11/18/2019 | 2:00 PM EST | Start Support Pack Preprocessing (uptime) phase | HEC/R3-Admin |  | lsinger@mit.edu
16 |  | 5:00 PM EST | PS1 System transport lock (transports not allowed into production) | HEC/R3-Admin |  | lsinger@mit.edu
17 |  | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | Frank Quern |  | lsinger@mit.edu | Banner id C1
18 |  | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker) |  | lsinger@mit.edu
19 |  | By 5:00 PM | Post message on Coupa web site about upcoming SAP outage. | VPF (Cecilia Talamantes) (Scott Ball) |  | n/a
20 |  | 18:00 | Final Copy of the Production Update Schedule (cutover plan) published and emailed. | Lori Singer |  | lsinger@mit.edu
21 |  | 9:00 PM EST | Start Support Pack Preprocessing (uptime) phase for GRC ACP System | HEC/R3-Admin |  | lsinger@mit.edu
22 | Thursday 12/6/2018 | By 4 PM | Schedule Pre & Post Trial Balance and ZJVP reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be in the future). Notify R3-Admin (R. Parker) and PM (Frank Quern) when jobs have been scheduled. | VPF Finance (Joe Siniscalchi) FIN BSA (Sandeep Nadendla) |  | lsinger@mit.edu
23 |  | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. For 2018: Program: ZHR_NEWHIRE_NOTIFICATION Varinants: SP2018 – 12/8 | Admin Systems (L. Kushkuley via Fire Fighter) |  | n/a | This program runs daily at 8am under Benefits batch id (ZZHRBENBTC01). It will run on Friday, December 7, and will run again on Sunday, December 9 (afternoon, when the jobs are released). So we need to re-run it only for Saturday, December 8.
24 |  | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker) |  | n/a
25 |  | By EOD | Set up job for GAP posting program ZGAPOST to run Monday after go-live. See instructions in doc ‘Set up GAP posting catchup job’, located in Spartans’ (HR-Payroll) Support Packs Test Plans dropbox folder. | Mary Donovan |  | lsinger@mit.edu
26 |  | 5:00 PM EST | MIT Handoff GRC ACP System for Upgrade | R3-Admin |  | sap-upgrade-core@mit.edu
27 |  | 5:00 PM EST | GRC ACP System Upgrade shutdown | HEC |  | sap-upgrade-core@mit.edu
28 |  | 5:00 PM EST (48 hrs) | GRC ACP System Upgrade (Refer to GRC (ACP) Upgrade spreadsheet) | HEC |  | sap-upgrade-core@mit.edu
29 | Friday 12/7/2018 | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM Monday). | ABAP Team (Eping Lucia Wei) |  | lsinger@mit.edu
30 |  | By noon | AIMS – Set AIMS job that runs M-F at 6 PM and posts JVs for Visitor parking reservations to be disabled on Friday, Dec 7th. | Nivedita Dhiman Dudley Kirkpatrick |  | lsinger@mit.edu
31 |  | By 2 PM | Download Facilities work order lists as back up for Monday Morning | Facilities (Bob Leonard) |  | lsinger@mit.edu
32 |  | By 2 PM | Download Housing work order lists as back up for Monday Morning | Facilities (Mike Sherman/Bob Leonard/Lisa St. Croix) |  | lsinger@mit.edu
33 |  | By 3:20 PM | Shift Concur outbound execution from 5:00 pm to 3:20pm | R3-Admin |  | lsinger@mit.edu | see R3 Upgrade Tasks spreadsheet
33a |  | By 3:20 PM | Shift start time of Friday Equifax jobs to execute at 3:30 PM rather than 6:00 PM | Gregg McGrath Laurie Farinella |  | lsinger@mit.edu
33b |  | By 3:30 PM | Reschedule Coupa payment integrations to run upon completion of A/P’s final payment job | Dudley Kirkpatrick |  | lsinger@mit.edu
34 |  | By 3:30 PM | Suspend weekend MITSIS cron job for the BIO feed: On batchadmin-east-prod-app-1 under the userid as_cron comment out the /sis/mitsis/applications/scripts/GEN/triggerBatch.sh /sis/cron biofeedsJob job. | ops (G. Gaudette) |  | lsinger@mit.edu
35 |  | By 4:00 PM | Workflow and JV Validation Reports · Workflow inbox report (Ross Monaghan/Steve Hoover) · JV Parked Documents Report (Ross Monaghan/Steve Hoover) · RFPs (John Larkin) | VPF (Ross Monaghan) (Steve Hoover) (John Larkin) |  | lsinger@mit.edu | covered w/ 35a
35a |  | 4:45 PM EST | Run SWI5 for Steve Hoover and save results (dropbox) | Sandeep Nadendla |  | lsinger@mit.edu
System Isolation: [complete]
36 | Friday 11/22/2019 | 5:00 PM EST | MIT Handoff SAP Mobile Platform (SMP) to HEC for Upgrade Processing | R3-Admin |  | lsinger@mit.edu | thru SAP ticket
37 |  | 5:30 PM EST | SAP Mobile Platform shutdown | HEC |  | lsinger@mit.edu
38 |  | 5:30 PM EST (24 hours) | SAP Mobile Platform Upgrade (Refer to the SAP Mobile (SMP) Upgrade worksheet) | HEC |  | lsinger@mit.edu
39 |  | 4:30 PM (5 Minutes) | Suspend Drop-box processing. | R3 Admin (Qian Kang) |  | sap-upgrade-core@mit.edu | see R3 Upgrade spreadsheet
40 |  | 16:45 | Disable COUPA Integration - In the following order disable: (1) requisitions integration, (2) POs, (3) invoices - Leave buytopay-req-auto-approval enabled | ops (George Gaudette) |  | sap-upgrade-core@mit.edu | verify buytopay-req-auto-approval
41 |  | 5 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). · Disable cron jobs owned by user edi on EDI server · Shutdown the web server · Shutdown the application server | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
42 |  | 17:00 | Disable/shut down/stop the following mulesoft applications: mit-compass - emailStatisticsDaily - pollSendDataToTerraDotta mit-ebuilder - ebuilder_poll_InvoicePayments - warningMessageEmail Pol mit-hr - createBadgeCache mit-student-appointments - awardPushPoll - out-of-balance-cron mit-surveys - work-order-rating-polling-job mit-parking-integrations-v1 - mit-parking-integrations-v1 | ops (G. Gaudette) |  | sap-upgrade-core@mit.edu | mit-compass - schedules disabled, app stopped mit-ebuilder - schedules disabled, app stopped mit-hr - schedules disabled, app stopped mit-student-appointments - schedules disabled, app stopped mit-surveys - schedules disabled, app stopped mit-parking-integrations-v1 - schedules stopped, app is left on
42a |  | 5:00 PM EST | Redirect parking.mit.edu to atlas.mit.edu at the F5 | ops (G. Gaudette) |  | lsinger@mit.edu
43 |  | 5 PM | Post status when system goes down on project wiki | PM ( Lori Singer) |  | sap-upgrade-core@mit.edu
44 |  | 5 PM | Post System Downtime Message (3 Down) | R3-Admin PM (Frank Quern) |  | sap-upgrade-core@mit.edu
45 |  | 5:00 PM EST | Bring down application servers. Production Environment becomes unavailable to users. | HEC/R3-Admin |  | sap-upgrade-core@mit.edu
46 |  | 5 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) | Frank Quern |  | sap-upgrade-core@mit.edu | Banner ID C2 (supervisors injury rpt)
47 |  | 5 – 7:00 PM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Joe Siniscalchi via email cc fquern@mit.edu, rcasey@mit.edu, nadendla@mit.edu that the reports are completed & downloaded. • VPF confirms the receipt of the Trial Balance Report. | R3-Admin (R. Parker) VPF (Joe Siniscalchi) |  | sap-upgrade-core@mit.edu
48 |  | 5 – 7:00 PM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday) • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • Save WT info to internal SAP table | R3-Admin (R. Parker) (G. Petrowsky) |  | sap-upgrade-core@mit.edu
Support Pack Application/HANA Upgrade and Processes: [complete]
49 | Friday 11/22/2019 | By 7:00 PM | MIT Handoff to HEC for PS1, ACP Upgrade Processing | R3-Admin |  | sap-upgrade-core@mit.edu
50 |  | 7:00 PM (12 hrs) | PS1 Enhancement Pack 8 support pack application (Refer to the ERP (PS1) Upgrade 2018 spreadsheet) | HEC |  | sap-upgrade-core@mit.edu
Post Upgrade Schedule and Processes: [in process]
51 | Saturday 11/23/2019 | 9:30 AM (12 hrs) | MIT Technical Post Upgrade Processing - Restore WT Table - Many more ... (Refer to MIT Post Processing Task List tab for details) | R3-Admin |  | sap-upgrade-core@mit.edu | GRC steps need to finish (last steps for this task)
52 |  | By noon | Execute MIT Web Deployments tasks (refer to MIT Web Deployments worksheet) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu | Saturday morning/noon (1:15 pm)
53 |  | during the above 12 hour window | Validation reports executed (trial balance reports) • R3-ADMIN notifies Joe Siniscalchi via email, cc to Frank Quern, Bob Casey, Sandeep Nadendla as soon as the trial balance is available for review • R3-ADMIN sends report to Joe Siniscalchi (jsinisca); unlock his id in PS1 if needed | R3-Admin (R. Parker) VPF Finance (Joe Siniscalchi) |  | sap-upgrade-core@mit.edu | after transports & generations
54 |  | 16:00 | IS&T Conference Call Check-in Core Team Check in at 4 pm on Saturday (use conference call webex line below) +1-617-324-0000 US Toll Number Access code: 641 869 587 | Project Manager (Lori Singer) |  | sap-upgrade-core@mit.edu
55 |  | 5:30 PM - 6:30 PM | MIT IS&T Post Upgrade Action Log - action log team members unlocked - action log execution unique for 2018: - refer to action log task list workbook | Action Log Team (R3, ABAP, SA) |  | sap-upgrade-core@mit.edu
55a |  | 21:00 | R3: Unlock operational IDs ZZMSMMCOUPA1 and ZZJCOMETA000 JDK: Execute Coupa B2P Cost Object Integration | R3 Dudley Kirkpatrick |  | sap-upgrade-core@mit.edu
56 | Sunday 12/9/2018 | By 7:30 AM | Post status message on cutover wiki page. Email to sap-validation-team@mit.edu that the validations will start on schedule | PM (Lori Singer) |  | sap-upgrade-core@mit.edu
57 |  | 8:15 | EDI Step 1 Once given the go ahead from PM: Turn on the EDI “gourmet-1” server (Re-enable cron jobs for user edi on EDI server) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
58 |  | 8:30 | EDI Step 2 Update TLE Paramenters - Change version in Tle from 750 to (TBD) | Tech Services (E. Prudden) |  | sap-upgrade-core@mit.edu | No change for 2018
59 |  | 8:45 | EDI Step 3 Start EDI Jobs (start sending EDI files) | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
59a |  | 8:45 | Restart all Atlas applications | Ops (George Gaudette) |  | sap-upgrade-core@mit.edu
60 |  | By 8:30 AM (5 Minutes) | Email to ist-sap@mit.edu • List of transports applied and any related issues. • List of jobs shifted in PS1 during cutover | R3-Admin (Rich Katkowski) (George Petrowsky) |  | sap-upgrade-core@mit.edu
61 |  | 9:00 | Unlock IS&T Teams (ABAPs, BAs, SAs, DW, GRC ids) | R3-Admin (G. Petrowsky) |  | sap-upgrade-core@mit.edu
61a |  | 9:00 | Re-run SWI5 for Steve Hoover and compare results with data from the 12/7 execution | Sandeep Nadendla |  | lsinger@mit.edu
62 |  | 9:00 AM - 10:30 AM | IST SAP Team Validations | All R3, ABAP, BSA, DW ids |  | sap-upgrade-core@mit.edu
63 |  | by 10:30am | TB Validation reports validated • Joe notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Joe Siniscalchi) (Bob Casey) |  | sap-upgrade-core@mit.edu
64 |  | by 10:30am | Post status message on cutover wiki page. Email to sap-validation-team@mit.edu that the validation is to start on schedule | PO (Frank Quern) |  | sap-upgrade-core@mit.edu
65 |  | 10:30 | Enable COUPA Integration in the following order: (1) requisitions integration (2) Pos (3) invoices | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
66 |  | 10:30 | Enable/start the following mulesoft applications: mit-compass - emailStatisticsDaily - pollSendDataToTerraDotta mit-ebuilder - ebuilder_poll_InvoicePayments mit-hr - createBadgeCache mit-student-appointments - awardPushPoll - out-of-balance-cron mit-surveys - work-order-rating-polling-job mit-parking-integrations-v1 - mit-parking-integrations-v1 | ops (G. Gaudette) |  | lsinger@mit.edu
66a |  | 10:30 | Redirect parking.mit.edu/* back to original (there is separate redirects for /manage and /admin on this) | ops (G. Gaudette) |  | lsinger@mit.edu
67 |  | 10:30 | Unlock validators (testers) | R3-Admin (G. Petrowsky) |  | sap-upgrade-core@mit.edu
68 |  | 10:30 AM - 12:30 PM (2 hours) | MIT Business Validation PS1 Data Validations & Transaction processing listed in section of the Validation spreadsheet performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs IS&T BSAs |  | sap-upgrade-core@mit.edu
69 |  | By 12:30 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs IS&T BAs & SAs |  | sap-upgrade-core@mit.edu
70 |  | 13:00 | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, POs, Team Leads) +1-617-324-0000 US Toll Number Access code: 642 538 749 | PM (Lori Singer) |  | sap-upgrade-core@mit.edu
Go Live
71 | Sunday 12/9/2018 | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu, warehouse@mit.edu) indicating decisions/results. | PM (Frank Quern) |  | sapbiz@mit.edu sap-upgrade-core@mit.edu ist-sap@mit.edu warehouse@mit.edu
72 |  | 1:30 PM – 2:30 PM | Unlock users (Facilities, SMART) Unlock all users (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ops-help@mit.edu, with a copy to ist-sap@mit.edu, update Atlas message. | R3-Admin (George Petrowsky) |  | sap-upgrade-core@mit.edu
73 |  | 2:30 PM Sunday (5 Minutes) | Enable Drop box | R3 Admin (Qian Kang) |  | sap-upgrade-core@mit.edu
74 |  | 14:30 | Reinstate weekend MITSIS Bio Feed cron job On batchadmin-east-prod-app-1 under the userid as_cron uncomment out the /sis/mitsis/applications/scripts/GEN/triggerBatch.sh /sis/cron biofeedsJob job. | ops (George Gaudette) |  | sap-upgrade-core@mit.edu
75 |  | 8PM – 12AM | Data Warehouse Job Validation • Eping (Lucia) Wei confirm job validation completion via email to sap-upgrade-core@mit.edu, warehouse-dev@mit.edu • Run extracts (10PM & 12AM) | R3-Admin |  | sap-upgrade-core@mit.edu
76 |  | By 6:30pm | Execute ProCard from Bank of America Feed | ABAP Team (Eping Lucia Wei) |  | sap-upgrade-core@mit.edu
77 | Monday morning 12/10/2018 | By 6 AM | Update the 3-down web page & SAPgui message. | R3-Admin (R. Parker) Project Manager (Lori Singer) |  | sap-upgrade-core@mit.edu
78 |  | By 6 AM | Remove SAP outage message on Coupa webpage. | VPF (Cecelia Talamantes) (Scott Ball) |  | sap-upgrade-core@mit.edu | schedule to expire at midnight
79 |  | By 6 AM | Remove Atlas and EHS messages. | Frank Quern |  | sap-upgrade-core@mit.edu
80 |  | By 6 AM | Post Atlas Banner Message with link to Known SAP Issues kb article | Frank Quern |  | sap-upgrade-core@mit.edu | if needed
81 |  | By 6 AM | Remove GAP Banner message | Deepa Salman |  | sap-upgrade-core@mit.edu
82 |  | By 6 AM | Validate Atlas and EHS outage messages have been removed (verify in IE, Firefox, Chrome) | HRP BSA (Frank Quern) |  | sap-upgrade-core@mit.edu
83 |  | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | PM (Lori Singer) |  | sap-upgrade-core@mit.edu
84 |  | By 10 AM | AIMS – Renable AIMS job that runs M-F at 6 PM and posts JVs for Visitor parking reservations. | Dudley Kirkpatrick Nivedita Dhiman |  | sap-upgrade-core@mit.edu
85 |  | By EOD | Review Qualtrics responses not captured during the outage. | Nivedita Dhiman |  | sap-upgrade-core@mit.edu
86 |  | By EOD | eBuider expense catch up | Nivedita Dhiman |  | sap-upgrade-core@mit.edu
87 |  | By 10 AM | Manually execute ZHR_NEWHIRE_NOTIFICATION with custom variants for Friday and Saturday through Batch ID. (see o email sap-upgrade-core@mit.edu when complete | HRP BSA (L. Kushkuley) |  | sap-upgrade-core@mit.edu | see task 23
88 | 2018-12-31 | 17:30 | Re-activate gui version detection/rejection for older SAP gui versions | R3-Admin (Ron Parker) |  | n/a

## R3 Upgrade Tasks
Task ID | Day |  | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
r1 | Monday | PS1 | 2018-12-03 | 9:00 | 2018-12-03 |  | 30 mins | Ron Parker | Ron changes profile adding parameters to default central instance profile | complete
r2 | Tuesday | PS1 | 2018-12-04 | 17:00 | 2018-12-04 |  | 30 mins | Ron Parker | Pre-upgrade Transports | complete | Two basis transports SF3K905217 SF3K905219
r3 | Wednesday | GRC - ACP | 2018-12-05 | 21:00 | 2018-12-05 |  |  | HEC/Ron Parker | Start SP preprocessing phase (uptime) | complete
r4 | Thursday | PS1 | 2018-12-06 | by 5 PM | 2018-12-06 | by 5 PM | N/A | Ron Parker | Save Wage type table (after system is locked) | complete
r5 |  | PS1 | 2018-12-06 | by 5 PM | 2018-12-06 | by 5 PM | N/A | Ron Parker | Snapshoft of Profiles (8 profiles)
r6 | Friday | PS1 | 2018-12-07 | 14:00 | 2018-12-07 | 14:00 |  | George Petrowsky | Stop the Roles to SAP Feed and related User Admin Jobs | complete
r7 |  | PS1 | 2018-12-07 | 14:00 | 2018-12-07 | 14:00 |  | George Petrowsky | Get extracts of the tables updated with User Admin procedures: - USR02 - USRBF2 - AGR_USERS - UST04 - UST10S - Extract all Authorization Definitions ( ZR3_AUTH_MIL_2 ) | complete
r8 |  | PS1 | 2018-12-07 | 14:00 | 2018-12-07 | 15:40 | 40 mins | George Petrowsky | Create the 8 files to use to Lock all IDs – about 40 minutes. This will start at 2 PM. | complete
r9 |  | PS1 | 2018-12-07 | 15:00 | 2018-12-07 | 19:00 | 2 hours | George Petrowsky | Shift all non-DW jobs to start after 6am on Monday | complete
r10 |  | PS1 | 2018-12-07 | by 3 PM | 2018-12-07 | by 3 PM | 30 mins | Qian Kang | Shift concur outbound execution from 5 to 3:20 Comment out the following on axplor 00 17 * * 1-5 su - sapdbmon -c "/export/home/sapdbmon/bin/rldb_tra_extract.pl /export/home/sapdbmon/script_config/tra_extract2prd.cfg" >>/export/home/sapdbmon/logs/log.travel_extracts_prd 2>&1 Run this, 20 15 * * 1-5 su - sapdbmon -c "/export/home/sapdbmon/bin/rldb_tra_extract.pl /export/home/sapdbmon/script_config/tra_extract2prd.cfg" >>/export/home/sapdbmon/logs/log.travel_extracts_prd 2>&1 | complete | on main cutover task list
r11 |  | SMP | 2018-12-07 | 5:00 PM EDT | 2018-12-07 | 17:00 | N/A | Ron Parker | MIT Handoff SAP Mobile Platform (SMP_ to HEC for Upgrade Processing | complete | scheduled thru ticket with SAP
r12 |  | PS1 | 2018-12-07 | 5:00 PM EDT | 2018-12-07 | 17:00 | N/A | Qian Kang | Suspend dropbox Comment out pull script on sftp02 Comment out pull 1file scripts on sftp02 Suspend this job on axplor 00 22 * * * su - sapdbmon -c "/home/sapdbmon/bin/citi_download.pl /home/sapdbmon/script_config/citi_download.cfg" >>/home/sapdbmon/logs/log.citi_download_prd 2>&1 Suspend this job on axplor 0 07 * * * su - infrp -c "/usr/bridges/prod/infrp/get_warehouse_extracts" >>/usr/bridges/prod/infrp/log.get_warehouse_extracts 2>&1 | complete | on main cutover task list
r13 |  | PS1 |  | 17:00 |  | 17:00 | N/A | Ron Parker | Request SAP bring down application systems | complete | scheduled thru ticket with SAP
r14 |  | PS1 |  | 17:00 |  | 17:30 | 30 minutes | George Petrowsky | Lock Users Force off any IDs still logged on | complete
r15 |  | PS1 |  | 17:00 |  | 17:30 | 30 minutes | Ron Parker | Disabling Logon groups | complete
r16 |  | PS1 |  | 17:00 |  | 17:30 | 30 minutes | Ron Parker | Run TB Reports | complete
r17 | Saturday |  |  | by 7:00 AM |  |  |  | HEC | User CUST1 in client zero (SAP reset password) | complete
r18 |  |  |  | 7:00 AM EDT |  | 6:00 PM EDT | 11 hours | R3 | R3-Admin action log | complete
|  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute SGEN Load Generations - Objects for all PS1 components - Regernerate already existing invalid loads - BSP Applications - Web Dynpros | complete
r19 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Restore Wage Types | complete
r20 |  | PS1 | 2018-12-08 | 7:00 | 2018-12-08 | 12:30 PM EDT | 45 mins | Rich Katkowski | Load Tranport buffer | complete
r21 |  |  |  | 8:00 |  |  | 4 hours | Rich Katkowski | Transports | complete | brief pause in process to check adjustmenst on notes
r22 |  | GRC - ACP | 2018-12-08 | 8:00 |  |  | 2 hours | Ron Parker | Execute SGEN Load Generations - Objects for all ACP components - Regernerate already existing invalid loads - BSP Applications - Web Dynpros | complete | system handed over to R3 9pm Friday
r23 |  | GRC - ACP | 2018-12-08 | 10:00 | 2018-12-08 | 10:30 | 0.5 hours | Rich Katkowski | Import GRC Transports | complete
r24 |  | GRC - ACP | 2018-12-08 | 10:30 | 2018-12-08 | 11:30 | 1 hour | Ron Parker | a) Deploy MIMEs (program WDG_MAINTAIN_UR_MIMES) b) Execute restore of GUI Interface Changes, Activation Flag for Function Exits (program RSMODRES) c) Execute transaction SIAC_PUBLISH_ALL_INT (publish services) d) Execute transaction SWU3 (verify Workflow Customizing) e) Execute TCC Servicetools Update (program RTCCTOOL) | complete
r25 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Generate features in client 0 for select transports | complete
r26 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Generate features in client 30 for select transports | complete
r27 |  |  | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Activate Asset Management enhancements LOG_EAM_SIMP LOG_EAM_CI_1 | complete
r28 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Deploy MIMEs (program WDG_MAINTAIN_UR_MIMES) | complete
r29 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute FI-SL XPRA: Generation GLU1, GLU2, FI-SL Programs (program RGZZGLUX) | complete
r30 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute update of FI-SL Programs (program RGBCFL00) | complete
r31 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute generation of ABAP code for validations/substitutions/rules (program RGUGBR00) | complete
r32 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute restore of GUI Interface Changes, Activation Flag for Function Exits (program RSMODRES) | complete
r33 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute transaction SIAC_PUBLISH_ALL_INT (publish services) | complete
r34 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute transaction SWU3 (verify Workflow Customizing) | complete
r35 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Execute TCC Servicetools Update (program RTCCTOOL) | complete
r36 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Verify SAP Kernel post-update adjustment via Z_SENDMAIL test | complete
r37 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  | 1 hour | Ron Parker | Run TB Reports -- Batch environment adjustment -- Trial Balance Batch Executions -- Trial Balance Report Extracts and Email notifications | complete | on main cutover task list
r38 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | George Petrowsky | User validations
r39 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | George Petrowsky | Roles feed file process
r40 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | BSI Test Connection
r41 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | George Petrowsky | Check/Test Open Text Connectivity
r42 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  | 15 min | Rich Katkowski | Point DST to Production | complete
r43 |  | All | 2018-12-08 |  | 2018-12-08 |  |  | All | Test of infrastucture
r44 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | Rich Katkowski | Validate Adobe form rendering - run fp_check_destination_service - run fp_pdf_test_00 - run fp_test_00 - run fp_test_003 - display W2 form - display W2 form instructions | complete
r45 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | R3 | user maintienance
r46 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | R3 | trusted links validations |  | RFC Connection validation
r47 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | R3 | drop box
r48 |  | ASAPI | 2018-12-08 |  | 2018-12-08 |  |  | Ron Parker | Restart ASAPI servers (production tier) | complete
r49 |  | Mendix | 2018-12-08 |  | 2018-12-08 |  |  | Qian Kang | Restart CSAIL and Comp Analysis in Mendix |  | ASAPI restart must complete first; this task is now performed by ops-help
r50 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | George Petrowsky | Shift back to weekend those jobs that normally occur on weekend
r51 |  | GRC - ACP | 2018-12-08 | 14:00 | 2018-12-08 |  | 30 minutes | Sarah Quigley | Run manually PS1 sync job
r52 |  | GRC - ACP | 2018-12-08 | 14:00 | 2018-12-08 | 16:00 | 1.50 hours | Sarah Quigley | GRC Validations
r53 |  | PS1 | 2018-12-08 |  | 2018-12-08 |  |  | George Petrowsky | Check that JCO MetaUser and Scorm users are unlocked in PS1: ZZJCOMETA000 (run any JCO app, e.g Disp PO) and ZZADMSCORM01 (open learning center course, e.g. event planning, chk table Z...)
r54 | Sunday | PS1 | 2018-12-09 |  | 2018-12-09 |  |  | Qian Kang | Enable drop box |  | on main cutover task list
r55 |  | PS1 | 2018-12-09 |  | 2018-12-09 |  |  | George Petrowsky | Verify that the system appears to be working as expected a. Execute the User Admin functions b. Check ST22, SM21

## MIT Web Deployments
SAP web components for Dec 7-11, 2018 cutover
[Note: we will stage as much as possible (non SAP) in OC11 datacenter by Dec 7 as needed]
# | Task description | RT Ticket | Execute | When | Comment
Mulesoft deployments:
| API mit-coupa-integrations-v1 (2.0.25) | 4734335 | yes | SAT 12/8 | ServiceNow ticket CHG0042567 - following SAP Transports
Java deployments for:
none scheduled at this time
NOTE: new ITS/WDA doman, use https://hecps1web01.mit.edu
| Server Name | Type
| atlas-ca-prod-app-1 | Atlas
| atlas-ca-prod-app-2 | Atlas
| atlas-ca-prod-app-3 | Atlas
| atlas-ca-prod-app-4 | Atlas
| atlas-oc11-4-prod-app-1 | Atlas
| atlas-oc11-4-prod-app-2 | Atlas
| atlas-oc11-4-prod-app-3 | Atlas
| atlas-oc11-4-prod-app-4 | Atlas
| atlas-ca-prod-db-1 | Database
| atlas-prod-db-1 | Database
| admsys-ca-prod-app-1 | Application
| admsys-ca-prod-app-2 | Application
| admsys-ca-prod-app-3 | Application
| admsys-ca-prod-app-4 | Application
| admsys-ca-prod-app-5 | Application
| admsys-ca-prod-app-6 | Application
| admsys-ca-prod-app-7 | Application
| admsys-ca-prod-app-8 | Application
| admsys-oc11-4-prod-app-1 | Application
| admsys-oc11-4-prod-app-2 | Application
| admsys-oc11-4-prod-app-3 | Application
| admsys-oc11-4-prod-app-4 | Application
| admsys-oc11-4-prod-app-5 | Application
| admsys-oc11-4-prod-app-6 | Application
| admsys-oc11-4-prod-app-7 | Application
| admsys-oc11-4-prod-app-8 | Application
| aprsys-ca-prod-app-1 | Application
| aprsys-ca-prod-app-2 | Application
| aprsys-oc11-4-prod-app-1 | Application
| aprsys-oc11-4-prod-app-2 | Application
| ehssys-ca-prod-app-1 | Application
| ehssys-ca-prod-app-2 | Application
| ehssys-oc11-4-prod-app-1 | Application
| ehssys-oc11-4-prod-app-2 | Application
| finsys-ca-prod-app-1 | Application
| finsys-ca-prod-app-2 | Application
| finsys-oc11-4-prod-app-1 | Application
| finsys-oc11-4-prod-app-2 | Application
| scorm-ca-prod-app-1 | Application
| scorm-ca-prod-app-2 | Application
| scorm-oc11-4-prod-app-1 | Application
| scorm-oc11-4-prod-app-2 | Application
| scorm-ca-prod-db-1 | Database
| scorm-ca-prod-db-2 | Database
| asapis-prod-app-1 | Application | Not replicated
| asapis-prod-app-2 | Application | Not replicated

## SAP Tickets
System ID | Description | Status
PS1 | 604157 / 2018 HECSR_STD PS1MIT Update Software Version of Application | Sent to SAP
-- ERP Support Package Updates
ACP | 606020 / 2018 HECSR_EMS_0 ACPMIT Upgrade Software Version of Application | Sent to SAP
SMP | 606674 / 2018 HECSR_STD SMPMIT Update Software Version of Application | Sent to SAP
NOTE:
DSP will probably be done after the first post-update payroll run

## HEC 2018 - ERP (PS1) Upgrade
PS1 System upgrade between 12/8 starting at 7:30 PM EDT and 12/9 7:30 AM EST | [5 empty] | Timezone: US Eastern
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
a | [5 empty] | MIT (R3-Admin) | Create Ticket EHP8 for ERP 6.0 SPS 11 (Incident 604157 / 2018 / HECSR_STD PS1MIT Update Software Version of Application). MPID: 1000587198 | complete
b | [5 empty] | MIT (R3-Admin) | To confirm in the ticket that preparation steps have been completed in OSS note SF3K905219 | complete
Extraction, Configuration and Check Phases | [7 empty] | complete
1 | 2018-12-05 | 14:00 | 2018-12-07 | 16:59 | 3 days | HEC | Extraction, Configuration, Check phases from Software Update Manager Tool, we will wait to Wednesday 5th afternoon in order to start with Preprocessing phase ( system lock)
2 | [6 empty] | During Extraction Phase, PS1 XML file is provided, it was created by HEC and validated by MIT
3 | [6 empty] | During Extraction Phase Import SPAM version 70 750 is mandatory
4 | [6 empty] | During configuration phase to configure to use the Standard mode ( Shadow Instance)/Define the parallel Process to be used in the Shadow Instance
5 | [6 empty] | During Configuration Phase (PREP_INTEGRATION/ADJUSTPRP) to provide Transport request provided by MIT SF3K905221 will be indicated in the service request ticket.
6 | [6 empty] | HEC To confirm/validate the target version of each ABAP component
Preprocessing Phase | [7 empty] | complete
7 | 2018-12-05 | 17:00 | 2018-12-05 | 19:00 | N/A | MIT (R3-Admin) | To confirm with an update in the ticket that HEC can proceed with Preprocessing phase ( lock development environment for any change) - MIT will update in ticket
8 | [5 empty] | HEC | Continue with preprocessing
9 | 2018-12-07 | 17:00 | 2018-12-07 | 17:30 |  | HEC | Isolation CI. Stop the PS1 Application Servers (AI01-AI07) at 05/12/2018 05:00PM EST
10 | [5 empty] | MIT (R3-Admin) | Redirect ADS from DSP to DST
| 2018-12-07 | 19:00 | 2018-12-07 | 21:00 |  | HEC | End_steps_Preprocessing_phase ( requires about 2 hrs.)
11 | [6 empty] | Suspend batch jobs
12 | [6 empty] | Logoff all users from Central Instance
13 | [6 empty] | Create full backup of intallation directory /usr/sap/PS1/ including SUM directory
14 | [6 empty] | Create Full Backup of HANA database
15 | [6 empty] | Stop HANA replication to HA node and DR site (Request through Software Update Manager Tool)
Execution and Post Processing Phase
17 | 2018-12-07 | 21:00 | 2017-12-08 | 9:00 | 12 hours | HEC | Execution Phase ( to run for about 7 hrs.)
19 | [6 empty] | after above step is completed, Execute a new HANA full backup ( 1 hr.)
20 | [5 empty] | HEC | Post-Processing phase ( 1 hr.)
22 | [6 empty] | Also during post-processing phase, manual task request to Start Suspended Jobs, we will not perform it, as agreed MIT will take care of this task later on
23 | [6 empty] | HANA Replication will be re-enable during Post-processing phase
24 | [5 empty] | HEC | Additonal Manual task after SUM process
Check on EA-HR 608 and SAP-HR 608 are in SP59
roll back kernel to 753 p201 and copy RFC libs from previous SAP Kernel version
25 | [6 empty] | CUST1 user creation and share credentials
26 | [6 empty] | HEC system health checks(monitoring tools, integration tools, PS1 system health)
System Handover
27 | 2018-12-09 | 9:30 |  |  |  | HEC | Handover PS1 Upgraded System to MIT
28 | [5 empty] | MIT (R3-Admin) | Perform Post-Upgrade tasks in PS1
Special note: For Central Instance and Application intances in the DR site, no further action is needed due to the fact we have snap-mirror in place for the installation directory

## HEC 2018 - GRC (ACP) Upgrade
ACP System upgrade between 12/5 starting at 9:00 PM EDT and 12/7 8:00 PM EST | [5 empty] | Timezone: US Eastern
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
a | [5 empty] | MIT (R3-Admin) | Create Ticket GRC update (Incident 606020 / 2018 / HECSR_STD ACPMIT Update Software Version of Application). MPID 2000569329 | complete
b | [5 empty] | MIT (R3-Admin) | To confirm in the ticket that preparation steps have been completed in OSS note | complete
Extraction, Configuration and Check Phases
1 | 2018-12-05 | 21:00 |  |  |  | HEC | Extraction, Configuration, Check phases from Software Update Manager Tool, we will wait to Wednesday 5th afternoon in order to start with Preprocessing phase ( system lock)
2 | [6 empty] | During Extraction Phase, PS1 XML file is provided, it was created by HEC and validated by MIT
3 | [6 empty] | During Extraction Phase Import SPAM version 70 750 is mandatory
4 | [6 empty] | During configuration phase to configure to use the Standard mode ( Shadow Instance)/Define the parallel Process to be used in the Shadow Instance
5 | [6 empty] | During Configuration Phase (PREP_INTEGRATION/ADJUSTPRP) to provide Transport request provided by MIT ACDK900423 will be indicated in the service request ticket.
6 | [6 empty] | HEC To confirm/validate the target version of each ABAP component
Preprocessing Phase
7 | 2018-12-06 | 0:01 | 2018-12-06 |  | N/A | MIT (R3-Admin) | To confirm with an update in the ticket that HEC can proceed with Preprocessing phase ( lock development environment for any change) - MIT will update in ticket
8 | [5 empty] | HEC | Continue with preprocessing
9 | [5 empty] | HEC
10 | [5 empty] | MIT (R3-Admin)
| 2018-12-06 | 17:01 | 2018-12-06 |  |  | HEC | End_steps_Preprocessing_phase ( requires about 2 hrs.)
11 | [6 empty] | Suspend batch jobs
12 | [6 empty] | Logoff all users from Central Instance
13 | [6 empty] | Create full backup of intallation directory /usr/sap/PS1/ including SUM directory
14 | [6 empty] | Create Full Backup of HANA database
15 | [6 empty] | Stop DB replication to HA node and DR site (Request through Software Update Manager Tool)
Execution and Post Processing Phase
17 | 2018-12-06 | 17:00 | 2018-12-07 | 5:00 | 12 hours | HEC | Execution Phase ( to run for about 7 hrs.)
19 | [6 empty] | after above step is completed, Execute a new DB full backup ( 1 hr.)
20 | [5 empty] | HEC | Post-Processing phase ( 1 hr.)
22 | [6 empty] | Also during post-processing phase, manual task request to Start Suspended Jobs, we will not perform it, as agreed MIT will take care of this task later on
23 | [6 empty] | DB Replication will be re-enable during Post-processing phase
24 | [5 empty] | HEC | Additonal Manual task after SUM process
Check on software components
25
26 | [6 empty] | HEC system health checks(monitoring tools, integration tools, PS1 system health)
System Handover
27 | 2018-12-07 | 6:00 |  |  |  | HEC | Handover PS1 Upgraded System to MIT
28 | [5 empty] | MIT (R3-Admin) | Perform Post-Upgrade tasks in PS1
Special note: For Central Instance and Application intances in the DR site, no further action is needed due to the fact we have snap-mirror in place for the installation directory

## HEC 2018 - SAP Mobile (SMP)
SMP System upgrade between 12/7 starting at 5:00 PM EDT and 12/8 5:00 PM EST
Start Date | Start Time | End Date | End Time | Task | Actions | Team | Status | Notes and wikis
2018-12-04 | 9:00 | 2018-12-04 | 17:00 | Pre-Steps | Download the media and put it on the server hec03v003968:/install/smp15 and change the owner as smdadm | L3 Basis | Pending
[5 empty] | Go to path /install/smp15 and run the command tar –zxvf SAPSMPRT3015P_1-20011875.TGZ & SAPSMPRT3015_0-20011875.TGZ | L3 Basis | Pending
[5 empty] | Check wiki https://wiki.wdf.sap.corp/wiki/pages/viewpage.action?pageId=1832846842 to se all is working fine. | L3 Basis | Pending
[5 empty] | Raise a ticket to backup team for full offline backup | L3 Basis | Pending | https://launchpad.support.sap.com/#/notes/2558055
2018-12-07 | 5:00PM | 2018-12-08 | 16:30 | Change from NFS to local FS | Stop the system and verify that any process is running | L3 Basis | Pending
[5 empty] | Take offline backup of existing NFS /usr/sap/<SID> SMP directory. Put the backup on /install/SMP_backup | L3 Basis | Pending
[5 empty] | Take an ASE backup (SMD and SMP3). Put the backup on /install/SMPASE_backup (DUMP) | L3 Basis | Pending
[5 empty] | Rename the NFS /usr/sap/SMD to /usr/sap/SMD_old | SM team | Pending
[5 empty] | Create a local mount point FS /usr/sap/SMD. SIze of Block should be Previous Size of NFS directory 30 GB | SM team | Pending
[5 empty] | Restore the backup from /install/SMP_backup to /usr/sap/SMD (local FS) | L3 Basis | Pending | https://launchpad.support.sap.com/#/notes/2543290
[5 empty] | Start the system and verify all is working fine | L3 Basis | Pending
|  |  |  | Perform the Update SAP MOBILE PLATFORM 3.0 SP13 to SP15 | Check the current version of SMP | L3 Basis | Pending
[5 empty] | Stop the system and verify that any process is running | L3 Basis | Pending
[5 empty] | Go to hec03v003968:/install/smp15 | L3 Basis | Pending
[5 empty] | run the following command as sidadm sh SilentInstall_Linux.sh | L3 Basis | Pending
[5 empty] | Installation of Support package will start | L3 Basis | Pending
[5 empty] | Installation has been finsished | L3 Basis | Pending
[5 empty] | Start the system and verify all is working fine | L3 Basis | Pending
[5 empty] | Confirm the installation logs (/usr/sap/SMD/MobilePlatform3/InstallLogs) | L3 Basis | Pending
[5 empty] | Go to /install/smp15 | L3 Basis | Pending
[5 empty] | run the following command as sidadm sh SilentInstall_Linux.sh | L3 Basis | Pending
[5 empty] | Installation of Patch will start | L3 Basis | Pending
[5 empty] | Installation has been finsished | L3 Basis | Pending
[5 empty] | Start the system and verify all is working fine | L3 Basis | Pending
[5 empty] | Confirm the installation logs (/usr/sap/SMD/MobilePlatform3/InstallLogs) | L3 Basis | Pending
2018-12-08 | 17:00 |  |  | Post-steps | Unmount the NFS /usr/sap/SMD_old | SM team | Pending
[5 empty] | Raise a ticket to backup team to verify that the backups are running. | L3 Basis | Pending

## GRC (ACP) Upgrade
ACP System upgrade between 12/5 starting at 9:00 PM and 12/7 9:00 PM (TB confirmed) | [5 empty] | Timezone: US Eastern
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
1 | 2018-11-26 | By EOD | 2017-11-26 | By EOD | N/A | MIT | Create ticket for ACP Upgrade downtime window 12/6 starting at 11:59 AM and 12/9 7:30 AM HEC TICKET: 606020 / 2018 HECSR_EMS_0 ACPMIT Upgrade Software Version of Application | completed
2 | 2018-12-05 | 21:00 | 2018-12-07 | 21:00 | 48 hours | HEC | ACP Upgrade (48 Hour Window)
3 | 2018-12-05 | 21:00 |  | 19:00 |  | HEC | Execution phase preparations (uptime) | completed
4 | 2018-12-06 | 17:00 | 2018-12-07 |  | 14 hours | HEC | Execution & post processing phases (downtime) | in process
5 | 2018-12-07 | 19:00 | 2018-12-07 | 21:00 | 2 hours | HEC | HEC system health checks(monitoring tools, integration tools, ACP system health)
Date
| 12/5/2018 by 12:00:00 PM |  |  |  |  | squigley | Back up copies of mitigating control assignments and the rule set in ACP. | complete
| 12/5/2018 by 5:00 PM |  |  |  |  | squigley | Ensure all Firefighter logs have been approved in ACP. | complete
Saturday
After Access Control 12.0 and YE SP upgrade
[6 empty] | squigley | Activate NWBC in SICF, and ensure services required for Touchstone authentication are active: AC 472B6A4A4ME2OJOGCB0PUKKKT CDC_EXT_SERVICE006ENMX6PUM8SITZTRV3IY627 GF1100205 BPXI9KP2BASOTAFYZA1IQQI7C GF1100220 BPXI9KP2BASOTAFYZA1IQQI7C GF1100222 BPXI9KP2BASOTAFYZA1IQQI7C GF1100304 BPXI9KP2BASOTAFYZA1IQQI7C GF1100393 BPXI9KP2BASOTAFYZA1IQQI7C GF1100397 BPXI9KP2BASOTAFYZA1IQQI7C GF110041 BPXI9KP2BASOTAFYZA1IQQI7C GF110069 BPXI9KP2BASOTAFYZA1IQQI7C GF1100804 BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_CUPAR BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_CUPRV BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_ERMRL BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_RAAL BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_RACL BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_RACOMPBPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_RARA BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_RARL BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_RARV BPXI9KP2BASOTAFYZA1IQQI7C GRAC_DAB_RAUA BPXI9KP2BASOTAFYZA1IQQI7C GRC DFFAEATGKMFLCDXQ04F0J7FXK SAML2 006ENMX6PUM8SITZTRV3IY627
| Saturday |  |  |  |  | Tester | Test description |  | Results | Comments
[6 empty] | squigley | Dashboard Reports: Access Rule Library Mitigating Control Library Risk Violations User Analysis Role Analysis Violations Comparisons
[6 empty] | squigley | User Level RA Report for for VPF and IS&T custom groups
[6 empty] | squigley | User Level simulation, adding a role to a user
Role level simulation, adding a transaction to a role
[6 empty] | squigley | Firefighter log reports
[6 empty] | squigley | Repository Object Sync job
[6 empty] | squigley | Firefighter test - Log into ACP--> PS1, run several transactions
[6 empty] | squigley | Run Firefighter log sync job
[6 empty] | rep | Firefighter Controller - Return Firefighter log to Firefighter for additional information. Ensure Touchstone authentication is active.
[6 empty] | squigley | Firefighter returns log with additional information requested. Ensure Touchstone authentication is active.
[6 empty] | rep | Approve log
[6 empty] | squigley | Run Repository Object Sync job in GRP.
[6 empty] | georgep | Roles Database user simulation test with GRC
[6 empty] | squigley | Validate selection of ruleset entries by running a textpad comparison with backed up files
[6 empty] | squigley | Validate mitigating control entries by running a textpad comparison with backed up file

## SAP Mobile (SMP) Upgrade
Task ID | Start Date | Start Time | End Date | End Time | Duration | Responsible | Description | Status
606674 / 2018 HECSR_STD SMPMIT Update Software Version of Application
| 2018-12-07 | 5:00 PM EDT | 2018-12-08 |  |  | HEC | Upgrade SAP Mobile Platform Runtime 3.0 from SP13 PL03 to SP15 PL01 | complete
| 2018-12-08 |  | 2018-12-08 |  |  | HEC | Upgrade JVM 8.1 to SP32 | complete
| 2018-12-08 |  | 2018-12-08 | 17:00 |  | HEC | HEC system health checks(monitoring tools, integration tools, SMP system health) | complete

## SAP Mobile Cutover Steps
Step | Date |  | Description | Point of Contact | Status
1 | 11/26 to 12/1 | 11/26 - 12/1 | upgrade to iOS 12 Should be completed before SP weekend - Validate steps needed on iPad (re-enter iTunes password - NO, reboot iPad - YES (by the iPad) , reset Agentry - NO) | Mike Sherman | complete
2 | FRI (Earlier) |  | Identify personnel on call (e.g. Evora IT) | Lee Collier | complete
3 | 12/1 - 12/3 | 12/1 - 12/3 | Use CASPER to push new Agentry files to mobile users (Agentry reset required) - Validate steps needed on iPad (re-enter iTunes password - NO, reboot iPad - NO, reset Agentry - YES) | Mike Sherman | complete
4 | SAT | 12/1 | Communicate new Agentry Files being deployed | Mike Sherman | complete
5 | MON | 12/3 | 6:45 am @ E19 | Lee Collier Bob Leonard | complete
6 | MON | 12/3 | 6:45 am @ 32 (CSG) | Jim Fragala | complete
7 | MON | 12/3 | 6:45 am @ WW15 | Nivedita Dhiman | complete
8 | THR (or earlier) | 12/6 | Communicate to the mobile community what (SAP Support Packs) is happening. Include documentation on reset steps by Lee C | Bob Leonard | complete
9 | FRI (or earlier) | 12/7 | Save all Facilities and Housing work orders | Bob Leonard | complete
10 | Friday | 12/7 | Verify no weekend work for current iPad users, Mobile users down at 5:00 PM official, GUI users down at 5:00 pm. Coordinate with the Operations Center and off shift supervisors. Use manual shop papers. | Bob Leonard | complete
11 |  | 12/8 | Apply SAP note 2647584 and added S_DEVELOP authorization to the ERP operational Account used by SMD for WorkManager; two transports note & auth | R3 admin | complete
12 |  | 12/8 | Regenerate and install SSO certificate (w attributes of DSA and SHA1) on ERP; anytime after 5:00pm on 12/7; install in both PS1 and SMP | R3 admin | complete
13 | When r3 admin done with SAP Support Packs Upgrade | 12/8 | Restart the SMP Cluster nodes after the SAP Support Packs upgrade is complete - notify cosmos2030@mit.edu that restart is successful | R3 admin | complete
14 | SAT | 12/8 | Validate that SMP mobile server is up | R3 admin | complete | After upgrade ~ 5:00 PM
15 |  | 12/8 | Execute program /SYCLO/CORE_RUNTIME_PARM_PROG per SAP note 2693231 to set parameter IGNORE_CONVERSION_ERROR value to X; in ERP post PS1 update | R3 admin | complete
16 | SAT | 12/8 5pm | unlock lcollier to allow the execution of an iPad sync | R3 admin | complete
17 | SAT | 12/8 5-9pm | execute SMP sync | Lee Collier | complete
18 | SUN | 12/9 | Mobile validations in production by business Validate steps needed on iPad (re-enter iTunes password - NO, reboot iPad - NO, reset Agentry - YES) | Bob Leonard, Mike Sherman
19 | SUN | 12/9 | Notify community successful (or need for backup plan) | Bob Leonard
20 | MON | 12/10 | Backup plan for mobile if cutover fails - Shop Papers | Lisa St. Croix
21 | MON | 12/11 | 6:45 am @ E19 | Lee Collier Bob Leonard
22 | MON | 12/11 | 6:45 am @ 32 (CSG) | Jim Fragala
23 | MON | 12/11 | 6:45 am @ WW15 | Nivedita Dhiman

## Escalation Path
Escalation Path
If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Garry Zacheiss will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday December 4th.
Functional Malfunction(s)
Joe Siniscalchi | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike MacDonald | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Laurie Veal | Business Process Owner (EH&S) / Weekend Coordinator
John Larkin | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Frank Quern | Project Manager
Mark Silis | Associate Vice President, IS&T
Garry Zacheiss | Director, IS&T
Ron Parker | Manager, R3 Admin
Stephen Koczur | SAP HEC
Gia Dinh | SAP Basis
Project Steering Committee
Escalation Support Team
Adina Ion | BSA FLE Support
Bob Casey | FLE PO
Frank Quern | HRP PO
Frank Quern | Project Manager
George Petrowsky | R3 Authorizations
George Petrowsky | Scrum Master
Jim Fragala | Facilities PO
Kevin Lyons | Atlas PO
Lisa Robinson | Scum Master
Gregg McGrath | Scrum Master
Ron Parker | Basis PO
Faith Hill | Data Warehouse Team
Brandin Tumeinski | Data Warehouse Team

## Validation
Production Validation
Production Validation will occur in NE49, W92, N52 and remotely. Validation is scheduled to start at 10:30 AM, however, please check the your email or the cutover page for the status of the cutover before coming into the office or starting to test remotely. The message will be updated by 9:30 AM if there are potential delays and by 10:30 AM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 9th. Frank will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/Joe Siniscalchi | Trial Balance Report validation. Ron Parker will email Joe Siniscalchi, Bob Casey, Sandeep Nadendla and Frank Quern when the reports have finished processing. Joe will notify Frank via telephone/email when validation is complete (Sunday morning). Frank will follow up with an email to the following:sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/Atlas ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu

## BSI Upgrade Tasks
Task ID | Date | Time | Duration | Responsible | Task description | Status | comments
Upgrade will be performed post cutover weekend

## OpenText (OTP) Upgrade
OTP System Upgrade
Task ID | Date | Time | Duration | Responsible | Task description | Status | comments
No upgrade planned for 2018