## To PS1 Post Upgrade Transports
To PS1 during go-live 11/23/2019
Request/Task | Type | Status | Transport Target | Category | Owner | Date | Time | Higher-Level Request | Short Description
Mods (SPAU/SPAU_ENH)
SF3K905435 | K | R | SF2 | SYST | REP | 2019-10-27 | 14:51 |  | R3ADM* PostUpdate SPAU SNOTE Resets - 20191015.01
SF3K905437 | K | R | SF2 | SYST | REP | 2019-10-27 | 14:55 |  | R3ADM* PostUpdate SPAU -Deleted Object Modification Logs
SF3K905441 | K | R | SF2 | SYST | RKATKOWS | 2019-10-27 | 14:55 |  | R3ADM* - Reset MSAG, SFPF per SPAU
SF3K905439 | K | R | SF2 | SYST | RKATKOWS | 2019-10-27 | 14:57 |  | R3ADM* - Reimplement note 2506115 per SPAU
SF3K905443 | K | R | SF2 | SYST | EPRUDDEN | 2019-10-27 | 14:58 |  | SP2019: SPAU Changes (EPRUDDEN)
SF3K905452 | W | R | SF2 | CUST | REP | 2019-10-27 | 14:59 |  | R3ADM* BC SET /SMERP/SAP_WORK_MANAGER_65_REF Activation
SF3K905454 | W | R | SF2 | CUST | REP | 2019-10-27 | 15:00 |  | R3ADM* BC SET /SMERP/SAP_INVENTORYMGR_43_REF Activation
SF3K905456 | K | R | SF2 | SYST | RKATKOWS | 2019-10-27 | 15:01 |  | R3ADM* OSS 2839334-BEN: Plan 457 catch-up contribution.
SF2K967562 | K | R | SH2 | SYST | REP | 2019-10-27 | 15:07 |  | R3ADM* PostUpdate SPAU -Deleted Obj. Modification Logs (SF2)
SF2K967568 | K | R | SH2 | SYST | MPRUDDEN | 2019-10-27 | 15:08 |  | SP2019: SPAU_ENH (MPRUDDEN)
SF2K967566 | K | R | SH2 | SYST | EPRUDDEN | 2019-10-27 | 15:09 |  | SP2019: SPAU_ENH (EPRUDDEN)
SH2K900967 | K | R | NIL | SYST | REP | 2019-10-27 | 15:22 |  | R3ADM* PostUpdate SPAU -Deleted Obj. Modification Logs (SH2)
Post (@SPS13) Update Developments
SF2K967148 | W | R | SH2 | CUST | RCASEY | 2019-10-27 | 15:37 |  | FI-AR: Open Learning Config
SF2K967150 | W | R | SH2 | CUST | RCASEY | 2019-10-27 | 15:37 |  | FI-AR: Open Learning Config 2
SF2K967152 | W | R | SH2 | CUST | RCASEY | 2019-10-27 | 15:43 |  | FI-AR: OL doc type name change
SF2K967352 | K | R | SH2 | SYST | AGROBLER | 2019-10-27 | 15:53 |  | Trying to select name by MITID (first time ABAP) - TEST
SF2K967592 | W | R | SH2 | CUST | GMCGRATH | 2019-10-29 | 10:08 |  | PY: Add MA EIN to PBRP in table V_T5UTI for TTs RT 5104416
SF3K905460 | K | R | SF2 | SYST | REP | 2019-11-04 | 10:48 |  | R3ADM* OSS 2853869 TAX: Added withholding not considered...
SF2K967599 | K | R | SH2 | SYST | LKUSHKUL | 2019-11-04 | 14:23 |  | Atlas New Hire RT 5105748: All empl.are eligible for SH tile
SF2K964386 | K | R | SH2 | SYST | MPRUDDEN | 2019-11-05 | 11:47 |  | ZUTTREQ: add ServiceNow No and Dual Dev support
SF2K967610 | K | R | SH2 | SYST | LKUSHKUL | 2019-11-12 | 8:47 |  | Atlas IPIA email correction RT 5105620
SF2K967585 | W | R | SH2 | CUST | RCASEY | 2019-11-19 | 13:43 |  | Maintain ZMITCORANGES table per RT#5095338

## SAP Xports in restricted phase
To SH2 (upgraded) |  |  | To SH1 (not upgraded)
Mods (SPAU/SPAU_ENH)
SF3K905435 | SF3K905435 - R3ADM* PostUpdate SPAU SNOTE Resets - 20191015.01
SF3K905437 | SF3K905437 - R3ADM* PostUpdate SPAU -Deleted Object Modification Logs
SF3K905441 | SF3K905441 - R3ADM* - Reset MSAG, SFPF per SPAU
SF3K905439 | SF3K905439 - R3ADM* - Reimplement note 2506115 per SPAU
SF3K905443 | SF3K905443 - SP2019: SPAU Changes (EPRUDDEN)
SF3K905452 | SF3K905452 - R3ADM* BC SET /SMERP/SAP_WORK_MANAGER_65_REF Activation
SF3K905454 | SF3K905454 - R3ADM* BC SET /SMERP/SAP_INVENTORYMGR_43_REF Activation
SF3K905456 | SF3K905456 - R3ADM* OSS 2839334-BEN: Plan 457 catch-up contribution.
SF2K967562 | SF2K967562 - R3ADM* PostUpdate SPAU -Deleted Obj. Modification Logs (SF2)
SF2K967568 | SF2K967568 - SP2019: SPAU_ENH (MPRUDDEN)
SF2K967566 | SF2K967566 - SP2019: SPAU_ENH (EPRUDDEN)
SH2K900967 | SH2K900967 - R3ADM* PostUpdate SPAU -Deleted Obj. Modification Logs (SH2)
Pre (@SPS11) and Post (@SPS13) Update Developments
SF2K967148 | SF2K967148 - RCASEY 7/26/2019 14:09:55 FI-AR: Open Learning Config | BC
SF2K967150 | SF2K967150 - RCASEY 7/26/2019 14:10:56 FI-AR: Open Learning Config 2 | BC
SF2K967152 | SF2K967152 - RCASEY 7/26/2019 14:12:40 FI-AR: OL doc type name change | BC
SF2K967352 | SF2K967352- AGROBLER Trying to select name by MITID (first time ABAP) – TEST | AG - same in SH1 | SF2K967352 | SF2K967352 - AGROBLER Trying to select name by MITID (first time ABAP) – TEST | AG, to PS1 11/4/2019
SF2K967592 | SF2K967592 - PY: Add MA EIN to PBRP in table V_T5UTI for TTs RT 5104416 | GMc - dual in SH1 | SH1K900906 | SH1K900906 - PY: Add MA EIN to PBRP in table V_T5UTI for TTs 87 99 100 | GMc, to PS1 10/28/19
SF3K905460 | SF3K905460 - R3ADM* OSS 2853869 TAX: Added withholding not considered... | GMc
SF2K967599 | SF2K967599 - Atlas New Hire RT 5105748: All empl.are eligible for SH tile | LJK/KLY/EC
SF2K964386 | SF2K964386 - ZUTTREQ: add ServiceNow No and Dual Dev support | MP (manually chg'd in SH1) | SH1K900908 | SH1K900908 - DO NOT TRANSPORT - Temp Fix to ZUTTREQ for Support Pack Proj | not moving to PS1, SH2 transport will be moved to PS1 during go-live
SF2K967610 | SF2K967610 - Atlas IPIA email correction RT 5105620 | LJK - dual in SH1 | SH1K900912 | SH1K900912 - Atlas IPIA email correction RT 5105620 | LJK, to PS1 11/7/2019am
SF2K967585 | SF2K967585 - Maintain ZMITCORANGES table per RT#5095338 | BC - dual in SH1 | SH1K900910 | SH1K900910 - CO: RT5095338 alloc more numbers to SDP WBS range | BC, to PS1 11/14/2019
Time and Absence Project (NOT moving to PS1 from SH2 on SP2019 go-live)
SF2K967396 | SF2K967396 - RT5081369 - Updates to the performance of Time Portal |  | SF2K967396 | SF2K967396 - RT5081369 - Updates to the performance of Time Portal | AG, JDK, to PS1 11/7/2019pm
SF2K967515 | SF2K967515 - RT5081369 - Time portal updates |  | SF2K967515 | SF2K967515 - RT5081369 - Time portal updates | "
SF2K967517 | SF2K967517 - RT5081369 - Time portal updates (2) |  | SF2K967517 | SF2K967517 - RT5081369 - Time portal updates (2) | "
SF2K967523 | SF2K967523 - RT5081369 - Time portal, duplicates bug fixes |  | SF2K967523 | SF2K967523 - RT5081369 - Time portal, duplicates bug fixes | "
SF2K967541 | SF2K967541 - RT5081369 - Take out delete requests on absence periods |  | SF2K967541 | SF2K967541 - RT5081369 - Take out delete requests on absence periods | "
SF2K967574 | SF2K967574 - RT5081369 - Manager-relation, admin-relation fixes
|  |  | SH1K900903 | SH1K900903 - RT5081369 - Time and Absence performance and bug fixes | "
|  |  | SH1K900917 | SH1K900917 - RT5081369 - Time and Absence bug fixes | AG, JDK, to PS1 11/13/2019
as of 20191119 11:15am

## Fiori in restricted phase
To test
CHG0046962 | to Test - timetrackingportal - Fiori components | in test, 20191017, 08:33 | time-tracking-build-dev-20191017-259
CHG0046970 | to Test - timetrackingportal - Fiori components | in test, 20191017, 12:56 | time-tracking-build-dev-20191017-268
CHG0047068 | to Test - timetrackingportal - Fiori components | in test, 20191025, 09:13 | time-tracking-build-dev-20191025-304
CHG0047074 | to Test - timetrackingportal - Fiori components | in test, 20191025, 14:15 | time-tracking-build-dev-20191025-308
CHG0047101 | to Test - timetrackingportal - Fiori components | in test, 20191028, 16:13 | time-tracking-build-dev-20191028-318
CHG0047112 | to Test - timetrackingportal - Fiori components | in test, 20191029, 16:17 | time-tracking-build-dev-20191029-339 | CHG0047193 was SN to Prod
CHG0047188 | to Test - parkingcoordinatorportal - Fiori components | in test, 20191105, 16:41 | parking-coordinator-build-dev-20191105-275 | CHG0047199 was SN to Prod
CHG0047304 | to Test - timetrackingportal - Fiori components | in test, 20191114, 08:46 | time-tracking-build-test_arno-20191114-412
CHG0047316 | to Test - timetrackingportal - Fiori components | pending | time-tracking-build-test-20191114-415
To Prod
CHG0047193 | to Prod - timetrackingportal - Fiori components | in PS1, 20191107, 17:01 | time-tracking-build-dev-20191029-339
CHG0047199 | to Prod - parkingcoordinatorportal - Fiori components | in PS1, 20191106, 12:48 | parking-coordinator-build-dev-20191105-275