## Test Plan
Disaster Recover Test - December 14, 2019
Procedure Step | Executed by | Duration | Start time | Completion time | Date | Notes
Pre-Test Activities
Notify users of scheduled downtime | MIT - Ron Parker |  |  |  | 2019-12-09
Verify network connectivity from MIT to Santa Clara | MIT - R3 Admin |  |  |  | 2019-12-10
Downtime notification for DR systems | SAP HEC |  |  |  | 2019-12-13
Send email list for DR activities | MIT - Lori Singer |  |  |  | 2019-12-12
Stop Friday night Data Warehouse extracts | MIT - Lucia Ma |  |  | 17:00 | 2019-12-13
Confirm back-up PS1 | SAP HEC |  |  | 18:00 | 2019-12-13
Confirm back-up OTP Database | SAP HEC |  |  | 18:00 | 2019-12-13
Confirm back-up OTP application | MIT - App Delivery |  |  | 18:00 | 2019-12-13
Confirm back-up ACP | SAP HEC |  |  | 18:00 | 2019-12-13
Confirm back-up DSP | SAP HEC |  |  | 18:00 | 2019-12-13
Confirm back-up of FTP | MIT - R3 Admin, App Delivery |  |  | 18:00 | 2019-12-13
Confirm back-up of BSP (BSI) | MIT - R3 Admin |  |  | 18:00 | 2019-12-13
Confirm back-up of SMP | SAP HEC |  |  | 18:00 | 2019-12-13
Confirm back-up of HMP (formerly DMP) | SAP HEC |  |  | 18:00 | 2019-12-13
Confirm back-up of DS1 | SAP HEC |  |  | 18:00 | 2019-12-13
Confirm back-up of HCC | SAP HEC |  |  | 18:00 | 2019-12-13
Test Activities
Stop or reschedule COUPA, DW | MIT - R3 Admin, App Delivery |  |  | 12:30AM | 2019-12-14
Stop or reschedule all batch jobs (In-bound Feeds, ERP batch jobs) | MIT - R3 Admin | 0:30 | 12:30AM | 1:00 | 2019-12-14
Shutdown interfaces (Coupa, Atlas, GAP) | MIT - R3 Admin, App Delivery | 0:30 | 12:30AM | 1:00 | 2019-12-14
Lock users (except testers) and verify that they are not online | MIT - R3 Admin | 0:30 | 12:30AM | 1:00 | 2019-12-14
Notify of Completion batch / interface job completion (notify R3-Admin, Brandin, Frank, Bob, Andrew)(MIT) | MIT - Ron Parker |  | 1:00 | 1:00 | 2019-12-14
Initiate notification to users (testers) | Ron Parker |  | 1AM | 1:00 | 2019-12-14
Entry of Test Data in Sterling | MIT | 0:45 | 1AM | 1:45AM | 2019-12-14
Change master data Transaction PA30 ECC | CPT - FQ |  |  |  | 2019-12-14
Payroll Simulation BSI transaction PUOC_10 | CPT - FQ |  |  |  | 2019-12-14
Generate Tax Form ADS Transaction PU19 | CPT - FQ |  |  |  | 2019-12-14
Create an RFP ECC/Open Text Atlas RFP | CPT - BC |  |  |  | 2019-12-14
Attach a document Atlas Open Text | CPT - BC |  |  |  | 2019-12-14
Bob and Frank notify team via slack that tasks are complete | BC/FQ |  | 1:45AM | 1:45AM
Take transaction Screen prints (of system status) | MIT - R3 Admin | 0:05 | 1:50AM | 1:55AM | 2019-12-14
Lock users (testers) | MIT - R3 Admin | 0:05 | 1:55AM | 2:00AM | 2019-12-14
Stop Rsync on FTP Server | MIT - R3 Admin | 0:15 | 2:00AM | 2:15 | 2019-12-14
Stop/Shut down OTP applications | MIT - App Delivery | 0:15 | 2:00 | 2:15 | 2019-12-14
MIT notifies SAP HEC readiness for DR Test | MIT - Ron Parker | 0:05 | 2:15 | 2:20 | 2019-10-14
Start email chain between MIT and SAP HEC for communication | Lori Singer |  | 2:20 | 2:20 | 2019-10-14
SAP declares (mock) disaster | SAP/MIT |  | 2:30AM | 2:30AM | 2019-10-14
Failover Activities - Failover, DNS Switch, Start Applications | SAP HEC | 3:00 | 3:00AM | 6:00AM | 2019-10-14
Stop HANA replication PS1, ACP, DSP, HCC, HMP, OTP, SMP | SAP HEC |  |  |  | 2019-10-14
Failover to Santa Clara PS1, ACP, DS1, DSP, HCC, HMP, OTP DB, SMP | SAP HEC |  |  |  | 2019-10-14
DNS Switch for PS1, ACP, DS1, DSP, FTP, HCC, HMP, OTP DB, SMP & SMP LB | SAP HEC |  |  |  | 2019-10-14
Start applications PS1, ACP, DS1, DSP, HCC, HMP HANA, OTP HANA, SMP | SAP HEC |  |  |  | 2019-10-14 | FTP directories to be mounted on PS1
SAP HEC to notify Ron Parker and team when all systems are up in Santa Clara | SAP HEC | 0:15 | 6:00 | 6:15 | 2019-10-14
Start applications OTP | MIT - App Delivery | 0:15 | 6:15 | 6:30 | 2019-10-14
MIT Load Balancer IP Address Switch to Santa Clara for PS1 & ACP & HCC | MIT - App Delivery | 0:15 | 6:30 | 6:45 | 2019-10-14
Restart Java applications | MIT - App Delivery |  | 6:45 | 8:00 |  | before MIT testing starts at 8AM
Change connection to PS1 for BSP in SAC | MIT - R3 Admin | 0:30 | 6:45 | 7:15 | 2019-10-14
Validate infrastructure | MIT - R3 Admin, App Delivery | 0:15 | 7:15 | 7:30 | 2019-10-14
Unlock test users & operational users in Santa Clara | MIT - R3 Admin | 0:15 | 7:30 | 7:45 | 2019-10-14 | will create list of test users
Notify SAP HEC of connection test successful | MIT - Ron Parker |  | 7:45 | 7:45 | 2019-10-14
MIT Testing | MIT | 2:00 | 8:00 | 10:00 | 2019-10-14
MIT testing of PS1, ACP, BSP, DS1, DSP, FTP, HCC, HMP, OTP, SMP (See functional test tab) | MIT |  |  |  | 2019-10-14
MIT informs SAP HEC DR testing completion | MIT - Ron Parker |  | 10L00 AM | 10:00 | 2019-10-14
Stop OTP applications | MIT - App Delivery | 0:15 | 10:00 | 10:15 | 2019-10-14
MIT to notify SAP HEC that OTP has been shut down | MIT or App Delivery |  | 10:15 | 10:15 | 2019-10-14
Failback | SAP HEC | 3:00 | 10:15 | 13:15 | 2019-10-14
Stop shut down applications PS1, ACP, DS1, DSP, HCC, HMP, SMP | SAP HEC |  |  |  | 2019-10-14
Failback to Sterling PS1, ACP, DS1, DSP, HCC, HMP, OTP DB, SMP | SAP HEC |  |  |  | 2019-10-14
MIT Load Balancer IP Address Switch to Sterling PS1 & ACP & HCC | MIT - App Delivery |  |  |  | 2019-10-14
OTP Application DNS Switch to sterling | SAP HEC |  |  |  | 2019-10-14
DNS Switch for PS1, ACP, DS1, DSP, FTP, HCC, HMP, OTP DB, SMP and SMP LB | SAP HEC |  |  |  | 2019-10-14
Start up applications PS1, ACP, DSP, HMP, DS1, HCC, OTP DB, SMP | SAP HEC |  |  |  | 2019-10-14
Start up applications FTP | MIT - R3 Admin |  |  |  | 2019-10-14
Verify monitoring and management tools functioning | SAP Team |  |  |  | 2019-10-14
SAP HEC to notify MIT when systems are up in Sterling | SAP Team |  | 13:15 | 13:15 | 2019-10-14
MIT Failback Testing |  | 1:00 | 1:15PM | 14:15 | 2019-10-14
MIT performs testing to confirm connectivity and operation | MIT - R3 Admin |  |  |  | 2019-10-14
MIT performs testing on PS1, ACP, BSP, DS1, DSP, FTP, HCC, HMP, OTP, SMP to confirm connectivity and operation | MIT - R3 Admin |  |  |  | 2019-10-14
Unlock users (ALL) | MIT - R3 Admin | 0:15 | 14:15 | 14:30 | 2019-10-14
Start or reschedule all batch jobs (in-bound Feeds, ERP batch jobs) | MIT - R3 Admin | 0:15 | 14:30 | 14:45 | 2019-10-14
Restart Java applications | MIT - App Delivery | 0:15 | 14:30 | 14:45 | 2019-10-14
Start up interfaces (Coupa, Atlas, GAP) | MIT - App Delivery and R3 Admin | 0:15 | 14:45 | 15:00 | 2019-10-14
Start Rsync on FTP Server | MIT - R3 Admin | 0:30 | 14:45 | 15:15 | 2019-10-14
Notify of Completion batch / interface job completion | MIT - Ron Parker |  | 15:15 | 15:15 | 2019-10-14
Notify users that DR Test is complete (SAP Production group) | MIT - Ron Parker |  | 15:15 | 15:15 | 2019-10-14
Restart Data Warehouse extracts | MIT - Lucia Ma |  | 3:15PM | 3:15PM | 2019-10-14
SAP regenerates Replication to Santa Clara PS1, ACP, DS1, DSP, HCC, HMP, OTP, SMP | SAP HEC | 1:00 | 15:15 | 16:15 | 2019-10-14

## Functional tests
Interface | ECC System | System being Tested | Transaction | Task | Responsible | phase
GUI | PS1 | Open Text | FB03 | Display RFP | CPT - BC | DR
GUI | PS1 | Open Text | FB03 | Display RFP Attachment | CPT - BC | DR
GUI | PS1 | ECC / Open Text | ZAR1 | Run AR Statements, Attach Invoice PDF | CPT - BC | DR
GUI | PS1 | Open Text | FB03 | Display AR Statement Attachment | CPT - BC | DR
GUI | PS1 | ADS |  | Display SPA Billing Document | CPT - BC | DR
GUI | PS1 | ECC | ZSTM | Summary Statement (multiple versions) | CPT - BC | DR
GUI | PS1 | ECC | ZDTR | Detailed Transaction Report | CPT - BC | DR
GUI | PS1 | ECC | ZJVSTAT | JV Parked Document WF Status | CPT - BC | DR
GUI | PS1 | ECC | ZRFPSTAT | AP Parked Document WF Status | CPT - BC | DR
GUI | PS1 | ECC | ZAR2 | AR Aging Report | CPT - BC | DR
GUI | PS1 | ECC | ZSCV | Parked Credit Card Documents | CPT - BC | DR
GUI | PS1 | ECC | PA30 | confirm master data change | CPT - FQ | DR
GUI | PS1 | ECC | PA30 | change master data | CPT - FQ | DR
GUI | PS1 | ADS | PU19 | Generate Tax Form | CPT - FQ | DR
GUI | PS1 | BSI | PUOC_10 | Payroll Simulation | CPT - FQ | DR
GUI | PS1 | ADS | SE38 | Execute the following programs: fp_check_destination_service fp_pdf_test_00 fp_test_00 fp_test_03 | R3 - RK | DR
GUI | PS1 | GRC | NWBC | Run NWBC in ACP for DR site, Run Dashboard reports, User Level RA report for VPF with PS1 as the selected system for the reports. | R3 - SQ | DR
GUI | PS1 | GRC |  | Log into ACP, run a Firefighter session to PS1, run SM21, ST22, ST03, ST06, other Basis transactions | R3 - SQ | DR
GUI | PS1 | ECC | OAAD/OAC0 | Verify App Servers - connection test | R3-Admin | DR
GUI | PS1 | SFTP | AL11 | verify user bridges | R3-Admin | DR
N/A | N/A | HCC | Direct URL | Test connection | R3-Admin | DR
GUI | PS1 | ECC | PA30 | confirm master data change did not carry back | CPT - FQ | Failback
GUI | PS1 | ADS | PU19 | Generate Tax Form | CPT - FQ | Failback
GUI | PS1 | BSI | PUOC_10 | Payroll Simulation | CPT - FQ | Failback
Atlas | PS1 | ECC / Open Text | Atlas RFP | Create an RFP | CPT - BC | Failback
Atlas | PS1 | Open Text | Atlas RFP | Attach a document | CPT - BC | Failback
GUI | PS1 | Open Text | FB03 | Display RFP | CPT - BC | Failback
GUI | PS1 | Open Text | FB03 | Display AR Statement Attachment - confirm DR entries did not carry back | CPT - BC | Failback

## SAP Mobile Functional tests
Interface | ECC System | System being Tested | Transaction | Task | Responsible | phase
iPad | SMP/PS1 | Work Manager | List WO | Display user Work list | CPT-AB | DR
iPad | SMP/PS1 | Work Manager | WO Operations | Display WO Operations | CPT-AB | DR
iPad | SMP/PS1 | Work Manager | WO History | Display WO History for equipment Master | CPT-AB | DR
iPad | SMP/PS1 | Work Manager | Time Report | Run Time Report for User | CPT-AB | DR
GUI | PS1 | ECC | zpmteamwork | display team work list | CPT-AB | DR
GUI | PS1 | Open Text | zpmteamwork | display attachment | CPT-AB | DR
GUI | PS1 | ECC | IW33 | Display work Order | CPT-AB | DR
GUI | PS1 | ECC | IW23 | Display Notification | CPT-AB | DR
Atlas | n/a | ECC | Search | Search for work in building | CPT-AB | DR

## DMP-DS1 tests
Data Warehouse 2.0 DR Validation Plan (DMP / DS1) |  |  |  |  | Dec 13-14, 2019
Day | Estimated Time | ID | Item | Who | Notes
Friday 12/13 | 23:00 | DW1 | Stop Warehouse Classic Batch Jobs (CRON) | Brandin
|  | DW2 | Disable all DataServices scheduled jobs | Brandin | In the DataServices Management Console
|  | DW3 | Stop all DataServices replication jobs | Brandin | SELECT * FROM WAREUSER_BASE.BATCH_JOB_PARAMETERS WHERE JOB_CODE IN ('JOB_REPL_ROLES','JOB_REPL_MITSIS') AND PARAMETER_CODE = 'PROCESS_CONT_DELTA_LOAD'; UPDATE WAREUSER_BASE.BATCH_JOB_PARAMETERS SET PARAMETER_VALUE = 'N' WHERE JOB_CODE IN ('JOB_REPL_ROLES','JOB_REPL_MITSIS') AND PARAMETER_CODE = 'PROCESS_CONT_DELTA_LOAD';
|  | DW4 | Run Data Validation Queries in DMP | Brandin | Run the “data” validation queries SELECT COUNT(*) FROM WAREUSER_BASE.WHROLES_EXPANDED; SELECT TOP 10 * FROM WAREUSER_BASE.BATCH_JOB_LOG ORDER BY WAREHOUSE_INSERT_TIMESTAMP; SELECT TOP 20 * FROM WAREUSER_BASE.PERSISTED_TABLES_AUDIT_LOG ORDER BY WAREHOUSE_INSERT_TIMESTAMP; SELECT COUNT(*) FROM SAPMIT.HRP1001;
Saturday Post Failover 12/14 | 8AM-10AM | DW5 | Test logging into DataServices Designer & Mgmt Console (DS1) from HEC System | Brandin | Dependent upon DMP-DR Up and Available Test with Enterprise & LDAP Accounts)
|  | DW6 | Check to see if SAP RFC Interface is available | Brandin | In the DataServices Management Console
|  | DW7 | Check each of the HANA SDA Connections is working from DMP-DR | Brandin
|  | DW8 | Try querying a HANA table from SQL Developer - DWPROD via the Oracle DBLink | Brandin | .odbc.ini (vhmitdmpdb.hec.mit.edu) SELECT * FROM WAREUSER_BASE.WHROLES_EXPANDED@HANA_WAREUSER.MIT.EDU;
|  | DW9 | Run DataServices jobs | Brandin | • Disable Copy back to DW PROD for JOB_REPL_HANA_PERSIST • JOB_REPL_HANA_PERSIST (Oracle / HANA) – “NEAR_REAL_TIME” • JOB_REPL_ROLES (Test out replication Agent & Roles Connectivity) • JOB_REPL_POWERFAIDS (SQL Server - Powerfaids) • JOB_SYNC_WC_SDA (Oracle - DWPROD) – “EARLY_LOAD” • JOB_SYNC_COEUS (Oracle - COEUS) • JOB_REPL_MITSIS (Test out replication Agent & MITSIS Connectivity) • JOB_REPL_QUALITY_CONTROL • Confirm emails generated, & entries in HANA tables (BATCH_JOB_LOG & PERSISTED_TABLES_AUDIT_LOG)
|  | DW10 | Run DS Job: • JOB_LOAD_SAP_OBJECTS (ECC / HANA) | Brandin | Dependent upon ABAP Stack availability
Post- Failback to Sterling 12/14 | 1:15PM-2:15PM | DW11 | Test logging into DataServices Designer & Mgmt Console (DS1) from HEC System | Brandin
|  | DW12 | Check to see if SAP RFC Interface is available | Brandin | In the DataServices Management Console
|  | DW13 | Check each of the HANA SDA Connections is working from DMP | Brandin
|  | DW14 | Try querying a HANA table from SQL Developer - DWPROD via the Oracle DBLink | Brandin | odbc.ini (vhmitdmpdb.hec.mit.edu) SELECT * FROM WAREUSER_BASE.WHROLES_EXPANDED@HANA_WAREUSER.MIT.EDU;
|  | DW15 | Run DataServices jobs | Brandin | • JOB_REPL_HANA_PERSIST (Oracle / HANA) – “NEAR_REAL_TIME” • JOB_REPL_ROLES (Test out replication Agent & Roles Connectivity) • JOB_REPL_POWERFAIDS (SQL Server - Powerfaids) • JOB_SYNC_WC_SDA (Oracle - DWPROD) – “EARLY_LOAD” • JOB_SYNC_COEUS (Oracle - COEUS) • JOB_REPL_MITSIS (Test out replication Agent & MITSIS Connectivity) • JOB_REPL_QUALITY_CONTROL • Confirm emails generated, & entries in HANA tables (BATCH_JOB_LOG & PERSISTED_TABLES_AUDIT_LOG)
|  | DW16 | Enable all DataServices scheduled jobs
|  | DW17 | Enable Warehouse Classic Chron Jobs (CRON) | Brandin