## HR-Payroll
Task | Transaction tested | Tester | Backup | Complete* | Comments/Issues
Employee transactions | PA30 & PA40 |  |  |  |  | *S=Sunday & M=Monday
New hire |  | SC rep** | SC rep** | S | Most transactions are processed through APR now so we'll hold anything we can to do on Sunday
Termination |  | SC rep** | SC rep** | S
Supplement |  | SC rep** | SC rep** | S
Salary change |  | SC rep** | SC rep** | S
Promotion |  | SC rep** | SC rep** | S
Hourly Student transactions | SHA
ZHR_HSA_LOG |  | SC rep** | SC rep** | S | validate the transaction can be executed; search for processed transactions
APR - Appt Process Redesign | ZHRAP |  |  |  | DLC users on Monday morning too
Hire |  | SC rep** | SC rep** | S/M
Termination |  | SC rep** | SC rep** | S/M
Supplement |  | SC rep** | SC rep** | S/M
Leave |  | SC rep** | SC rep** | S/M
Change |  | SC rep** | SC rep** | S/M
ePaystub | Atlas About Me | SC rep | SC rep | S
eW-2 | Atlas About Me | SC rep | SC rep | S
direct deposit | PA30 & Atlas About Me | SC rep | SC rep | S
tax withholding | PA30 & Atlas About Me | SC rep | SC rep | S
deductions | ZPYDEDUCT | SC rep | SC rep | S
eSDS | Atlas Salary Distribution
exempt |  | DLC user | DLC user | M
non-exempt; reg & premium |  | DLC user | DLC user | M
grad student RA; stipend & tuition |  | DLC user | DLC user | M
eDACCA | Atlas Salary Distribution
Search by each criteria |  | DLC user | DLC user | M
Certify Q1 20xx DACCA |  | DLC user | DLC user | M
Enter Time Sheet | Atlas Time and Vacation Entry | SC rep |  | S
Approve/Distribute Time Sheets | Atlas Time and Vacation Approval
Approve SC time sheets |  | Darren/Chris | Darren/Chris | S
Gross to Net | Off-cycle work bench or simulation
Exempt |  | Darren | Leslie | S
Non-exempt |  | Darren | Leslie | S
Additional Tax amounts-federal |  | Darren | Leslie | S
Additional Tax amounts -state |  | Darren | Leslie | S
401K max & catchup in Dec |  | Darren | Leslie | S
Time Evaluation | PT60 | Leslie | Darren | S
CDU - exempt | ZPYCDU2 |  |  |  | Run simulations
MAP |  | Darren | Leslie | S
RA tuition |  | Darren | Leslie | S
vacation credits |  | Darren | Leslie | S
off campus |  | Darren | Leslie | S
reduced EB |  | Darren | Leslie | S
Tax Reporter | PU19
Print W2 form |  | Darren | Leslie | S
Print 1099R form |  | Darren | Leslie | S
Print W2C form |  | Darren | Leslie | S
Reports
Missing IT9004 report | ZPYRMISSING9004 | Leslie | Darren | S
Vaca/Sick payout for ZW | S_AHR_61015611 | Leslie | Darren | S | Wage Type Statement
Sick cost out report | ZPYSCOR | Leslie | Darren | S
Appointment error messages | ZPYR_APPT_MESSAGES | Leslie | Darren | S
Glacier New Hire Report | zpy_nra_glac | Marsha |  | M
Student bio feed log | zpy_mitsis_log | Leslie | Darren | S
Payroll Validation Audit | zpy_pay_val_rpt | Darren | Leslie | S
Leave accrual | PT50 | Darren | Leslie | S
Feeds
Lincoln Daily feed - manual | ZHRALE | Darren | ?? | S | see tab Lincoln feed for details
Contacts/Location
Leslie - on site NE49 3-7715
Scott - on site NE49 4-7208
Validators onsite:
Leslie | lesliem
Chris Durham | cfdurham
Validators remote:
Darren | darrenjs |  |  | S | SC Rep may help per DS

## HR
Type | Transaction | Assigned to | Backup | Backup
SAPGUI | Benefits Enrollment | Diane | Meaghan Murray
ESS | Benefits Enrollment | Diane | Meaghan Murray
ESS Personal Info | Home address | Diane | Meaghan Murray
| Ethnicity | Diane | Meaghan Murray
| Work Address | Diane | Meaghan Murray
| Emergency Contact | Diane | Meaghan Murray
| MITAlert (check links only) | Diane | Meaghan Murray
| Eduction History | Diane | Meaghan Murray
Learning Center | Register for training | Diane | Meaghan Murray |  | tasks to be done on EL Tab
| Cancel registration | Diane | Meaghan Murray |  | tasks to be done on EL Tab
Contacts/Location - updated for 2018:
Diane Sullivan - at home |  | 781-325-6591
Meaghan Murray - at home
Mike MacDonald - at home |  | 857-294-1361

## EL
Type | Transaction | Assigned to | Backup | Notes
Learner | Access the Learning Center, both by certificate and username/password login: Jane will test Duo / Melissa will test certificates and touchstone | Mae Jones / Melissa Kavlakli | Melissa Kavlakli | All Atlas transactions will be validated on PC : Melissa (IE & Chrome) and Mac: Mae (Safari & Firefox).
| Create EHS Profile | Mae Jones | Melissa Kavlakli
| View My Courses / Filters / Course Evals | Mae Jones | Melissa Kavlakli
| View Course Catalog / Filters | Mae Jones | Melissa Kavlakli
| Register for a course (verify auto email) if possible a multi-day course | Mae Jones | Melissa Kavlakli
| Cancel a course (verify auto email) | Mae Jones | Melissa Kavlakli
| Prebook a course (verify auto email) | Mae Jones | Melissa Kavlakli
| Adding to a calendar for a classroom course | Mae Jones | Melissa Kavlakli
| Continue a previously started WBT (verify auto email) Cognito Course | Mae Jones | Melissa Kavlakli
| Book into new WBT (verify auto email) | Mae Jones | Melissa Kavlakli
| Cancel a WBT (verify auto email) | Mae Jones | Melissa Kavlakli
| Complete a WBT (verify auto email) | Mae Jones | Melissa Kavlakli
| Enroll & Complete a Learning Bundle | Mae Jones | Melissa Kavlakli
| Complete Ergo Course / Make sure receive email (does not need to be completed during validation testing time frame) | Melissa Kavlakli | Jane White
Instructor | Run Attendee list | Melissa Kavlakli | Jane White
Registrar | Create a course session | Melissa Kavlakli | Jane White
| Book Jane into Course session | Melissa Kavlakli | Jane White
| Cancel Jane in course session | Melissa Kavlakli | Jane White
TNI Admin | Create a Requirement Set | Melissa Kavlakli | Jane White
| Create a Training Group | Melissa Kavlakli | Jane White
| Send Manual Email: Test cc | Melissa Kavlakli | Jane White
| Add Jane as member to Training group (Jane will verify entry via her profile) | Melissa Kavlakli | Jane White
| Run EHS training reports | Melissa Kavlakli | Jane White
| Test the completion uploader | Melissa Kavlakli | Jane White
| Profile administration | Melissa Kavlakli | Jane White
| Training Reconciliation | Melissa Kavlakli | Jane White
| Publish if possible | Melissa Kavlakli | Jane White
Contacts/Location
Jane - at home 978-475-5843
Melissa-at home 617-230-9458
Mae - at home 781-583-8808
Note: | Vaidated by Melissa, added Mae jones for assignments
Validated for 2017 by Melissa, no changes from last year
Updates 11/28/16 by Melissa
updates 11/30/2015 with input from Melissa.

## Lincoln Feed
Lincoln File Steps
Sunday December 10, 2017
Lincoln Files
1. Campus Service Center shuts down Lincoln job on Friday, December 9, any time before 3pm
2. Lincoln files are generated on a regular schedule, at 6pm, but are not loaded because the job is not active.
3. R3-Admin shuts down SAP Dropbox on Friday, December 2 at 4pm
4. R3-Admin will identify the Lincoln file which will arrive in the dropbox after 6pm om Friday, Dec 9. He will then manually copy the Lincoln files from the SAP Dropbox to SAP sapin directory by Sunday at 11 (or when IS&T validations begin, and sends an e-mail message with sequence numbers of the files. Email kushkul, knolet, donovan, lesliem.
5. George will assign userid ZZHRLLFEED01 ownership to Karen so she can process the files
6. Karen will load the files on Sunday, as part of Sunday validation. Files should be available in SAP sapin directory by the Sunday IS&T validation window.
a. Cannot be loaded until 10:30 (or whenever validation go ahead is given from IS&T) and ZZHRLLFEED01 user id has been unlocked
7. Larissa and Karen will review the logs once all files are processed.
8. Karen notifiy Darren to review the logs.
9. Darren will notify Karen when his validations are complete.
8. If successful, Karen will email list that file was successful, and will start up Lincoln job, with Larissa's assistance (in preparation to Monday time files).
9. If not successful, Mark Sprague and Lincoln Basis are on call. IST will email list that file was unsuccessful with details of the errors
a. Larissa and Karen are IS&T point person for issues
10. Karen requests r3accts returns ZZHRLLFEED01 ownership to Laurie19
Note:
Karen will reach out to Mark so he will ask Lincoln Workforce center “to keep the volume light”, i.e. key only essential data on Friday. So hopefully we’ll have only one file on Friday, with not much data; just to make the validation easier/quicker - COMPLETE
Email List
1. Larissa Kushkuley
2. Mark Sprague (msprague@ll.mit.edu)
3. r3-Admin
4. Leslie Wright
5. Karen Nolet
6. Scott Ball
7. Frank Quern
8. Mary Donovan

## Kronos
Kronos File Steps
Sunday December 10, 2017
Kronos Files
1. Mike Sherman will send Kronos file to dropbox (1 person) Friday about 3:30.
2. George will assign userid ZZPYBATCH001 ownership to Karen so she can process the files
3. Karen will load the file on Sunday, as part of Sunday validation. File should be available in SAP sapin directory by the Sunday IS&T validation window.
4. Cannot be loaded until 11:00 (or whenever validation go ahead is given from IS&T) and ZZPYBATCH001 user id has been unlocked
5. Larissa and Karen will review the output.
6. If successful, Karen will email list that file was successful.
7. If not successful, Mike Sherman is on call. IST will email list that file was unsuccessful with details of the errors
a. Larissa and Karen are IS&T point person for issues
8. Karen requests r3accts returns ZZPYBATCH001 ownership to Laurie19
Note:
Mike has been contacted with this plan. Mike's cell # is 617-799-4819
Email List
1. Larissa Kushkuley
2. Mike Sherman
3. r3-Admin
4. Leslie Wright
5. Karen Nolet
6. Scott Ball
7. Frank Quern