## Action Log
SAP - Consolidated Action Log
This document is used by IS&T and Business Process Owners as a guide to validate SAP systems after a database copy, infrastructure update and version upgrade. | [8 empty] | Performed in Environment? | [25 empty] | Dependencies or Timing Issues | Notes
Task # | User/Resp | Area | Dev/ Config / Trx. | DB Copy | Infra Update | Upgrade | R3 Auth | Description | SF3 Refresh |  | SF3 Post SP Application |  | SF8 Refresh |  | SF6 Refresh |  | SF2 Post SP |  | SF2 Refresh |  | SE1 Refresh |  | SH2 Refresh |  | SH2 Post SP Application |  | PS1 Post SP Application |  | SH1 Refresh |  | SH3 |  | SF8 Refresh
[9 empty] | Required Task | Task Status | Required Task | Task Status | Required Task |  | Required Task | Task Status | Required Task | a | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status
1 | Ron Parker | Email Notification | SE38 | Yes | Yes | Yes |  | Program ZBRSMAIL provides a mechanism to modify, replace, append, or write to tables Zemctrl and Zehcat. It is also possible to delete all of the rows of either of the two tables. These tables are used in the email redirection/distribution process. (Download values in ZEHCAT and ZEMCTRL tables) | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
2 | Ron Parker | Email Notification |  | Yes | Yes | Yes |  | Reset table settings for Z_SENDMAIL : 1. delete all entries from ZEMCTRL. 2. replace the contents of ZEHCAT with two rows: HNCAT=<space><space>, CMODE=X, ACTION=X, All other fields=<space>; HNCAT=++, CMODE=X, ACTION=X, All other fields=<space> | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
3 | Ron Parker | Email Notification | Config | Yes | Yes | Yes |  | Redirect e-mail notifications. Transaction SE30 Call View Maintenance. Table: ZEHCAT E-mail control table - handling categories. Action: Redirect Emailto: user@mit.edu or Action: Cancel. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes |  |  | Pre-refresh settings exported and then import after the refresh.
4 | Ron Parker | ITS | SICF |  |  |  |  | Activate /default_host/sap/public/bc/its/mimes | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate | Complete | validate |  | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate
5 | Ron Parker | ITS | SICF |  |  |  |  | 1. SICF 2. /default_host/sap/public/bc/icons 3. Menu >> Service/Host 4. Activate Object S_ICF_ADM Object class AAAB Activity 07 ICF: Name of Virtual Host ' ' ICF: GUID of ICF Service/Alias 000000000000000000000000 ICF: Service/Host/Alias NODE | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate | Complete | validate |  | validate | complete | validate | complete | validate |  | validate | complete | validate |  | validate
6 | Karen Nolet | HR | SE38 | Yes | N/A | N/A | Z_DEV_HR_SCRAMBLE_DATA Z_ALL_HR | Scramble HR data before system is open to others for validation | No | n/a | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes -limited |  | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | Yes |  |  | Do not scramble any environment without confirmation from SP PM - We will not be scrambling MITIDs or KERBIDs in SF2 - SE1 - scramble ssn and bank acct numbers
7 | Lucia Ma | MM | OMJ3 | Yes | Yes | Yes | Z_DEV_ACTION_LOG_LMA | Ensure Inventory printers are not directed to the production environment. Go to IMG: Materials management -> Inventory management and physical inventory -> Output determination -> Printer determination -> Printer determination by plant/storage location. (T_code: OMJ3) Change printers to MRP5. | Yes | complete | No | complete | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
8 | Lucia Ma | MM | SPRO or SM30 (V_024_N) | Yes | Yes | Yes |  | Ensure Purchasing Group printers are not directed to the production environment. Go to IMG: Materials management -> Purchasing -> Messages ->Assign Output Devices to Purchasing Group. Change printers to MRP5. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
9 | Lucia Ma | MM | SM30 | Yes | Yes | Yes |  | Ensure ISP printouts are not directed to the production environment. Transaction SM30. Table: ZISPREQ Hit maintain and change printers to MRP5. Also modify USERID, USERPWD and PRINTER in table ZCAPARM. Check the values in ZV_MT_BROAD and ZV_MT_LOFTWARE do not have production values. | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
10 | Lucia Ma | Classification | CT04 |  |  |  | Z#GL:CT04 | Change Facilities IO printer classification characteristic to print to spool MRP5, not a production printer. Looking for "DISTRIBUTION" | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
11 | Lucia Ma | Cross App | SE38 | Yes | Yes | Yes |  | Run Program ZCOC020 | Yes |  | No | n/a | No | n/a | Yes |  | No | n/a | No | n/a | No | n/a | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | No | n/a
12 | Lucia Ma | Workflow | SEWTYPV |  |  |  | Z#AA:WKFLADM | Reactivate all workflow event linkages. (Tcode: SWETYPV) | validate | complete | validate | complete | validate | complete | Yes |  | validate | complete | validate | Complete | validate |  | validate | complete | validate | complete | validate |  | validate | complete | Yes |  | Yes
13 | Lucia Ma | Email Notification | SM30 |  |  |  | Z#EM:02_ZEM0 | Update ZEHCAT table to allow e-mail messages to be sent for commitment posting errors (first time entry into ZEHCAT) also make sure "FA" ~ "FZ" are redirected. Also check EL email redirection (ZHR_EMAIL_AREA, ZHR_EMAIL_PROC which email area 'LSO') | validate | complete | No | n/a | validate | complete | Yes |  | No | n/a | validate | Complete | validate |  | validate | complete | No | n/a | No | n/a | validate | complete | Yes |  | No | n/a |  | Table ZHR_EMAIL_PROC should be restored to its pre-refresh state after the refresh.
14 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | DoF validation: Enter program GBT30FIF and search (do Find in program) for GLL. (There should be none, only GAL.) If GLL is found, then regenerate validation rules from step above. NOTE: the "30" in the program name is based on the client in which the program is run, i.e. change to "25" if the client is 025, etc. Also looking for TEMP_STRUCT-SGTXT in GBT30COJ. | validate | complete | validate | complete | validate | complete | Yes |  | validate | complete | validate | Complete | validate |  | validate | complete | validate | complete | validate |  | validate | complete | Yes |  | Yes
15 | Ron Parker | FI/CO | SE38 | Yes | Yes | Yes |  | Generate validations/substitutions and sets. Run program RGUGBR00 with params: *,*,xxxxxx NOTE: This step should be completed only after all transports have been applied to the system, because transports containing validation rules will overwrite and require regeneration. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
16 | Lucia Ma | FI | SE38 | Yes | Yes | Yes |  | Regenerate FBV1 JV fast entry template: Run RFFAKP01 with parameters program = SAPLF040, application = PRPOS | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
17 | Lucia Ma | CO user exits | CMOD | Yes | Yes | Yes |  | Enter projects COOPA003, COOMKS01, WBSENHA, CATS0002 select "components" with "change" mode, make sure all exits are activated (green dots). If any component is not noted with a green dot, then return to CMOD screen, and deactivate, then reactivate the project, and confirm the project is activated./If deactivated, all users with CMOD need to check theirs as a follow up. | validate | complete | validate | complete | validate | complete | Yes |  | validate | complete | validate | Complete | validate |  | validate | complete | validate | complete | validate |  | validate | complete | Yes |  | Yes
18 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | Run programs RK811XST to convert transaction groups for CO allocations (incl. Business cycles). No parameters necessary. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
19 | E. Prudden | IXOS | OAC3 | Yes | Yes | Yes | Z_DEV_ACTION_LOG_LMA | IXOS Archive Link Setting. Transaction OAC3 Change View "Links for Content Repositories": Overview. (ALSO NEED FOR SPONSORED BILL ARCHIVE KL-10/30/03) If Ron doesn't put a value in there, don't have to modify it (look at the Cont.Rep.ID field and using the pulldown, make sure that the production values are not being referenced). | validate | complete | validate | complete | validate | complete | Yes |  | validate | complete | validate | Complete | validate |  | validate | complete | validate | complete | validate |  | validate | complete | validate |  | Yes
20 | E. Prudden | LO-EDI & HR-EDI | WE20 | Yes | Yes | Yes |  | Change the Receiver Port for Outbound Parameters. Transaction WE20 (Partner Profiles). Double click on "Partner Number" then dobule click on "Outbound Parmtrs". New screen come up. Change the "Receiver Port" under "Outbound Options". To confirm, check table EDP13 (field RCVPOR). | Yes | complete | validate | complete | Yes | complete | Yes |  | validate | complete | Yes | Complete | Yes |  | Yes | complete | validate | complete | No | n/a | Yes | complete | Yes |  | Yes
21 | G. McGrath | HR | SM30 |  |  |  |  | Validate entries in table ZHRRETIREE_PLANS | No | n/a | No | n/a | No | n/a | No |  | No | n/a | validate | Complete | validate |  | No | N/A | Yes | complete | validate |  | No | N/A | No | N/A | No | n/a
22 | G. McGrath / R3-Admin | Payroll | Dev |  |  |  |  | Update signature on check: "Void V Void" in all testing environments via transport. SHOULD NEVER GO TO PS1. Verify by transaction SE78, table Z_TTBT (SF2K927761 HRPP: Void Signiture File) | Yes | complete | validate | complete | Yes | complete | Yes |  | validate | complete | validate | Complete | validate |  | Yes | complete | validate | complete | validate |  | Yes | complete | Yes |  | Yes |  |  | transport SF2K960932
23 | E. Prudden | EHS / TEM | SM37 |  |  |  | IDs: ZZEHSBATCH01 ZZHRTEMBTC01 ZZHRELBTCH01 | 1. Under ID ZZHRTEMBTC01 - set up periodic job PE_CREATE_TEM_ACCESS, for program ZPE_CREATE_USER (no variant), triggered by event Z_TEM_SETUP. 2. Under ID ZZHRELBTCH01 – set up periodic job ZTN_LINCOLN_PI_TRAINEE_FEED, for program ZTN_LINCOLN_PI_TRAINEE_FEED (variant PI_TRAINEE), triggered by event Z_PIT. 3. Under ID ZZEHSBATCH01 – set up periodic job ZEHS_ROLESDB_WA_RELATS, for program ZEHS_ROLESDB_WA_RELATS (variant BATCH), triggered by event Z_ERR. 4. Under ID ZZEHSBATCH01 – set up periodic job ZEHS_SCHED_INCORRECT_EMAIL_JOB, for program ZEHS_SCHED_INCORRECT_EMAIL_JOB (NO variant), triggered by event Z_EHS_INCORRECT_TRAINEE. | No | n/a | No | n/a | Yes | complete | Yes |  | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | validate |  | Yes | complete | Yes |  | Yes |  |  | For SF2 Refresh only ZPE_CREATE_USER need be scheduled.
24 | G. McGrath | Payroll | PE01 |  |  |  |  | If refreshing a test environment determine if the control record should be checked during payrun processing if so comment out check from schema ZIN0. This setting should never be commented out in a production environment. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | No | n/a | Yes | complete | Yes |  | Yes
25 | R. Casey | FI | OB52 or ZFICLOSE |  |  |  | Z_CA_ZFICLOSE_POST_PER_OPN_CLO or Z#GL:OB52 or ID: ZZCAZFICLOSE | Open current FI posting period. Execute the following jobs: - OPEN NEW MONTH FOR MIT COA (USER ZZGLCLOSE001) - PCARD POSTING DATE ROLLOVER (USER ZZPRBATCH001) - SCHEDULE MANAGER VARIANT CUR (USER ZZFISCHDPC01) - RRPPERIOD FLIP (USER ZZAPBATCH001) - FLIP PERIOD ON PARKED SAJV'S (USER ZZGLCLOSE001) | Yes | complete | No | n/a | Yes | complete | Yes |  | No | n/a | validate | Complete | Yes |  | Yes |  | No | n/a | validate |  | Yes |  | Yes |  | Yes |  | Timing Issue in PS1
26 | R3-ADMIN | All | [5 empty] | Dropbox pointed to new test environment (if SF2 point to dev environment) | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | validate | Complete | No | n/a | Yes | N/A | No | n/a | No | n/a | Yes | complete | No | N/A | No | n/a | as needed
27 | G. McGrath | Payroll | SE38 |  |  |  |  | Test BSI 10.0 connection. Execute program RPUBTCU0, select BSI Version 10.0 and execute. Test OC transaction (select a pernr) and verify BSI tax calculation is generated. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | validate |  | Yes | complete | Yes |  | Yes
28 | G. McGrath | Payroll | PU19 |  |  |  |  | Test ADS connection. Execute Test Run of Tax Forms for individual pernrs via transaction PU19. | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | validate |  | Yes | complete | Yes |  | Yes
29 | G. McGrath | HR | SM30 |  |  |  |  | Compare Wage Type table: V_512W_O | No | n/a | Yes | complete | No | n/a | No |  | Yes | complete | Yes | Complete | No | n/a | No | N/A | Yes | complete | Yes |  | No | N/A | No | N/A | No | n/a
30 | Sharon DiLiberto | HR/Feed |  |  |  |  | Z_DEV_S_ACTION_LOG_02_ZUT0 | Check and verify/set ZUTARCHIVECRTL table | Yes | complete | validate | complete | Yes | complete | Yes |  | No | n/a | validate | Complete | validate |  | Yes | complete | validate | complete | No | n/a | Yes | complete | Yes |  | Yes
31 | G. McGrath | Payroll | SM30 |  |  |  |  | Check HR Payroll constant table: V_T511P, V_T511K | No | n/a | Yes | complete | No | n/a | No |  | Yes | complete | Yes | Complete | No | n/a | No | N/A | Yes | complete | Yes |  | No | N/A | Yes |  | Yes |  |  | a transport may be needed to correct the value of NNRCT in table V_T511K
32 | G. McGrath | Payroll | SPRO |  |  |  |  | Check PDF Validity Date for the tax form: V_T5UX7 Forms: HR_F_W2, HR_F_W2C, HR_F_1099R, HR_F_1099RC | No | n/a | Yes | complete | No | n/a | No |  | Yes | complete | Yes | Complete | No | n/a | No | N/A | Yes | complete | Yes |  | No | N/A | Yes |  | Yes
33 | G. McGrath | Payroll | SPRO |  |  |  |  | Check table V_51TA_B to ensure W2 Box 14 custom text changes are preserved. | No | n/a | Yes | complete |  |  |  |  | Yes | complete | Yes | Complete | No | n/a | No | N/A | Yes | complete | Yes |  | No | N/A
34 | R3-ADMIN | Infra-structure | [5 empty] | Turn on the FAX Gateway | Yes | complete | validate | complete | Yes | complete | Yes |  | validate | complete | Yes | Complete | Yes |  | Yes | complete | validate | complete | validate |  | Yes | complete | Yes |  | Yes
35 | R3-ADMIN | Infra-structure | [5 empty] | Establish target systems Operation Mode (work process distributions) | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes
36 | BASIS | HR | PA40 |  |  |  |  | The features generation program, RPUMKG00, to activate generated programs related to HR features. | No | n/a | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | No | n/a | No | N/A | Yes | complete | Yes |  | No | N/A | No | N/A | No | n/a
37 | E. Prudden | TLE EDI | SAP Instance Info |  |  |  |  | In TLE, change the "Application Server" name, the "Gateway Server Name" and the "Host Name" (this action log item is only required for the hardware renewal project) | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | No | n/a |  | SP Proj: see cut-over plan Is this relevant for 2014? No.
38 | R. Casey | FIN |  | Yes | Yes | Yes |  | Execute Trial Balance | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | complete | Yes |  | No | n/a | No | N/A | No | N/A | No | n/a |  | Use for post SP upgrade comparisons
39 | E. Prudden | ECAT Pointers | [5 empty] | Switch ECAT Pointers 1) In the edi subsystem (TLE), for every one of the 50+ vendors, change 2 settings (i.e. in TLE terms, the "interchange reference" and the "application"). 2) The web team needs to change the pointer on their end for the ECAT app | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | obsolete | No | n/a | No | n/a | No | N/A | No | N/A | No | n/a | as needed | make the switch when we switch to the test environment
40 | L. Collier | NRL Notifications |  |  |  |  | Z_NRL_C_ALL_FUNCTIONS | 1. Transaction IL02 • Select all functional locations in NRL Hierarchy. • For each Functional location go to Partner screen (by clicking on partner icon) • Remove existing Partners. • Back • Save. 2. Transaction IE02 • Select all equipment assigned to functional locations in NRL hierarchy • For each equipment item go to partner screen • Remove existing partners • Back • Save 3. Check data • Transaction IE07 • Use Functional location structure selection option for equipment, multiple selection option • Select all nodes of NRL functional locations • List will reflect all equipment in NRL functional locs • In selection screen also make sure that object check box for partners is selected • Run transaction • List display will show all partners assigned to equipment assigned to NRL functional locations • Review and make sure that no one who gets emails in production will get confusion email from QA system (unless necessary for specific test) | Yes | complete | No | n/a | Yes | complete | Yes | hold | No | n/a | Yes | Complete | Yes |  | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes |  | Yes
41 | E. Prudden | Stock Room | OXK1 | N |  | Y |  | Check if screen 9101, 9102, 9103, 9104, 9105, 9106, 9107, 9110, 9111, and 9112 exist in Function Group KACB (ABAP program SAPLKACB). If theses screens are missing, using transaction OXK1 (or report RBKNT001) to generate the screen. To generate screen: from OXK1, go to the menu option Subscreen -> Generate All. To generate the transport request: from OXK1, go to menu option Subscreen -> Transport (pick up the 9xxx screen one by one). | validate | complete | Yes | complete | No | n/a | No | n/a | Yes | complete | Validate | Complete | No | n/a | validate | complete | Yes | complete | validate |  | validate | complete | No | N/A | No | n/a
42 | FLE Team (Bob Casey) | FI | OB52 or ZFICLOSE |  |  |  | ID: ZZGLCLOSE001 | Schedule period end closing jobs – ZFICLOSE Controlling Area SING Variant Controlling Area MIT Variant | No | n/a | No | n/a | No | n/a |  |  | No | n/a | Yes | Complete | No | n/a | No | N/A | No | n/a | No | n/a | No | N/A | No | N/A | No | n/a
43 | L. Kushkuley | [5 empty] | Z_DEV_S_ACTION_LOG_02_ZPY2 | Validate/Update entries in the ZHR_SRV_LINK table | validate | complete | validate | complete | validate | complete |  |  | validate | complete | validate | Complete | validate |  | validate | complete | validate | complete | No | n/a | validate | complete | validate |  | validate
44 | G. Petrowsky/R3-Admin | Infra-structure | [5 empty] | Validate daily id sync is operational ID: ZZROLESFEED Jobs: ZR3_DAILY_MOIRA_&_SAP_ID_SYNC_2 ZR3_EXTID_MAINT | Yes | complete | Yes | complete | Yes | complete |  |  | Yes | complete | Yes | Complete | Yes |  | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes |  | Yes |  |  | ensure operational when SF2 is ever refreshed
45 | Karen Nolet | HR | PA30 |  |  |  |  | Reconnect APR test IDs, R3EDUI01- R3EDUI09, to PERNRs after refresh of test systems SH1, SH2, SH3. Map infotype 0105 SYSID & EMAIL. Change Infotype 0002 name. SysID example: R3edui01 Email example: R3EDUI01@MIT.EDU Name example, Fname: Test user, Lname: R3edui01 | No | n/a | No | n/a | No | n/a |  |  | No | n/a | Yes | Complete | No | n/a | Yes | complete | No | n/a | No | n/a | Yes |  | Yes |  | No | n/a |  | Assignments: 00000852 R3EDUI01 00001034 R3EDUI03 00001155 R3EDUI09 00001294 R3EDUI02 00001568 R3EDUI06 00003725 R3EDUI08 00003812 R3EDUI04 00005572 R3EDUI05 00003825 R3EDUI07 00008057 R3EDUI10
46 | Lucia Ma | EL | SM30 |  |  |  |  | Check email redirection for LSO: two tables (ZHR_EMAIL_PROC with LSO and ZEHCAT with HW) | Yes | complete | validate | complete | Yes | complete |  |  | validate | complete | validate | Complete | validate |  | Yes | complete | validate | complete | No | n/a | Yes | complete | Yes |  | Yes
47 | L. Kushkuley | HR | [5 empty] | Replace the production URLS with the ‘test’ environment URLS in the following two tables: ZHR_NH_TILE_STEP ZHR_EMAIL_PROC New Hire table ZHR_NH_TILE_STEP Verify application URLs are correct, e.g. Benefits Enrollment | Yes | complete | validate | complete | Yes | complete |  |  | validate | complete | validate | Complete | Yes |  | Yes | complete | validate | complete | No | n/a | Yes | complete | Yes |  | Yes |  |  | For SF2 only ZHR_NH_TILE_STEP needs update should be in the table restore.
48 | R3-ADMIN | DW | SM30 |  |  |  |  | Execute only in a non-production environment. Update the following entries in table ZV_MT_WAREHOUSE: FTP value must be set to be identical to FTP_TEST PP value must be set to be identical to PP_TEST | Yes | complete | validate | complete | Yes | complete |  |  | validate | complete | validate | Complete | Yes |  | Yes | complete | validate | complete | No | n/a | Yes | complete |  |  | Yes
49 | Gregg McGrath | PY | SE38 | N |  | Y |  | Display the source code of RPCGET00_FUP0009 using SE38 and validate that the “PROVIDE” after option 3 is the one that is active as shown below. * Modification as of note 454352. * 1) use all records between period begin and end (SAP standard) * PROVIDE * FROM p0009 BETWEEN aper-begda AND aper-endda. * 2) use only records valid on period end * PROVIDE * FROM p0009 BETWEEN aper-endda AND aper-endda. * 3) use only records valid on payment date PROVIDE * FROM p0009 BETWEEN aper-chkdt AND aper-chkdt. | No | n/a | validate | complete | No | n/a |  |  | validate | complete | validate | Complete | No | n/a | No | N/A | validate | complete | validate |  | No | N/A | No | n/a | No | n/a |  | a transport will be required to re-apply a mod to RPCGET00_FUP0009
50 | Ken LeVie | AP | SM30 | Yes |  | Y | Z#CA:TM_ZCA0 | ZCAPARM Proj Group Seq Description Value From: APPYT IP 1 IP ADDRESS ftp.paymode.com To: APPYT IP 1 IP ADDRESS testftp.paymode.com | Yes | complete | No | n/a |  |  |  |  | No | n/a | validate | Complete | Yes |  | Yes | complete | No | n/a | validate |  | Yes | complete
51 | Ken LeVie | AP | SM30 | Yes |  | Y | Z#CA:TM_ZXPD | ZV_MT_AP Value: elink-http4.bankofamerica.com SD3YTHS5 TSTAH9SI | Yes | complete | No | n/a |  |  |  |  | No | n/a | validate | Complete | validate |  | Yes | complete | No | n/a | validate |  | Yes | complete | [5 empty] | SF2: Table restore?
52 | Gregg McGrath | AP/PY | SM30 | N |  | Y |  | Use SM30 to validate entry "%%SAPSCRIPT_MMM_03" in table TTDTG has a value of "Mar" for language "EN" rather than "March". | No | n/a | Yes | complete |  |  |  |  | Yes | complete | validate | Complete | No | n/a | No | N/A | Yes | complete | validate |  | No | N/A
53 | R3-ADMIN |  | SWF5 |  |  |  |  | There is a switch framework setup to allow the enhancement to RH_SFI_SYNCHRONIZE_EMPL_DATA to be enabled. This custom enhancement is attached to both the ZHR_SFSF_ENH business function and ZHR0 package. | No | n/a | No | n/a | [6 empty] | validate | Complete | validate |  | No: TBD; N/A: N/A; No: No; n/a: n/a; No: TBD; N/A: N/A
54 | E. Prudden | Coupa | SM30 | Yes | N/A | N/A |  | In ZCAPARM, change the Coupa URL prefixes to reflect the non-production environment. | Yes | complete | No | n/a |  |  |  |  | No | n/a | validate | Complete | Yes |  | Yes |  | No | n/a | No | n/a | Yes | complete
For SH2, the following ZCAPARM url records should be: | bar: No to n/a
[8 empty] | COUPA BPURL 1 https://mit-dev.coupahost.com/requisition_headers/ | [14 empty] | N/A: complete
COUPA BPURL 2 https://mit-dev.coupahost.com/order_headers/ | bar: No to n/a
COUPA BPURL 3 https://mit-dev.coupahost.com/invoices/ | bar: No to n/a
For SF2, the following ZCAPARM url records should be: | bar: No to n/a
COUPA BPURL 1 https://mit-test.coupahost.com/requisition_headers/ | bar: No to n/a
COUPA BPURL 2 https://mit-test.coupahost.com/order_headers/ | bar: No to n/a
COUPA BPURL 3 https://mit-test.coupahost.com/invoices/ | bar: No to n/a
55 | Eping Wei | All | SA38 | N | N | Y |  | DW Extracts | No | [9 empty] | no |  | No | n/a | No: Yes; No: No; n/a: n/a |  |  | SH2 - post SP upgrades only
57 | Ken Le Vie | AP | [5 empty] | AP Tax Report extract and compare (runtime ~ 60 mins) | No | [9 empty] | no |  | No | n/a | No: Yes; n/a: complete; No: No; n/a: n/a |  |  | SH2 - post SP upgrades only
56 | Mark Prudden | HR | SE38 | N/A | N/A | Yes |  | Execure program RPUPAV00 via SE38 or SA 28 Run with the following selections: County Group: 10 Personnel Number: run for all PERNRS Delimitation Date: use default (current date) | Yes | complete | Execute for 2021 Support Pack only | [11 empty] | No: validate |  | for 2021 only

## scorm refresh
DB Refresh request:
Short description: Refresh Test SCORM database from Production
Click here to view Change Request: CHG0036657
Comments:
Send database refresh request to db-help@mit.edu
The relevant servers are:
scorm-oc11-4-prod-db-1 - Production DB
scorm-ca-prod-db-1 - Production DR DB
scorm-oc11-7-test-db-1 - Test DB
scorm-ca-test-db-1 - Test DR DB
There are no databases on those servers other than the SCORM databases.
Content Files:
The SCORM engine consists of two pieces – the SCORM SQL Database, and the actual web based content files on the file system.
Send web based content sync request to ops-help@mit.edu
Ops needs to copy the web based content files on the file system from prod to dev.
Sync the content of /var/www/html/adminappsts.mit.edu/courses/ on scorm-dev-app.mit.edu from the Production SCORM servers.
example sn request:
INC0106740
Sync from scorm-ca-prod-nfs:/share/ to scorm-nj-test-nfs:/share/.
Email to db-help@mit.edu:
Hello,
In preparation for refreshing our SAP test environment we need the Test SCORM database refreshed as well with a copy of the Production SCORM database (as of eod 10/22 if possible – current if not) by 10/31/2018.
The relevant servers are:
scorm-oc11-4-prod-db-1 Production DB
scorm-ca-prod-db-1 - Production DR DB
scorm-oc11-7-test-db-1 - Test DB
scorm-ca-test-db-1 - Test DR DB
It is my understanding that there are no databases on those servers other than the SCORM databases. If this is incorrect let me know.
Regards,
Email to ops-help.mit.edu:
Hello,
In preparation for refreshing our SAP test environment we have requested a refresh of the SCORM test database; in addition to the db refresh we need the SCORM web based content file system from production copied to the test environment by 10/31/2018. Please coordinate this effort with dba-help which will handle the db refresh.
Sync from scorm-ca-prod-nfs:/share/ to scorm-nj-test-nfs:/share/.
Regards,

## Table Restores
Z1942
ZEHCAT
ZEMCTRL
ZFFPM
ZHR_FEEDREGISTRY
ZHR_SRV_LINK
ZUTARCHIVECRTL
ZCA_MULE_USERS
ZGAP_CENTR_ROLES
ZHRX
ZHR_NH_TILE_STEP
ZCAGROUPS
ZCAPARM | We store the environment specific survey IDs for Qualtrics surveys in the table ZCAPARM
ZHR_NG_TILE
ZHR_NG_TILE_STEP
ZHR_EMAIL_PROC
ZHR_EMAIL_INFTY
ZHR_EMAIL_SUBJEC
ZHRCSPSETTINGS
ZB01 | (the SF2 value is in the KEEP transport – not sure if it’s really needed)
ZUT_TRANS_AUDIT
ZISPREQ