## PS1 Transport List
To PS1 during go-live 12/4/2021 |  |  |  | as of 12/03/2021 1:15pm
Request/Task | Owner | Date | Time | Short Description
Mods (SPAU/SPAU_ENH)
SF3K905903 | REP | 2021-11-03 | 14:44 | R3ADM* PostUpdate SPAU NOTE Resets - 20211021.01
SF3K905905 | RKATKOWS | 2021-11-03 | 14:50 | R3ADM* - Reimpliment OSS 229558 per spau
SF3K905907 | FQUERN | 2021-11-03 | 14:57 | PP: RPCMAUT_USTAX_CALC mod for suppl tax types multi dist cd
SF3K905909 | FQUERN | 2021-11-03 | 14:59 | PP: RPCMASUT_USTAX_INDEP mod for 1099-R processing
SF3K905911 | LKUSHKUL | 2021-11-03 | 15:00 | SPAU: MP000000 DYNP automatic adjustment
SF2K970311 | LMA | 2021-11-03 | 15:02 | SP2021 - SPAU-ENH Enhancement Adjustment
SF2K970313 | EPRUDDEN | 2021-11-03 | 15:03 | SP2021 - SPAU-ENH Enhancement Adjustment
SF2K970302 | MPRUDDEN | 2021-11-03 | 15:04 | SP2021 - SPAU-ENH Enhancement Adjustment (Remove SF Enh)
Pre and Post Update Developments
SF2K970261 | REP | 2021-11-04 | 9:27 | R3ADM* External OS Command "ZUT_FTP_TO_DW"
SF2K970281 | GEORGEP | 2021-11-04 | 9:28 | R3ADM* RT5750582 S_LOG_COM AUTH for FTP_TO_DW (REP
SF2K970123 | LMA | 2021-11-04 | 9:28 | RT 5741888: DW - ZWHFTP
SF2K970072 | EPRUDDEN | 2021-11-04 | 11:07 | RT 5741888: iNFR: RFC_REMOTE_PIPE is not supported by SAP
SF2K970317 | LMA | 2021-11-04 | 11:08 | RT 5741888: iNFR: RFC_REMOTE_PIPE is not supported by SAP 2
SF2K970343 | MPRUDDEN | 2021-11-08 | 8:33 | SP2021: Update IT0015 user exit to account for new IT3430
SF2K969976 | CORNEM | 2021-11-08 | 9:32 | INC0674422 - ADP Code Update - ZADP_PRCHECK_CUST_20210823
SF2K970038 | CORNEM | 2021-11-08 | 9:32 | INC0691190 - ADP Code Update - ZADP_PRCHECK_CUST_20210908 &
SF2K970078 | CORNEM | 2021-11-08 | 9:33 | INC0699716 - ADP Code Update - ZADP_PRCHECK_PROC_20210914 an
SF2K970188 | AGROBLER | 2021-11-08 | 9:33 | INC0699716 - ADP Code Update - ZADP_PRCHECK_PROC_20210914 v2
SF2K970225 | CORNEM | 2021-11-08 | 9:33 | INC0716393 - ADP Code Update - ZADP_PRCHECK_PROC_20211013
SF2K970298 | AGROBLER | 2021-11-08 | 9:34 | INC0722773 - ADP Code Update 20211020
SF2K970283 | ECUNNING | 2021-11-08 | 10:04 | RT5769207 - New Special Pay Program Supplement
SF2K970296 | ECUNNING | 2021-11-08 | 10:05 | 5769207 - HR New Acton Reason Code -Spec Pay Prgm Supp - PDF
SF2K970339 | LMA | 2021-11-09 | 9:02 | RT 5741888: iNFR: RFC_REMOTE_PIPE is not supported by SAP 3
SF2K970321 | LKUSHKUL | 2021-11-09 | 15:37 | WorkPartners Outbound feed: performance improvement
SF2K970356 | REP | 2021-11-10 | 14:22 | R3ADM* External Command ZUT_UNIX_NCFTPPUT update
SF2K970364 | LKUSHKUL | 2021-11-16 | 8:58 | GAP: new rates in the table zgap_dept_pref2
SF2K970315 | AGROBLER | 2021-11-18 | 7:55 | INC0739765 - GAP Pay Increase Utility
SF2K970369 | KBUEGEL | 2021-11-22 | 8:58 | INC0739765 - GAP Pay Increase Utility v1.01
SF2K970372 | KBUEGEL | 2021-11-24 | 7:27 | INC0739765 - GAP Pay Increase Utility v1.02
SF2K970385 | LKUSHKUL | 2021-12-03 | 10:36 | GAP:limit number of returned records | (to be imported after Saturday post support package action log activities)