## Communication & Contacts
Communication
Cutover status messages will be sent to the project team and business validators and posted on the project cutover wiki page beginning at noon on Friday 12/1 through noon on Monday 12/4. The Project Manager or designee will update/send these messages as needed. A conference call number (zoom) is available for check-ins during the weekend and for the Go/No Go call at 1:00pm on Sunday.
Conference Call Line: Zoom
Zoom link will be updated to wiki and added to scheduled project check-in meetings
Project wiki link: | https://wikis.mit.edu/confluence/display/sapscripts/2023+Year+End+SAP+Support+Pack+Project
Responsibilities
Coordinators for the weekend’s activities are listed below. o IS&T is responsible for: § System Update § Action log execution and coordination § User support during production validation § Communication via email and conference call as to whether the update is proceeding as scheduled § Resolve and escalate issues where needed o Business area validation coordinators are responsible for § Coordination of production validation § Notify PM & Functional BSA immediately if any issues are found § Update PM when production validation is completed
Email Lists
sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members
sap-validation-team@mit.edu | All members of validation team plus all members of escalation team
sap-upgrade-core@mit.edu | Support Pack Core Team members
sap-upgrade-steering-committee@mit.edu | Steering Committee members
sapgui-updates@mit.edu | Used to notify specific users who need to upgrade their gui version
ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team
SAP Conntact Information
Name | Phone | Email
Steve Koczur | 610 745-6281 | stephen.koczur@sap.com
Gia Dinh |  | gia.dinh@sap.com
SAP hotline (Ent Cloud Services) | 504 355 1695
Contact Information
Area | Name | Location | Contact Telephone # | Email
IS&T - Project Manager | Kevin Lyons |  | 617-258-6483 | klyons@mit.edu
A/P | John Larkin |  | Refer to online directory | jlarkin@mit.edu
Parking Office for Commuting Benefits applications | Robynn Cruz |  | Refer to online directory | Refer to online directory
Charitable Giving Office | Traci Swartz |  | Refer to online directory | Refer to online directory
VPF | Joe Siniscalchi |  | Refer to online directory | Refer to online directory
VPF | Steve Hoover |  | Refer to online directory | Refer to online directory
VPF | Ross Monaghan |  | Contact PM | rmonagha@mit.edu
VPF – Travel | Kathy McGrath | Off Campus | Contact PM | Refer to online directory
Dept. of Facilities | Bob Leonard | Off Campus | Contact PM | RLEONARD
Dept. of Facilities | Steve Fosher |  | Contact PM | snfosh22@mit.edu
Dept. of Facilities | Lisa St. Croix |  | Contact PM | lstcroix@mit.edu
EHS | Grace Mlady |  | Contact PM | gmlady@mit.edu
EHS | Jessica Van |  | Refer to online directory | jvan@mit.edu
EHS | Suzanne Adams | Off Campus | Contact PM | sma@mit.edu
HR Coordinator | Mike MacDonald | Off Campus | Refer to online directory | mikemacd@mit.edu
HR/Benefits | Jenna Godfrey | Off Campus | Contact PM | godfreyj@mit.edu
EL | Melissa Kavlakli | Off Campus | Contact PM | mjpotter@mit.edu
EL | Jane White | Off Campus | Contact PM | jwc@mit.edu
EL | Mae Jones | Off Campus | Contact PM | maejones@mit.edu
Procurement | Cindy Vye | Off Campus | Contact PM | CI24314
VPF – HR/Payroll | Leslie Wright | Off Campus | Refer to online directory | lesliem@mit.edu
VPF – HR/Payroll | Darren Scartissi | Off Campus | Refer to online directory | darrenjs@mit.edu
IS&T - R3-Admin | George Petrowsky | Off Campus | Refer to online directory | georgep@mit.edu
IS&T - R3-Admin | Ron Parker | Off Campus | Refer to online directory | rep@mit.edu
IS&T - HR Product owner | Frank Quern | Off Campus | Refer to online directory | fquern@mit.edu
IS&T - FLE Product Owner | Bob Casey | Off Campus | Refer to online directory | rcasey@mit.edu
IS&T – Facilities/Parking | Lee Collier | Off Campus | Refer to online directory | lcollier@mit.edu
IS&T – Logistics | Ken Levie | Off Campus | Refer to online directory | levie@mit.edu
IS&T – Log/FIN/EHS Team Coordinator | Bob Casey | Off Campus | Refer to online directory | rcasey@mit.edu
IS&T – Ops | George Gaudette | Off Campus | Refer to online directory | gaudette@mit.edu
IS&T – Ops | Paul Cronin | Off Campus | Refer to online directory | croninp@mit.edu
IS&T - Data warehouse | Warehouse support team | Off Campus | Refer to online directory | warehouse-dev@mit.edu
IS&T – HRP | Gregg McGrath | Off Campus | Refer to online directory | gmcgrath@mit.edu
IS&T – OIS | Olu Brown | Off Campus |  | obrown@mit.edu
IS&T - OIS | Server Operations | Off Campus | 617-775-3302 | Team Line
Monday Morning Coverage
Area | Name | Location | Time | Email
Help Desk | Team | Off Campus | 6:00am
FAC | Lee Collier | Off Campus | 7:30am | lcollier@mit.edu
HRP | Cindy DeSimone | Off Campus | 7:30am | cindyo@mit.edu
R3-Admin | R3 Team | Off Campus | 7:30am | r3-admin@mit.edu
ABAP | Elda Prudden | Off Campus | 7:30am | eprudden@mit.edu
ABAP | Mark Prudden | Off Campus | 7:30am | mprudden@mit.edu
FLE | IS&T SA Team | Off Campus | 8:00am + | administrative-systems@mit.edu
HRP | IS&T SA Team | Off Campus | 8:00am + | hrpay-sppt@mit.edu

## Cutover Task List
# | Date | Time (EST) | Action / Task | Person(s) Responsible | Status | Upon completion send email to: | Comments
Pre-Update Schedule and Processes:
1 |  |  | Schedule review meetings: - R3 Cutover Planning (3-4 weeks prior to cutover) - IS&T Cutover Review (3-4 weeks prior) - IS&T Action Log Review (1-2 weeks prior) - IS&T Transport Review (1 week prior) | Kevin Lyons | Done | n/a
2 |  |  | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team | Done | n/a
3 |  |  | IS&T cutover weekend planning/review meeting. | IS&T-SAP | Done | n/a
4 | Tuesday 11/28/2023 | 12:00 | Transport Review Meeting Final review all issues in RT project queue, transport list, and web components. | IS&T-SAP | Done | n/a
5 | Tuesday 11/28/2023 | 14:00 | Email ops-help with list of web application deployment requests for Sunday morning. (refer to MIT Web Deployment tab for details) | PM ( Kevin Lyons) | Done | klyons@mit.edu | Atlas Giving (Gregg / Frank)
6 | Tuesday 11/28/2023 | By EOD | Submit Atlas Banner Message Request to Atlas Team for 12/1 | Frank Quern | Done | n/a
7 | Tuesday 11/28/2023 | By EOD | Submit Coupa Outage Message Request to Procurement for 12/1 | Leslie Wright/Jeff Rosa | Done | n/a
8 | Tuesday 11/28/2023 | By EOD | Submit Outage/Injury Message to EH&S for Review | Frank Quern | Done | n/a
9 | Tuesday 11/28/2023 | By EOD | Submit Outage Banner Message Request to GAP support | Frank Quern | Done | n/a
10 | Tuesday 11/28/2023 | By 5:00 PM | Send message to MIT-SAP community (including SMART) about upcoming SAP outage. (see project wiki for message draft) | Kevin Lyons | Done | klyons@mit.edu | chk Wiki
11 | Wednesday 11/29/2023 | By 9:00 AM | Post messages on Atlas about upcoming SAP outage. (message can be found on the project wiki cut-over page) | Frank Quern | Done | klyons@mit.edu | Banner id S9
12 | Wednesday 11/29/2023 | By 5:00 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker) | Done | klyons@mit.edu
13 | Wednesday 11/29/2023 | By 5:00 PM | Post message on Coupa web site about upcoming SAP outage. | VPF (Jeff Rosa) | Done | n/a
14 | Wednesday 11/29/2023 | 17:00 | Final Copy of the Production Update Schedule (cutover plan) published to wiki and emailed to Business Contacts and sap-upgrade-core. | Kevin Lyons | Done | klyons@mit.edu
15 | Wednesday 11/29/2023 | 17:00 | PS1: Start Support Pack Preprocessing (uptime) phase | HEC/R3-Admin | Done | klyons@mit.edu
16 | Wednesday 11/29/2023 | 17:00 | PS1: System transport lock (transports not allowed into production) | HEC/R3-Admin | Done | klyons@mit.edu
17 | Wednesday 11/29/2023 | 18:00 | GRC: Start Support Pack Preprocessing (uptime) phase for GRC ACP System | HEC/R3-Admin | Done | klyons@mit.edu
18 | Thursday 11/30/2023 | By 4 PM | Schedule Pre & Post Trial Balance and ZJVP reports to be used by R3-Admin for controlled data comparisons. (Pre-trial balance will run on Friday. Post-trial balance will run on Saturday). Notify R3-Admin (R. Parker) and PM (Kevin Lyons) when jobs have been scheduled. | VPF (Ross Monaghan) VPF (Bob Casey) - | Done | klyons@mit.edu
19 | Thursday 11/30/2023 | By EOD | Create New Hire notification variants for Friday & Saturday suspended runs. For 2023: Program: ZHR_NEWHIRE_NOTIFICATION, variant SP2023: 12/3 Program: ZHR_SUSPENSION_NOTIFICATION, variant SP2023 RE-RUN | Admin Systems (L. Kushkuley via Fire Fighter) | Done | klyons@mit.edu
20 | Thursday 11/30/2023 | By EOD | R3-Admin email message reminding key community members of the upcoming system outage. | R3-Admin (R. Parker) | Done | n/a
21 | Thursday 11/30/2023 | By EOD | Set up job for GAP posting program ZGAPOST to run Monday after go-live. See instructions in doc ‘Set up GAP posting catchup job’, located in Spartans’ (HR-Payroll) Support Packs Test Plans dropbox folder. | Frank / Larissa | Done | klyons@mit.edu | Sunday's job will catch up Fri/Sat posting
22 | Friday 12/1/2023 | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM Monday). | ABAP Team (Eping Lucia Wei) | Done | klyons@mit.edu
23 | Friday 12/1/2023 | By 2 PM | Download Housing work order and Facilities work order lists as back up for Monday Morning | Facilities (Bob Leonard) Lee Collier | Done | klyons@mit.edu
24 | Friday 12/1/2023 | By 3:20 PM | Shift Concur outbound execution from 5:00 pm to 3:20pm (includes Roles DB) | R3-Admin (Qian) | Done | klyons@mit.edu | see R3 Upgrade Tasks spreadsheet
25 | Friday 12/1/2023 | By 3:20 PM | Shift start time of Friday Equifax & CCC jobs to execute at 3:30/3:45 PM rather than 6:00/6:30 PM | Gregg McGrath Johana Reyes | Done | klyons@mit.edu
26 | Friday 12/1/2023 | 3:00PM | Kickoff Coupa requisition integration to run at 3:00PM buytopay-reqs-coupa-to-sap | Bob Casey | Done | klyons@mit.edu | Ops-Help (George Gaudette) to run buytopay-reqs-coupa-to-sap
27 | Friday 12/1/2023 | By 3:30 PM | Suspend weekend MITSIS cron job for the BIO feed: On batchadmin-east-prod-app-1 under the userid as_cron comment out the /sis/mitsis/applications/scripts/GEN/triggerBatch.sh /sis/cron biofeedsJob job. | Ops (G. Gaudette) | Done | klyons@mit.edu
28 | Friday 12/1/2023 | by 5PM | Email Raisa, Hima, and Brandin to bring down DW DB connections | Kevin Lyons | Done | klyons@mit.edu
29 | Friday 12/1/2023 | 4:45PM | Run Workflow and JV Validation Reports for Ross Monaghan · Workflow inbox report (Ross Monaghan) · JV Parked Documents Report (Ross Monaghan) · RFPs (Joannie Edmonds) | VPF (Ross Monaghan) Bob Casey | Done | klyons@mit.edu | covered w/ 35a
30 | Friday 12/1/2023 | 4:45 PM EST | Run SWI5-Workflow Inbox for Ross Monaghan and save results (dropbox) | VPF (Ross Monaghan) Bob Casey | Done | klyons@mit.edu
31 | Friday 12/1/2023 | 18:00 | GRC: MIT Handoff GRC ACP System for Upgrade (downtime activities) | R3-Admin | Done | email list
32 | Friday 12/1/2023 | 6:00 PM | GRC: GRC ACP System Upgrade (downtime activities) (Refer to HEC 2022- GRC (ACP) Upgrade spreadsheet) | HEC | Done | email list
System Isolation:
33 | Friday 12/1/2023 | 4:30 PM (30 Minutes) | Suspend Drop-box processing. | R3 Admin (Qian Kang) | Done | email list | see R3 Upgrade spreadsheet
34 | Friday 12/1/2023 | 16:45 | Disable all mit-coupa-integrations scheduled jobs (Mulesoft) AFTER buytopay-reqs-coupa-to-sap completes | ops (George Gaudette) | Done | email list | Disable all integrations after buytopay-reqs-coupa-to-sap completed. No specific order required when disabling Coupa integrations any longer
35 | Friday 12/1/2023 | 16:45 | Mulesoft - disable all mit-procurement-v2 scheduled jobs smart:batch-cost-objects-to-coupa smart:batch-invoices-to-sap smart:batch-suppliers-to-coupa smart:batch-suppliers-to-coupa-full-sync smart:batch-users-and-approval-groups-to-coupa | ops (George Gaudette) | Done | email list | Email to OPS-HELP@mit.edu
36 | Friday 12/1/2023 | 16:45 | AWS - disable all SMART Coupa AWS jobs including new Coupa SIM AWS job | Application-Support (Tienie Pritchard) | Done | email list | Email to application-support@mit.edu
37 | Friday 12/1/2023 | 16:45 | Mulesoft: Disable mit-merchant-services-v1 integration stripe:batch-payouts-to-sap Poll | Ops (George Gaudette) | Done
38 | Friday 12/1/2023 | 17:00 | Disable the following scheduled jobs (Mulesoft): mit-ebuilder: All mit-hr: All mit-student-appointments: All mit-surveys: All mit-people: Only "clearCaches Poll" mit-parking-integrations-v1: All | ops (G. Gaudette) | Done | email list | - mit-ebuilder - schedules disabled - mit-hr - schedules disabled - mit-student-appointments - schedules disabled - mit-surveys - schedules disabled - mit-parking-integrations-V1 - schedules stopped
39 | Friday 12/1/2023 | 5 PM | Post status when system goes down on project wiki | PM ( Kevin Lyons) | Done | email list
40 | Friday 12/1/2023 | 5 PM | Post System Downtime Message (3 Down) | R3-Admin | Done | email list
41 | Friday 12/1/2023 | 5 PM | Atlas – update banner message for outage (stronger language) indicating SAP is down (including EHS specific message activating their manual reporting of injuries) | Frank Quern | Done | email list | Banner ID C2 (supervisors injury rpt)
42 | Friday 12/1/2023 | 5 – 8:00 PM | Validation Reports (Trial Balance) executed in SAP. • Ron notifies Ross Monaghan via email cc fquern@mit.edu, rcasey@mit.edu that the reports are completed & downloaded to dropbox. * Dropbox (MIT)\2023 Support Pack Validation Reports • Ross Monaghan confirms the receipt of the Trial Balance Report. | R3-Admin (R. Parker) VPF (Ross Monaghan) | Done | email list
43 | Friday 12/1/2023 | 5 – 8:00 PM | Limited activity in PS1. • With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday) • Shift Benefits Feed (WEEKLY SUNDAY CARRIER FEEDS OE) execution from 6 AM Sunday morning to 10 PM Sunday night using the Benefits Batch id ZZHRBENBTC01. • Users locked • Save WT info to internal SAP table | R3-Admin (R. Parker) (G. Petrowsky) | Done | email list
Support Pack Application/HANA upgrade and Processes: [in process]
44 | Friday 12/1/2023 | By 8:00 PM | MIT Handoff to HEC for PS1 Upgrade Processing | R3-Admin | Done | email list
45 | Friday 12/1/2023 | 8:00 PM (~13 hours) | PS1 support pack application (Refer to the HEC 2023 - ERP (PS1) Upgrade 2023 spreadsheet) | HEC | Done | email list
Post Upgrade Schedule and Processes: [in process]
46 | Saturday 12/2/2023 | 9:00 AM (8 hours) | MIT Technical Post Upgrade Processing - Restore WT Table - Many more ... (Refer to MIT Post Processing Task List tab for details) | R3-Admin | Done | email list | GRC steps need to finish (last steps for this task)
47 | Saturday 12/2/2023 | TBD | Execute MIT Web Deployments tasks (refer to MIT Web Deployments worksheet) | Ops (George Gaudette) | Done | email list
48 | Saturday 12/2/2023 | during the above 8 hour window | Validation reports executed (trial balance reports) • R3-ADMIN notifies Ross Monaghan via email, cc to Kevin Lyons, Bob Casey as soon as the trial balance is available for review • R3-ADMIN sends report to Ross Monaghan; unlock his id in PS1 if needed | R3-Admin (R. Parker) VPF Finance (Ross Monaghan) | Done | email list | after transports & generations
49 | Saturday 12/2/2023 | during the above 8 hour window | Restart Open Text application server | Ops (George Gaudette) | N/A |  | needed to be restarted for action log items
50 | Saturday 12/2/2023 | during the above 8 hour window | Restart Atlas/Admin Apps Java apps | Ops (George Gaudette) | Done
51 | Saturday 12/2/2023 | 4:30PM | IS&T Conference Call Check-in Core Team Check in at 4:30 pm on Saturday | Project Manager (Kevin Lyons) | Done | email list
52 | Saturday 12/2/2023 | 4:30 PM - 6:00 PM | MIT IS&T Post Upgrade Action Log - action log team members unlocked - action log execution unique for 2023: - refer to action log task list workbook | Action Log Team (R3, ABAP, SA) | Done | email list
52a | Saturday 12/2/2023 | 18:00 | Update Work Order Numbers Ranges to use new 8* series. Manual update to remove 8* series from SAP table ZMITCORANGES (client 030) | R. Casey | Done | klyons@mit.edu, lcollier@mit.edu | 2023 ONLY, remove next year
52b | Saturday 12/2/2023 | 18:00 | Community Giving - Update table entries | G. McGrath | Done | klyons@mit.edu, fquern@mit.edu | 2023 ONLY, remove next year
53 | Saturday 12/2/2023 | 18:00 | SAP Work Manager and Inventory Manager - Test synch with devices | Lee Collier | Done | email list
54 | Saturday 12/2/2023 | 18:00 | R3: Unlock all operational IDs | R3 | Done | email list
55 | Sunday 12/3/2023 | By 7:30 AM | Post status message on cutover wiki page. Email to sap-validation-team@mit.edu that the validations will start on schedule | PM (Kevin Lyons) | Done | email list
56 | Sunday 12/3/2023 | by 8:30AM | Restart all Atlas applications | Ops (George Gaudette) | N/A | email list
57 | Sunday 12/3/2023 | by 8:30AM | Enable Mulesoft COUPA (Procure to Pay) Integrations (all at once) https://mit-coupa-integrations.cloudhub.io/coupa-integrations/v1 | ops (George Gaudette) | Done | email list | No specific order to enabling Coupa integrations. Enable all at once
58 | Sunday 12/3/2023 | by 8:30AM | Enable Mulesoft MIT Procurement Integrations (all at once) https://mit-procurement-v2-test.us-e1.cloudhub.io//api | ops (George Gaudette) | Done | email list | Email to ops-help@mit.edu
59 | Sunday 12/3/2023 | by 8:30AM | Enable all SMART Coupa AWS jobs, including Coupa SIM AWS job | Application-Support (Tienie Pritchard) | Done | email list | Email to application-support@mit.edu
60 | Sunday 12/3/2023 | by 8:30AM | Mulesoft: Enable mit-merchant-services-v1 integration stripe:batch-payouts-to-sap Poll | Ops (George Gaudette) | Done | email list
61 | Sunday 12/3/2023 | by 8:30AM | Enable the following scheduled jobs (Mulesoft): mit-ebuilder: All mit-hr: All mit-student-appointments: All mit-surveys: All mit-people: Only "clearCaches Poll" mit-parking-integrations-v1: All | ops (G. Gaudette) | Done | email list
62 | Sunday 12/3/2023 | By 8:30 AM (5 Minutes) | Email to ist-sap@mit.edu • List of transports applied and any related issues. • List of jobs shifted in PS1 during cutover | R3-Admin (Rich Katkowski) (George Petrowsky) | Done | email list
63 | Sunday 12/3/2023 | 8:00 | Unlock IS&T Teams (ABAPs, BAs, SAs, DW, GRC / FF ids) | R3-Admin (G. Petrowsky) | Done | email list
64 | Sunday 12/3/2023 | 9:00 | Re-run SWI5 (workflow inbox for users) for rmonagha and compare results with data from the 12/1 execution | Bob Casey | Done | klyons@mit.edu
65 | Sunday 12/3/2023 | 8:30 AM - 10:30 AM | IST SAP Team Validations | All R3, ABAP, BSA, DW ids | Done | email list
66 | Sunday 12/3/2023 | by 10:30am | TB Validation reports validated • Ross Monaghan notifies Kevin Lyons and SAP core team when validation of the trial balance report is complete. | VPF Finance (Ross Monaghan) (Bob Casey) | Done | email list
67 | Sunday 12/3/2023 | by 10:30am | Post status message on cutover wiki page. Email to sap-validation-team@mit.edu that the validation is to start on schedule | PM (Kevin Lyons) | Done | email list
68 | Sunday 12/3/2023 | by 10:30am | Manually execute ZHR_NEWHIRE_NOTIFICATION and ZHR_SUSPENSION_NOTIFICATION with custom variants for Saturday through Batch ID. | HRP BSA (L.Kushkuley) | Done | email list
69 | Sunday 12/3/2023 | 10:30 | Unlock validators (testers) | R3-Admin (G. Petrowsky) | Done | email list
Business Validation Phase
70 | Sunday 12/3/2023 | 10:30AM | email stakeholders (monthly update email) and business validators (sap-validation-team@mit.edu) that testing can start | PM (Kevin Lyons) | Done
71 | Sunday 12/3/2023 | 10:30 AM - 12:30 PM (2 hours) | MIT Business Validation PS1 Data Validations & Transaction processing listed in section of the Validation spreadsheet performed by designated users; Atlas will be available for validation; All servers will be available. | BPOs VPF (Ross Monaghan) IS&T BSAs | In Progress | email list
72 | Sunday 12/3/2023 | 10:30 AM - 12:30 PM (2 hours) | eBuilder expense catch up – validate eBuilder and catchup with ebuilder_catchupInvoicePayments Poll and other polls as necessary | Lee Collier/ George Gaudette/eBuilder team (Jacob Friis, Lee Collier) | Done | email list
73 | Sunday 12/3/2023 | 10:30 AM - 12:30 PM (2 hours) | Review Qualtrics responses not captured during the outage (Run Mulesoft polls etc. as needed to resolve any issues) | Lee Collier/ George Gaudette | Done | email list
74 | Sunday 12/3/2023 | By 12:30 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs IS&T BAs & SAs |  | email list
75 | Sunday 12/3/2023 | 13:00 | Conference Call Check-in Go/No Go conference call Sunday | PM (Kevin Lyons) |  | email list
Go Live
76 | Sunday 12/3/2023 | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu, warehouse@mit.edu) indicating decisions/results. | PM (Kevin Lyons) | N/A | sapbiz@mit.edu email list ist-sap@mit.edu warehouse@mit.edu
77 | Sunday 12/3/2023 | After conf call | Email Raisa, Hima and Brandin to restart DW DB connections | PM (Kevin Lyons) |  | klyons@mit.edu
78 | Sunday 12/3/2023 | 1:30 PM – 2:30 PM | Unlock users (Facilities, SMART) Unlock all users (R3-Admin notifies operations center at 3-1500). At end of unlock send message to ist-sap@mit.edu, update Atlas message. | R3-Admin (George Petrowsky) |  | email list
79 | Sunday 12/3/2023 | 2:30 PM Sunday | Enable Event Driven Jobs in SAP | R3 Admin |  | email list
80 | Sunday 12/3/2023 | 2:30 PM Sunday (5 Minutes) | Enable Drop box | R3 Admin (Qian Kang) |  | email list
81 | Sunday 12/3/2023 | after conf call | Reinstate weekend MITSIS Bio Feed cron job On batchadmin-east-prod-app-1 under the userid as_cron uncomment out the /sis/mitsis/applications/scripts/GEN/triggerBatch.sh /sis/cron biofeedsJob job. | ops (George Gaudette) |  | email list
82 | Sunday 12/3/2023 | check after 10PM run starts | Data Warehouse Job Validation • Eping (Lucia) Wei confirm job validation completion via email to email list, warehouse-dev@mit.edu • Run extracts (10PM & 12AM) | R3-Admin |  | email list
83 | Sunday 12/3/2023 | After conf call | Execute ProCard from Bank of America Feed | ABAP Team (Eping Lucia Wei) |  | email list
84 | Monday morning 12/4/2023 | By 6 AM | Update the 3-down web page & SAPgui message. | R3-Admin (R. Parker) |  | email list
85 | Monday morning 12/4/2023 | By 6 AM | Remove SAP outage message on Coupa webpage. | VPF (Leslie Wright/Jordan Lewis) - Bob Casey |  | email list
86 | Monday morning 12/4/2023 | By 6 AM | Remove Atlas and EHS messages. | Frank Quern |  | email list
87 | Monday morning 12/4/2023 | By 6 AM | Post Atlas Banner Message with link to Known SAP Issues kb article | Frank Quern |  | email list | if needed
88 | Monday morning 12/4/2023 | By 6 AM | Remove GAP Banner message | Frank Quern |  | email list
89 | Monday morning 12/4/2023 | By 6 AM | Validate Atlas and EHS outage messages have been removed (verify in IE, Firefox, Chrome) | HRP BSA (Frank Quern) |  | email list
90 | Monday morning 12/4/2023 | By 6 AM | Email notification to the MIT Community stating the update has been completed and Production is available. | PM (Kevin Lyons) |  | email list
91 | TBD - if needed | 00:01AM EST | DSP Application Software Update (uptime and downtime activities) - refer to HEC 2023-SAP tickets for more information | HEC |  | email list

## R3 Upgrade Tasks
Task ID | Day |  | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
r00 | Monday | PS1 | 2023-11-27 | 9:00 | 2023-11-27 |  | 30 mins | Ron Parker | Ron changes profile adding parameters to default central instance profile N/A 2023 | N/A
r0 | Wednesday | PS1 | 2023-11-29 | 9:00AM | 2023-11-29 | by 5:00 PM | 30 mins | R3 | Pre-upgrade Transports (verify transport numbers) NOT APPLICABLE 2023 | N/A
r1 | Wednesday | PS1 | 2023-11-29 | after 5:00 PM | 2023-11-29 | after 5:00 PM |  | HEC/Ron Parker | locking PS1 development environment,can start after payroll (verify task description). No transports can be imported after this step.
r2 | Wednesday | GRC - ACP | 2023-11-29 | 6:00PM | 2022-11-29 | 6:00PM |  | HEC/Ron Parker | Start SP preprocessing phase (uptime)
r3 | Thursday | PS1 | 2023-11-30 | by 5 PM | 2023-11-30 | by 8PM | N/A | Ron Parker | Save Wage type table (after system is locked)
r4 | Thursday | PS1 | 2023-11-30 | by 5 PM | 2023-11-30 | by 8 PM | N/A | Ron Parker | Snapshoft of Profiles (8 profiles)
r5 | Friday | PS1 | 2023-12-01 | 14:00 | 2023-12-01 | 14:00 |  | George Petrowsky | Stop the Roles to SAP Feed and related User Admin Jobs
r6 |  | PS1 | 2023-12-01 | 14:00 | 2023-12-01 | 14:00 |  | George Petrowsky | Get extracts of the tables updated with User Admin procedures: - USR02 - USRBF2 - AGR_USERS - UST04 - UST10S - Extract all Authorization Definitions ( ZR3_AUTH_MIL_2 )
r7 |  | PS1 | 2023-12-01 | 14:00 | 2023-12-01 | 15:40 | 40 mins | George Petrowsky | Create the 9 files to use to Lock all IDs – about 40 minutes. This will start at 2 PM.
r8 |  | PS1 | 2023-12-01 | 15:00 | 2023-12-01 | 8PM | 2 hours | George Petrowsky | Shift all non-DW jobs to start after 6am on Monday
r9 |  | PS1 | 2023-12-01 | by 3 PM | 2023-12-01 | by 3 PM | 30 mins | Qian Kang | Shift concur outbound execution from 5 to 3:20 Comment out the following on axplor 00 17 * * 1-5 su - sapdbmon -c "/export/home/sapdbmon/bin/rldb_tra_extract.pl /export/home/sapdbmon/script_config/tra_extract2prd.cfg" >>/export/home/sapdbmon/logs/log.travel_extracts_prd 2>&1 Run this, 20 15 * * 1-5 su - sapdbmon -c "/export/home/sapdbmon/bin/rldb_tra_extract.pl /export/home/sapdbmon/script_config/tra_extract2prd.cfg" >>/export/home/sapdbmon/logs/log.travel_extracts_prd 2>&1 |  | on main cutover task list
r10 |  | PS1 | 2023-12-01 | 4:30 PM EDT | 2023-12-01 | 17:00 | 30 minutes | Qian Kang | Suspend dropbox Comment out pull script on sftp02 Comment out pull 1file scripts on sftp02 Suspend this job on axplor 00 22 * * * su - sapdbmon -c "/home/sapdbmon/bin/citi_download.pl /home/sapdbmon/script_config/citi_download.cfg" >>/home/sapdbmon/logs/log.citi_download_prd 2>&1 Suspend this job on axplor 0 07 * * * su - infrp -c "/usr/bridges/prod/infrp/get_warehouse_extracts" >>/usr/bridges/prod/infrp/log.get_warehouse_extracts 2>&1 |  | on main cutover task list
r11 |  | PS1 | 2023-12-01 | 17:00 |  | 17:00 | N/A | Ron Parker | Request SAP bring down application servers, N/A since users locked out | N/A? chk w SAP | scheduled thru ticket with SAP
r12 |  | PS1 | 2023-12-01 | 17:00 |  | 17:00 | 30 minutes | George Petrowsky | Lock Users Force off any IDs still logged on
r13 |  | PS1 | 2023-12-01 | 17:00 |  | 17:00 | 30 minutes | Ron Parker | Disabling Logon groups
r14 |  | PS1 | 2023-12-01 | 17:00 |  | Finish by 8:00 PM | 1 hour | Ron Parker | Run Trial Balance Reports
-- R3 Handoff to SAP HEC team to perform downtime upgrade activities, returned to R3 Saturday morning --
| Saturday |  |  | 9 AM (approx) |  | 6:00 PM EDT | 8 hours | R3 | R3-Admin action log
r15 |  | SAP BTP | 2023-12-02 | 9 AM (approx) | 2023-12-02 | 11:00 | 1-2 hours | Qian | SAP BTP HANA DB Upgrade
r16 |  | PS1 | 2023-12-02 | 9:00 | 2023-12-02 | 11:00 | 2 hours | Ron Parker | Execute SGEN Load Generations - Objects for all PS1 components - Regernerate already existing invalid loads - BSP Applications - Web Dynpros
r17 |  | PS1 | 2023-12-02 | 11:00 | 2023-12-02 | 13:00 | .5 hours | Ron Parker | Restore Wage Types
r18 |  | PS1 | 2023-12-02 | 11:30 | 2023-12-02 | 13:30 | 1 hour | Rich Katkowski | Load Tranport buffer
r19 |  | PS1 | 2023-12-02 | 12:30 | 2023-12-02 | 14:30 | 1 hour | Rich Katkowski | Transports |  | brief pause in process to check adjustments on notes
r20 |  | GRC - ACP | 2023-12-02 | 10:00 | 2023-12-02 | 10:00 | 1.5 hours | Ron Parker | Execute SGEN Load Generations - Objects for all ACP components - Regernerate already existing invalid loads - BSP Applications - Web Dynpros |  | Start time depends on when SAP hands over GRC
r21 |  | GRC - ACP | 2023-12-02 | 11:30 | 2023-12-02 | 12PM | 0.5 hours | Rich Katkowski | Import GRC Transports
r22 |  | GRC - ACP | 2023-12-02 | 12PM | 2023-12-02 | 1PM | 1 hour | Ron Parker | a) Deploy MIMEs (program WDG_MAINTAIN_UR_MIMES) b) Execute restore of GUI Interface Changes, Activation Flag for Function Exits (program RSMODRES) c) Execute transaction SIAC_PUBLISH_ALL_INT (publish services) d) Execute transaction SWU3 (verify Workflow Customizing) e) Execute TCC Servicetools Update (program RTCCTOOL)
r23 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Generate features in client 0 for select transports
r24 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Generate features in client 30 for select transports
r25 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Deploy MIMEs (program WDG_MAINTAIN_UR_MIMES)
r26 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Execute FI-SL XPRA: Generation GLU1, GLU2, FI-SL Programs (program RGZZGLUX)
r27 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Execute update of FI-SL Programs (program RGBCFL00)
r28 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Execute generation of ABAP code for validations/substitutions/rules (program RGUGBR00)
r29 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Execute restore of GUI Interface Changes, Activation Flag for Function Exits (program RSMODRES)
r30 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Execute transaction SIAC_PUBLISH_ALL_INT (publish services)
r31 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Execute transaction SWU3 (verify Workflow Customizing)
r32 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Execute TCC Servicetools Update (program RTCCTOOL)
r33 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Verify SAP Kernel post-update adjustment via Z_SENDMAIL test
r34 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  | 1 hour | Ron Parker | Run Trial Balance Reports -- Batch environment adjustment -- Trial Balance Batch Executions -- Trial Balance Report Extracts and Email notifications |  | on main cutover task list
r35 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | George Petrowsky | User validations
r36 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | George Petrowsky | Roles feed file process
r37 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | BSI Test Connection
r38 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | George Petrowsky | Check/Test Open Text Connectivity
r39 |  | PS1 | 2023-12-02 | 3:30PM | 2023-12-02 |  | 15 min | Rich Katkowski | Point DST to Production (after PS1 transports)
r40 |  | SAP HCC | [5 empty] | Ron Parker | Restart SAP Cloud Connector (HCC)
r41 |  | SAP BTP | [5 empty] | Qian | Restart SAP Agentry and Work Manager and Inventory Manager applications
r42 |  | All | 2023-12-02 |  | 2023-12-02 |  |  | All | Test of infrastucture
r43 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | Rich Katkowski | Validate Adobe form rendering - run fp_check_destination_service - run fp_pdf_test_00 - run fp_test_00 - run fp_test_003 - display W2 form - display W2 form instructions
r44 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | R3 | user maintienance
r45 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | R3 | trusted links validations |  | RFC Connection validation
r46 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | R3 | drop box
r47 |  | ASAPI | 2023-12-02 |  | 2023-12-02 |  |  | Ron Parker | Restart ASAPI servers (production tier)
r48 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | George Petrowsky | Shift back to weekend those jobs that normally occur on weekend
r49 |  | GRC - ACP | 2023-12-02 | see task notes | 2023-12-02 |  | 30 minutes | Sarah Quigley | Run manually PS1 sync job (after trial balance
r50 |  | GRC - ACP | 2023-12-02 | after r51 | 2023-12-02 | 16:00 | 1.50 hours | Sarah Quigley | GRC Validations
r51 |  | PS1 | 2023-12-02 |  | 2023-12-02 |  |  | George Petrowsky | Check that JCO MetaUser and Scorm users are unlocked in PS1: ZZJCOMETA000 (run any JCO app, e.g Disp PO) and ZZADMSCORM01 (open learning center course, e.g. event planning, chk table Z...)
all activities complete by 4:30PM
r52 | Sunday | PS1 | 2023-12-03 |  | 2023-12-03 |  |  | Qian Kang | Enable drop box |  | on main cutover task list
r53 |  | PS1 | 2023-12-03 |  | 2023-12-03 |  |  | R3 | Verify that the system appears to be working as expected a. Execute the User Admin functions b. Check ST22, SM21

## MIT Web Deployments
SAP web components for Dec 1-3 cutover
# | Task description | SN Ticket | Execute | When | Comment
Mulesoft deployments:
Java deployments for:
| Atlas Giving: giving-1.0.17.war | CHG0064949 | George G (Ops) to import at 6p Friday
| Atlas Configuration: atlas-configuration-integration-20231108-565 | CHG0064950 | George G (Ops) to import at 6p Friday
NOTE: new ITS/WDA doman, use https://hecps1web01.mit.edu
| Server Name | Type | Apps | Comment
| atlas-ca-prod-app-1 | Application, DR | Atlas, Atlas Service Center | DR
| atlas-ca-prod-app-2 | Application, DR | Atlas, Atlas Service Center | DR
| atlas-ca-prod-app-3 | Application, DR | Atlas, Atlas Service Center | DR
| atlas-ca-prod-app-4 | Application, DR | Atlas, Atlas Service Center | DR
| atlas-oc11-4-prod-app-1 | Atlas | Atlas, Atlas Service Center
| atlas-oc11-4-prod-app-2 | Atlas | Atlas, Atlas Service Center
| atlas-oc11-4-prod-app-3 | Atlas | Atlas, Atlas Service Center
| atlas-oc11-4-prod-app-4 | Atlas | Atlas, Atlas Service Center
| atlas-ca-prod-db-1 | Database, DR | Oracle DB
| atlas-prod-db-1 | Database | Oracle DB
| admsys-ca-prod-app-1 | Application, DR | jv, newhire, persinfo, events, emp-newhire | DR
| admsys-ca-prod-app-2 | Application, DR | jv, newhire, persinfo, events, emp-newhire | DR
| admsys-ca-prod-app-3 | Application, DR | paystubs, w2, w4, directdeposit, atlas-settings | DR
| admsys-ca-prod-app-4 | Application, DR | paystubs, w2, w4, directdeposit, atlas-settings | DR
| admsys-ca-prod-app-5 | Application, DR | commuting, sap-doc-attach, learning, disabilities, atlas-giving, LMSIntegration | DR
| admsys-ca-prod-app-6 | Application, DR | commuting, sap-doc-attach, learning, disabilities, atlas-giving, LMSIntegration | DR
| admsys-ca-prod-app-7 | Application, DR | vactrac, nimbus, pdfservice, diversity, gapdashboard, vpfforms | DR
| admsys-ca-prod-app-8 | Application, DR | vactrac, nimbus, pdfservice, diversity, gapdashboard, vpfforms | DR
| admsys-ca-prod-app-9 | Application, DR | pfml, newgrad, ipia | DR
| admsys-ca-prod-app-10 | Application, DR | pfml, newgrad, ipia | DR
| admsys-oc11-4-prod-app-1 | Application | jv, newhire, persinfo, events, emp-newhire
| admsys-oc11-4-prod-app-2 | Application | jv, newhire, persinfo, events, emp-newhire
| admsys-oc11-4-prod-app-3 | Application | paystubs, w2, w4, directdeposit, atlas-settings
| admsys-oc11-4-prod-app-4 | Application | paystubs, w2, w4, directdeposit, atlas-settings
| admsys-oc11-4-prod-app-5 | Application | commuting, sap-doc-attach, learning, disabilities, atlas-giving, LMSIntegration
| admsys-oc11-4-prod-app-6 | Application | commuting, sap-doc-attach, learning, disabilities, atlas-giving, LMSIntegration
| admsys-oc11-4-prod-app-7 | Application | vactrac, nimbus, pdfservice, diversity, gapdashboard, vpfforms
| admsys-oc11-4-prod-app-8 | Application | vactrac, nimbus, pdfservice, diversity, gapdashboard, vpfforms
| admsys-oc11-4-prod-app-9 | Application | pfml, newgrad, ipia
| admsys-oc11-4-prod-app-10 | Application | pfml, newgrad, ipia
| aprsys-ca-prod-app-1 | Application, DR | apr-changes, apr-hires, apr-inbox, apr-leaves, apr-supplements, termination | DR
| aprsys-ca-prod-app-2 | Application, DR | apr-changes, apr-hires, apr-inbox, apr-leaves, apr-supplements, termination | DR
| aprsys-oc11-4-prod-app-1 | Application | apr-changes, apr-hires, apr-inbox, apr-leaves, apr-supplements, termination
| aprsys-oc11-4-prod-app-2 | Application | apr-changes, apr-hires, apr-inbox, apr-leaves, apr-supplements, termination
| ehssys-ca-prod-app-1 | Application, DR | injury, inspection, inspection_admin, roomset, settings, sara | DR
| ehssys-ca-prod-app-2 | Application, DR | injury, inspection, inspection_admin, roomset, settings, sara | DR
| ehssys-oc11-4-prod-app-1 | Application | injury, inspection, inspection_admin, roomset, settings, sara
| ehssys-oc11-4-prod-app-2 | Application | injury, inspection, inspection_admin, roomset, settings, sara
| finsys-ca-prod-app-1 | Application, DR | safo, settings001s, po, edacca, rfp, jvsuite, b2pforms | DR
| finsys-ca-prod-app-2 | Application, DR | safo, settings001s, po, edacca, rfp, jvsuite, b2pforms | DR
| finsys-oc11-4-prod-app-1 | Application | safo, settings001s, po, edacca, rfp, jvsuite, b2pforms
| finsys-oc11-4-prod-app-2 | Application | safo, settings001s, po, edacca, rfp, jvsuite, b2pforms
| scorm-ca-prod-app-1 | Application, DR | EngineWebServices, ScormEngineInterface
| scorm-ca-prod-app-2 | Application, DR | EngineWebServices, ScormEngineInterface | DR
| scorm-oc11-prod-app-1 | Application | EngineWebServices, ScormEngineInterface
| scorm-oc11-prod-app-2 | Application | EngineWebServices, ScormEngineInterface
| scorm-ca-prod-db-1 | Database, DR | MySQL database | DR
| scorm-oc11-4-prod-db-1 | Database | MySQL database
| asapis-prod-app-1 | Application | asapis | Not replicated / no DR
| asapis-prod-app-2 | Application | asapis | Not replicated / no DR

## HEC 2023- SAP Tickets
System ID | Description | Status
PS1: | Service Request 6461161 (ERP Production / Application Software Update)
ACP: | Service Request 6274882 (GRC Production / Application Software Update)
HAP: | Service Request 6076482 (OpenText Production / Database Software Update)
DSP: | Service Requests 6472501 and 6472691 ( Adobe Document Services Production / Application Software Update)

## HEC 2023 - ERP (PS1) Upgrade
PS1 System upgrade between 11/29/2023 starting at 5:00 PM EST and 12/2/2023 9:00 AM EST
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
a | [5 empty] | MIT (R3-Admin) | Create Ticket for EHP8 for ERP 6.0 SPS 21 w/HR SP 0124 (Service Request 6461161): Update Application Software. MPID: 2001481534
b | [5 empty] | MIT (R3-Admin) | To confirm in the ticket that preparation steps have been completed including import of OSS note transport SF3K905901
Extraction, Configuration and Check Phases
1 | 2023-11-29 | 17:00 | 2023-12-01 | 17:00 |  | HEC | Extraction, Configuration, Check phases from Software Update Manager Tool
2 | [6 empty] | During Extraction Phase, PS1 XML file is provided, it was created by HEC and validated by MIT
3 | [6 empty] | During Extraction Phase Import SPAM version 7.50/0086 is mandatory
4 | [6 empty] | During configuration phase to configure to use the Standard mode ( Shadow Instance)/Define the parallel Process to be used in the Shadow Instance
5 | [6 empty] | During Configuration Phase (PREP_INTEGRATION/ADJUSTPRP) to provide Transport request provided by MIT N/A will be indicated in the service request ticket.
6 | [6 empty] | HEC To confirm/validate the target version of each ABAP component
Preprocessing Phase
7 | 2023-11-29 | 17:00 | 2023-11-29 | 17:00 | N/A | MIT (R3-Admin) | To confirm with an update in the ticket that HEC can proceed with Preprocessing phase ( lock development environment for any change) - MIT will update in ticket
8 | [5 empty] | HEC | Continue with preprocessing
9 | 2023-12-01 | by 5:00 PM |  |  |  | MIT (R3-Admin) | Redirect ADS from DSP to DST
| 2023-12-01 | 20:00 | 2023-12-01 | 22:00 |  | HEC | End_steps_Preprocessing_phase ( requires about 2 hrs.)
10 | [6 empty] | Suspend batch jobs
11 | [6 empty] | Logoff all users from Central Instance
12 | [6 empty] | Create full backup of installation directory /usr/sap/PS1/ including SUM directory
13 | [6 empty] | Create Full Backup of HANA database
14 | [6 empty] | Stop HANA replication to HA node and DR site (Request through Software Update Manager Tool)
Execution and Post Processing Phase
15 | 2023-12-01 | 22:00 | 2023-12-02 | 9:00 |  | HEC | Execution Phase ( to run for about 7 hrs.)
16 | [6 empty] | after above step is completed, Execute a new HANA full backup ( 1 hr.)
17 | [5 empty] | HEC | Post-Processing phase ( 1 hr.)
18 | [6 empty] | Also during post-processing phase, manual task request to Start Suspended Jobs, we will not perform it, as agreed MIT will take care of this task later on
19 | [6 empty] | HANA Replication will be re-enable during Post-processing phase
20 | [6 empty] | HEC system health checks(monitoring tools, integration tools, PS1 system health)
System Handover
21 | 2023-12-02 | by 9:00:00 AM |  |  |  | HEC | Handover PS1 Upgraded System to MIT
22 | [5 empty] | MIT (R3-Admin) | Perform Post-Upgrade tasks in PS1
?? | [6 empty] | Discuss Additional supporting backups post-upgrade
Special note: For Central Instance and Application intances in the DR site, no further action is needed due to the fact we have snap-mirror in place for the installation directory

## HEC 2023 - GRC (ACP) Upgrade
ACP System upgrade between 11/29 starting at 6:00 PM EDT and 12/2 9:00 AM EST
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
a | [5 empty] | MIT (R3-Admin) | Create Ticket for NetWeaver 7.52 SPS 13 w/Access Control 12.0 SPS 22 (Service Request 6274882). Update Application Software. MPID 2001483602
b | [5 empty] | MIT (R3-Admin) | To confirm in the ticket that preparation steps have been completed in OSS note
Extraction, Configuration and Check Phases
1 | 2023-11-29 | 18:00 | 2023-12-01 | 17:00 |  | HEC | Extraction, Configuration, Check phases from Software Update Manager Tool (Preprocessing including, development lock, can start after the completion Extraction, Configuration and Check phases).
2 | [6 empty] | During Extraction Phase, PS1 XML file is provided, it was created by HEC and validated by MIT
3 | [6 empty] | During Extraction Phase Import SPAM version 7.52/0086 is mandatory
4 | [6 empty] | During configuration phase to configure to use the Standard mode ( Shadow Instance)/Define the parallel Process to be used in the Shadow Instance
5 | [6 empty] | During Configuration Phase (PREP_INTEGRATION/ADJUSTPRP) to provide Transport request provided by MIT (N/A) will be indicated in the service request ticket.
6 | [6 empty] | HEC To confirm/validate the target version of each ABAP component
Preprocessing Phase
7 | 2023-11-29 | 18:00 | 2023-12-01 | 17:00 | N/A | HEC | Can proceed upon completion of the Extraction, Configuration and Check Phases
8 | 2023-12-01 | 17:00 | 2023-12-01 | 17:30 |  | MIT (R3-Admin) | Lock users
9 | 2023-12-01 | 18:00 | 2023-12-01 | 20:00 |  | HEC | End_steps_Preprocessing_phase ( requires about 2 hrs.)
10 | [6 empty] | Suspend batch jobs
11 | [6 empty] | Logoff all users from Central Instance
12 | [6 empty] | Create full backup of intallation directory /usr/sap/PS1/ including SUM directory
13 | [6 empty] | Create Full Backup of ASE database
14 | [6 empty] | Stop DB replication to HA node and DR site (Request through Software Update Manager Tool)
Execution and Post Processing Phase
15 | 2023-12-01 | 20:00 | 2023-12-02 | 8:00 | 12 hours | HEC | Execution Phase ( to run for about 7 hrs.)
16 | [6 empty] | after above step is completed, Execute a new DB full backup ( 1 hr.)
17 | [5 empty] | HEC | Post-Processing phase ( 1 hr.)
18 | [6 empty] | Also during post-processing phase, manual task request to Start Suspended Jobs, we will not perform it, as agreed MIT will take care of this task later on
19 | [6 empty] | DB Replication will be re-enable during Post-processing phase
20 | [5 empty] | HEC | Additonal Manual task after SUM process
21 | [6 empty] | Check on software components
22 | [6 empty] | HEC system health checks(monitoring tools, integration tools, ACP system health)
System Handover
23 | 2023-12-02 | 9:00 |  |  |  | HEC | Handover Upgraded ACP System to MIT
[6 empty] | MIT (R3-Admin) | Perform Post-Upgrade tasks in ACP
Special note: For Central Instance and Application intances in the DR site, no further action is needed due to the fact we have snap-mirror in place for the installation directory

## GRC (ACP) Upgrade
ACP System Support Package update between 06:00 PM on 11/29/2023 and 08:00 AM on 12/2/2023 | [5 empty] | Timezone: US Eastern
Task ID | Start Date | Time | End Date | Time | Duration | Responsible | Task description | Status
1 |  |  |  |  | N/A | MIT | Create ticket for ACP Upgrade downtime window 12/1/2022 starting at 06:00 PM and ending by 12/2/2022 08:00 AM HEC TICKET: Service Request 6274882: Update Application Software.
2 | 2023-11-29 | 18:00 | 2023-12-02 | 8:00 |  | HEC | ACP Upgrade (62 Hour Window)
3 | 2023-11-29 | 18:00 | 2023-12-01 | 17:00 |  | HEC | Execution phase preparations (uptime)
4 | 2023-12-01 | 18:00 | 2023-12-02 | 6:00 | 12 hours | HEC | Execution & post processing phases (downtime)
5 | 2023-12-02 | 6:00 | 2023-12-02 | 8:00 | 2 hours | HEC | HEC system health checks(monitoring tools, integration tools, ACP system health)
Date
| 2023-11-29 | by 5:30 PM |  |  |  | squigley | Back up copies of mitigating control assignments and the rule set in ACP.
| 2023-11-29 | by 5:30 PM |  |  |  | squigley | Ensure all Firefighter logs have been approved in ACP.
Saturday
| Saturday |  |  |  |  | Tester | Test description |  | Results | Comments
[6 empty] | squigley | Dashboard Reports: Access Rule Library Mitigating Control Library Risk Violations User Analysis Role Analysis Violations Comparisons
[6 empty] | squigley | User Level RA Report for for VPF user groups and IS&T custom groups
[6 empty] | squigley | User Level simulation, adding a role to a user
Role level simulation, adding a transaction to a role
[6 empty] | squigley | Firefighter log reports
[6 empty] | squigley | Repository Object Sync job
[6 empty] | squigley | Firefighter test - Log into ACP--> PS1, run several transactions
[6 empty] | squigley | Run Firefighter log sync job
[6 empty] | rep | Firefighter Controller - Return Firefighter log to Firefighter for additional information. Ensure Touchstone authentication is active.
[6 empty] | squigley | Firefighter returns log with additional information requested. Ensure Touchstone authentication is active.
[6 empty] | rep | Approve log
[6 empty] | squigley | Run Repository Object Sync job in GRP.
[6 empty] | georgep | Roles Database user simulation test with GRC
[6 empty] | squigley | Validate selection of ruleset entries by running a textpad comparison with backed up files
[6 empty] | squigley | Validate mitigating control entries by running a textpad comparison with backed up file

## SAP Mobile Cutover Steps
2023 Plan
Step | Day | Date | Description | Answer/Note | Point of Contact | Status
1 |  | TBD | Will IPA be compatible with iOS16 and iOS17 | Not required for 2023 | Lee Collier | Not Required
2 |  | TBD | Will we need to update the APK on the Inventory Device | Not required for 2023 | Lee Collier | Not Required
3 |  | TBD | Lee needs to have an inventory device by 10/26 for testing | Lee has Zebra Device | Stephen Fosher | Completed
4 |  | TBD | Distribute new IPA files to business testers (not needed) | Not applicable for 2023 | Evora | Not Required
4 |  | TBD | Identify personnel on call (e.g. Evora IT) |  | Lee Collier | Completed
6 | 11/26 to 12/1 |  | upgrade to iOS 17 Should be completed before SP weekend - Validate steps needed on iPad (re-enter iTunes password - NO, reboot iPad - YES (by the iPad) , reset Agentry - NO) | Not in scope | Mike Sherman | Handled later by DOF IT
5 | TUE | 2023-11-28 | Lee to send reminder about on call to Evora IT |  | Lee Collier | Completed
8 | THR | 2023-11-29 | 100% Online Support - no need for Bob Leonard to book E19 Conference Room for Monday Support | Support will be remote | Bob Leonard | Not Required
6 | THR | 2023-11-29 | Bob Leonard will send a Communication to Facilities employees that the SAP system will be down for SAP Support Pack go live. Communicate to the mobile community what (SAP Support Packs) is happening. |  | Bob Leonard
7 | FRI | 2023-12-01 | Send out communication to 2nd shift, 3rd shift, custodial, operations center. Verify no weekend work for current iPad users, Mobile users down at 5:00 PM official, GUI users down at 5:00 pm. Coordinate with the Operations Center and off shift supervisors. Use manual shop papers. |  | Bob Leonard
11 |  |  | Mike Sherman to have current production IPA ready for backup/recovery purposes | Not required for 2023 | Mike Sherman | Not Required
8 | FRI | 2023-12-01 | No dependency on Month End or Year End activities | No dependencies | Lisa St. Croix | Completed
9 | FRI (or earlier) | 2023-12-01 | Bob will save all Facilities and Housing work orders. Bob will send email to Kevin Lyons and Frank Quern (cc Lee Collier) |  | Bob Leonard
14 |  |  | Distribute new IPA files to business testers | Not required for 2023 | Mike Sherman | Not Required
11 | SAT | 2023-12-02 | Unlock lcollier to allow the execution of an iPad sync |  | R3 admin
12 | SAT | 12/2 by 5:30pm | Validate that SMP mobile server is up |  | Lee Collier
13 | SAT | 12/2 by 5:30pm | Verify whether a reset of agentry client is necessary - send email to cosmos of what is found |  | Lee Collier
14 | SAT | 12/2 by 5:30 pm | Evora needs to be available Saturday/Sunday |  | Evora
15 | SAT | 12/2 by 5:30pm | execute SMP sync |  | Lee Collier
16 | SAT | 12/2 by 5:30pm | Sync with iPad and inventory device |  | Lee Collier
17 | SUN | 12/3 10:30 AM | Mobile validations in production by business Validate steps needed on iPad (re-enter iTunes password - NO, reboot iPad - NO, reset Agentry - YES). Bob will validate iOS16 and iOS17 |  | Bob Leonard, Mike Sherman
18 | SUN | 12/3 10:30 AM | Stephen Fosher to do cutover validation against inventory manager |  | Stephen Fosher
24 | SUN |  | If Bob Leonard Passes testing. Use Jamfpro to push new IPA files to mobile users (work manager reset required?) - Verify steps needed to be executed by end users on iPad (e.g. re-enter iTunes password - NO, reboot iPad - NO, reset IPA - YES) | Not required for 2023 | Mike Sherman | Not required
25 | SUN | 2020-12-03 | Mike Sherman will Communicate new IPA being deployed to Cosmos2030, support pack PM, frank quern, 2nd, 3rd shifts, and operations center | Not required for 2023 | Mike Sherman | Not required
19 | SUN | 12/3 After 1PM Conf Call | Communication will be sent that everything is all clear to Cosmos2030, Kevin Lyons, Frank Quern, 2nd , 3rd shifts, custodial, and operations center |  | Bob Leoanrd
20 | MON | 2023-12-04 | Execute backup plan for mobile and/or SAP cutover fails - Shop Papers |  | Lisa St. Croix
21 | MON | 2023-12-04 | 6:30 am 100% remote support |  | Bob Leonard/Lee Collier
22 | MON | 2023-12-04 | In case there is an issue: Notify community successful (or need for backup plan) |  | Bob Leonard

## Escalation Path
Escalation Path
If an issue is found, please contact Kevin Lyons AND the Escalation Support Team person for your area immediately. The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall. If the problem cannot be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Olu Broan will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.
All people listed below must ensure that they can be reached on Sunday November 24th
Functional Malfunction(s)
Ross Monaghan | Business Process Owner (VPF FAR Team) / Weekend Coordinator
Mike MacDonald | Business Process Owner (HR) / Weekend Coordinator
Melissa Kavlakli | Business Process Owner (EL) / Weekend Coordinator
Leslie Wright | Business Process Owner (Payroll) / Weekend Coordinator
Bob Leonard | Business Process Owner (Facilities) / Weekend Coordinator
Jessica Van | Business Process Owner (EH&S) / Weekend Coordinator
John Larkin | Business Process Owner (Accounts Payable) / Weekend Coordinator
Catastrophic Malfunction
Kevin Lyons | Project Manager
Mark Silis | Vice President, IS&T
Eamon Kearns | Sr. Director, IS&T
Olu Brown | Director, IS&T
Ron Parker | Manager, R3 Admin
Stephen Koczur | SAP HEC
Gia Dinh | SAP Basis
Escalation Support Team
Bob Casey | FLE PO
Frank Quern | HRP PO
Kevin Lyons | Project Manager
George Petrowsky | R3 Authorizations
Rich Katkowski | Scrum Master
Lee Collier | Facilities PO
Lisa Robinson | Scum Master
Gregg McGrath | Scrum Master
Ron Parker | Basis PO
Faith Hill | Data Warehouse Team
Brandin Tumeinski | Data Warehouse Team

## Validation
Production Validation
Production Validation will occur in NE49, W92, N52 and remotely. Validation is scheduled to start at 10:30 AM, however, please check the your email or the cutover page for the status of the cutover before coming into the office or starting to test remotely. The message will be updated by 9:30 AM if there are potential delays and by 10:30 AM if testing can start. Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.
Kevin Lyons will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 3. Kevin will be responsible for the following activities: o Coordinating telephone message, emails with changes / updates o Escalating issues o Communicating validation results o Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday
Transaction Information | Description | Person(s) Responsible | Comments
Report Testing | Run a trial balance | R3-Admin/TBD | Trial Balance Report validation. Ron Parker will email Ross Monaghan (rmonagha), Bob Casey, and Kevin Lyons when the reports have finished processing. Ross will notify Kevinvia telephone/email when validation is complete (Sunday morning). Kevin will follow up with an email to the following:sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu
IS&T Action Log |  | Admin Systems/Tech Services | IS&T executes the PS1 section of the action log. Each IS&T team member will notify the action log team when his/her steps are complete. Kevin will follow up with an email to the following lists when action log is complete. sap-validation-team@mit.edu, sap-upgrade-core@mit.edu
SAP GUI/Atlas | Refer to FLE validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Kevinwill be notified by test coordinator for each area when testing for the area is complete. Kevin will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu
SAP GUI/Atlas ESS/EL | Refer to HRP validation plan on project wiki’s cut-over page | See PS1 Validation list | The noted individuals will test/validate the transactions identifed in the validation test plan located on the project wiki cutover plan page. Kevin will be notified by test coordinator for each area when testing for the area is complete. Kevin will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu

## BSI Upgrade Tasks
Task ID | Date | Time | Duration | Responsible | Task description | Status | comments
Upgrade will be performed post cutover weekend