## HR-Payroll
Task | Transaction tested | Tester | Backup | Complete* | Comments/Issues
Employee transactions | PA30 & PA40 |  |  |  |  | *S=Sunday & M=Monday
New hire |  | SC rep** | SC rep** | S | Most transactions are processed through APR now so we'll hold anything we can to do on Sunday
Termination |  | SC rep** | SC rep** | S
Supplement |  | SC rep** | SC rep** | S
Salary change |  | SC rep** | SC rep** | S
Promotion |  | SC rep** | SC rep** | S
Hourly Student transactions | SHA
ZHR_HSA_LOG |  | SC rep** | SC rep** | S | validate the transaction can be executed; search for processed transactions
APR - Appt Process Redesign | ZHRAP |  |  |  | DLC users on Monday morning too
Hire |  | SC rep** | SC rep** | S/M
Termination |  | SC rep** | SC rep** | S/M
Supplement |  | SC rep** | SC rep** | S/M
Leave |  | SC rep** | SC rep** | S/M
Change |  | SC rep** | SC rep** | S/M
ePaystub | Atlas About Me | SC rep | SC rep | S
eW-2 | Atlas About Me | SC rep | SC rep | S
direct deposit | PA30 & Atlas About Me | SC rep | SC rep | S
tax withholding | PA30 & Atlas About Me | SC rep | SC rep | S
deductions | ZPYDEDUCT | SC rep | SC rep | S
eSDS | Atlas Salary Distribution
exempt |  | DLC user | DLC user | M
non-exempt; reg & premium |  | DLC user | DLC user | M
grad student RA; stipend & tuition |  | DLC user | DLC user | M
eDACCA | Atlas Salary Distribution
Search by each criteria |  | DLC user | DLC user | M
Certify Q1 20xx DACCA |  | DLC user | DLC user | M
Enter Time Sheet | Atlas Time and Vacation Entry | SC rep |  | S
Approve/Distribute Time Sheets | Atlas Time and Vacation Approval
Approve SC time sheets |  | Darren/Chris | Darren/Chris | S
Gross to Net | Off-cycle work bench or simulation
Exempt |  | Darren | Leslie | S
Non-exempt |  | Darren | Leslie | S
Additional Tax amounts-federal |  | Darren | Leslie | S
Additional Tax amounts -state |  | Darren | Leslie | S
401K max & catchup in Dec |  | Darren | Leslie | S
Time Evaluation | PT60 | Leslie | Darren | S
CDU - exempt | ZPYCDU2 |  |  |  | Run simulations
MAP |  | Darren | Leslie | S
RA tuition |  | Darren | Leslie | S
vacation credits |  | Darren | Leslie | S
off campus |  | Darren | Leslie | S
reduced EB |  | Darren | Leslie | S
Tax Reporter | PU19
Print W2 form |  | Darren | Leslie | S
Print 1099R form |  | Darren | Leslie | S
Print W2C form |  | Darren | Leslie | S
Reports
Missing IT9004 report | ZPYRMISSING9004 | Leslie | Darren | S
Vaca/Sick payout for ZW | S_AHR_61015611 | Leslie | Darren | S | Wage Type Statement
Sick cost out report | ZPYSCOR | Leslie | Darren | S
Appointment error messages | ZPYR_APPT_MESSAGES | Leslie | Darren | S
Student bio feed log | zpy_mitsis_log | Leslie | Darren | S
Payroll Validation Audit | zpy_pay_val_rpt | Darren | Leslie | S
Leave accrual | PT50 | Darren | Leslie | S
Feeds
Lincoln Daily feed - manual | ZHRALE | Darren | ?? | S | see tab Lincoln feed for details
Contacts/Location
Validators onsite:
Validators remote:
Darren Scartissi | darrenjs |  |  | S | SC Rep may help per DS
Leslie Wright | lesliem

## HR
Location | Type | Transaction | Assigned to | Backup | Pass/ Fail | Notes
SAPGUI | Life Events (0378) | Benefits Enrollment | Jenna Godfrey | Cari Angellotti |  | As this is production, each year we typically partner with benefits to have them hold on to a few life event forms to be processed ASAP on Monday morning following the update.
| Total Comp Report | Process w/o sending | Jenna Godfrey | Meaghan Murray |  | Benefits FF Role Needed
Atlas/ About Me | MITAlert | Check links only | Jenna Godfrey | Meaghan Murray
| Check in on your 401k | Check links only | Jenna Godfrey | Meaghan Murray
| Your Total Comp Statement | Check links only | Jenna Godfrey | Meaghan Murray
| My Profile/ Personal Information | Home address | Jenna Godfrey | Meaghan Murray
|  | Directory Information | Jenna Godfrey | Meaghan Murray
|  | Work Address | Jenna Godfrey | Meaghan Murray
|  | Ethnicity | Jenna Godfrey | Meaghan Murray
|  | Disability Status | Jenna Godfrey | Meaghan Murray
|  | Emergency Contact | Jenna Godfrey | Meaghan Murray
|  | Eduction History | Jenna Godfrey | Meaghan Murray
| Benefits/ View Your Health and Insurance Benefits | Check links only | Jenna Godfrey | Meaghan Murray
| Benefits/ Initial Benefits Enrollment | Check links only | Jenna Godfrey | Meaghan Murray
| Benefits/ Employee Tuition Assistance | Check links only | Jenna Godfrey | Meaghan Murray
| Benefits/ Children's College Scholarship | Check links only | Jenna Godfrey | Meaghan Murray
| Benefits/ MIT Childcare Center Scholarship | Check links only | Jenna Godfrey | Meaghan Murray
| Benefits/ Other Benefit Links | Check links only | Jenna Godfrey | Meaghan Murray
Atlas/ Home | Time and Vacation Entry | Sick Time & Leave Reporting
| HRIS Feed Administration | WP Demographic File | Jenna Godfrey | Meaghan Murray |  | Process but do NOT send to WP
| I-9 Administration | Check links only | Jenna Godfrey | Meaghan Murray
| Benefits Administration - Children's College Scholarship Inbox | Check links only | Jenna Godfrey | Meaghan Murray
| Benefits Administration - MIT Childcare Center Scholarship Inbox | Check links only | Jenna Godfrey | Meaghan Murray
Contacts/Location - updated for 2023:
Jenna Godfrey - at home | 518-596-2583
Meaghan Murray - at home
Mike MacDonald - at home

## EL
Type | Transaction | Assigned to | Backup | Notes
Learner | Create EHS Profile | Jane White Dezieck | Melissa Kavlakli | All Atlas transactions will be validated on PC: Melissa (Chrome); Jane on Mac (Firefox).
| View My Courses / Filters / Course Evals | Jane White Dezieck | Melissa Kavlakli
| View Course Catalog / Filters | Jane White Dezieck | Melissa Kavlakli
| Register for a course (verify auto email) if possible a multi-day course | Jane White Dezieck | Melissa Kavlakli
| Cancel a course (verify auto email) | Jane White Dezieck | Melissa Kavlakli
| Prebook a course (verify auto email) | Jane White Dezieck | Melissa Kavlakli
| Adding to a calendar for a classroom course | Jane White Dezieck | Melissa Kavlakli
| Continue a previously started WBT (verify auto email) Cognito Course | Jane White Dezieck | Melissa Kavlakli
| Book into new WBT (verify auto email) | Jane White Dezieck | Melissa Kavlakli
| Cancel a WBT (verify auto email) | Jane White Dezieck | Melissa Kavlakli
| Complete a WBT (verify auto email) | Jane White Dezieck | Melissa Kavlakli
| Enroll & Complete a Learning Bundle | Jane White Dezieck | Melissa Kavlakli
| Run Attendee list | Melissa Kavlakli | Jane White Dezieck
Instructor | Create a course session | Melissa Kavlakli | Jane White Dezieck
Registrar | Book Mae into Course session | Melissa Kavlakli | Jane White Dezieck
| Cancel Mae in course session | Melissa Kavlakli | Jane White Dezieck
| Create a Requirement Set | Melissa Kavlakli | Jane White Dezieck
TNI Admin | Create a Training Group | Melissa Kavlakli | Jane White Dezieck
| Send Manual Email: Test cc | Melissa Kavlakli | Jane White Dezieck
| Add Jane as member to Training group (Jane will verify entry via her profile) | Melissa Kavlakli | Jane White Dezieck
| Run EHS training reports | Melissa Kavlakli | Jane White Dezieck
| Test the completion uploader | Melissa Kavlakli | Jane White Dezieck
| Profile administration | Melissa Kavlakli | Jane White Dezieck
| Training Reconciliation | Melissa Kavlakli | Jane White Dezieck
| Publish if possible | Melissa Kavlakli | Jane White Dezieck
Contacts/Location | Melissa-at home 617-230-9458
Jane - at home 978-475-5843
Note:

## Lincoln Feed
Lincoln File Steps
Sunday 12/8/2024
2024 - will let the automatic process execute; just review logs after execution.
Step | Lincoln Files
0 | Notify LL to sendcampus files by 2:00 pm
1 | Campus Service Center shuts down Lincoln job on Friday, December 1, any time before 3pm (after files have been loaded - take 1/2 hour)
2 | Lincoln files are generated on a regular schedule, at 6pm, but are not loaded because the job is not active. LL should make a change and save it to make sure something will go through.
3 | R3-Admin shuts down SAP Dropbox on Friday, December 6 at 4pm
4 | Wait for Drop box to start. Verify files came in and are processed. Review Logs.
5 | Larissa and Karen will review the logs once all files are processed.
6 | Karen notifiy Darren to review the logs.
7 | Darren will notify Karen when his validations are complete.
7a | If successful, Karen will notify HRP service center that they can start up the Lincoln job.
Note: (none identified at this time)
Email List
1. Larissa Kushkuley
2. Tim Riley
3. r3-Admin
4. Leslie Wright
5. Karen Nolet
6. Frank Quern

## Kronos
Kronos File Steps
Sunday 11/24/2019 (did not execute for 2022; no plan for execution for 2023; no plan for 2024)
Will follow regular processing associated with weekly payroll.
Kronos Files
1. Mike Sherman will send Kronos file to dropbox (1 person) Friday about 3:30.
2. George will assign userid ZZPYBATCH001 ownership to Karen so she can process the files
3. Karen will load the file on Sunday, as part of Sunday validation. File should be available in SAP sapin directory by the Sunday IS&T validation window.
4. Cannot be loaded until 11:00 (or whenever validation go ahead is given from IS&T) and ZZPYBATCH001 user id has been unlocked
5. Larissa and Karen will review the output.
6. If successful, Karen will email list that file was successful.
7. If not successful, Mike Sherman is on call. IST will email list that file was unsuccessful with details of the errors
a. Larissa and Karen are IS&T point person for issues
8. Karen requests r3accts returns ZZPYBATCH001 ownership to LLG
Note:
Mike has been contacted with this plan. Mike's cell # is 617-799-4819
Email List
1. Larissa Kushkuley
2. Mike Sherman
3. r3-Admin
4. Leslie Wright
5. Karen Nolet
6. Frank Quern