## HR-Payroll
Task | Transaction tested | Tester | Backup | Complete* | Comments/Issues
Employee transactions | PA30 & PA40 |  |  |  |  | *S=Sunday & M=Monday
New hire |  | SC rep** | SC rep** | S | Most transactions are processed through APR now so we'll hold anything we can to do on Sunday
Termination |  | SC rep** | SC rep** | S
Supplement |  | SC rep** | SC rep** | S
Salary change |  | SC rep** | SC rep** | S
Promotion |  | SC rep** | SC rep** | S
Hourly Student transactions | SHA
ZHR_HSA_LOG |  | SC rep** | SC rep** | S | validate the transaction can be executed; search for processed transactions
Grad Student transactions | PA30 & PA40
New appointment |  | SC rep** | SC rep** | S | Only if we receive source documents prior to Sunday; if not it will be validated during the week
Change appointment |  | SC rep** | SC rep** | S
Cancel appointment |  | SC rep** | SC rep** | S
Delimit appointment |  | SC rep** | SC rep** | S
APR - Appt Process Redesign | ZHRAP |  |  |  | DLC users on Monday morning too
Hire |  | SC rep** | SC rep** | S/M
Termination |  | SC rep** | SC rep** | S/M
Supplement |  | SC rep** | SC rep** | S/M
Leave |  | SC rep** | SC rep** | S/M
Change |  | SC rep** | SC rep** | S/M
ePaystub | Atlas Self Service | SC rep | SC rep | S
eW-2 | Atlas Self Service | SC rep | SC rep | S
direct deposit | PA30 & Atlas Self Service | SC rep | SC rep | S
tax withholding | PA30 & Atlas Self Service | SC rep | SC rep | S
deductions | ZPYDEDUCT | SC rep | SC rep | S
eSDS | Atlas Manage People
exempt |  | DLC user | DLC user | M
non-exempt; reg & premium |  | DLC user | DLC user | M
grad student RA; stipend & tuition |  | DLC user | DLC user | M
eDACCA | SAPweb
Search by each criteria |  | DLC user | DLC user | M
Certify Q1 20xx DACCA |  | DLC user | DLC user | M
Enter Time Sheet | Atlas Time Entry | SC rep |  | S
Approve/Distribute Time Sheets | Atlas Manage People
Approve SC time sheets |  | Darren/Chris | Darren/Chris | S
SRS Vacation Tracker | Atlas Manage People | DLC user | DLC user | M
Appt Process Redesign | Gui - ZHRAP | SC rep | SC rep | S
Gross to Net | Off-cycle work bench or simulation
Exempt |  | Darren | Leslie | S
Non-exempt |  | Darren | Leslie | S
Additional Tax amounts-federal |  | Darren | Leslie | S
Additional Tax amounts -state |  | Darren | Leslie | S
401K max & catchup in Dec |  | Darren | Leslie | S
Time Evaluation | PT60 | Leslie | Darren | S
CDU - exempt | ZPYCDU2 |  |  |  | Run simulations
MAP |  | Darren | Leslie | S
RA tuition |  | Darren | Leslie | S
vacation credits |  | Darren | Leslie | S
off campus |  | Darren | Leslie | S
reduced EB |  | Darren | Leslie | S
Tax Reporter | PU19
Print W2 form |  | Darren | Leslie | S
Print 1099R form |  | Darren | Leslie | S
Print W2C form |  | Darren | Leslie | S
Reports
Missing IT9004 report | ZPYRMISSING9004 | Leslie | Darren | S
Vaca/Sick payout for ZW | S_AHR_61015611 | Leslie | Darren | S | Wage Type Statement
Sick cost out report | ZPYSCOR | Leslie | Darren | S
Appointment error messages | ZPYR_APPT_MESSAGES | Leslie | Darren | S
Glacier New Hire Report | zpy_nra_glac | Marsha |  | M
Student bio feed log | zpy_mitsis_log | Leslie | Darren | S
Payroll Validation Audit | zpy_pay_val_rpt | Darren | Leslie | S
Leave accrual | PT50 | Darren | Leslie | S
Feeds
Lincoln Daily feed - manual | ZHRALE | Darren | ?? | S | see tab Lincoln feed for details
Contacts/Location
Leslie - on site NE49 3-7715
Scott - on site NE49 4-7208
Validators will be onsite:
Leslie | lesliem
Darren | darrenjs
Chris Durham | cfdurham

## HR
Type | Transaction | Assigned to | Backup | Backup
SAPGUI | Benefits Enrollment | Diane | Mike Peretti | Riley Hart
ESS | Benefits Enrollment | Diane | Mike Peretti | Riley Hart
ESS Personal Info | Home address | Diane | Mike Peretti | Riley Hart
| Ethnicity | Diane | Mike Peretti | Riley Hart
| Work Address | Diane | Mike Peretti | Riley Hart
| Emergency Contact | Diane | Mike Peretti | Riley Hart
| MITAlert (check links only) | Diane | Mike Peretti | Riley Hart
| Eduction History | Diane | Mike Peretti | Riley Hart
Learning Center | Register for training | Diane | Mike Peretti | Riley Hart
| Cancel registration | Diane | Mike Peretti | Riley Hart
Contacts/Location
Diane - at home
Riley - at home
Michael Peretti at home

## EL
Type | Transaction | Assigned to | Backup | Notes
Learner | Access the Learning Center, both by certificate and username/password login: Jane will test Duo / Melissa will test certificates and touchstone | Jane White / Melissa Kavlakli | Melissa Kavlakli | All Atlas transactions will be validated on PC : Melissa (IE & Chrome) and Mac: Jane (Safari & Firefox).
| Create EHS Profile | Jane White | Melissa Kavlakli
| View My Courses / Filters / Course Evals | Jane White | Melissa Kavlakli
| View Course Catalog / Filters | Jane White | Melissa Kavlakli
| Register for a course (verify auto email) if possible a multi-day course | Jane White | Melissa Kavlakli
| Cancel a course (verify auto email) | Jane White | Melissa Kavlakli
| Prebook a course (verify auto email) | Jane White | Melissa Kavlakli
| Adding to a calendar for a classroom course | Jane White | Melissa Kavlakli
| Continue a previously started WBT (verify auto email) Cognito Course | Jane White | Melissa Kavlakli
| Book into new WBT (verify auto email) | Jane White | Melissa Kavlakli
| Cancel a WBT (verify auto email) | Jane White | Melissa Kavlakli
| Complete a WBT (verify auto email) | Jane White | Melissa Kavlakli
| Enroll & Complete a Learning Bundle | Jane White | Melissa Kavlakli
| Complete Ergo Course / Make sure receive email (does not need to be completed during validation testing time frame) | Melissa Kavlakli | Jane White
Instructor | Run Attendee list | Melissa Kavlakli | Jane White
Registrar | Create a course session | Melissa Kavlakli | Jane White
| Book Jane into Course session | Melissa Kavlakli | Jane White
| Cancel Jane in course session | Melissa Kavlakli | Jane White
TNI Admin | Create a Requirement Set | Melissa Kavlakli | Jane White
| Create a Training Group | Melissa Kavlakli | Jane White
| Send Manual Email: Test cc | Melissa Kavlakli | Jane White
| Add Jane as member to Training group (Jane will verify entry via her profile) | Melissa Kavlakli | Jane White
| Run EHS training reports | Melissa Kavlakli | Jane White
| Test the completion uploader | Melissa Kavlakli | Jane White
| Profile administration | Melissa Kavlakli | Jane White
| Training Reconciliation | Melissa Kavlakli | Jane White
| Publish if possible | Melissa Kavlakli | Jane White
Contacts/Location
Jane - at home 978-475-5843
Melissa-at home 617-230-9458
Note: | Updates 11/28/16 by Melissa
updates 11/30/2015 with input from Melissa.

## Lincoln Feed
Lincoln File Steps
Sunday December 4, 2016
Lincoln Files
1. Campus Service Center shuts down Lincoln job on Friday, December 2, any time before 3pm
2. Lincoln files are generated on a regular schedule, at 6pm, but are not loaded because the job is not active.
3. R3-Admin shuts down SAP Dropbox on Friday, December 2 at 4pm
4. R3-Admin will identify the Lincoln file which will arrive in the dropbox after 6pm om Friday, Dec 2. He will then manually copy the Lincoln files from the SAP Dropbox to SAP sapin directory by Sunday at 11 (or when IS&T validations begin, and sends an e-mail message with sequence numbers of the files. Email kushkul, knolet, donovan, lesliem.
5. George will assign userid ZZHRLLFEED01 ownership to Karen so she can process the files
6. Karen will load the files on Sunday, as part of Sunday validation. Files should be available in SAP sapin directory by the Sunday IS&T validation window.
a. Cannot be loaded until 10:30 (or whenever validation go ahead is given from IS&T) and ZZHRLLFEED01 user id has been unlocked
7. Larissa and Karen will review the logs once all files are processed.
8. Karen notifiy Darren to review the logs.
9. Darren will notify Karen when his validations are complete.
8. If successful, Karen will email list that file was successful, and will start up Lincoln job, with Larissa's assistance (in preparation to Monday time files).
9. If not successful, Mark Sprague and Lincoln Basis are on call. IST will email list that file was unsuccessful with details of the errors
a. Larissa and Karen are IS&T point person for issues
10. Karen requests r3accts returns ZZHRLLFEED01 ownership to Laurie19
Note:
Karen will reach out to Mark so he will ask Lincoln Workforce center “to keep the volume light”, i.e. key only essential data on Friday. So hopefully we’ll have only one file on Friday, with not much data; just to make the validation easier/quicker - COMPLETE
Email List
1. Larissa Kushkuley
2. Mark Sprague (msprague@ll.mit.edu)
3. r3-Admin
4. Leslie Wright
5. Karen Nolet
6. Scott Ball
7. Frank Quern
8. Mary Donovan

## Kronos
Kronos File Steps
Sunday December 4, 2016
Kronos Files
1. Mike Sherman will send Kronos file to dropbox (1 person) Friday about 3:30.
2. George will assign userid ZZPYBATCH001 ownership to Karen so she can process the files
3. Karen will load the file on Sunday, as part of Sunday validation. File should be available in SAP sapin directory by the Sunday IS&T validation window.
4. Cannot be loaded until 11:00 (or whenever validation go ahead is given from IS&T) and ZZPYBATCH001 user id has been unlocked
5. Larissa and Karen will review the output.
6. If successful, Karen will email list that file was successful.
7. If not successful, Mike Sherman is on call. IST will email list that file was unsuccessful with details of the errors
a. Larissa and Karen are IS&T point person for issues
8. Karen requests r3accts returns ZZPYBATCH001 ownership to Laurie19
Note:
Mike has been contacted with this plan.
Email List
1. Larissa Kushkuley
2. Mike Sherman
3. r3-Admin
4. Leslie Wright
5. Karen Nolet
6. Scott Ball
7. Frank Quern