## Full SF2 to SH2 Transport List
Full SF2-to-SH2 Transport List |  |  |  | as of 11/29/2023, 1:00pm
Request/Task | Owner | Date | Time | Short Description |  | To PS1 on go-live weekend?
Mods (SPAU/SPAU_ENH)
SF3K906360 | REP | 2023-10-31 | 11:14 | R3ADM* PostUpdate (SF3) SPAU Note Resets |  | Yes | Not in SH1
SF3K906362 | REP | 2023-10-31 | 11:15 | R3ADM* PostUpdate (SF3) SPAU Note Reset |  | Yes | Not in SH1
SF3K906364 | RKATKOWS | 2023-10-31 | 11:17 | R3ADM* OSS 2295568 - Reimplement per SPAU |  | Yes | Not in SH1
SF2K973234 | EPRUDDEN | 2023-10-31 | 11:18 | SP2023: SPAU_ENH |  | Yes | Not in SH1
SF2K973236 | MPRUDDEN | 2023-10-31 | 11:19 | SP2023 SPAU_ENH adjustments to implicit enhancements |  | Yes | Not in SH1
SF2K973232 | LMA | 2023-10-31 | 11:20 | SP2023: SPAU_ENH - 1042 & 1099 |  | Yes | Not in SH1
SF2K973249 | EPRUDDEN | 2023-10-31 | 11:21 | SP2023: SPAU_ENH - z_mm_fill_ekko_prtnr_flds not needed |  | Yes | Not in SH1
Pre and Post Update Developments |  |  |  | yellow=already in ps1 | Seq into PS1
SF2K973267 | BENOO | 2023-10-31 | 17:43 | Open Enrollment 2024 Changes (part 37) | 1 | No
SF2K973274 | BENOO | 2023-11-01 | 7:40 | Open Enrollment 2024 Changes (part 38) | 2 | No
SF2K973284 | JDUDLEYK | 2023-11-01 | 13:10 | PPO+ Plan for retirees | 3 | No
SF2K973277 | BENOO | 2023-11-03 | 10:31 | Open Enrollment 2024 Changes (part 39) | 4 | No
SF2K973288 | REP | 2023-11-03 | 16:09 | R3ADM* FILECMCUST "REJECT_EMPTY_PATH" Setting |  | Yes | Not in SH1
SF2K973297 | BENOO | 2023-11-03 | 18:50 | Open Enrollment 2024 Changes (part 40) | 5 | No
SF2K973290 | JDUDLEYK | 2023-11-07 | 11:55 | Open Enrollment 2024 Changes (part 41) | 6 | No
SF2K973081 | KBUEGEL | 2023-11-08 | 7:43 | INC0973895 - GSU GAP Award Extra Information | 9 | No
SF2K973313 | JDUDLEYK | 2023-11-08 | 8:03 | Open Enrollment - remove aged out dependents | 7 | No
SF2K973315 | KBUEGEL | 2023-11-08 | 13:57 | INC0973895 - GSU GAP Award Extra Information 2 | 11 | No
SF2K973328 | BENOO | 2023-11-09 | 16:00 | Fix OE Year dates oin ZHR_OE_PCCS_APPL_EMAILS | 17 | No
SF2K973331 | LKUSHKUL | 2023-11-13 | 6:33 | GAP: load the rates for aid year 2024 | 16 | No
SF2K973336 | JDUDLEYK | 2023-11-13 | 11:04 | Health Care FSA and HSA limit 2023/4 updates | 8 | No
SF2K973339 | AGROBLER | 2023-11-13 | 13:31 | INC0973895 - grad union changes XXVII | 12 | No
SF2K973148 | KBUEGEL | 2023-11-13 | 16:27 | INC0973895 - GSU GAP Award Extra Information | 10 | No
SF2K973317 | GEORGEP | 2023-11-14 | 9:22 | R3ADM* RT6385523 Role for GSU process for Op ID (VANECKJ | 13 | No
SF2K973325 | GEORGEP | 2023-11-14 | 9:24 | R3ADM* RT6385998 Add Upd IT0035 to GSU Role (KBUEGEL | 14 | No
SF2K973306 | BENOO | 2023-11-14 | 12:06 | New Hire/Open Enrollment 2024 Changes (part 1) |  | No
SF2K973348 | GEORGEP | 2023-11-14 | 14:29 | R3ADM* RT6385998 Add IT0006, Funcs, to GSU Role 3(KBUEGEL | 15 | No
SF2K973323 | KBUEGEL | 2023-11-15 | 13:35 | INC0973895 - GSU GAP Award Extra Information 3 | 18 | No
SF2K973280 | CORNEM | 2023-11-15 | 14:20 | INC1174820 - Updates to the Atlas-Charitable Contributions a |  | Yes | Not in SH1
SF2K973354 | AGROBLER | 2023-11-16 | 10:26 | INC0973895 - New semester linkpass values for grad student | 19 | No
SF2K973321 | KBUEGEL | 2023-11-16 | 10:26 | INC0973895 - GSU GAP Award Extra Information 4 | 20 | No
SF2K973359 | KBUEGEL | 2023-11-16 | 13:05 | INC0973895 - GSU GAP Award Extra Information 5 | 21 | No
SF2K973352 | MPRUDDEN | 2023-11-16 | 14:43 | Fix numeric formatting issues in eSDS View Dollars screen |  | Yes | Not in SH1
SF2K973295 | BENOO | 2023-11-17 | 7:20 | Open Enrollment 2024 - Benefit Plan Option text chngs (6) |  | No
SF2K973361 | BENOO | 2023-11-17 | 7:20 | Open Enrollment 2024 Changes (part 42) |  | No
SF2K973366 | LCOLLIER | 2023-11-17 | 8:47 | 6390801 PM TKD0245882 OC15 New Building | 22 | No
SF2K973368 | MPRUDDEN | 2023-11-17 | 11:48 | Fix numeric format issues in eSDS View Dollars screen - Pt 2 |  | Yes | Not in SH1
SF2K973344 | BENOO | 2023-11-17 | 15:34 | New Hire/Open Enrollment 2024 Changes (part 2) |  | No
SF2K973381 | CORNEM | 2023-11-20 | 7:40 | INC1202151 - SAP SP 2023 - Issue with testing credcard with |  | No | Not in SH1
SF2K973387 | CORNEM | 2023-11-21 | 7:36 | INC1202151 - SAP SP 2023 - Issue with testing credcard with |  | No | Not in SH1
SF2K973374 | JDUDLEYK | 2023-11-21 | 8:54 | New Hire/Open Enrollment 2024 Changes (part 3) |  | No
SF3K906374 | RKATKOWS | 2023-11-21 | 10:41 | R3ADM* OSS 2617459-v2 Batch Request: Fix empty response. |  | Yes | Not in SH1
SF2K973282 | LMA | 2023-11-21 | 12:47 | DoF: new Work Order ranage |  | Yes | Not in SH1
SF2K973377 | AGROBLER | 2023-11-21 | 15:24 | INC0973895 - new student commuter permit type | 25 | No
SF2K973379 | AGROBLER | 2023-11-21 | 15:25 | INC0973895 - new student commuter permit type | 26 | No
SF2K973372 | KBUEGEL | 2023-11-21 | 15:44 | INC0973895 - GSU GAP Award Extra Information 6 | 23 | No
SF2K973364 | CORNEM | 2023-11-22 | 11:42 | INC1202773 - 2023 SAP Support Packs (broken links in SH2) |  | Yes | Not in SH1
SF2K973400 | KBUEGEL | 2023-11-27 | 14:51 | INC0973895 - GSU GAP Award Extra Information 7 | 24 | No
SF2K973403 | AGROBLER | 2023-11-27 | 19:43 | INC0973895 - new student commuter permit type II | 27 | No
SF2K973405 | AGROBLER | 2023-11-27 | 19:44 | INC0973895 - new student commuter permit type III | 28 | No
SF2K973407 | JDUDLEYK | 2023-11-29 | 10:47 | New Hire Enrollment: Trad/Choice Warnings on ITS |  | No
Pre and Post Update Developments
SF2K970261 | REP | 2021-11-04 | 9:27 | R3ADM* External OS Command "ZUT_FTP_TO_DW" | Y
SF2K970281 | GEORGEP | 2021-11-04 | 9:28 | R3ADM* RT5750582 S_LOG_COM AUTH for FTP_TO_DW (REP | Y
SF2K970123 | LMA | 2021-11-04 | 9:28 | RT 5741888: DW - ZWHFTP | Y
SF2K970072 | EPRUDDEN | 2021-11-04 | 11:07 | RT 5741888: iNFR: RFC_REMOTE_PIPE is not supported by SAP | Y
SF2K970317 | LMA | 2021-11-04 | 11:08 | RT 5741888: iNFR: RFC_REMOTE_PIPE is not supported by SAP 2 | Y
SF2K970343 | MPRUDDEN | 2021-11-08 | 8:33 | SP2021: Update IT0015 user exit to account for new IT3430 | Y
SF2K969976 | CORNEM | 2021-11-08 | 9:32 | INC0674422 - ADP Code Update - ZADP_PRCHECK_CUST_20210823 | Y
SF2K970038 | CORNEM | 2021-11-08 | 9:32 | INC0691190 - ADP Code Update - ZADP_PRCHECK_CUST_20210908 & | Y
SF2K970078 | CORNEM | 2021-11-08 | 9:33 | INC0699716 - ADP Code Update - ZADP_PRCHECK_PROC_20210914 an | Y
SF2K970188 | AGROBLER | 2021-11-08 | 9:33 | INC0699716 - ADP Code Update - ZADP_PRCHECK_PROC_20210914 v2 | Y
SF2K970225 | CORNEM | 2021-11-08 | 9:33 | INC0716393 - ADP Code Update - ZADP_PRCHECK_PROC_20211013 | Y
SF2K970298 | AGROBLER | 2021-11-08 | 9:34 | INC0722773 - ADP Code Update 20211020 | Y
SF2K970283 | ECUNNING | 2021-11-08 | 10:04 | RT5769207 - New Special Pay Program Supplement | Y
SF2K970296 | ECUNNING | 2021-11-08 | 10:05 | 5769207 - HR New Acton Reason Code -Spec Pay Prgm Supp - PDF | Y
SF2K970339 | LMA | 2021-11-09 | 9:02 | RT 5741888: iNFR: RFC_REMOTE_PIPE is not supported by SAP 3 | Y
SF2K969829 | BOTHAM | 2021-11-09 | 13:16 | INC0592009 ISchO Sunapsis RFCs v1 | N (to PS1 12/9)
SF2K970068 | GEORGEP | 2021-11-09 | 13:16 | R3ADM* RT5700404 Role for ZZMSHRISCHO1 ISchO extract (HABIBE | N (to PS1 12/9)
SF2K970109 | GEORGEP | 2021-11-09 | 13:17 | R3ADM* RT5747266 New AuGr for HR ISchO Mass Export (HABIBEAR | N (to PS1 12/9)
SF2K970093 | BOTHAM | 2021-11-09 | 13:18 | INC0592009 ISchO Sunapsis RFCs v2 DATAFEED and Mass Import | N (to PS1 12/9)
SF2K970111 | GEORGEP | 2021-11-09 | 13:18 | R3ADM* RT5747266 New Roles for HR ISchO Project (HABIBEAR | N (to PS1 12/9)
SF2K970120 | BOTHAM | 2021-11-09 | 13:19 | INC0592009 ISchO Sunapsis RFCs v3 DATAFEED and Mass Import | N (to PS1 12/9)
SF2K970129 | BOTHAM | 2021-11-09 | 13:20 | INC0592009 ISchO Sunapsis RFCs v4 DATAFEED and Mass Import | N (to PS1 12/9)
SF2K970140 | BOTHAM | 2021-11-09 | 13:20 | INC0592009 ISchO Sunapsis RFCs v5 DATAFEED and Mass Import | N (to PS1 12/9)
SF2K970170 | CORNEM | 2021-11-09 | 13:21 | INC0712071 - SF2: Issues with SUNAPSIS_MASS_EXPORT | N (to PS1 12/9)
SF2K970186 | CORNEM | 2021-11-09 | 13:22 | INC0712071 - SF2: Issues with SUNAPSIS_MASS_EXPORT | N (to PS1 12/9)
SF2K970196 | BOTHAM | 2021-11-09 | 13:22 | INC0592009 ISchO Sunapsis RFCs v6 DATAFEED and Mass Import | N (to PS1 12/9)
SF2K970208 | BOTHAM | 2021-11-09 | 13:22 | INC0592009 ISchO Sunapsis RFCs v7 Mass Import | N (to PS1 12/9)
SF2K970293 | BOTHAM | 2021-11-09 | 13:23 | INC0592009 ISchO Sunapsis RFCs v8 DATAFEED and Mass Import | N (to PS1 12/9)
SF2K970300 | BOTHAM | 2021-11-09 | 13:23 | INC0592009 ISchO Sunapsis RFCs v9 Mass Import | N (to PS1 12/9)
SF2K970321 | LKUSHKUL | 2021-11-09 | 15:37 | WorkPartners Outbound feed: performance improvement | Y
SF2K970356 | REP | 2021-11-10 | 14:22 | R3ADM* External Command ZUT_UNIX_NCFTPPUT update | Y
SF2K970364 | LKUSHKUL | 2021-11-16 | 8:58 | GAP: new rates in the table zgap_dept_pref2 | Y
SF2K970333 | BOTHAM | 2021-11-16 | 14:27 | INC0592009 ISchO Sunapsis RFCs v10 Datafeed and Mass Import | N (to PS1 12/9)
SH2K901127 | REP | 2021-11-17 | 17:04 | R3ADM* Table Z1942 Table Contents -BACKUP | N
SF2K970315 | AGROBLER | 2021-11-18 | 7:55 | INC0739765 - GAP Pay Increase Utility | Y
SF2K970369 | KBUEGEL | 2021-11-22 | 8:58 | INC0739765 - GAP Pay Increase Utility v1.01 | Y
SF2K970372 | KBUEGEL | 2021-11-24 | 7:27 | INC0739765 - GAP Pay Increase Utility v1.02 | Y
SF2K970374 | BOTHAM | 2021-12-01 | 12:40 | INC0592009 ISchO Sunapsis RFCs v10 Datafeed and Mass Import | N (to PS1 12/9)
SF2K970387 | BOTHAM | 2021-12-03 | 8:45 | INC0592009 ISchO Sunapsis RFCs v12 Datafeed | N (to PS1 12/9)
SF2K970385 | LKUSHKUL | 2021-12-03 | 10:36 | GAP:limit number of returned records | Y
SF2K970389 | BOTHAM | 2021-12-03 | 11:47 | INC0592009 ISchO Sunapsis RFCs v13 Datafeed | N (to PS1 12/9)