## Transport List for go-live
Transport List for go-live |  |  |  | as of 12/03/2024, 2:00pm
Request/Task | Owner | Date | Time | Short Description | To PS1 on go-live weekend? | Only in SH2 (i.e. not in SH1)
Mods (SPAU/SPAU_ENH)
SF3K906468 | REP | 2024-10-28 | 23:24 | R3ADM* PostUpdate (SF3) SPAU Note Resets | Yes | Only in SH2
SF3K906472 | RKATKOWS | 2024-10-28 | 23:26 | R3ADM* OSS 2295568 - Reimplement per SPAU | Yes | Only in SH2
SF3K906470 | RKATKOWS | 2024-10-28 | 23:28 | R3ADM* - OSS 454352 - Reimplement per SPAU | Yes | Only in SH2
SF3K906476 | RKATKOWS | 2024-10-28 | 23:29 | R3ADM* OSS 3470796 - Reset v_t7usben03v | Yes | Only in SH2
SF3K906478 | FQUERN | 2024-10-28 | 23:29 | HRP MOD Resets for V_T511P Constants Table | Yes | Only in SH2
SF3K906480 | EPRUDDEN | 2024-10-28 | 23:30 | SP2024: Reapplication of mods | Yes | Only in SH2
SF3K906482 | FQUERN | 2024-10-28 | 23:31 | SP2024 SPAU Adjust RPCGET00_FUP0009 | Yes | Only in SH2
SF3K906484 | FQUERN | 2024-10-28 | 23:32 | SP2024 SPAU Confirm Adjustment (RPCGET00_FUP009) | Yes | Only in SH2
SF3K906486 | REP | 2024-10-28 | 23:33 | R3ADM* OSS 3482369 ST14: Inaccurate Table Size Determination | Yes | Only in SH2
SF2K974901 | MPRUDDEN | 2024-10-28 | 23:34 | SP2024 SPAU_ENH adjustments to implicit enhancement | Yes | Only in SH2
SF2K974903 | EPRUDDEN | 2024-10-28 | 23:35 | SP2024: SPAU_ENH adjustment to implicit enhancement | Yes | Only in SH2
Pre and Post Update Developments |  |  |  | yellow=already in ps1
SF2K974909 | JDUDLEYK | 2024-10-30 | 16:52 | HRBEN: 2025 Health FSA Contrib Limit | Yes |  | re-import needed to ensure latest version is retained in PS1 (after SF3K906478)
SF3K906488 | RKATKOWS | 2024-11-01 | 14:28 | R3ADM* OSS 3464582-SAP GUI HTML Control: ABAP dump occurs. | Yes | Only in SH2
SF2K974922 | SQUIGLEY | 2024-11-04 | 6:35 | R3ADM* RT6575779 New role Z_SAP_GRAC_ACC_FOR_GRC_LTDRFC4 | Yes | Only in SH2
SF2K974912 | GMCGRATH | 2024-11-05 | 12:15 | PY:Restore W2 MIT custom box 14 headings | Yes | Only in SH2
SF2K974480 | BMARTIR | 2024-11-07 | 18:06 | INC1372700 - FLSA Threshold Report - Issues with Job Exclusi | Yes | Only in SH2
SF3K906490 | RKATKOWS | 2024-11-13 | 10:12 | R3ADM* OSS 2617459-v2 Batch Request: Fix empty response. | Yes | Only in SH2
SF2K974933 | BMARTIR | 2024-11-13 | 10:22 | INC1438729 - SH2: Timesheet issue - Missing user name | Yes |  | production issue approved for go-live transport list
SF3K906492 | RKATKOWS | 2024-11-14 | 10:39 | R3ADM* OSS 3514409-RW: Missing Headers and Titles in Report. | Yes | Only in SH2
SF2K974950 | LKUSHKUL | 2024-11-18 | 14:52 | APR: SP2024: Bad Links in Welcome/Appointment Change Email | Yes | Only in SH2
SF2K974958 | GEORGEP | 2024-11-19 | 15:16 | R3ADM* RT6583134 Add Z_VPF_S_CN60 to SVC_CTR_SUPER (LESLIEM | Yes | Only in SH2