## SH1 Tests
Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Notes | SH1 Before Output records | SH1 After Output records | Variances | Percent matched
Before Pre-Support Pack install
Run BCBS | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/bcbs | 2009-11-25 | 2009-11-25 | Desiree R. | Complete
Run Vision | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2009-11-25 | 2009-11-25 | Desiree R. | Complete
Run Fidelity HR | zhr_fidelity | hr/fid_hr | 2009-11-25 | 2009-11-25 | Desiree R. | Complete
Run Cobra Terms | ZHRCSB02 | hr/crosby; | 2009-11-25 | 2009-11-25 | Desiree R. | Complete
Weekly Payroll Processing (43/2009) for a list of pernrs | Script: Non-Exempt Payroll Test for Support Pack Update 2008.doc |  | 2009-11-25 | 2009-11-25 | Mary D. | Complete
Run Monthly Payroll Processing for period 10/2009 for a list of pernrs |  |  | 2009-11-25 | 2009-11-25 | Mary D. | Complete
Run Fidelity Weekly Contributions | Scheduled Job ZPYIO_FID_CNTRIB | py/fid_cntrib | 2009-11-25 | 2009-11-25 | Sharon | Complete
Run Fidelity Monthly Contributions | Scheduled Job ZPYIO_FID_CNTRIB | py/fid_cntrib | 2009-11-25 | 2009-11-25 | Sharon | Complete
Run FSA Weekly Contributions | ZPYIO_FSA_CONTRIB | py/fsa_dep | 2009-11-25 | 2009-11-25 | Sharon | Complete | 0 records
Run FSA Monthly Contributions | ZPYIO_FSA_CONTRIB | py/fsa_dep | 2009-11-25 | 2009-11-25 | Sharon | Complete
Run LL Bank Feed | zpy_ll_bank_detail | py/ll_bank | 2009-11-25 | 2009-11-25 | Alan M. | Complete |  | 4 | 4 | 0 | 100%
Run Mitsis Biofeed | ZMITSIS | hr/mitsis_dem | 2009-11-25 | 2009-11-25 | Alan M. | Complete | input feeds data does not match perfectly | 26 in 20 updated | 26 in 16 updated | 4 | 80%
Run Web Gradaid | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2009-11-25 | 2009-11-25 | Alan M. | Complete | input feeds | updated 10 appts | updated 10 appts | 0 | 100%
After Pre-Support Pack install
Run BCBS and compare to the before version in SH1 using ultra edit | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/bcbs | 2009-12-02 | 2009-12-02 | Desiree R. | Complete
Run Vision and compare to the before version in SH1 using ultra edit | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2009-12-02 | 2009-12-02 | Desiree R. | Complete
Run Fidelity HR and compare to the before version in SH1 using ultra edit | zhr_fidelity | hr/fid_hr | 2009-12-02 | 2009-12-02 | Desiree R. | Complete |  | 1303
Run Cobra Terms and compare to the before version in SH1 using ultra edit | ZHRCSB02 | hr/crosby; | 2009-12-02 | 2009-12-02 | Desiree R. | Complete |  | 188
Rerun Weekly Payroll Processing (43/2009) for the same weekly pernr list | Script: Non-Exempt Payroll Test for Support Pack Update 2008.doc | n/a | 2009-12-02 | 2009-12-02 | Gregg M. | Complete
Rerun Monthly Payroll Processing for period 10/2009 for the same monthly pernr list | Script: Exempt Payroll Test for Support Pack Update 2008.doc | n/a | 2009-12-02 | 2009-12-02 | Gregg M. | Complete
Run Fidelity Weekly Contributions and compare to the before version in SH1 using ultra edit | Scheduled Job ZPYIO_FID_CNTRIB | py/fid_cntrib | 2009-12-02 | 2009-12-02 | Sharon | Complete |  | 23 | 23 |  | 100%
Run Fidelity Monthly Contributions and compare to the before version in SH1 using ultra edit | Scheduled Job ZPYIO_FID_CNTRIB | py/fid_cntrib | 2009-12-02 | 2009-12-02 | Sharon | Complete |  | 26 | 26 |  | 100%
Run FSA Weekly Contributions and compare to the before version in SH1 using ultra edit | ZPYIO_FSA_CONTRIB | py/fsa_dep | 2009-12-02 | 2009-12-02 | Sharon | Complete |  | 0 | 0
Run FSA Monthly Contributions and compare to the before version in SH1 using ultra edit | ZPYIO_FSA_CONTRIB | py/fsa_dep | 2009-12-02 | 2009-12-02 | Sharon | Complete |  | 6 | 6 |  | 100%
Run LL Bank Feed and compare to before version in SH1 using ultra edit | zpy_ll_bank_detail | py/ll_bank | 2009-12-02 | 2009-12-02 | Alan M. | Complete | input feeds | 4 | 4 | 0 | 100%
Run Mitsis Biofeed and compare to before version in SH1 using ultra edit | ZMITSIS | hr/mitsis_dem | 2009-12-02 | 2009-12-02 | Alan M. | Complete | input feeds data does not match perfectly | 26 in 20 updated | 26 in 16 updated | 4 | 80%
Run Web Gradaid and compare to before version in SH1 using ultra edit | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2009-12-02 | 2009-12-02 | Alan M. | Complete | input feeds | updated 10 appts | updated 10 appts | 0 | 100%
Run Lincoln inbound feed - HR/PY data, reviewed the messages/spot checked the data | ZHRALE | n/a | 2009-12-02 | 2009-12-02 | Larissa | Complete | Files 932, 934
Run Lincoln inbound feed - time data, reviewed the messages/spot checked the data | ZHRALE | n/a | 2009-12-02 | 2009-12-02 | Larissa | Complete | File 000
Payroll Results Comparison (ZW) | RPCALCU0 / RPCPRRU0 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Complete |  |  |  |  | 100%
EDACCA TABLE COMPARISON | SE16 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Complete |  |  |  |  | 100%
Payroll Results Comparison (ZM) | RPCALCU0 / RPCPRRU0 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Complete |  |  |  |  | 100%
EDACCA TABLE COMPARISON | SE16 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Complete |  |  |  |  | 100%
Individual Test Cases
Run Time Eval | RPTIME00 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass
Run a Payroll Journal | RPCLJNU0 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | ZM Oct'09
Run Wage Type Reporter | H99CWTR0 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | ZM Sept'09 WT 652D
Run Banking Transfer processes | ZPREDME, RFFOUS_C & T |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | ZM Oct'09
Run 3PR process | RPCALCU0, RPURMU00, RPURMP00 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | ZW 48.2009
Post a payroll | RPCIPE00_OLD, PCP0 post |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | ZM 10.2009
Run OC w/ Subsq process |  |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | pernr 62599
Check process status | PUST |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | pernr 62599
Test Tax Reporter | PU19, run & print a single test W-2 |  | 2009-12-02 | 2009-12-02 | Gregg M. | Pass | pernr 62599
Create an employee position | ZOMC |  | 2009-12-03 | 2009-12-03 | Mary D. | Pass
Master Data Maintenance | PA30 |  | 2009-12-03 | 2009-12-03 | Mary D. | Pass
Dynamic Action | PA40 |  | 2009-12-03 | 2009-12-03 | Mary D. | Pass
Benefits Enrollment | HRBEN0001 |  | 2009-12-03 | 2009-12-03 | Mary D. | Pass
Generate an Off Cycle Check | OC Workbench |  | 2009-12-03 | 2009-12-03 | Mary D. | Pass
Set up payroll deduction (non-benefits) | ZPYDEDUCT |  | 2009-12-03 | 2009-12-03 | Mary D. | Pass
Create a graduate position | ZOMCGST |  | 2009-12-03 | 2009-12-03 | Mary D. | Pass
New Hire Enrollment via ESS | ESS |  | 2009-12-03 | 2009-12-03 | Desiree R. | Pass
Group Enrollment via HRBEN0012 | HRBEN0012 |  | 2009-12-03 | 2009-12-03 | Desiree R. | Pass
Termination via HRBEN0014 | HRBEN0014 |  | 2009-12-03 | 2009-12-03 | Desiree R. | Pass
ALE log functionality | ZHRALELOG |  | 2009-12-02 | 2009-12-02 | Alan M. | Pass
Dyanmic Resource Menu | PSVR |  | 2009-12-02 | 2009-12-02 | Emily C. | Pass
Master Data Catalog | OOC3 |  | 2009-12-02 | 2009-12-02 | Emily C. | Pass
Dynamic Attendance Menu | PSV1 |  | 2009-12-02 | 2009-12-02 | Emily C. | Pass
Dyanmic Business Event Menu | PSV2 |  | 2009-12-02 | 2009-12-02 | Emily C. | Pass
Vacation Tracker: Employee Form | ESS |  | 2009-12-02 | 2009-12-03 | Lavanya | Pass
Vacation Tracker: Admin Report | SAPWeb |  | 2009-12-02 | 2009-12-03 | Lavanya | Pass
Kronos Outbound |  |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
LL Leave Accruals Outbound |  |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
LL Time Audit |  |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Update PA0003 PDC Recalc Date | ZHRPT_UPDT_RECAC_DATE |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Transaction to control Time Sheet entry access | ZTSO |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Time Sheet: Maintain Times | CAT2 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Time Evaluation | PT60 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Display Time Sheet Data | CATSSHOW |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Quota Overview | PT50 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Time Evaluation Messages Display | RPTERL00 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Transfer External -> Time Management | CAT6 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Kronos inbound time interface | ZPTKRONOS_TIME_INBOUND |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Display Cluster B2 | PT66 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Unapproved Time Entries Report | ZPYR_UNAPPR_TIME |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Time Approval Scheduled Outage | ZTSO |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
HR/PT: Update PA0003 PDC Recalc Date | ZHRPT_UPDT_PDC |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Kronos outbound accruals (Prod) | ZPTKRONOS_ACCRUL_OUT |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
HR: Maintain Calculation Rules | PE02 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Display and Delete Single Records in Database PCL2 | RPUP2D00 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Fast Entry of Time Data | PA71 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Creates Functions and Operations | PE04 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Display Absence Quota Information | RPTQTA10 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Time Management: Error Handling | RPTERR00 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Lincoln Time Audit | ZHR_AUDIT_LINCOLN_TIME (same as #21) |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Time Sheet: Display Times | CAT3 |  | 2009-12-03 | 2009-12-03 | Lavanya | Pass
Exempt Appointment Processing | Identified on test script catalog |  | 2009-12-02 | 2009-12-02 | Cindy | Pass
Non-exempt Appointment Processing | Identified on test script catalog |  | 2009-12-02 | 2009-12-02 | Cindy | Pass