## Overview and Assumptions
Timeframe for Test Execution
Comparison Test: 11/9/2009 - 11/13/2009 (holiday on 11/11)
Integration Test: 11/16/2009 - 11/20/2009
Assumptions:
Production snapshot as of midnight 10/19/2009
Test system will be available by start of day 11/9/2009
Comparison test consists of four payroll comparisons:
Weekly Non-Exempt (payweek 43 (10/12/09-10/18/2009))
Monthly Exempt (October)
Pension Payroll Lump Sum (October 31, 2009)
Pension Monthly Annuity Run (November 2009)
Overview of integration test strategy:
Generate payroll and run interfaces simulating the production payroll processes
Compare production (PS1) results to test system (SH2) results
Research discrepancies; resolve system issues
Execute select test scripts hiting key functionality not executed during pay run processes
Comparison Tools:
Create comparison reports using the EPIUSE variance monitor tool
Net pay comparisons in excel
Net pay comparison using EPIUSE variance monitor
Ultra Compare
Fox Pro
Overview of User Acceptance Test:
Test Scripts identified in the HR/Payroll Master Test Script Catalog Payroll will be run and payruns will be executed for:
Non exempt:
Cycle 1: week 44/2009 (10/19/2009-10/25/2009)
| Offcycle: | TBD
Cycle 2: week 45/2009 (10/26/2009-11/1/2009)
| Offcycle: | TBD
| Cycle 3: week 46/2009 (11/2/2009-11/8/2009) | ASR will use this period for its weekly test.
Exempt:
| Cycle 1: month | November | 2009 | ASR will use this period for its monthly test.
| Cycle 2: month | December | 2009
| Cycle 3: month | January | 2010
| Pension: | n/a
Business Owner buy-in

## Comparision Run Schedule
Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Prep files ready? | Notes | No. of files matched | PS1 Output records | SH2 Output records | Variances | Percent matched
Verify Feed Registry Archive Control Tables are correct for the environment | SM30 | n/a | 2009-11-10 | 2009-11-10 | SD | complete | n/a
Re-configure EDI Test Environment to accept files from SH2 |  | n/a | 2009-11-10 | 2009-11-10 | LK | complete | n/a
Confirm w/ R3 that Lincoln configuration for EDI is active |  | n/a | 2009-11-10 | 2009-11-10 | LK | complete | n/a | Per Eric Ngo - The logical system is RC2CLNT400.
DW extract of HR/Pay data | Multiple | n/a | 2009-11-10 | 2009-11-10 | Elena | complete | n/a
Run FSA Census outbound interface using Ultracompare compare file to Sunday production run (10/18). | ZPYIO_FSA_CENSUS | py/fsa_census | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | run before payroll (checks the control record so we want the right period executed) |  | 2592 | 2592 | 0 | 100
Run FSA Enroll outbound interface (looks at the control record) using Ultracompare compare file to Sunday production run (10/18). | ZPYIO_FSA_ENROLLMENT | py/fsa_census | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | run before payroll (checks the control record so we want the right period executed) |  | 2928 | 2928 | 0 | 100
Weekly Payroll Processing (43/2009) | Script: Non-Exempt Payroll Test for Support Pack Update 2008.doc |  | 2009-11-12 | 2009-11-12 | MD | complete | n/a | Passed
Pension Payroll - Lump Sum Run |  |  | 2009-11-11 | 2009-11-11 | FQ/GM | complete |  | Passed
Pension Payroll - Annuity Run |  |  | 2009-11-10 | 2009-11-11 | FQ/GM | complete | Yes
MIT Holiday |  |  | 2009-11-11 | 2009-11-11
Run HR Fidelity outbound interface; using ultracompare compare file to Sunday production run (10/18). | zhr_fidelity | hr/fid_hr | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts, Orig run 10/18; chgs made 10/19 | 1 | 594 | 599 | 17 | 97.138
Benefits outbound: BCBS using ultracompare compare file to Sunday production run (10/18). Run for dates 10/18 - 100 days thru 10/18 + 45. In IDOC Cleanup allow retro 40 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/bcbs | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts |  | 340239 | 340251 | 186 | 99.9489
Benefits outbound: Delta using ultracompare compare file to Sunday production run (10/18). Run for dates 10/18 - 100 days thru 10/18 + 45. In IDOC Cleanup allow retro 40 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/delta | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts |  | 58965 | 58782 | 30 | 99.9489
Benefits outbound: Tufts using ultracompare compare file to Sunday production run (10/18). Run for dates 10/18 - 100 days thru 10/18 + 45. In IDOC Cleanup allow retro 40 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/tufts | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts | 1 | 16940 | 16888 | 6 | 99.9645
Benefits outbound: Vision using ultracompare compare file to Sunday production run (10/18). Run for dates 10/18 - 100 days thru 10/18 + 45. There is currently no retro limit in IDOC Cleanup. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts | 1 | 47637 | 47637 | 12 | 99.9748
Run Express Scripts outbound; using ultracompare compare file to Sunday production run (10/18). | ZHRESIFEED | py/fsa_enroll | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts | 1 | 16225 | 16231 | 22 | 99.8643
Run Crosby Outbound terminations; using ultracompare compare files to Sunday production runs (10/18). | ZHRCSB02 | hr/crosby; | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts | 1 | 27 | 27 | 0 | 100
Run Crosby Outbound new entrants for the prior month (Sep); using ultracompare compare files to Sunday production runs (10/1). | ZHRCSB02 | hr/crosby_new | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts | 1 | 252 | 251 | 5 | 97.9675
Run Crosby Outbound dependents aging out; based on file created 10/1 for November ageoffs using ultracompare compare files to production runs (10/1). | ZHRCSB03 | hr/crosby_dep | 2009-11-12 | 2009-11-12 | Desiree R. | complete | Yes | can run w/ DW extracts | 1 | 34 | 34 | 0 | 100
Run Metpay Census outbound interface; using ultracompare compare file to Sunday production run (10/18). | ZPY_METPAY_CENSUS_DATA | hr/metpcensus | 2009-11-12 | 2009-11-12 | Desiree R./SD | complete | Yes | can run w/ DW extracts DOH different on retirees. RT 1079780 Bug in PS1 too. | 1 | 13882 | 13882 | 500 | 96
Run Health Insurance Resposibility Disclosure (HIRD); outbound to Crosby | ZHR_OUTBOUND_HIRD_DATA | hr/hird |  |  | Desiree R. | complete | Yes | can run w/ DW extracts | 4 | 233 | 235 | 2 | 99.1416
Payroll Results Comparison (ZW) |  |  | 2009-11-12 | 2009-11-12 | Gregg M. | complete | - |  | n/a | 4032 |  | 3 | 99.93
Payroll Results Comparison (ZP) |  |  | 2009-11-12 | 2009-11-12 | Gregg M. | complete | - |  | n/a | 5646 |  | 25 | 99.56
FI POSTING COMPARISON (ZP) |  |  | 2009-11-12 | 2009-11-12 | Gregg M. | complete | - |  | n/a | 5665 |  | 8 | 99.86
EDACCA TABLE COMPARISON |  |  | 2009-11-13 | 2009-11-13 | Gregg M. | complete | - |  | n/a | 3276 |  | 3 | 99.91
FI POSTING COMPARISON (ZW) |  |  | 2009-11-13 | 2009-11-13 | Gregg M. | complete | - |  | n/a | 4042 |  | 10 | 99.75
(After Payroll Execution) Weekly Outbound Interfaces
Timesheet file to MITSIS (combined w/ Grad Student Gross Pay) using ultracompare compare files to Wed production runs (10/21) | ZPYIO_MITSIS_TIM | py/mitsis_tim | 2009-11-12 | 2009-11-12 | SD | complete | Yes | Passed | 1 | 2528 | 2524 | 4 | 99.84
| Dates From Wednesday to Wednesday |  | 2009-11-12 | 2009-11-12 | SD | complete | n/a
LL salary distribution weekly gross pay using ultracompare compare files to Wed production runs (10/21) | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2009-11-12 | 2009-11-12 | SD | complete | Yes | Passed | 1 | 6540 | 6539 | 1 | 99.98
| Check for errors on filezilla |  | 2009-11-12 | 2009-11-12 | SD | complete | n/a
LL non-exempt leave accruals (this is a daily interface) using ultracompare compare files to Wed production runs (10/21) | Scheduled job ZHR_LL_ACCRUALS_OUT Check for errors on filezilla. | py/ll_leave | 2009-11-12 | 2009-11-12 | Lavanya G. | complete | Yes | Passed | 1 | 3029 | 3015 |  | 99.5
Leave balance accruals for Facilities Service Staff (this is a daily interface) | ZPTKRONOS_ACCRUL_OUT | py/facil_leav | 2009-11-12 | 2009-11-12 | Lavanya G. | complete | Yes | Passed | 1 | 2506 | 2506 | 400 | 84
FSA (Crosby). Compare results to production file using ultracompare compare files to Wed production runs (10/21) | ZPYIO_FSA_CONTRIB | py/fsa_dep | 2009-11-12 | 2009-11-12 | SD | complete | Yes | Ties to production. | 1 | 402 | 402 | 0 | 100
Fidelity pension file (weekly 401 pension contributions) Use ZW Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS using ultracompare compare files to Wed production runs (10/21) | Scheduled Job ZPYIO_FID_CNTRIB | py/fid_cntrib | 2009-11-12 | 2009-11-12 | SD | complete | Yes | Passed 6 variances | 1 | 2370 | 2370 | 6 | 99.8
LL Bank details (this is a daily extract) | zpy_ll_bank_detail | py/ll_bank | 2009-11-12 | 2009-11-12 | Alan M. | complete | Yes | equal to production. | 8 | 27 | 27 | 0 | 100
Student Bio Feed (MITSIS) | ZMITSIS | hr/mitsis_dem | 2009-11-12 | 2009-11-12 | Alan M. | complete | Yes | equal to production. | 5 | 124 | 124 | 0 | 100
Grad Appointment Inbound (this is a daily feed) | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2009-11-12 | 2009-11-12 | Alan M. | complete | Yes | equal to production. | 7 | 65 | 65 | 0 | 100
Compare results to production | Check for errors on filezilla . |  | 2009-11-12 | 2009-11-12 | SD | complete | n/a
Monthly Payroll Interface Activities
Monthly LL Feed (production files from 10/20-25); IDOC files needed - decrypt and copy to test system's sapin directory | ZHRALE, ZHRALELOG | n/a | 2009-11-12 | 2009-11-12 | LK | complete | requested
Service Center/Benefits office enters taxes, deduction & benefits for nine Lincoln new hires/rehires (not necessary for 2009) |  |  | - | - | Scott Ball/Benefits | skip | n/a
Additional Payroll Interface Activities (before planned monthly run)
Weekly Fidelity Percent Inbound; use Friday file (10/23); compare reports to prod reports; spot-check the loaded data | ZPYII_FID_PCT | py/fid_pct | 2009-11-12 | 2009-11-12 | SD | complete | Yes | Passed | 1 | 35 | 35 | 0 | 100
Weekly Tech Cash Inbound; use Friday file (10/23).; compare reports to prod reports; spot-check the loaded data | ZPYII_DED | py/tech_cash | 2009-11-12 | 2009-11-12 | SD | complete | Yes | Passed | 1 | 526 | 526 | 0 | 100
Metpay Home/Auto inbound; compare reports to prod reports; spot-check the loaded data | ZPY_METPAY_IN | py/metp-ded | 2009-11-12 | 2009-11-12 | SD | complete | Yes | Passed | 1 | 4 | 4 | 0 | 100
Monthly Payroll Processing | Script: Exempt Payroll Test for Support Pack Update 2008.doc |  | 2009-11-12 | 2009-11-12 | FQ | complete | n/a
Payroll Results Comparison (ZM) |  |  | 2009-11-13 | 2009-11-13 | Gregg M. | complete | - | 97% exact match | n/a | 12619 |  | 417 | 96.7
EDACCA TABLE COMPARISON |  |  | 2009-11-13 | 2009-11-13 | Gregg M. | complete | - |  | n/a | 10506 |  | 364 | 96.54
FI POSTING COMPARISON |  |  | 2009-11-13 | 2009-11-13 | Gregg M. | complete | - |  | n/a | 12614 |  | 449 | 96.44
(After Monthly Payroll Payroll Execution) Outbound Interfaces (Comparisons to production files)
Fidelity contributions outbound - monthly Use ZM Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS | ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2009-11-16 | 2009-11-16 | SD | complete | Yes | 51 401K catch up 100 gross pay | 1 | 6190 | 6176 | 151 | 97.5
| Dates TBD |  | 2009-11-16 | 2009-11-16 | SD | complete | n/a
EDS contributions outbound - monthly Include both weekly and monthly | ZPYIO_EDS_CNTRIB | py/eds_cntrib | 2009-11-16 | 2009-11-16 | LK/SD | complete | Yes | YTD taxable earning differences on monthly, missing 1 pay week for weekly. Monthly reconciled as 250 gross pay, 50 401K catup, 6 other pretax ded's | 1 | 10624 | 10596 | 310 | 97
| Check for errors on filezilla |  | 2009-11-16 | 2009-11-16 | LK/SD | complete | n/a
FSA contributions outbound - monthly Use monthly variant, change start date/time to before payroll run, check test, enter handliing rule 001 | ZPYIO_FSA_CONTRIB | py/fsa_dep | 2009-11-16 | 2009-11-16 | SD | complete | Yes | few differences | 1 | 1941 | 1941 | 21 | 98.9
Credit Union contributions Run for dates from PS1's last run email thru end of monthly payrun | ZPYIO_CU_UNION | py/cu | 2009-11-16 | 2009-11-16 | SD | complete | Yes | differences are explainable. weekly payroll is missing the last payroll deductions. All but 9 have been explained as chg ded amt or DDTKN | 1 | 3136 | 3135 | 1387 | 55.7
John Hancock (long term care) contributions | ZPYIO_HANCOCK | py/hancock | 2009-11-16 | 2009-11-16 | SD | complete | Yes |  | 1 | 643 | 641 | 9 | 98.6
TIAA-CREF (457B) contributions (10/28 File) | ZPYIO_TIAA_CREF | py/tiaa_cref | 2009-11-16 | 2009-11-16 | SD | complete | Yes | exact match | 1 | 216 | 216 | 0 | 100
EDS HR Outbound 10/28 File) Run from start date/time as ran in production from 10/28 | ZHR_FIDELITY | hr/eds_hr | 2009-11-16 | 2009-11-16 | SD | complete | Yes | 10 days of keying different, mostly address/email addresses | 1 | 741 | 700 | 200+ | 73
LL Salary distribution monthly gross pay | ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2009-11-16 | 2009-11-16 | SD | complete | Yes |  | 1 | 2343 | 2340 | 3 | 99.8
Inbound Interface Comparisons
Load LL Time Files (10/26/2009) - weekly IDOC file - need to copy to test system's sapin directory | ZHRALE | n/a | 2009-11-16 | 2009-11-16 | LK/EN | complete | requested | Eric will review
Run LL time audit (10/26/2009) - weekly | ZPYII_LL_AUDT_TM | py/ll_audt_tm | 2009-11-16 | 2009-11-16 | Lavanya G. | complete | Yes | LL will review (ccassidy)
Run LL HR/Payroll audit files (10/26/2009) - weekly | ZHRALF02 | py/ll_audt_py | 2009-11-16 | 2009-11-16 | LK | complete | Yes | Validated by Colleen Passed
Service Center/Benefits office enters taxes, deduction & benefits for remaining Lincoln new hires/rehires |  |  | 2009-11-16 | 2009-11-16 | Scott Ball/Benefits | skip | n/a
Run Kronos Feed and compare IT2001/2002 records with change date of (date file was executed, changed by whomever ran the file) or time eval results. (10/26/2009) - weekly | ZHR_INBOUND_TIME | py/facil_time | 2009-11-16 | 2009-11-16 | Lavanya G. | complete | Yes |  | 1 | 2198 | 2518 | 300 | 88
Parking Standard Internal deductions - monthly copy to test system's sapin directory (Use 11/16 file if available) | ZPYII_DED | py/parking | 2009-11-16 | 2009-11-16 | SD | complete | requested | 1 record locked | 1 | 4294 | 4294 | 1 | 99.9
Tpass Standard Internal deductions - monthly; (use 11/16 file if available or use 10/16 file & edit date to a Nov date) | ZPYII_DED | py/t_pass | 2009-11-16 | 2009-11-16 | SD | complete | requested |  | 1 | 3449 | 3449 | 4 | 99.8
Long Term Care (John Hancock) - monthly; (use 11/16 file if available or 10/16 file & edit date to a Nov date) | zpyii _hancock | py/hancock | 2009-11-16 | 2009-11-16 | SD | complete | No |  | 1 | 6 | 6 |  | 100
State Quarterly - outbound report - quarterly; (use 10/01 file) | ZPY_STATE_QTR | py/mass_sqe | 2009-11-16 | 2009-11-16 | SD | complete | Yes | Overstated because there are more ssn's entered on new employees hired in Sep | 1 | 18250 | 24433
MA Health - outbound report - quarterly; Reports 3rd qtr YTD MA /701, excludes RDBP, EL and includes only EmpStat = 3. Use mass health variant, chg to 3rd qtr for current yr (use 10/01 file) | se38 ZPY_MASS_HEALTH | py/mass_hlth | 2009-11-16 | 2009-11-16 | SD | complete | Yes | SH2 tally includes non-active | 1 | 18268 | 18504 | 14 retros 6 voids 4 misc other | 99.86
Run weekly payroll - limited (44/2009) |  |  | 2009-11-17 | 2009-11-17 | Gregg M. | complete | n/a
Run LL gross pay file for weekly outbound for payweek 44, Compare the output to pay week 44. | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2009-11-17 | 2009-11-17 | SD | complete | n/a |  | 1 | 6822 | 5938 | 33 pernrs | 87.0419
Run Individual Test Cases | 1 |  | 2009-11-17 | 2009-11-20 | Alan M. | complete |  | equals production
Run Individual Test Cases | 6 |  | 2009-11-17 | 2009-11-20 | Cindy D. | complete
Run Individual Test Cases | 20 |  | 2009-11-17 | 2009-11-20 | Desiree R. | complete
Run Individual Test Cases | 12 |  | 2009-11-17 | 2009-11-20 | Emily C. | complete
Run Individual Test Cases | 2 |  | 2009-11-17 | 2009-11-20 | Frank Q. | complete
Run Individual Test Cases | 24 |  | 2009-11-17 | 2009-11-20 | Gregg M. | complete
Run Individual Test Cases | 1 |  | 2009-11-17 | 2009-11-20 | Larissa K. | complete
Run Individual Test Cases | 2 |  | 2009-11-17 | 2009-11-20 | Lavanya G. | complete
Run Individual Test Cases | 14 |  | 2009-11-17 | 2009-11-20 | Mary D. | complete
Legend:
Pay run execution
Section Heading
Lincoln Lab

## Pre-test Prep
Non-Exempt Only
Exempt Only
Relevant to both exempt and non-exempt
MITSIS file* (contains non-exempt changes as well)
MITSIS gross pay file
Pension
Copy the following in-bound files:
10/22/2009 EDS In-bound Lump Sum File
10/22/2009 EDS In-bound Annuity File
HR-Payroll Team
Create Datafiles sub-folders for feedloads and comparisons (prod & test)
Copy production archived files to Datafiles folder area.
Student Bio Feed
Keep LL Audit files
Parking file
TPASS file
Grad Appointment feed
LL Feeds - have Wai-ming copy files to test environment's sapin directory
| Archive Directory | Files Copied | # of Files
1 | hr/bcbs
2 | hr/crosby
3 | hr/crosby_dep
4 | hr/crosby_new
5 | hr/delta
6 | hr/eds_hr
7 | hr/eds_hr
8 | hr/hird
9 | hr/metpcensus
10 | hr/mitsis_dem
11 | hr/tufts
12 | hr/vision
13 | py/cu
14 | py/eds_cntrib
15 | py/facil_leav
16 | py/facil_time
17 | py/fid_cntrib
18 | py/fid_cntrib
19 | py/fid_pct
20 | py/fsa_census
21 | py/fsa_census
22 | py/fsa_dep
23 | py/fsa_dep
24 | py/fsa_enroll
25 | py/gradaid
26 | py/hancock
27 | py/hancock
28 | py/ll_audt_py
29 | py/ll_audt_tm
30 | py/ll_bank
31 | py/ll_leave
32 | py/ll_sal_dst
33 | py/ll_sal_dst
34 | py/mass_hlth
35 | py/mass_sqe
36 | py/metp-ded
37 | py/mitsis_tim
38 | py/parking
39 | py/t_pass
40 | py/tech_cash
41 | py/tiaa_cref

## For Next Year
Suggestions for next year
1 | Run Mass Health Report and Sate Quarterly Earning Report earlier in list of programs since the data is from the prior quarter
2 | Add more aliases (Laurie/Leslie) so HR Payroll support team can view payroll results