## Sheet1
| 2008 Support Packs |  |  |  | 2009 Support Packs
PS1 Snapshot for SF3 | 2008-09-22 |  |  | PS1 Snapshot for SF3 | 2009-09-28
SAP SP Release date | 2008-10-16 |  |  | SAP SP Release date | 2009-10-15
PS1 Snapshot for SH2 | 2008-10-20 |  |  | PS1 Snapshot for SH2 | 2009-10-19
SF3 System Refresh | 5 days | Tue 10/14/2008 | Mon 10/20/2008 | SF3 System Refresh | 5 days | Mon 10/5/2009 | Fri 10/09/2009
SFK Update | 4 days | Tue 10/21/2008 | Fri 10/24/2008 | SFK Update | 3 days | Tue 10/20/2009 | Fri 10/23/2009
SF3 Update | 5 days | Mon 10/27/2008 | Fri 10/31/2008 | SF3 Update | 5 days | Mon 10/26/2009 | Wed 10/28/2009
SF2 Update | 3 days | Mon 11/03/2008 | Wed 11/05/2008 | SF2 Update | 3 days | Sat 10/31/2009 | Mon 11/02/2009
SH2 System Refresh | 3 days | Mon 10/27/2008 | Wed 10/29/2008 | SH2 System Refresh | 3 days | Tue 11/03/2009 | Thu 11/05/2009
SH2 Update | 3 days | Thu 10/30/2009 | Wed 11/5/2008 | SH2 Update | 3 days | Fri 11/06/2009 | Sun 11/08/2009
|  |  |  | PS1 Snapshot for SF6 | 2009-10-19
|  |  |  | SF6 System Refresh | 3 days | TBD - Nov 2009 | TBD - Nov 2009
|  |  |  | SF6 Update | 3 days | TBD - Nov 2009 | TBD - Nov 2009
|  |  |  | SF7 Update | 3 days | TBD - Nov 2009 | TBD - Nov 2009
|  |  |  | SH2 Status Change | EOD | Fri 12/11/2009 | TBD | SH2 becomes the unscrambled production support testing system.
|  |  |  | SH1 Status Change | EOD | Fri 12/11/2009 | Thu 12/31/2009 | SH1 becomes a reference system until 12/31/2009.
|  |  |  | SF5 Status Change | EOD | Fri 12/11/2009 | Thu 12/31/2009 | SF5 becomes a reference system until 12/31/2009.
PS1 Update | 3 days | Fri 12/12/2008 | Sun 12/14/2008 | PS1 Update | 3 days | Fri 12/11/2009 | Sun 12/13/2009
PS1 Snapshot for SH1 | 2008-12-31
PS1 Snapshot for SF5 | 2008-12-31 |  |  | PS1 Snapshot for SF5 | 2009-12-16 |  |  | Taken after the production update
|  |  |  | SF5 System Refresh/Update | 4 days | Mon 01/04/2010 | Thu 01/07/2009 | SF5 resumes its role as the scrambled production support testing system.
|  |  |  | PS1 Snapshot for SF8 | 2009-12-16 |  |  | Taken after the production update
|  |  |  | SF8 System Refresh/Update | 4 days | Tue 01/25/2010 | Fri 01/28/2010
System Upgrade Order of transports:
1. Application of Support Packs
2. SF3 Transports related to SPs
3. SF2 Transports related to SPs
System Refresh Order of transports (for SH2)
1. Snapshot refresh
2. Transports to production between date of snapshot and freeze
3. System Upgrade Order of transports listed above