## Overview and Assumptions
Timeframe for Test Execution
Comparison Test: 11/11/2010-12/6/2010 (3 holidays)
Integration Test: see comparision test
Assumptions:
Production snapshot as of midnight 10/18/2010
Test system will be available by start of day 11/11/2010
Comparison test consists of four payroll comparisons:
| Weekly Non-Exempt (payweek 42 (10/11/2010-10/17/2010)) | LL | 43/2010
| Monthly Exempt (October) | MC | 44/2010 | Cycle 1 | Leslie will identify cost objects
Pension Payroll Lump Sum (October 31, 2010)
Pension Monthly Annuity Run (Nov 2010)
Overview of integration test strategy:
Generate payroll and run interfaces simulating the production payroll processes.
Compare test system SH3-Solaris results to PS1 Production results
Research discrepancies; resolve system issues
Execute select test scripts hiting key functionality not executed during pay run processes
Comparison Tools:
Create comparison reports using the EPIUSE variance monitor tool
Net pay comparisons in excel
Net pay comparison using EPIUSE variance monitor
Ultra Compare
Fox Pro
Overview of User Acceptance Test:
Test Scripts identified in the HR/Payroll Master Test Script Catalog Payroll will be run and payruns will be executed for:
Non exempt:
| Cycle 1: week | n/a
| Offcycle: | n/a
| Cycle 2: week | n/a
| Offcycle: | n/a
| Cycle 3: week | n/a | Use ASR? | n/a
Exempt:
| Cycle 1: month | n/a
| Cycle 2: month | n/a | Use ASR? | n/a
Cycle 3: month
Pension:
| Pension will be tested via the comparison runs listed above | n/a
Business Owner buy-in

## Pre-test Prep
Non-Exempt Only
Exempt Only
Relevant to both exempt and non-exempt
MITSIS file* (contains non-exempt changes as well)
MITSIS gross pay file
Pension
Copy the following in-bound files:
3/24/2010 EDS In-bound Lump Sum File
3/24/2010 EDS In-bound Annuity File
HR-Payroll Team
Create Datafiles sub-folders for feedloads and comparisons (prod & test) | [6 empty] | complete | 2010-03-08
Copy production archived files to Datafiles folder area.
Student Bio Feed (MITSIS)
Keep LL Audit files
Parking file
TPASS file
Grad Appointment feed
LL Feeds - have Wai-ming copy files to test environment's sapin directory
| Archive Directory | Files Copied | # of Files | in/out | can be loaded locally? | task link
1 | hr/bcbs |  |  | out
2 | hr/crosby |  |  | out
3 | hr/crosby_dep |  |  | out
4 | hr/crosby_new |  |  | out
5 | hr/delta |  |  | out
6 | hr/eds_hr |  |  | out
7 | hr/fid_hr |  |  | out
8 | hr/hird |  |  | out
9 | hr/metpcensus |  |  | out
10 | hr/mitsis_dem |  |  | out
11 | hr/tufts |  |  | out
12 | hr/vision |  |  | out
13 | py/cu |  |  | out
14 | py/eds_cntrib |  |  | out
15 | py/facil_leav |  |  | out
16 | py/facil_time |  | 1 | in | Yes | 74
17 | py/fid_cntrib |  |  | out
18 | py/fid_cntrib |  |  | out
19 | py/fid_pct |  |  | in | No, | 48 | Set up job to load based on event. Wai-ming should ensure i_fcp event will trigger in SH1. Move file through drop box to test HW. File has been moved to server in prep for move through the dropbox
20 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
22 | py/fsa_dep |  |  | out
23 | py/fsa_dep |  |  | out
24 | py/fsa_enroll |  |  | out
25 | py/gradaid |  | 5/5/5 | in |  | 39
26 | py/hancock |  |  | in | Yes | 77
27 | py/hancock |  |  | out
28 | py/ll_audt_py
29 | py/ll_audt_tm
30 | py/ll_bank |  |  | out
31 | py/ll_leave |  |  | out
32 | py/ll_sal_dst |  |  | out
33 | py/ll_sal_dst |  |  | out
34 | py/mass_hlth |  |  | out
35 | py/mass_sqe |  |  | out
36 | py/metp-ded | dmetficw.094.20101021000000 | 1 | in | Yes | 50
37 | py/mitsis_tim |  |  | out
38 | py/parking |  | 1/1 | in | No | 75
39 | py/t_pass |  | 1 | in | No | 76
40 | py/tech_cash | dtcshded.325.20101022000000 | 1 | in | Yes | 49
41 | py/tiaa_cref |  |  | out
42 | py/metpcont | dmetficw.094.20101021000000
43 | hr/mitsis_dem [MITSIS Biographic/Demographic files] |  | 6/6 | in |  | 38
44 | Lincoln inbound |  | 22 | in |  | 40
45 | Lincoln appts audit |  | 1
46 | Lincoln supplements audit |  | 1
47 | Lincoln actions audit |  | 1
48 | Lincoln time audit |  | 1 |  |  | 71
49 | Pension Payroll EDS In-bound Annuity File |  | 1 | in | yes | 9
50 | Pension Payroll EDS In-bound Lump Sum File |  | 1 | in | yes | 8

## Comparision Run Schedule
Task # | Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Prep files ready? | Batch ID | Job Set # | Special Variant in PS1? | Update variant in sh3 | Notes | No. of files matched | PS1 | SH3 | Variances | Percent matched
| Set up SP Variants for all the feeds |  |  | 2010-10-06 | 2010-10-15 | Mary D. Larissa Sharon | Complete
| Execute ZM Payroll simulation in PS1 |  |  | 2010-10-18 | 2010-10-18 | Gregg | Complete
| Run HIRD report in PS1- do not send, retain file for comparison |  |  | 2010-10-18 | 2010-10-18 | SD | Complete |  | ZZHRBENBTC01 |  | Y- needs to be updated |  | So we have a comparison
| SF3 - After 10/4 snapshot applied and before support packs implemented, run ZM simulation for 10/2010 - use Gregg's rem stmt variant |  |  | 2010-10-20 | 2010-10-20 | Gregg | Complete | [5 empty] | Aliases in sf3?
| SF3 - After support packs implemented, run ZM simulation for 10/2010 - use Greggs rem stmt variant |  |  | 2010-11-02 | 2010-11-02 | Gregg | Complete
| Compare BEFORE and AFTER results of 10/2010 ZM, compare to the PS1 copy of well. |  |  | 2010-11-02 | 2010-11-03 | Gregg | Complete | [5 empty] | SF3 before v. after were identical. Each with 2 variances from PS1 due to IT0210 changes post simulation prior to copy. | 19228 | 19230 | 19230 | 2 explained | 100
| SF3 - Execute Business Owner validation steps |  |  | 2010-11-03 | 2010-11-03 | HR Payroll Team | Complete
a | MIT Holiday |  |  | 2010-11-11 |  | All |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
1 | Verify Feed Registry Archive Control Tables are correct for the environment | SM30 | n/a | 2010-11-11 | 2010-11-11 | SD |  | n/a |  |  |  |  | Part of the action log. | n/a | n/a | n/a | n/a | n/a
2 | Re-configure EDI Test Environment to accept files from SH3 |  | n/a | 2010-11-11 | 2010-11-11 | Ron, Larisaa will remind him |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
3 | Confirm w/ R3 that Lincoln configuration for EDI is active |  | n/a | 2010-11-11 | 2010-11-11 | Ron Parker |  | n/a |  |  |  |  | Per Eric Ngo - The logical system is RC2CLNT400.(Ron should verify) | n/a | n/a | n/a | n/a | n/a
b | Execute ZM Payroll simulation in sh3 |  |  | 2010-11-11 | 2010-11-11 | Gregg M. |  | Yes |  |  |  |  | Compare to PS1 run. Use single line rem-statement. Log and report tie out. Don't need to wait for steps 1,,3 | 1
4 | DW extract of HR/Pay data | Multiple | n/a | 2010-11-12 | 2010-11-12 | Elena |  | n/a |  |  |  |  | Payrolls and feeds may be running | 8
5 | Set up job for Job Set 1 - update variants with correct days. | Multiple |  | 2010-11-11 | 2010-11-11 | Sharon D |  |  | ZZHRBENBTC01
6 | Outbound Run FSA Census outbound interface using Ultracompare compare file to Sunday production run (10/17). | ZPYI0170_FSA_CENSUS_DATA | py/fsa_census | 2010-11-11 | 2010-11-12 | Desiree R. |  | -- | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution | 1
7 | Outbound Run FSA Enroll outbound interface (looks at the control record) using Ultracompare compare file to Sunday production run (10/17). | ZPYI0170_FSA_ENROLLMENT_DATA | py/fsa_enroll | 2010-11-11 | 2010-11-12 | Desiree R. |  | -- | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution | 1
8 | Weekly Payroll Processing (42/2010) | Script: Non-Exempt Payroll Test for Support Pack Update 2008.doc |  | 2010-11-11 | 2010-11-11 | MD |  | n/a |  |  |  |  | see comparisons results in step 22 below | - | - | - | - | -
9 | Pension Payroll - Lump Sum Run (10/31/2010) |  |  | 2010-11-11 | 2010-11-11 | FQ/GM |  | Yes |  |  |  |  | Where do files come from? encrypted file dumps decrypted file processes correctly | 1
10 | Pension Payroll - Annuity Run (11/2010) |  |  | 2010-11-11 | 2010-11-11 | FQ/GM |  | Yes |  |  |  |  | Where do files come from? see comparisons results in step 23 below | - | - | - | - | -
[14 empty] | n/a | n/a | n/a | n/a | n/a
11 | Set up job for Job Set 2 - update variants with correct days. | Run 11/11, do not need payroll results. |  | 2010-11-11 | 2010-11-11 | Sharon D | [6 empty] | Run 11/11, do not need payroll results.
12 | Outbound Run HR Fidelity outbound interface; using ultracompare compare file to Sunday production run (10/17). | zhr_fidelity | hr/fid_hr | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SPFID WKLY PS1 |  | can run w/ DW extracts, Orig run 3/14; chgs made 10/19 | 1
13 | Outbound Benefits outbound: BCBS using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. In IDOC Cleanup allow retro 10 days-variant all set. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/bcbs | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP BC OED/ SP BCBS PRD OE |  | can run w/ DW extracts; comparison will be made to the production run (EDI)
14 | Outbound Benefits outbound: Delta using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/delta | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP DELTA OE for both |  | can run w/ DW extracts; comparisons were made to production Differences were address changes, terminations, Campus Police (didn’t exclude them in SH1 run)
15 | Outbound Benefits outbound: Tufts using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/tufts | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP TUFTS OE for both |  | can run w/ DW extracts; comparison will be made to the production run (EDI) | 1
16 | Outbound Benefits outbound: Vision using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. There is currently no retro limit in IDOC Cleanup. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP VISION OE for both |  | can run w/ DW extracts comparison will be made to the production run (EDI) | 1
17 | Outbound Run Express Scripts outbound; using ultracompare compare file to Sunday production run (10/17). | ZHR_ESI_FEED | hr/esi | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP FULLFILE OE |  | can run w/ DW extracts | 1
18 | Outbound Run Crosby Outbound terminations; using ultracompare compare files to Sunday production runs (10/17). *** follow all the way through to vendor *** | ZHRCSB02 | hr/crosby; | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SPZHRCSB02_RPT |  | can run w/ DW extracts | 1
19 | Outbound Run Crosby Outbound new entrants for the prior month (Sept); using ultracompare compare files to Sunday production runs (9/1). | ZHRCSB02 | hr/crosby_new | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP_ZHRCSB02_NH |  | can run w/ DW extracts | 1
20 | Outbound Run Crosby Outbound dependents aging out; based on file created 10/1 for Nov ageoffs using ultracompare compare files to production runs (11/1). | ZHRCSB03 | hr/crosby_dep | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP_ZHRCSB03DEP |  | can run w/ DW extracts | 1
21 | Outbound Run Metpay Census outbound interface; using ultracompare compare file to Sunday production run (10/17). | ZPY_METPAY_CENSUS_DATA | hr/metpcensus | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP PRODUCTION |  | can run w/ DW extracts | 1
22 | Outbound Run Health Insurance Resposibility Disclosure (HIRD); outbound to Crosby | ZHR_OUTBOUND_HIRD_DATA | hr/hird | 2010-11-11 | 2010-11-12 | Desiree Emily |  | -- | Run Manually | 2 | No |  | Is there a file to compare to - save in step? can run w/ DW extracts | 1
23 | Payroll Results Comparison (ZW) |  |  | 2010-11-12 | 2010-11-15 | Gregg M. |  | n/a | [5 empty] | n/a
24 | Payroll Results Comparison (ZP) |  |  | 2010-11-12 | 2010-11-15 | Gregg M. |  | n/a | [5 empty] | n/a
25 | FI POSTING COMPARISON (ZP) |  |  | 2010-11-12 | 2010-11-15 | Gregg M. |  | n/a |  |  |  |  | accounts | n/a
26 | EDACCA TABLE COMPARISON |  |  | 2010-11-15 | 2010-11-15 | Gregg M. |  | n/a | [5 empty] | n/a
27 | FI POSTING COMPARISON (ZW) |  |  | 2010-11-15 | 2010-11-15 | Gregg M. |  | n/a |  |  |  |  | accounts | n/a
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| (After Payroll Execution) Weekly Outbound Interfaces | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
28 | Set up job for Job Set 3 - update variants with correct days. |  |  | 2010-11-11 | 2010-11-11 | Mary |  |  | ZZPYBATCH001
29 | Set up job for Job Set L3 - update variants with correct days. |  |  | 2010-11-11 | 2010-11-11 | Alan |  |  | ZZHRLLFEED01
30 | Outbound Timesheet file to MITSIS (combined w/ Grad Student Gross Pay) using ultracompare compare files to Wed production runs (10/20) | ZPYIO_MITSIS_TIM | py/mitsis_tim | 2010-11-12 | 2010-11-12 | Alan |  | Yes |  | 3 | Y |  |  | 1
31 |  | Dates From Wednesday to Wednesday |  | 2010-11-12 | 2010-11-12 | Alan |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
32 | Outbound LL salary distribution weekly gross pay using ultracompare compare files to Wed production runs (10/20) File to be sent to Lincoln. | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2010-11-12 | 2010-11-12 | Alan |  | -- | ZZHRLLFEED01 | L3 | SP1ZW |  | Check for errors on filezilla | 1
33 | [7 empty] | n/a | ZZHRLLFEED01 |  | SP2ZW |  |  | n/a | n/a | n/a | n/a | n/a
34 | Outbound LL non-exempt leave accruals (this is a daily interface) using ultracompare compare files to Wed production runs (10/20) | Scheduled job ZHR_LL_ACCRUALS_OUT Check for errors on filezilla. | py/ll_leave | 2010-11-12 | 2010-11-12 | Alan |  | -- | ZZHRLLFEED01 | L3 | SP |  |  | 1
35 | Outbound Leave balance accruals for Facilities Service Staff (this is a daily interface) | ZPTKRONOS_ACCRUL_OUT | py/facil_leav | 2010-11-12 | 2010-11-12 | Karon M. |  | -- | ZZPYBATCH001 | 3 | y |  | internal test performed; additionally subsequent test performed with facilities | 1
36 | Outbound FSA (Crosby). Compare results to production file using ultracompare compare files to Wed production runs (10/20) | ZPYIO_FSA_CONTRIB /ZPY0170_FSA_CONTRIB | py/fsa_dep | 2010-11-12 | 2010-11-12 | Cindy D. |  | -- | ZZPYBATCH001 | 3 | SP_WEEKLY |  |  | 1
37 | Outbound Fidelity pension file (weekly 401 pension contributions) Use ZW Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS using ultracompare compare files to Wed production runs (10/20) | Scheduled Job ZPYIO_FID_CNTRIB/ ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2010-11-12 | 2010-11-12 | Gregg |  | -- | ZZPYBATCH001 | 3 | SP_ZWAUTOMATI |  |  | 1
38 | Outbound LL Bank details (this is a daily extract) | zpy_ll_bank_detail | py/ll_bank | 2010-11-12 | 2010-11-12 | Alan M. |  | -- | ZZPYBATCH001 | L3 | No-run adhoc |  |  | 1
39 | Inbound Student Bio Feed (MITSIS) (10/19-10/25) | ZMITSIS | hr/mitsis_dem | 2010-11-12 | 2010-11-12 | Alan M. |  | Yes | ZZHRMITSIS01 | IB1These 3 must run per day, one after the other | No |  | both old and new complete | 5
40 | Inbound Grad Appointment Inbound (this is a daily feed) (10/19-10/25) | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2010-11-12 | 2010-11-12 | Alan M. |  | Yes | ZZHRGRADAPT01 |  | No |  | both old and new complete | 7
41 | Inbound LL daily feed (10/19-10/25) run 5 feeds (one week) |  |  | 2010-11-12 | 2010-11-12 | Alan M. |  | Yes | ZZHRLLFEED01 |  | No |  | Check for errors on filezilla | 22
42 | [13 empty] | n/a | n/a | n/a | n/a | n/a
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Monthly Payroll Interface Activities | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Inbound LL Feed (production files from 10/19-10/25 Tues-Mon)include weekly, monthly and time; IDOC files needed - decrypt and copy to test system's sapin directory - IS THIS THE SAME AS ITEM#40 ABOVE -YES | ZHRALE, ZHRALELOG | n/a | 2010-11-12 | 2010-11-12 | LK | skip | Yes |  |  |  |  | duplicate of step 40 | n/a | n/a | n/a | n/a | n/a
| Service Center/Benefits office enters taxes, deduction & benefits for nine Lincoln new hires/rehires (not necessary for 2009 or 2010) LESLIE |  |  | - | - | Scott Ball/Benefits | skip | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Additional Payroll Interface Activities (before planned monthly run) | Need to coordinate with Alan's run's |  |  |  |  | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
43 | Inbound Weekly Fidelity Percent Inbound; use Friday file (10/22); compare reports to prod reports; spot-check the loaded data | ZPYII_FID_PCT | py/fid_pct | 2010-11-12 | 2010-11-12 | Run by Mary, compares by Gregg |  | Yes | ZZPYBATCH001 | IB2 |  |  | Trigger through drop box in Linux version. | 1
44 | Inbound Weekly Tech Cash Inbound; use Friday file (10/22).; compare reports to prod reports; spot-check the loaded data | ZPYII_DED | py/tech_cash | 2010-11-12 | 2010-11-12 | Run by Mary, compares by Gregg |  | Yes | ZZPYBATCH001 | IB2 |  |  |  | 1
45 | Inbound Metpay Home/Auto inbound; compare reports to prod reports; spot-check the loaded data (10/21) | ZPY_METPAY_IN | py/metp-ded | 2010-11-12 | 2010-11-12 | Run by Mary, compares by Karon |  | Yes | ZZPYBATCH001 | IB2 |  |  |  | 1
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Monthly Payroll Processing | Script: Exempt Payroll Test for Support Pack Update 2008.doc |  | 2010-11-13 | 2010-11-13 | MD |  | n/a |  |  |  |  | see results below | n/a | n/a | n/a | n/a | n/a
46 | Payroll Results Comparison (ZM) |  |  | 2010-11-15 | 2010-11-16 | Gregg M. |  | - | [5 empty] | n/a
47 | EDACCA TABLE COMPARISON |  |  | 2010-11-16 | 2010-11-16 | Gregg M. |  | - |  |  |  |  | see detail notes tab | n/a
48 | FI POSTING COMPARISON |  |  | 2010-11-16 | 2010-11-16 | Gregg M. |  | - |  |  |  |  | accounts compared | n/a
49 | ZM 3-Party Processing - Does this need to be separate - is on ZM checklist. Test garnishments to A/P, have Ken execute his piece. |  |  | 2010-11-17 | 2010-11-17 | Gregg M. |  | n/a |  |  |  |  | ZM 3PR pp 03.2010 new vs. old are a match - 33 vendor payment line items in each = 100% | n/a
| (After Monthly Payroll Payroll Execution) Outbound Interfaces (Comparisons to production files) | [5 empty] | - | [5 empty] | Set up jobs Friday. | n/a | n/a | n/a | n/a | n/a
50 | Set up job for Job Set 4 - update variants with correct days. |  |  | 2010-11-12 | 2010-11-12 | Mary |  |  | ZZPYBATCH001
51 | Set up job for Job Set L4 - update variants with correct days. |  |  | 2010-11-12 | 2010-11-12 | Alan |  |  | ZZHRLLFEED01
52 | Outbound Fidelity contributions outbound - monthly Use ZM Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS | ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2010-11-15 | 2010-11-15 | Gregg |  | -- | ZZPYBATCH001 | 4 | SP_ZM_AUTOMATI |  |  | 1
53 |  | Dates TBD |  | 2010-11-15 | 2010-11-15 |  | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
54 | Outbound EDS contributions outbound - monthly Include both weekly and monthly | ZPYIO_EDS_CNTRIB/ZPYI004_0_TOW_CONTRIB | py/eds_cntrib | 2010-11-15 | 2010-11-15 | Gregg |  | -- | ZZPYBATCH001 | 4 | SP_ZM_ZW |  |  | 1
55 |  | Check for errors on filezilla |  | 2010-11-15 | 2010-11-15 | LK/SD | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
56 | Outbound FSA contributions outbound - monthly Use monthly variant, change start date/time to before payroll run, check test, enter handliing rule 001 | ZPYIO_FSA_CONTRIB /ZPY0170_FSA_CONTRIB | py/fsa_dep | 2010-11-15 | 2010-11-15 | Cindy D. |  | -- | ZZPYBATCH001 | 4 | SP_Monthly |  |  | 1
57 | Outbound Credit Union contributions Run for dates from PS1's last run email thru end of monthly payrun | ZPYIO_CU_UNION / ZHRPY_CREDIT_UNION | py/cu | 2010-11-15 | 2010-11-15 | Gregg |  | -- | ZZPYBATCH001 | 4 | SP_VAR_ZM_ZW |  |  | 1
58 | Outbound John Hancock (long term care) contributions | ZPYIO_HANCOCK /ZPYI006_0_JHK_LTCPRE | py/hancock | 2010-11-15 | 2010-11-15 | Frank |  | -- | ZZPYBATCH001 | 4 | SP_ZM_ZW |  |  | 1
59 | Outbound TIAA-CREF (457B) contributions (10/27File) | ZPYIO_TIAA_CREF/ZPY_457B_CONTRIB_OUT | py/tiaa_cref | 2010-11-15 | 2010-11-15 | Frank |  | -- | ZZPYBATCH001 | 4 | SP__ZMAUTOMATI |  |  | 1
60 | Outbound EDS HR Outbound 10/17 File Run from start date/time as ran in production from 10/28 | ZHR_FIDELITY | hr/eds_hr | 2010-11-15 | 2010-11-15 | Frank |  | -- | ZZPYBATCH001 | 4 | SP_EDS AUTOMAT |  | 5 extra records due to LL Feed additional file decrytion test. | 1
61 | Outbound LL Salary distribution monthly gross pay | ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2010-11-15 | 2010-11-15 | Alan |  | -- | ZZHRLLFEED01 | L4 | SP-ZM |  |  | 1
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Inbound Interface Comparisons | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
62 | Load LL Time Files (10/25/2010 upto 10 files) - weekly IDOC file - need to copy to test system's sapin directory Larissa - is this the same as the LL Daily feed? Separate set of files than th linkcoln feed in step 40. | ZHRALE | n/a | 2010-11-16 | 2010-11-16 | Alan/KM/EN |  | Yes |  | IB3 |  |  | TBD (may be that Eric will review) | 13
63 | Run LL time audit (10/25/2010) - weekly | ZPYII_LL_AUDT_TM | py/ll_audt_tm | 2010-11-16 | 2010-11-16 | Eric |  | Yes |  |  |  |  | TBD (may be that LL will review (ccassidy))
64 | Run LL HR/Payroll audit files (10/25/2010) - weekly | ZHRALF02 | py/ll_audt_py | 2010-11-16 | 2010-11-16 | Eric |  | -- |  |  |  |  | Validated by Collen in the past | n/a | n/a | n/a | n/a | n/a
65 | Service Center/Benefits office enters taxes, deduction & benefits for remaining Lincoln new hires/rehires |  |  | 2010-11-16 | 2010-11-16 | Scott Ball/Benefits | skip | n/a |  |  |  |  | Does Lincoln want special cases added - ask Leslie to coordinate. | n/a | n/a | n/a | n/a | n/a
66 | Inbound Run Kronos Feed and compare IT2001/2002 records with change date of (date file was executed, changed by whomever ran the file) or time eval results. (10/25/2010) - weekly | ZHR_INBOUND_TIME | py/facil_time | 2010-11-16 | 2010-11-17 | Run by Mary, validation by KM |  | Yes | ZZPYBATCH01 | IB4 |  |  |  | 1
67 | Inbound Parking Standard Internal deductions - monthly copy to test system's sapin directory (Use 10/25 file if available) | ZPYII_DED | py/parking | 2010-11-16 | 2010-11-17 | Run by Mary, validation by FQ |  | Yes | ZZPYBATCH01 | IB4 |  |  | loaded encrypted through drop box | 1
68 | Inbound Tpass Standard Internal deductions - monthly; (use 11/16 file) (pre Nov payrun) 4 files, imputed income file is blank. | ZPYII_DED | py/t_pass | 2010-11-16 | 2010-11-17 | Run by Mary, validation by FQ |  | Yes | ZZPYBATCH01 | IB4 |  |  | loaded locally | 1
69 | Inbound Long Term Care (John Hancock) - monthly; (use 11/16 file) (pre Nov payrun) | zpyii _hancock | py/hancock | 2010-11-16 | 2010-11-17 | Run by Mary, validation by MD |  | Yes | ZZPYBATCH01 | IB4 |  |  |  | 1
70 | State Quarterly - outbound report - quarterly; Run Q3 2010 | pu19 sui wage reporting | ?- what should we do with this and next step - ask leslie? | 2010-11-16 | 2010-11-17 | SD/GM |  | -- | [5 empty] | 1
71 | Outbound MA Health - outbound report - quarterly; Reports 3rd qtr YTD MA /701, excludes RDBP, EL and includes only EmpStat = 3. Use mass health variant, chg to 1st qtr for current yr Run Q3 2010 | se38 ZPY_MASS_HEALTH | py/mass_hlth. | 2010-11-16 | 2010-11-17 | SD/GM |  | -- |  |  |  |  | ICESA file 16775 pernr rows 16774 match exactly = 100% Match - 1 minor mismatch due to a middle name being added to pernr 48973 on 4/27/10 in Linux system only | 1
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
72 | Run weekly payroll - limited (43/2010). Mary Note: This run will be for only LL run. Test cases after this run will be for week 44/2010. |  |  | 2010-11-17 | 2010-11-17 | Gregg M. |  | n/a |  |  |  |  | Just run LL files. Check with Eric if he wants to continue this testing, ot is the big comperw enough | n/a | n/a | n/a | n/a | n/a
73 | Run LL gross pay file for weekly outbound for payweek 43 Compare the output to pay week 43. File to be sent to Lincoln for comparison | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2010-11-17 | 2010-11-17 | Alan |  | n/a | ZZHRLLFEED01 | L5 |  |  | Execute only if testing feed to LL. Campus compares and send to LL. | n/a | n/a | n/a | n/a | n/a
73B | Update SH3 will any PS1 updates conducted after 10/18: * eW-2 parameters *eW-2 false positives *Update Payroll control records for earliest retro date |  |  |  |  | Mary , Gregg, Frank
| Open up testing for SIT test cases. | [12 empty] | n/a | n/a | n/a | n/a | n/a
74 | Validate access to sh3 |  |  | 2010-11-19 | 2010-11-19 | All testers
75 | APR View a transaction |  |  | 2010-11-19 |  | Scott/Amanda
76 | ESS - non Benefits |  |  | 2010-11-19 |  | Leslie
77 | SAP Web - eDACCA, eSDS, time approvals |  |  | 2010-11-19 |  | Leslie
78 | OM |  |  | 2010-11-19 |  | Leslie & Cindy
79 | E-Learning |  |  | 2010-11-19 |  | Jane/Emily/et al
80 | Exempt (Little Cayman - Mary,Cindy will support) |  |  | 2010-11-22 |  | Ana
81 | Non-Exempt (Little Cayman - Mary,Cindy will support) |  |  | 2010-11-22 |  | Mae
82 | Students (Little Cayman - Mary,Cindy will support) |  |  | 2010-11-22 |  | Mae
83 | APR |  |  | 2010-11-22 |  | Kristen/Amanda
84 | ASR |  |  | 2010-11-22 |  | Judy/Lisa/Adrienne/Emily
85 | ESS-Benefits (Desiree help with Campus Police setup) |  |  | 2010-11-22 |  | Diane/Anne/Shawn
86 | Faculty Chair |  |  | 2010-11-22 |  | Jean D
87 | OM - org unit |  |  | 2010-11-22 |  | Anne
88 | Pension |  |  | 2010-11-22 |  | Diane
89 | Execute Cycle 1 Payrolls |  |  | 2010-11-24 |  | Laurie19
90 | Miscellaneous (Gregg, support for garnishment tests) |  |  |  |  | Leslie/Scott/Tricia/Cindy/Mary/Desiree/Gregg
91 | Year End Reporting (Frank,Gregg for support) |  |  | 2010-11-24 |  | Laurie19
92 | Validations of all above transactions to be completed by 12/3/2010 |  |  |  | 2010-12-03 | All
Legend:
Pay run execution
Section Heading
Lincoln Lab
Note on P24: robertsd: PS1 Comparison
Note on P26: robertsd: PS1 comparison
Note on P27: robertsd: PS1 Comparison

## Detail Notes
Detail Notes:
Step 4 | DW | Program ZWHPAYROLL_RESULTS_NEW; extracted for 2/22/2010; 6 files:
|  | wh-payruns.asc - 14084 | 14084
|  | wh-paydet.asc - 161194 | 161194
|  | wh-payarrs.asc - 652 | 652
|  | wh-pay_dd.asc - 2348 | 2348
|  | wh-paymnt.asc - 13443 | 13443
|  | wh-paypers.asc - 14084 | 14084
Program ZWHPAYROLL_FIN; extracted for 2/22/2010 -- 3/2/2010; 2 files:
|  | wh-pay_fi_docs.asc - 2082 | 2082
|  | wh-pay_fi_post.asc - 212717 | 212717
420604
Step 54 | PY | ZM eDACCA Comparison
ZM edacca compare of 26963 rows in each system had 6 rows with small differences on a single pernr.
Mary checked the pernr (35400) and found the differences were due from a calculation difference in tuition (RTD1) resulting after termination by feeds that were run on different days - where term date was set as interface run date (term date in new is 04/22/10 & term date in old is 04/23/10).
- gm
Since the daily rate for tuition is calculated based on the total number of days in the appt, the daily rate in the new sh1 is higher since it term’d one day earlier.
-md

## Batch IDs and aliases
Batch ID assignments | PS1 Owners
ZZHRBENBTC01 | Sharon
ZZPYBATCH001 | Laurie
ZZHRGRDAPT01 | Scott
ZZHRMITSIS01 | Scott
ZZHRLLFEED | Tricia Sullivan-Mullen
Laurie19 | Laurie

## For Next Year
Suggestions for next year
1 | Run Mass Health Report and State Quarterly Earning Report earlier in list of programs since the data is from the prior quarter
2 | Add more aliases (Laurie/Leslie) so HR Payroll support team can view payroll results