## Overview and Assumptions
Timeframe for Test Execution
Comparison Test: 11/11/2010-12/6/2010 (3 holidays)
Integration Test: see comparision test
Assumptions:
Production snapshot as of midnight 10/18/2010
Test system will be available by start of day 11/11/2010
Comparison test consists of four payroll comparisons:
| Weekly Non-Exempt (payweek 42 (10/11/2010-10/17/2010)) | LL | 43/2010
| Monthly Exempt (October) | MC | 44/2010 | Cycle 1 | Leslie will identify cost objects
Pension Payroll Lump Sum (October 31, 2010)
Pension Monthly Annuity Run (Nov 2010)
Overview of integration test strategy:
Generate payroll and run interfaces simulating the production payroll processes.
Compare test system SH3-Solaris results to PS1 Production results
Research discrepancies; resolve system issues
Execute select test scripts hiting key functionality not executed during pay run processes
Comparison Tools:
Create comparison reports using the EPIUSE variance monitor tool
Net pay comparisons in excel
Net pay comparison using EPIUSE variance monitor
Ultra Compare
Fox Pro
Overview of User Acceptance Test:
Test Scripts identified in the HR/Payroll Master Test Script Catalog Payroll will be run and payruns will be executed for:
Non exempt:
| Cycle 1: week | n/a
| Offcycle: | n/a
| Cycle 2: week | n/a
| Offcycle: | n/a
| Cycle 3: week | n/a | Use ASR? | n/a
Exempt:
| Cycle 1: month | n/a
| Cycle 2: month | n/a | Use ASR? | n/a
Cycle 3: month
Pension:
| Pension will be tested via the comparison runs listed above | n/a
Business Owner buy-in

## Pre-test Prep
Non-Exempt Only
Exempt Only
Relevant to both exempt and non-exempt
MITSIS file* (contains non-exempt changes as well)
MITSIS gross pay file
Pension
Copy the following in-bound files:
3/24/2010 EDS In-bound Lump Sum File
3/24/2010 EDS In-bound Annuity File
HR-Payroll Team
Create Datafiles sub-folders for feedloads and comparisons (prod & test) | [6 empty] | complete | 2010-03-08
Copy production archived files to Datafiles folder area.
Student Bio Feed (MITSIS)
Keep LL Audit files
Parking file
TPASS file
Grad Appointment feed
LL Feeds - have Wai-ming copy files to test environment's sapin directory
| Archive Directory | Files Copied | # of Files | in/out | can be loaded locally? | task link
1 | hr/bcbs |  |  | out
2 | hr/crosby |  |  | out
3 | hr/crosby_dep |  |  | out
4 | hr/crosby_new |  |  | out
5 | hr/delta |  |  | out
6 | hr/eds_hr |  |  | out
7 | hr/fid_hr |  |  | out
8 | hr/hird |  |  | out
9 | hr/metpcensus |  |  | out
10 | hr/mitsis_dem |  |  | out
11 | hr/tufts |  |  | out
12 | hr/vision |  |  | out
13 | py/cu |  |  | out
14 | py/eds_cntrib |  |  | out
15 | py/facil_leav |  |  | out
16 | py/facil_time |  | 1 | in | Yes | 74
17 | py/fid_cntrib |  |  | out
18 | py/fid_cntrib |  |  | out
19 | py/fid_pct |  |  | in | No, | 48 | Set up job to load based on event. Wai-ming should ensure i_fcp event will trigger in SH1. Move file through drop box to test HW. File has been moved to server in prep for move through the dropbox
20 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
22 | py/fsa_dep |  |  | out
23 | py/fsa_dep |  |  | out
24 | py/fsa_enroll |  |  | out
25 | py/gradaid |  | 5/5/5 | in |  | 39
26 | py/hancock |  |  | in | Yes | 77
27 | py/hancock |  |  | out
28 | py/ll_audt_py
29 | py/ll_audt_tm
30 | py/ll_bank |  |  | out
31 | py/ll_leave |  |  | out
32 | py/ll_sal_dst |  |  | out
33 | py/ll_sal_dst |  |  | out
34 | py/mass_hlth |  |  | out
35 | py/mass_sqe |  |  | out
36 | py/metp-ded | dmetficw.094.20101021000000 | 1 | in | Yes | 50
37 | py/mitsis_tim |  |  | out
38 | py/parking |  | 1/1 | in | No | 75
39 | py/t_pass |  | 1 | in | No | 76
40 | py/tech_cash | dtcshded.325.20101022000000 | 1 | in | Yes | 49
41 | py/tiaa_cref |  |  | out
42 | py/metpcont | dmetficw.094.20101021000000
43 | hr/mitsis_dem [MITSIS Biographic/Demographic files] |  | 6/6 | in |  | 38
44 | Lincoln inbound |  | 22 | in |  | 40
45 | Lincoln appts audit |  | 1
46 | Lincoln supplements audit |  | 1
47 | Lincoln actions audit |  | 1
48 | Lincoln time audit |  | 1 |  |  | 71
49 | Pension Payroll EDS In-bound Annuity File |  | 1 | in | yes | 9
50 | Pension Payroll EDS In-bound Lump Sum File |  | 1 | in | yes | 8

## Comparision Run Schedule
Task # | Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Prep files ready? | Batch ID | Job Set # | Special Variant in PS1? | Update variant in sh3 | Notes | No. of files matched | PS1 | SH3 | Variances | Percent matched | Reasons for differences
| Set up SP Variants for all the feeds |  |  | 2010-10-06 | 2010-10-15 | Mary D. Larissa Sharon | Complete
| Execute ZM Payroll simulation in PS1 |  |  | 2010-10-18 | 2010-10-18 | Gregg | Complete
| Run HIRD report in PS1- do not send, retain file for comparison |  |  | 2010-10-18 | 2010-10-18 | SD | Complete |  | ZZHRBENBTC01 |  | Y- needs to be updated |  | So we have a comparison
| SF3 - After 10/4 snapshot applied and before support packs implemented, run ZM simulation for 10/2010 - use Gregg's rem stmt variant |  |  | 2010-10-20 | 2010-10-20 | Gregg | Complete | [5 empty] | Aliases in sf3?
| SF3 - After support packs implemented, run ZM simulation for 10/2010 - use Greggs rem stmt variant |  |  | 2010-11-02 | 2010-11-02 | Gregg | Complete
| Compare BEFORE and AFTER results of 10/2010 ZM, compare to the PS1 copy of well. |  |  | 2010-11-02 | 2010-11-03 | Gregg | Complete | [5 empty] | SF3 before v. after were identical. Each with 2 variances from PS1 due to IT0210 changes post simulation prior to copy. | 19228 | 19230 | 19230 | 2 explained | 100
| SF3 - Execute Business Owner validation steps |  |  | 2010-11-03 | 2010-11-03 | HR Payroll Team | Complete
a | MIT Holiday |  |  | 2010-11-11 |  | All |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
1 | Verify Feed Registry Archive Control Tables are correct for the environment | SM30 | n/a | 2010-11-11 | 2010-11-11 | SD | Complete | n/a |  |  |  |  | Part of the action log. | n/a | n/a | n/a | n/a | n/a
2 | Re-configure EDI Test Environment to accept files from SH3 |  | n/a | 2010-11-11 | 2010-11-11 | Ron, Larisaa will remind him | Complete | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
3 | Confirm w/ R3 that Lincoln configuration for EDI is active |  | n/a | 2010-11-11 | 2010-11-11 | Ron Parker | Complete | n/a |  |  |  |  | Per Eric Ngo - The logical system is RC2CLNT400.(Ron should verify) | n/a | n/a | n/a | n/a | n/a
b | Execute ZM Payroll simulation in sh3 |  |  | 2010-11-11 | 2010-11-11 | Gregg M. | Not done - is ok not to do | Yes |  |  |  |  | Compare to PS1 run. Use single line rem-statement. Log and report tie out. Don't need to wait for steps 1,,3 | 1
4 | DW extract of HR/Pay data | Multiple | n/a | 2010-11-12 | 2010-11-12 | Elena |  | n/a |  |  |  |  | Payrolls and feeds may be running | 8
5 | Set up job for Job Set 1 - update variants with correct days. | Multiple |  | 2010-11-11 | 2010-11-11 | Sharon D | Complete |  | ZZHRBENBTC01
6 | Outbound Run FSA Census outbound interface using Ultracompare compare file to Sunday production run (10/17). | ZPYI0170_FSA_CENSUS_DATA | py/fsa_census | 2010-11-11 | 2010-11-12 | Desiree R. | Complete | -- | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution | 1 | 2700 | 2700 | 2 | 99.99
7 | Outbound Run FSA Enroll outbound interface (looks at the control record) using Ultracompare compare file to Sunday production run (10/17). | ZPYI0170_FSA_ENROLLMENT_DATA | py/fsa_enroll | 2010-11-11 | 2010-11-12 | Desiree R. | Complete | -- | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution | 1 | 3010 | 3010 | 2 | 99.99
8 | Weekly Payroll Processing (42/2010) | Script: Non-Exempt Payroll Test for Support Pack Update 2008.doc |  | 2010-11-11 | 2010-11-11 | MD | Complete | n/a |  |  |  |  | see comparisons results in step 22 below | - | - | - | - | -
9 | Pension Payroll - Lump Sum Run (10/31/2010) |  |  | 2010-11-11 | 2010-11-11 | FQ/GM | Complete | Yes |  |  |  |  | Where do files come from? encrypted file dumps decrypted file processes correctly | 1
10 | Pension Payroll - Annuity Run (11/2010) |  |  | 2010-11-11 | 2010-11-11 | FQ/GM | Complete | Yes |  |  |  |  | Where do files come from? see comparisons results in step 23 below | - | - | - | - | -
[14 empty] | n/a | n/a | n/a | n/a | n/a
11 | Set up job for Job Set 2 - update variants with correct days. | Run 11/11, do not need payroll results. |  | 2010-11-11 | 2010-11-11 | Sharon D | Complete | [5 empty] | Run 11/11, do not need payroll results.
12 | Outbound Run HR Fidelity outbound interface; using ultracompare compare file to Sunday production run (10/17). | zhr_fidelity | hr/fid_hr | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SPFID WKLY PS1 |  | can run w/ DW extracts, Orig run 3/14; chgs made 10/19 | 1 | 610 | 613 | 58 | 91.6
13 | Outbound Benefits outbound: BCBS using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. In IDOC Cleanup allow retro 10 days-variant all set. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/bcbs | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP BC OED/ SP BCBS PRD OE |  | can run w/ DW extracts; comparison will be made to the production run (EDI) |  | 354984 | 355581 | 816 | 99.98
14 | Outbound Benefits outbound: Delta using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/delta | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP DELTA OE for both |  | can run w/ DW extracts; comparisons were made to production Differences were address changes, terminations, Campus Police (didn’t exclude them in SH1 run) |  | 59652 | 59799 | 167 | 99.98
15 | Outbound Benefits outbound: Tufts using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/tufts | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP TUFTS OE for both |  | can run w/ DW extracts; comparison will be made to the production run (EDI) | 1 | 10419 | 10754 | 341 | 97
16 | Outbound Benefits outbound: Vision using ultracompare compare file to Sunday production run (10/17). Run for dates 10/17 - 100 days thru 10/17 + 45. There is currently no retro limit in IDOC Cleanup. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP VISION OE for both |  | can run w/ DW extracts comparison will be made to the production run (EDI) | 1 | 52865 | 52921 | 64 | 99.9
17 | Outbound Run Express Scripts outbound; using ultracompare compare file to Sunday production run (10/17). | ZHR_ESI_FEED | hr/esi | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP FULLFILE OE |  | can run w/ DW extracts | 1 | 16074 | 16080 | 32 | 99.9
18 | Outbound Run Crosby Outbound terminations; using ultracompare compare files to Sunday production runs (10/17). *** follow all the way through to vendor *** | ZHRCSB02 | hr/crosby; | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SPZHRCSB02_RPT |  | can run w/ DW extracts | 1 | 60 | 60 | 0 | 100
19 | Outbound Run Crosby Outbound new entrants for the prior month (Sept); using ultracompare compare files to Sunday production runs (9/1). | ZHRCSB02 | hr/crosby_new | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP_ZHRCSB02_NH |  | can run w/ DW extracts | 1 | 314 | 314 | 1 | 99.7
20 | Outbound Run Crosby Outbound dependents aging out; based on file created 10/1 for Nov ageoffs using ultracompare compare files to production runs (11/1). | ZHRCSB03 | hr/crosby_dep | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP_ZHRCSB03DEP |  | can run w/ DW extracts | 1 | 34 | 34 | 0 | 100
21 | Outbound Run Metpay Census outbound interface; using ultracompare compare file to Sunday production run (10/17). | ZPY_METPAY_CENSUS_DATA | hr/metpcensus | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | ZZHRBENBTC01 | 2 | SP PRODUCTION |  | can run w/ DW extracts | 1 | 14086 | 14088 | 1180 | 91.7 | For retirees the program randomly selects which of the two pernrs the retiree has, resulting in sometimes the CUR record is picked, sometimes the RDBP. The variance is due to which reocrd was selected - so address might be the same but spelled differently between two records.
22 | Outbound Run Health Insurance Resposibility Disclosure (HIRD); outbound to Crosby | ZHR_OUTBOUND_HIRD_DATA | hr/hird | 2010-11-11 | 2010-11-12 | Desiree Emily | Complete | -- | Run Manually | 2 | No |  | Is there a file to compare to - save in step? can run w/ DW extracts | 1 | 68 | 68 | 1 | 98.6 | One record with a character difference. Not Support pack related, due to special character conversion and whicj id and machine the extract was run.
23 | Payroll Results Comparison (ZW) |  |  | 2010-11-12 | 2010-11-15 | Gregg M. | Complete | n/a | [5 empty] | n/a | 3996 | 3993 | 23 | 99.9 | 100% verified
24 | Payroll Results Comparison (ZP) |  |  | 2010-11-12 | 2010-11-15 | Gregg M. | Complete | n/a | [5 empty] | n/a | 5680 | 5697 | 31 | 99.99 | 100% verified
24a | Payroll Results Comparison (ZP)Lump Sum | [5 empty] | Complete | [6 empty] | n/a | 44 | 44 | 0 | 100
25 | FI POSTING COMPARISON (ZP) |  |  | 2010-11-12 | 2010-11-15 | Gregg M. | Complete | n/a |  |  |  |  | accounts | n/a | 25 | 25 | 6 | 76 | appears reasonable
25a | FI POSTING COMPARISON (ZP)Lump Sum | [5 empty] | Complete | [6 empty] | n/a | 4 | 4 | 0 | 100
26 | EDACCA TABLE COMPARISON |  |  | 2010-11-15 | 2010-11-15 | Gregg M. | Complete | n/a | [5 empty] | n/a | 10492 | 10488 | 2 | 99.99 | 100% verified
27 | FI POSTING COMPARISON (ZW) |  |  | 2010-11-15 | 2010-11-15 | Gregg M. | Complete | n/a |  |  |  |  | accounts | n/a | 1744 | 1743 | 23 | 99 | appears reasonable
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| (After Payroll Execution) Weekly Outbound Interfaces | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
28 | Set up job for Job Set 3 - update variants with correct days. |  |  | 2010-11-11 | 2010-11-11 | Mary | Complete |  | ZZPYBATCH001
29 | Set up job for Job Set L3 - update variants with correct days. |  |  | 2010-11-11 | 2010-11-11 | Alan | Complete |  | ZZHRLLFEED01
30 | Outbound Timesheet file to MITSIS (combined w/ Grad Student Gross Pay) using ultracompare compare files to Wed production runs (10/20) | ZPYIO_MITSIS_TIM | py/mitsis_tim | 2010-11-12 | 2010-11-12 | Alan | Complete | Yes |  | 3 | Y |  |  | 1 | 2217 | 2217 | 0 | 100%
31 |  | Dates From Wednesday to Wednesday |  | 2010-11-12 | 2010-11-12 | Alan | Complete | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
32 | Outbound LL salary distribution weekly gross pay using ultracompare compare files to Wed production runs (10/20) File to be sent to Lincoln. | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2010-11-12 | 2010-11-12 | Alan |  | -- | ZZHRLLFEED01 | L3 | SP1ZW |  | Check for errors on filezilla | 1 | 5898 | 5898 | 1 | 99.99 | Compare results: retro adj in prd not in sh3 - ok
33 | [7 empty] | n/a | ZZHRLLFEED01 |  | SP2ZW |  |  | n/a | n/a | n/a | n/a | n/a
34 | Outbound LL non-exempt leave accruals (this is a daily interface) using ultracompare compare files to Wed production runs (10/20) | Scheduled job ZHR_LL_ACCRUALS_OUT Check for errors on filezilla. | py/ll_leave | 2010-11-12 | 2010-11-12 | Alan | Complete | -- | ZZHRLLFEED01 | L3 | SP |  |  | 1 | 3171 | 3169 | 167 | 95 | Compare results:time eval run out of seq ( in prod - run after leave accr)
35 | Outbound Leave balance accruals for Facilities Service Staff (this is a daily interface) | ZPTKRONOS_ACCRUL_OUT | py/facil_leav | 2010-11-12 | 2010-11-12 | Karon M. | Complete | -- | ZZPYBATCH001 | 3 | y |  | internal test performed; additionally subsequent test performed with facilities | 1 | 2410 | 2410 | 0 | 100
36 | Outbound FSA (Crosby). Compare results to production file using ultracompare compare files to Wed production runs (10/20) | ZPYIO_FSA_CONTRIB /ZPY0170_FSA_CONTRIB | py/fsa_dep | 2010-11-12 | 2010-11-12 | Cindy D. | Complete | -- | ZZPYBATCH001 | 3 | SP_WEEKLY |  |  | 1 | 445 | 445 | 1 | 99.99 | 1 Variance due to manual entry
37 | Outbound Fidelity pension file (weekly 401 pension contributions) Use ZW Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS using ultracompare compare files to Wed production runs (10/20) | Scheduled Job ZPYIO_FID_CNTRIB/ ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2010-11-12 | 2010-11-12 | Gregg | Complete | -- | ZZPYBATCH001 | 3 | SP_ZWAUTOMATI |  |  | 1 | 2300 | 2306 | 8 | 99.7 | 100% verified
38 | Outbound LL Bank details (this is a daily extract) | zpy_ll_bank_detail | py/ll_bank | 2010-11-12 | 2010-11-12 | Alan M. | Complete | -- | ZZPYBATCH001 | L3 | No-run adhoc |  |  | 1 | 11 | 11 | 0 | 100
39 | Inbound Student Bio Feed (MITSIS) (10/19-10/25) | ZMITSIS | hr/mitsis_dem | 2010-11-12 | 2010-11-12 | Alan M. | Complete | Yes | ZZHRMITSIS01 | IB1These 3 must run per day, one after the other | No |  | both old and new complete | 5
40 | Inbound Grad Appointment Inbound (this is a daily feed) (10/19-10/25) | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2010-11-12 | 2010-11-12 | Alan M. | Complete | Yes | ZZHRGRADAPT01 |  | No |  | both old and new complete | 7
41 | Inbound LL daily feed (10/19-10/25) run 5 feeds (one week) |  |  | 2010-11-12 | 2010-11-12 | Alan M. | Complete | Yes | ZZHRLLFEED01 |  | No |  | Check for errors on filezilla | 22
42 | [13 empty] | n/a | n/a | n/a | n/a | n/a
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Monthly Payroll Interface Activities | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Inbound LL Feed (production files from 10/19-10/25 Tues-Mon)include weekly, monthly and time; IDOC files needed - decrypt and copy to test system's sapin directory - IS THIS THE SAME AS ITEM#40 ABOVE -YES | ZHRALE, ZHRALELOG | n/a | 2010-11-12 | 2010-11-12 | LK | skip | Yes |  |  |  |  | duplicate of step 40 | n/a | n/a | n/a | n/a | n/a
| Service Center/Benefits office enters taxes, deduction & benefits for nine Lincoln new hires/rehires (not necessary for 2009 or 2010) LESLIE |  |  | - | - | Scott Ball/Benefits | skip | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Additional Payroll Interface Activities (before planned monthly run) | Need to coordinate with Alan's run's |  |  |  |  | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
43 | Inbound Weekly Fidelity Percent Inbound; use Friday file (10/22); compare reports to prod reports; spot-check the loaded data | ZPYII_FID_PCT | py/fid_pct | 2010-11-12 | 2010-11-12 | Run by Mary, compares by Gregg | Complete | Yes | ZZPYBATCH001 | IB2 |  |  | Trigger through drop box in Linux version. | 1 | 41 | 41 | 0 | 100
44 | Inbound Weekly Tech Cash Inbound; use Friday file (10/22).; compare reports to prod reports; spot-check the loaded data | ZPYII_DED | py/tech_cash | 2010-11-12 | 2010-11-12 | Run by Mary, compares by Gregg | Complete | Yes | ZZPYBATCH001 | IB2 |  |  |  | 1 | 495 | 495 | 0 | 100
45 | Inbound Metpay Home/Auto inbound; compare reports to prod reports; spot-check the loaded data (10/21) | ZPY_METPAY_IN | py/metp-ded | 2010-11-12 | 2010-11-12 | Run by Mary, compares by Karon | Complete | Yes | ZZPYBATCH001 | IB2 |  |  |  | 1 | 3 | 3 | 0 | 100
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Monthly Payroll Processing | Script: Exempt Payroll Test for Support Pack Update 2008.doc |  | 2010-11-13 | 2010-11-13 | MD | Complete | n/a |  |  |  |  | see results below | n/a | n/a | n/a | n/a | n/a
46 | Payroll Results Comparison (ZM) |  |  | 2010-11-15 | 2010-11-16 | Gregg M. | Complete | - | [5 empty] | n/a | 12901 | 12885 | 546 | 95.8 | verified to IT changes, with additional spot checks
47 | EDACCA TABLE COMPARISON |  |  | 2010-11-16 | 2010-11-16 | Gregg M. | Complete | - |  |  |  |  | see detail notes tab | n/a | 10624 | 10553 | 342 | 96.8 | verified to IT changes, with additional spot checks
48 | FI POSTING COMPARISON |  |  | 2010-11-16 | 2010-11-16 | Gregg M. | Complete | - |  |  |  |  | accounts compared | n/a | 71 | 69 | 38 |  | total DB/CR variance 1.19% [99% total overall dollar match], median % of accounts with a variance = .07%, average % of accounts with a variance = 4.13%
49 | ZM 3-Party Processing - Does this need to be separate - is on ZM checklist. Test garnishments to A/P, have Ken execute his piece. |  |  | 2010-11-17 | 2010-11-17 | Gregg M. |  | n/a |  |  |  |  | ZM 3PR pp 03.2010 new vs. old are a match - 33 vendor payment line items in each = 100% | n/a
| (After Monthly Payroll Payroll Execution) Outbound Interfaces (Comparisons to production files) | [5 empty] | - | [5 empty] | Set up jobs Friday. | n/a | n/a | n/a | n/a | n/a
50 | Set up job for Job Set 4 - update variants with correct days. |  |  | 2010-11-12 | 2010-11-12 | Mary | Complete |  | ZZPYBATCH001
51 | Set up job for Job Set L4 - update variants with correct days. |  |  | 2010-11-12 | 2010-11-12 | Alan | Complete |  | ZZHRLLFEED01
52 | Outbound Fidelity contributions outbound - monthly Use ZM Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS | ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2010-11-15 | 2010-11-15 | Gregg | Complete | -- | ZZPYBATCH001 | 4 | SP_ZM_AUTOMATI |  |  | 1 | 6329 | 6322 | 48 | 99.3 | 100%verified
53 |  | Dates TBD |  | 2010-11-15 | 2010-11-15 |  | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
54 | Outbound EDS contributions outbound - monthly Include both weekly and monthly | ZPYIO_EDS_CNTRIB/ZPYI004_0_TOW_CONTRIB | py/eds_cntrib | 2010-11-15 | 2010-11-15 | Gregg | Complete | -- | ZZPYBATCH001 | 4 | SP_ZM_ZW |  |  | 1 | 10777 | 10760 | 2913 | 73 | 95%verified
55 |  | Check for errors on filezilla |  | 2010-11-15 | 2010-11-15 | LK/SD | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
56 | Outbound FSA contributions outbound - monthly Use monthly variant, change start date/time to before payroll run, check test, enter handliing rule 001 | ZPYIO_FSA_CONTRIB /ZPY0170_FSA_CONTRIB | py/fsa_dep | 2010-11-15 | 2010-11-15 | Cindy D. | Complete | -- | ZZPYBATCH001 | 4 | SP_Monthly |  |  | 1 | 2087 | 2088 | 4 | 99.99 | variances due to manual entries
57 | Outbound Credit Union contributions Run for dates from PS1's last run email thru end of monthly payrun | ZPYIO_CU_UNION / ZHRPY_CREDIT_UNION | py/cu | 2010-11-15 | 2010-11-15 | Gregg | Complete | -- | ZZPYBATCH001 | 4 | SP_VAR_ZM_ZW |  |  | 1 | 3012 | 3006 | 56 | 98.2 | Difference changes in Credit Union,new or stopped CU deduction
58 | Outbound John Hancock (long term care) contributions | ZPYIO_HANCOCK /ZPYI006_0_JHK_LTCPRE | py/hancock | 2010-11-15 | 2010-11-15 | Frank | Complete | -- | ZZPYBATCH001 | 4 | SP_ZM_ZW |  |  | 1 | 602 | 603 | 2 | 99.99 | 100% verified
59 | Outbound TIAA-CREF (457B) contributions (10/27File) | ZPYIO_TIAA_CREF/ZPY_457B_CONTRIB_OUT | py/tiaa_cref | 2010-11-15 | 2010-11-15 | Frank | Complete | -- | ZZPYBATCH001 | 4 | SP__ZMAUTOMATI |  |  | 1 | 215 | 216 | 1 | 100 | Test indicator in sh3 file - ok
60 | Outbound EDS HR Outbound 10/17 File Run from start date/time as ran in production from 10/28 | ZHR_FIDELITY | hr/eds_hr | 2010-11-15 | 2010-11-15 | Frank | Complete | -- | ZZPYBATCH001 | 4 | SP_EDS AUTOMAT |  |  | 1 | 749 | 634 | 115 | 85 | All pernrs had Master data changes
61 | Outbound LL Salary distribution monthly gross pay | ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2010-11-15 | 2010-11-15 | Alan | Complete | -- | ZZHRLLFEED01 | L4 | SP-ZM |  |  | 1 | 2451 | 2446 | 11 | 99.99 | 4 records were different pernrs #s created for new hires, rest were manual adjustments not recorded in SH3 - ok
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Inbound Interface Comparisons | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
62 | Load LL Time Files (10/25/2010 upto 10 files) - weekly IDOC file - need to copy to test system's sapin directory Larissa - is this the same as the LL Daily feed? Separate set of files than th linkcoln feed in step 40. | ZHRALE | n/a | 2010-11-16 | 2010-11-16 | Alan/KM/EN | Complete | Yes |  | IB3 |  |  | TBD (may be that Eric will review) | 13
63 | Run LL time audit (10/25/2010) - weekly | ZPYII_LL_AUDT_TM | py/ll_audt_tm | 2010-11-16 | 2010-11-16 | Eric |  | Yes |  |  |  |  | TBD (may be that LL will review (ccassidy))
64 | Run LL HR/Payroll audit files (10/25/2010) - weekly | ZHRALF02 | py/ll_audt_py | 2010-11-16 | 2010-11-16 | Eric |  | -- |  |  |  |  | Validated by Collen in the past | n/a | n/a | n/a | n/a | n/a
65 | Service Center/Benefits office enters taxes, deduction & benefits for remaining Lincoln new hires/rehires |  |  | 2010-11-16 | 2010-11-16 | Scott Ball/Benefits | skip | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
66 | Inbound Run Kronos Feed and compare IT2001/2002 records with change date of (date file was executed, changed by whomever ran the file) or time eval results. (10/25/2010) - weekly | ZHR_INBOUND_TIME | py/facil_time | 2010-11-16 | 2010-11-17 | Run by Mary, validation by KM | Complete | Yes | ZZPYBATCH01 | IB4 |  |  |  | 1 | 2107 | 2107 | 0 | 100
67 | Inbound Parking Standard Internal deductions - monthly copy to test system's sapin directory (Use 10/25 file if available) | ZPYII_DED | py/parking | 2010-11-16 | 2010-11-17 | Run by Mary, validation by FQ | Complete | Yes | ZZPYBATCH01 | IB4 |  |  | loaded encrypted through drop box | 1 | 4193 | 4193 | 4 | 100 | $ errors- all legitimate.
68 | Inbound Tpass Standard Internal deductions - monthly; (use 11/16 file) (pre Nov payrun) 4 files, imputed income file is blank. Process 1 file - post tax TPAss | ZPYII_DED | py/t_pass | 2010-11-16 | 2010-11-17 | Run by Mary, validation by FQ | Complete | Yes | ZZPYBATCH01 | IB4 |  |  | loaded locally | 1 | 130 | 130 | 0 | 100
69 | Inbound Long Term Care (John Hancock) - monthly; (use 11/16 file) (pre Nov payrun) | zpyii _hancock | py/hancock | 2010-11-16 | 2010-11-17 | Run by Mary, validation by MD | Complete | Yes | ZZPYBATCH01 | IB4 |  |  |  | 1 | 12 | 12 | 1 | 99 | 100% verified
70 | State Quarterly - outbound report - quarterly; Run Q3 2010 | pu19 sui wage reporting | ?- what should we do with this and next step - ask leslie? | 2010-11-16 | 2010-11-17 | SD/GM | Complete | -- | [5 empty] | 1 | 17167 | 17167 | 16 | 99.99 | 100% verified
71 | Outbound MA Health - outbound report - quarterly; Reports 3rd qtr YTD MA /701, excludes RDBP, EL and includes only EmpStat = 3. Use mass health variant, chg to 1st qtr for current yr Run Q3 2010 | se38 ZPY_MASS_HEALTH | py/mass_hlth. | 2010-11-16 | 2010-11-17 | SD/GM | Complete | -- | [5 empty] | 1 | 18710 | 18707 | 7 | 99.99 | 100% verified
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
72 | Run weekly payroll - limited (43/2010). Mary Note: This run will be for only LL run. Test cases after this run will be for week 44/2010. |  |  | 2010-11-17 | 2010-11-17 | Gregg M. | Complete | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
73 | Run LL gross pay file for weekly outbound for payweek 43 Compare the output to pay week 43. File to be sent to Lincoln for comparison | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2010-11-17 | 2010-11-17 | Alan | Complete | n/a | ZZHRLLFEED01 | L5 |  |  | Execute only if testing feed to LL. Campus compares and send to LL. |  | 8742 | 6166 | 9 | 99.9 | 2 employees (7 recs are new hires diff pernrs- -system) 1 employee (2 records) retro adj in prd not in sh3 - 11 (added 2567 recs) employees in prd with retros not in sh3 - all issues ok
73B | Update SH3 will any PS1 updates conducted after 10/18: * eW-2 parameters *eW-2 false positives *Update Payroll control records for earliest retro date |  |  |  |  | Mary , Gregg, Frank | Complete
| Open up testing for SIT test cases. | [12 empty] | n/a | n/a | n/a | n/a | n/a
74 | Validate access to sh3 |  |  | 2010-11-19 | 2010-11-19 | All testers | Complete
75 | APR View a transaction |  |  | 2010-11-19 |  | Scott/Amanda | Complete
76 | ESS - non Benefits |  |  | 2010-11-19 |  | Leslie | Complete
77 | SAP Web - eDACCA, eSDS, time approvals |  |  | 2010-11-19 |  | Leslie | Complete
78 | OM |  |  | 2010-11-19 |  | Leslie & Cindy | Complete
79 | E-Learning |  |  | 2010-11-19 |  | Jane/Emily/et al | Complete
80 | Exempt (Little Cayman - Mary,Cindy will support) |  |  | 2010-11-22 |  | Ana | Complete
81 | Non-Exempt (Little Cayman - Mary,Cindy will support) |  |  | 2010-11-22 |  | Mae | Complete
82 | Students (Little Cayman - Mary,Cindy will support) |  |  | 2010-11-22 |  | Mae | Complete
83 | APR |  |  | 2010-11-22 |  | Kristen/Amanda | Complete
84 | ASR |  |  | 2010-11-22 |  | Judy/Lisa/Adrienne/Emily | Complete
85 | ESS-Benefits (Desiree help with Campus Police setup) |  |  | 2010-11-22 |  | Diane/Anne/Shawn | Complete
86 | Faculty Chair |  |  | 2010-11-22 |  | Jean D | Complete
87 | OM - org unit |  |  | 2010-11-22 |  | Anne | Complete
88 | Pension |  |  | 2010-11-22 |  | Diane | Complete
89 | Execute Cycle 1 Payrolls |  |  | 2010-11-24 |  | Laurie19 | Complete
90 | Miscellaneous (Gregg, support for garnishment tests) |  |  |  |  | Leslie/Scott/Tricia/Cindy/Mary/Desiree/Gregg | Complete
91 | Year End Reporting (Frank,Gregg for support) |  |  | 2010-11-24 |  | Laurie19 | Complete
92 | Validations of all above transactions to be completed by 12/3/2010 |  |  |  | 2010-12-03 | All | Complete
Legend:
Pay run execution
Section Heading
Lincoln Lab
Note on P24: robertsd: PS1 Comparison
Note on P26: robertsd: PS1 comparison
Note on P27: robertsd: PS1 Comparison

## Detail Notes
Detail Notes:
Step 4 | DW | Program ZWHPAYROLL_RESULTS_NEW; extracted for 2/22/2010; 6 files:
|  | wh-payruns.asc - 14084 | 14084
|  | wh-paydet.asc - 161194 | 161194
|  | wh-payarrs.asc - 652 | 652
|  | wh-pay_dd.asc - 2348 | 2348
|  | wh-paymnt.asc - 13443 | 13443
|  | wh-paypers.asc - 14084 | 14084
Program ZWHPAYROLL_FIN; extracted for 2/22/2010 -- 3/2/2010; 2 files:
|  | wh-pay_fi_docs.asc - 2082 | 2082
|  | wh-pay_fi_post.asc - 212717 | 212717
420604
Step 54 | PY | ZM eDACCA Comparison
ZM edacca compare of 26963 rows in each system had 6 rows with small differences on a single pernr.
Mary checked the pernr (35400) and found the differences were due from a calculation difference in tuition (RTD1) resulting after termination by feeds that were run on different days - where term date was set as interface run date (term date in new is 04/22/10 & term date in old is 04/23/10).
- gm
Since the daily rate for tuition is calculated based on the total number of days in the appt, the daily rate in the new sh1 is higher since it term’d one day earlier.
-md

## Batch IDs and aliases
Batch ID assignments | PS1 Owners
ZZHRBENBTC01 | Sharon
ZZPYBATCH001 | Laurie
ZZHRGRDAPT01 | Scott
ZZHRMITSIS01 | Scott
ZZHRLLFEED | Tricia Sullivan-Mullen
Laurie19 | Laurie

## For Next Year
Suggestions for next year
1 | Hi Mary, One of the zutarchivecrtl or zhr_feed registry tables is messed up on the monthly metpay contributions. I don’t see the issue so I ran the weekly outbound one instead and ran the comparison. All 179 records matched except for the header line which has a run date imbedded. I think comparing just the weekly should be good enough for this feed, but let me know if you think otherwise. This SH3 environment was missing some of the set up needed to run the feeds that we ran a few times. I talked with Frank about getting these tables copied from either SH1 or SH2 so we don’t have to struggle to run them. I will ask the development team if that will affect their testing since their business analysts test in SF5. For our testing Zehcat was missing all hr/payroll feeds. I entered them manually. 3 Cobra feeds and the LL Bank feed were not set up to run in SH3. We can’t use the production version because they send out to different locations. This is my recommendation for next time. Sharon Sharon DiLiberto
2 | Hi Mary, Alan’s LL leave accruals ran too late in the schedule. We should run the LL leave accruals with 10/18/2010 before running the non-exempt time eval/payroll on the next year’s list. LK has been working with Alan. I wonder if this affected the Kronos Leave Accruals too? Sharon
3 | Make sure Lincoln has accesss to test system. They use Citrix and had issue in 2010 - sh3 needed to be added.
4 | Make sure web links, communications are established for test system - EL, APR.
5 | Sharon: . I will recommend that we get a copy of the zehcat, zutarchivecrtl and zhr_feed_registry from a better environment next time to reduce the problems that we incurred.
6 | Sharon: I will also recommend the Larissa be allowed in to test the EDI connection as part of the action log items. I also had to set up every vendor’s login credential in a view that can’t be exported and imported to this new environment.
7 | Emilly: we need to have the ASR files uploaded from the archive server to the proper server for each environment so that the ASR Faculty spreadsheet works correctly. This would need to be done before we can do ASR testing. We completely missed this in SH3 as we haven't used this environment yet. Is this something we could add to your list?