## Results(1)
id | Queue | Subject | Status | TimeEstimated | TimeWorked | TimeLeft | Priority | FinalPriority | Owner | Requestors | Due | Told | Created | Resolved | Issue Stage | Test Phase | Environment | Severity | Transport # Sequence Old | SAP Project Name | Sub Area | Assigned To | Operating System | Issue Phase | PS1 Business Area | Root Cause | Category | Transport # Sequence | Browser | Company Code | Issue Found In
1393223 | SAP::Test Issues | SAP 2010: Resolving SPAU_ENH - BAdI / Enhancements | resolved | 0 | 0 | 0 | 1 | 0 | waiming | waiming@mit.edu | 1970-01-01 | 2010-11-05 20:47 | 2010-11-04 18:44 | 2010-11-12 16:00 | Fixed |  | SF2 |  |  | SAP Support Pack 2010 |  | waiming |  | Analysis |  | Routine Maintenance |  | Released & imported into SH3.SF2K949501 - SP10/RT#1393223: Enhancement ZIW31SF2K949503 - Supp Pack 2010: SPAU_ENH for ZIBAPI_ALM_ORD_MOD2SF2K949505 - Supp Pack 2010 1393223 Adjust Z_ENH_LSO_PARTICIPATION_INSERTSF2K949507 - Supp Pack 2010: SPAU_ENH for ZAP_RFP_TRANS_FV60_SETTINGSF2K949511 - SP10/RT#1393223: Enhancements ZZ_ENH_... |  |  | SAP Gui
1393315 | SAP::Test Issues | SAP 2010: FI Program Generations triggered from PA40 (IT0000) | resolved | 0 | 0 | 0 | 2 | 0 | rep | cindyo@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-04 19:31 | 2010-11-24 05:20 |  | Unit | SF2 | Low |  | SAP Support Pack 2010 | [7 empty] | No transport required.Step to generate affected objects will be included in go-live R3-Action-Log. |  |  | SAP Gui
1394275 | SAP::Test Issues | SAP2010 HR: ZHRLTD_ASSIGN error | resolved | 0 | 0 | 0 | 0 | 0 | cindyo | cindyo@mit.edu | 1970-01-01 | 2010-11-08 19:25 | 2010-11-05 16:34 | 2010-11-12 16:05 | Fixed | Unit | SF2 | High |  | SAP Support Pack 2010 | HR/Payroll | cindyo |  | Complete |  |  |  | Released & imported into SH3.SF3K903397 R3ADM* OSS 1514455 - Dump UNCAUGHT_EXCEPTION by hiring |  |  | SAP Gui
1394285 | SAP::Test Issues | SAP2010 HR:IT9033 Audit Report | resolved | 0 | 0 | 0 | 0 | 0 | cindyo | cindyo@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-05 16:44 | 2010-11-08 17:06 | Fixed | Unit | SF2 |  |  | SAP Support Pack 2010 | HR/Payroll | cindyo |  | Complete |  |  |  | No transport required. |  |  | SAP Gui
1394298 | SAP::Test Issues | SAP 2010 - HR Payroll - DSM errors | resolved | 0 | 0 | 0 | 0 | 0 | donovan | donovan@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-05 16:55 | 2010-11-10 19:02 | Fixed | Unit | SF2 | Low |  | SAP Support Pack 2010 | HR/Payroll | donovan |  | Review |  |  |  | No transport required. |  |  | SAP Gui
1394674 | SAP::Test Issues | SAPWeb Create/Change JV can't use WBS | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | fuller@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-05 21:27 | 2010-11-12 16:14 | Fixed | Unit | SF2 | Severe |  | SAP Support Pack 2010 | JV Suite | fuller |  | Development | JV | SAP Defect | Defect | Released & imported into SH3.SF3K903395 R3ADM* OSS 1496055 - FBV1/FB01/fast entry: Message KI 235 |  |  | SAPweb
1397279 | SAP::Test Issues | SAP 2010 - EHS - WWI fails to operate in Windows 7 | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | lcollier@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-08 13:40 | 2010-11-23 18:41 | Assigned | Unit | SH3 | Medium |  | SAP Support Pack 2010 | EH&S | jrtuttle |  |  | EHS |  | Defect | No transport required.Will require upgrading EHS staff's (identified in this ticket) GUI to patch level 16. |  | CUR | Other
1397513 | SAP::Test Issues | SAP 2010: EDI - Possible issue with inbound EDI invoices in SF2 | resolved | 0 | 0 | 0 | 0 | 0 | eprudden | eprudden@mit.edu | 1970-01-01 | 2010-11-12 16:45 | 2010-11-08 15:41 | 2010-11-12 16:48 | Fixed | Unit | SF2 |  |  | SAP Support Pack 2010 | Logistics | rep |  | Analysis |  | Infrastructure |  | No transport required. |  |  | SAP Processing
1397757 | SAP::Test Issues | GuiXT Issue: Technically Completing Work Orders | resolved | 0 | 0 | 0 | 0 | 0 | mzhovnir | lstcroix@plant.mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-08 18:18 | 2010-11-18 04:13 | Assigned | Unit | SF2 | High |  | SAP Support Pack 2010 | Logistics | mzhovnir |  | Analysis |  |  |  | No transport required.Fix provided by GuiXT vendor. |  |  | SAP Gui
1397770 | SAP::Test Issues | GuiXT: Action Log Button | resolved | 0 | 0 | 0 | 0 | 0 | mzhovnir | lstcroix@plant.mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-08 18:30 | 2010-11-18 04:16 | Assigned | Unit | SF2 | High |  | SAP Support Pack 2010 |  | mzhovnir | [5 empty] | No transport required.Fix provided by GuiXT vendor. |  |  | SAP Gui
1397775 | SAP::Test Issues | GuiXT: Put In Process | resolved | 0 | 0 | 0 | 0 | 0 | mzhovnir | lstcroix@plant.mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-08 18:34 | 2010-11-18 04:15 | Assigned | Unit |  | High |  | SAP Support Pack 2010 | Logistics | mzhovnir |  | Analysis |  |  |  | No transport required.Fix provided by GuiXT vendor. |  |  | SAP Gui
1398450 | SAP::Test Issues | SAP 2010 - HRP ZHR_HOURLY_GRAD | resolved | 0 | 0 | 0 | 0 | 0 | alanm | alanm@mit.edu | 1970-01-01 | 2010-11-10 14:13 | 2010-11-09 13:57 | 2010-11-12 16:16 | Fixed | Unit | SF2 | High |  | SAP Support Pack 2010 | HR/Payroll | alanm |  | Complete |  | SAP Defect | Defect | Released & imported into SH3.SF3K903397 (see ticket 1394275) |  |  | SAP Gui
1398904 | SAP::Test Issues | SAP 2010 - HR Payroll - Error in transaction ZHRRETIREE_ANNUITY | resolved | 0 | 0 | 0 | 0 | 0 | donovan | donovan@mit.edu, robertsd@mit.edu | 1970-01-01 | 2010-11-15 15:17 | 2010-11-09 17:08 | 2010-11-15 16:49 | Assigned | Unit | SF2 |  |  | SAP Support Pack 2010 | HR/Payroll | waiming |  | Analysis |  |  |  | No transport required (at this time). |  |  | SAP Gui
1399148 | SAP::Test Issues | SAP 2010 - HR Payroll - Registered Partner Dependent Type showing up in ESS and GUI on IT0021 | resolved | 0 | 0 | 0 | 0 | 0 | robertsd | robertsd@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-09 19:27 | 2010-11-10 16:39 | Assigned | Unit | SF2 |  |  | SAP Support Pack 2010 | HR/Payroll | mprudden |  | Analysis |  |  |  | Released & imported into SH3.SF2K949522 - UPG: Hide Registered Partner Dependent Type in ESS |  |  | SAPweb
1399303 | SAP::Test Issues | Fi Line Item Validation errors cause call transaction error in JVSuite, RFP & JV Upload | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | fuller@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-09 20:58 | 2010-11-19 04:22 | Assigned | Unit | SF2 | Medium |  | SAP Support Pack 2010 | JV Suite | fuller |  | Development | JV | Undetermined | Defect | Released & imported into SH3SF2K949517 SP10/RT#1399303: JV Upload, JVSuite & RFP FI LItem Val |  |  | SAPweb
1399891 | SAP::Test Issues | SAP 2010 - HR Payroll - Buttons missing from UPI Education search page | resolved | 0 | 0 | 0 | 0 | 0 | donovan | mprudden@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-10 15:20 | 2010-11-10 16:44 | Assigned | Unit | SF2 |  |  | SAP Support Pack 2010 | HR/Payroll | mprudden |  | Development |  |  |  | Released & imported into SH3.SF2K949509 - UPG: Fixes to 2010 Support Pack Issues in ESS |  |  | SAP Gui
1400177 | SAP::Test Issues | FI: Convert FI Validation/Substitution Mods to Enhancements | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | fuller@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-10 17:53 | 2010-11-19 04:09 | Test | Unit | SF2 | Medium | SF2K949491 | SAP Support Pack 2010 | JV Suite | fuller |  | UA Testing | JV | Routine Maintenance | Enhancement | Released & imported into SH3SF2K949491 FI: RT#1400177 Convert Val/Subs Mods to EnhancementsSF2K949513 SP10/RT#1400177: FI: Convert FI Validation/Substitution Mods |  |  | SAP Gui
1400185 | SAP::Test Issues | AR: Support Package 3 mods converted to enhancements | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | fuller@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-10 17:56 | 2010-11-19 04:11 | Fixed | Development Integration | SF2 | Medium | SF2K949489 | SAP Support Pack 2010 | Financial | fuller |  | UA Testing | AR | Routine Maintenance | Enhancement | Released & imported into SH3SF2K949489 AR: RT#1400185 Support Pack 3 mods converted to enhancements |  | CUR | SAP Gui
1401511 | SAP::Test Issues | SAP 2010 - AP - 1042S form interface change | resolved | 0 | 0 | 0 | 0 | 0 | levie | levie@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-12 13:41 | 2010-11-12 13:53 | Fixed | Unit | SF2 | High |  | SAP Support Pack 2010 | Logistics | levie |  | Complete | AP | SAP Defect | Defect | No transport required. |  | CUR | SAP Gui
1404995 | SAP::Test Issues | SAP 2010: EL: Overview Link on Registar Tab in Portal does not work in Safari | rejected | 0 | 0 | 0 | 0 | 0 | ecunning | ecunning@mit.edu | 1970-01-01 | 2010-11-17 19:43 | 2010-11-16 18:48 | 2010-11-24 05:21 | No Correction Required | Unit | SF2 | Low |  | SAP Support Pack 2010 | HR/Payroll | nugentd | Mac OS | Analysis | EL | Infrastructure | Defect | No transport required.Not supported by SAP in this version. | Macintosh Safari 4 |  | SAPweb ESS
1406401 | SAP::Test Issues | FW: Critical BEN/OE: Change zhr_mark_oe_pcp to look at DOCN2 | resolved | 0 | 0 | 0 | 0 | 0 | robertsd | robertsd@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-17 22:28 | 2010-12-03 21:34 | Assigned | Unit |  |  |  | SAP Support Pack 2010 | HR/Payroll | robertsd |  | Development | HRPY |  |  | Critical Production IssueRequires dual testingSee ticket 1399477SF2K949541 - Benefits: unmark PCP for Open Enrollment |  |  | SAP Gui
1406459 | SAP::Test Issues | SAP 2010 ZC92 - BDC screen missing | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | rcasey@mit.edu | 1970-01-01 | 2010-11-30 12:36 | 2010-11-18 00:23 | 2010-12-03 21:30 | Retest | System Integration | SH3 | Severe |  | SAP Support Pack 2010 | Financial | rcasey |  | UA Testing | CS | Infrastructure | Defect | Released and imported into SH3.SF2K949551 - SP10/RT#1406459: ZC92 BDC screen missing |  | CUR | SAP Gui
1407157 | SAP::Test Issues | SAP2010 HR/PAY: Infotype numbers | resolved | 0 | 0 | 0 | 0 | 0 | cindyo | cindyo@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-18 16:24 | 2010-11-19 04:14 | Fixed | Unit | SF2 | Low |  | SAP Support Pack 2010 | HR/Payroll | cindyo |  | Development |  | Routine Maintenance |  | Released & imported into SH3.SF2K949547 HR/Pay: Infotype text (support Pk 2010) |  |  | SAP Gui
1407292 | SAP::Test Issues | ZAR3 - line item text not copied into document line item | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | rcasey@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-18 17:31 | 2010-12-03 21:34 | Retest | Development Integration | SH3 | High |  | SAP Support Pack 2010 | Financial | rcasey |  | Development | AR | Missed in testing | Defect | Critical Production IssueRequires dual testingSee ticket #1404494Released and imported into SH3SF2K949535 - AR: RT#1404494 Line Item text incorrect |  | CUR | SAP Gui
1407632 | SAP::Test Issues | CO Validation - CO Item, Step 1 not working for KN, RP doc types | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | rcasey@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-18 20:39 | 2010-11-24 05:26 | Assigned | Development Integration | SF2 |  |  | SAP Support Pack 2010 | Financial | rcasey |  | Development |  |  |  | Resolved with transports associated with SP RT # 1400177. |  |  | SAP Gui
1408130 | SAP::Test Issues | HTTP POST - system fail in SF2 and SH3 | open | 0 | 0 | 0 | 0 | 0 | waiming | waiming@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-19 14:47 | 1970-01-01 |  | Unit | SF2 |  |  | SAP Support Pack 2010 |  | rep |  | Analysis |  |  |  | No transport required. R3-Admin needs to propagate the SAPHTTP change to the updated SAP Server kernel environments including production at go-live. |  |  | SAP Processing
1408287 | SAP::Test Issues | SAP 2010 - HRPayroll - ESS function-ePaystub not available in ESS | resolved | 0 | 0 | 0 | 0 | 0 | donovan | lesliem@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-19 16:17 | 2010-11-20 02:10 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | HR/Payroll | rep |  | Analysis |  |  |  | No transport required. |  |  | SAPweb
1408297 | SAP::Test Issues | RE: SAP 2010 - HRPayroll - ESS function-ePaystub not available in ESS | resolved | 0 | 0 | 0 | 0 | 0 | donovan | donovan@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-19 16:21 | 2010-11-20 02:32 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 | HR/Payroll | rep |  | Analysis |  | Infrastructure |  | No transport required. |  |  | SAPweb
1408310 | SAP::Test Issues | SAPweb Problem: Can't create requisition | resolved | 0 | 0 | 0 | 0 | 0 | levie | lstcroix@plant.mit.edu | 1970-01-01 | 2010-11-19 18:35 | 2010-11-19 16:27 | 2010-11-20 02:17 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | Web | rep |  | Analysis |  | Infrastructure |  | No transport required. |  |  | SAPweb
1408317 | SAP::Test Issues | SAPweb: Visitor Parking | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | lstcroix@plant.mit.edu | 1970-01-01 | 2010-11-19 19:14 | 2010-11-19 16:33 | 2010-11-30 17:33 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | Web | rep |  |  | Parking | Infrastructure |  | No transport required. |  | CUR | SAPweb
1408394 | SAP::Test Issues | End users are unable to access front end OAS applications for EHS and Parking in SH3 | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | lcollier@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-19 17:17 | 2010-11-20 02:35 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | Web | rep |  | Analysis |  | Infrastructure |  | No transport required. |  |  | SAPweb
1408567 | SAP::Test Issues | SAP 2010 APR Error submitting APR Supplement with Org Unit | resolved | 0 | 0 | 0 | 0 | 0 | donovan | agilbert@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-19 19:23 | 2010-12-03 21:06 |  | System Integration | SH3 | High |  | SAP Support Pack 2010 | Web |  | Windows XP |  |  |  |  | Web object to be moved:apr-supplementsThis object has been moved to the test environment accessing SH3; it will need to be moved into production as part of go-live. | Windows IE 7 |  | SAPweb
1408577 | SAP::Test Issues | SAP 2010 - APR - Employee Gateway has old version of APR | resolved | 0 | 0 | 0 | 0 | 0 | agilbert | agilbert@mit.edu | 1970-01-01 | 2010-11-19 19:44 | 2010-11-19 19:28 | 2010-11-19 19:53 | Assigned | System Integration | SH3 | High |  | SAP Support Pack 2010 | HR/Payroll | agilbert |  | Development |  | Infrastructure | Defect | No transport required. | Windows IE 7 |  | SAPweb
1408629 | SAP::Test Issues | SAP 2010 - HRPayroll - Link on ePaystub to eW2 is generating erronous error | resolved | 0 | 0 | 0 | 0 | 0 | alanm | lesliem@mit.edu | 1970-01-01 | 2010-11-20 17:26 | 2010-11-19 19:53 | 2010-11-22 16:30 | Fixed | System Integration | SH3 |  |  | SAP Support Pack 2010 | Web | bmcavin |  | Analysis |  |  |  | No transport required. |  |  | SAPweb
1408929 | SAP::Test Issues | SAP2010EHS Greencard Won't Launch in PI/Space Reg App | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | veal@mit.edu | 1970-01-01 | 2010-11-23 21:31 | 2010-11-20 00:04 | 2010-11-23 21:31 | Assigned | System Integration | SH3 | Severe |  | SAP Support Pack 2010 | EH&S | sseligma |  | Analysis | EHS |  | Defect |  | Firefox 3 | CUR | SAPweb
1409707 | SAP::Test Issues | Quality Center not allowing access without running as administrator | resolved | 0 | 0 | 0 | 0 | 0 | ssawyer | lcollier@mit.edu | 1970-01-01 | 2010-11-22 15:41 | 2010-11-22 13:06 | 2010-11-24 05:25 | Assigned |  |  |  |  | SAP Support Pack 2010 | Test Mgmt | ssawyer |  | Analysis |  |  |  | No transport required.Instructions for resolving issue included in this ticket. |  |  | Other
1409722 | SAP::Test Issues | SAP 2010 APR HTTP 500 page | resolved | 0 | 0 | 0 | 0 | 0 | Nobody | agilbert@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-22 13:25 | 2010-11-22 17:50 | Test |  |  | High |  | SAP Support Pack 2010 | Web | [9 empty] | SAPweb
1409741 | SAP::Test Issues | SAP2010 LOG VPIS Problem Creating VPIS Reservation | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | lstcroix@plant.mit.edu | 1970-01-01 | 2010-11-30 19:02 | 2010-11-22 13:38 | 2010-12-03 21:42 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | Web | lma |  | Analysis | Parking |  |  | Released and imported into SH3.SF2K948295 - VP: RT#1238981 & 1409741 (Problem Creating VPIS Reservation)SF2K949561 - SP10\RT#1409741: Problem Creating VPIS Reservation |  |  | SAPweb
1409833 | SAP::Test Issues | SAP 2010 - HRPayroll - PDF link on eW-2 and ePaystub not retrieving forms | resolved | 0 | 0 | 0 | 0 | 0 | donovan | donovan@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-22 14:36 | 2010-11-22 16:31 | Assigned |  | SH3 |  |  | SAP Support Pack 2010 | Web | mberger |  | Analysis |  | Infrastructure |  | No transport required.
1409864 | SAP::Test Issues | SAP 2010 - HRPayroll - APR error on SPOG | new | 0 | 0 | 0 | 0 | 0 | jkogera | lesliem@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-22 14:51 | 1970-01-01 | [5 empty] | SAP Support Pack 2010 |  | jkogera | [5 empty] | No transport required.
1410326 | SAP::Test Issues | SAP 2010 LOG VPIS ZVPBATCH Order Settlement incorrect | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | lstcroix@plant.mit.edu | 1970-01-01 | 2010-11-24 16:55 | 2010-11-22 19:05 | 2010-11-24 16:55 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | Logistics | waiming |  | Analysis | Parking |  |  | No transport required. |  | CUR
1410414 | SAP::Test Issues | SAP 2010 - Financial - Error on Forecast Planning ZPUP for closed projects | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | liuying@mit.edu | 1970-01-01 | 2010-11-24 17:23 | 2010-11-22 20:08 | 2010-11-24 17:37 | No Correction Required | System Integration | SH3 |  |  | SAP Support Pack 2010 | Financial |  |  | Analysis |  |  |  | No transport required. |  |  | SAP Gui
1410428 | SAP::Test Issues | SAP 2010 HRPayroll - DSM error trying to clone pernrs from PS1 to SH3 | resolved | 0 | 0 | 0 | 0 | 0 | rep | donovan@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-22 20:17 | 2010-11-22 21:22 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | R/3 Admin | rep |  | Analysis |  | Infrastructure |  | No transport required |  |  | SAP Gui
1410452 | SAP::Test Issues | SAP 2010 - HR - Unable to access SH3 portal off campus | resolved | 0 | 0 | 0 | 0 | 0 | rep | jfw@mit.edu | 1970-01-01 | 2010-11-22 21:24 | 2010-11-22 20:33 | 2010-11-24 16:51 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | R/3 Admin | rep |  | Analysis |  | Infrastructure |  | No transport required. |  |  | Other
1410480 | SAP::Test Issues | RE: SAP 2010 HRPayroll - DSM error trying to clone pernrs from PS1 to SH3 | resolved | 0 | 0 | 0 | 0 | 0 | donovan | rep@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-22 20:56 | 2010-11-23 14:15 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 | R/3 Admin | rep |  | Analysis |  |  |  | Duplicate ticket |  |  | Other
1410518 | SAP::Test Issues | RE: SAP 2010 HRPayroll - DSM error trying to clone pernrs from PS1 to SH3 | resolved | 0 | 0 | 0 | 0 | 0 | donovan | donovan@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-22 21:14 | 2010-11-23 14:16 | Assigned |  |  |  |  | SAP Support Pack 2010 | HR/Payroll | rep |  | Analysis |  |  |  | Duplicate ticket |  |  | Other
1410519 | SAP::Test Issues | SAP 2010 - HR - SH3 portal does not launch properly using Firefox on Windows7 | resolved | 0 | 0 | 0 | 0 | 0 | ecunning | jfw@mit.edu | 1970-01-01 | 2010-11-23 21:19 | 2010-11-22 21:15 | 2010-11-23 21:19 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 | HR/Payroll | rep |  | Analysis |  | Knowledge/Human error |  | No transport required.Resolved with JavaScript setting in Firefox. |  |  | Other
1410591 | SAP::Test Issues | RE: SAP 2010 - HR - Unable to access SH3 portal off campus | resolved | 0 | 0 | 0 | 0 | 0 | Nobody | rep@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-22 21:53 | 2010-11-24 16:49 | [5 empty] | SAP Support Pack 2010 | [7 empty] | Duplicate ticket.
1410709 | SAP::Test Issues | RE: SAP 2010 - HR - Unable to access SH3 portal off campus | resolved | 0 | 0 | 0 | 0 | 0 | rep | jfw@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-23 01:48 | 2010-11-24 05:32 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | R/3 Admin | rep |  | Analysis |  | Infrastructure |  | Duplicate ticket. |  |  | Other
1411046 | SAP::Test Issues | SAP2010_AP_IXOS image links not working | resolved | 0 | 0 | 0 | 0 | 0 | levie | levie@mit.edu, wdwyer@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-23 14:10 | 2010-12-03 20:00 |  | UAT | SH3 |  |  | SAP Support Pack 2010 |  | levie |  | UA Testing |  |  | Issue | authorizaton needed in sh3 |  | CUR | SAP Gui
1411121 | SAP::Test Issues | Financial: When creating a JV SAPGui button missing | resolved | 0 | 0 | 0 | 0 | 0 | rcasey |  | 1970-01-01 | 1970-01-01 | 2010-11-23 14:50 | 2010-12-03 22:51 | Retest | System Integration | SH3 | Severe |  | SAP Support Pack 2010 | JV Suite | lma |  | Analysis | JV |  | Defect |  | Firefox 3 | CUR | SAP Gui
1411157 | SAP::Test Issues | Financial: Delete button not displaying to delete row. | resolved | 0 | 0 | 0 | 0 | 0 | ssawyer |  | 1970-01-01 | 1970-01-01 | 2010-11-23 15:05 | 2010-11-29 16:18 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 | Financial | dflander | Windows XP |  | JV |  |  | No transport required. |  | CUR
1411278 | SAP::Test Issues | Logistics: Automated script fails on Create Vendor Master US | resolved | 0 | 0 | 0 | 0 | 0 | ssawyer |  | 1970-01-01 | 1970-01-01 | 2010-11-23 16:10 | 2010-11-29 16:20 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 |  | levie | Windows XP |  |  |  |  | No transport required. |  | CUR
1411279 | SAP::Test Issues | RE: SAP 2010 - HR - Unable to access SH3 portal off campus | resolved | 0 | 0 | 0 | 0 | 0 | rep | rep@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-23 16:10 | 2010-11-24 16:48 | Assigned |  | SH3 |  |  | SAP Support Pack 2010 | R/3 Admin | rep | [5 empty] | Duplicate ticket. |  |  | Other
1411318 | SAP::Test Issues | SAP2010EHS PDF of SARA Worksheet Won't Display | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | mjpotter@mit.edu, veal@mit.edu | 1970-01-01 | 2010-11-23 21:30 | 2010-11-23 16:31 | 2010-11-23 21:30 |  | System Integration | SH3 | Severe |  | SAP Support Pack 2010 | EH&S | sseligma |  | Analysis | EHS |  | Defect |  | Firefox 3 | CUR | SAPweb
1411584 | SAP::Test Issues | FW: [Ist_ehsms_r3_sh3] Finding# 36592 assigned to Hao B Nguyen | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | hbnguyen@mit.edu | 1970-01-01 | 2010-11-24 20:27 | 2010-11-23 19:36 | 2010-11-24 20:27 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 | EH&S | lcollier |  | Analysis | EHS |  |  |  |  | CUR
1411600 | SAP::Test Issues | SAP 2010 EHS: Embedded links in Inspections emails do not work | resolved | 0 | 0 | 0 | 0 | 0 | lcollier | hbnguyen@mit.edu, veal@mit.edu | 1970-01-01 | 2010-11-24 16:40 | 2010-11-23 19:43 | 2010-11-29 16:22 | Assigned | System Integration | SH3 | High |  | SAP Support Pack 2010 | EH&S | lcollier |  | Analysis | EHS |  |  | Released and imported into SH3.SF2K949567 - YE Support Pack: logic to include SH3 mapping to test server |  | CUR
1411698 | SAP::Test Issues | RE: SAP 2010 - HR - Unable to access SH3 portal off campus | resolved | 0 | 0 | 0 | 0 | 0 | Nobody | jfw@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-23 20:51 | 2010-11-24 16:55 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 | [7 empty] | Duplicate ticket.
1411753 | SAP::Test Issues | RE: SAP 2010 - HR - Unable to access SH3 portal off campus | resolved | 0 | 0 | 0 | 0 | 0 | Nobody | rep@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-23 21:32 | 2010-11-24 05:31 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 | [5 empty] | Infrastructure
1411771 | SAP::Test Issues | RE: SAP 2010 - HR - Unable to access SH3 portal off campus | resolved | 0 | 0 | 0 | 0 | 0 | Nobody | jfw@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-23 21:45 | 2010-11-24 05:29 |  | System Integration | SH3 |  |  | SAP Support Pack 2010 | [5 empty] | Infrastructure
1411833 | SAP::Test Issues | SAP 2010 - HR - Cannot launch webgui in SH3 portal | resolved | 0 | 0 | 0 | 0 | 0 | ecunning | jfw@mit.edu | 1970-01-01 | 2010-11-24 18:54 | 2010-11-23 22:48 | 2010-11-24 18:54 | Assigned | System Integration | SH3 |  |  | SAP Support Pack 2010 |  | rep |  | Analysis | [6 empty] | Other
1412360 | SAP::Test Issues | FW: SAP test JV area-ZJVX function failed | resolved | 0 | 0 | 0 | 0 | 0 | rcasey | rcasey@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-24 16:26 | 2010-12-03 21:55 | Retest | UAT | SH3 | High |  | SAP Support Pack 2010 | JV Suite | lma |  | Analysis | TECR |  | Defect |  |  | TECR | SAP Gui
1412566 | SAP::Test Issues | SP2010_AP_ YEPAY ZPAY file not available for ftp to test ip | resolved | 0 | 0 | 0 | 0 | 0 | Nobody | levie@mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-24 18:56 | 2010-11-30 14:19 | Assigned | UAT | SH3 | High |  | SAP Support Pack 2010 |  | levie |  | Analysis | AP | Undetermined | Issue | issue related to SH3 environment only. Program limitation prevent complete transmission to test server. Test has been modified to a manual screening of file content and format. |  |  | SAP Gui
1415241 | SAP::Test Issues | IPM2, IPMD and IPM3 | resolved | 0 | 0 | 0 | 0 | 0 | mzhovnir | lstcroix@plant.mit.edu | 1970-01-01 | 1970-01-01 | 2010-11-29 21:25 | 2010-11-30 17:17 | Assigned |  | SH3 |  |  | SAP Support Pack 2010 | Logistics | waiming |  | Analysis |  |  |  | No transport required.
1419913 | SAP::Test Issues | SP2010_AP_can not link image to webrfp doc | open | 0 | 0 | 0 | 0 | 0 | levie | levie@mit.edu | 1970-01-01 | 1970-01-01 | 2010-12-03 19:49 | 1970-01-01 | Assigned |  | SH3 |  |  | SAP Support Pack 2010 | Logistics | levie |  | Analysis