## Sheet1
ReportTansactionName | SP_YEAR | Counts | Title | MIT custom? Y/N | Team Responsible (HR/PY; Fin; EHS; Logistics; ABAP; Basis) | Test during Unit test? Y/N/TBD | Unit test person responsible | Unit Test Result Pass/Fail | Test during System Integration Test? Y/N/TBD | Included in System Integration Test End-to-end Scenario? Y/N | System Integration Test End-to-end scenario name | System Integration Test Person responsible | Notes
Report-RSEOUT00 | 2010-09-01 | 1109762 | Process All Selected IDocs (EDI) | No | Logistics/HR | Yes | Elda/Larissa
Transaction-PA30 | 2010-09-01 | 410009 | Maintain HR Master Data | No | HR/Payroll | Yes | HR/Pay Team
Transaction-ZHRI_TIMESHEET | 2010-09-01 | 242247 | HR ESS - Timesheet Entry | Yes | HR/Payroll | Yes | Mark
Transaction-ZHR_9003_POST_PROCES | 2010-09-01 | 204270 |  | Yes | HR/Payroll | Yes | Cindy
Transaction-PP02 | 2010-09-01 | 150202 | Maintain Plan Data (Open) | No | HR/Payroll | Yes | Alan
Transaction-ZHRI_TS_ADMIN | 2010-09-01 | 87526 | HR ITS - Timesheet Administration | Yes | HR/Payroll | Yes | Mark
Report-ZHR_9003_POST_PROCESSING | 2010-09-01 | 84875 | HR: Maintain additional infotypes related to 9003 | Yes | HR/Payroll | Yes | Cindy
Transaction-PA20 | 2010-09-01 | 77427 | Display HR Master Data | No | HR/Payroll | Yes | HR/Pay Team
Transaction-ZHRI_ESDSV | 2010-09-01 | 49716 | ESDS - View-Only | Yes | HR/Payroll | Yes | Mark
Transaction-PUOC_10 | 2010-09-01 | 48016 | Off-Cycle Workbench USA | No | HR/Payroll | Yes | Gregg | [5 empty] | Full cycle testing
Transaction-ZHRI_TEM_USER_CHECK | 2010-09-01 | 31697 | Check if user is set for TEM access | Yes | HR/Payroll | Yes | Mark | [5 empty] | Emily will check to see if still in use after EL implementation.
Transaction-ZPE_PV3I | 2010-09-01 | 31318 | Book Attendance R/3 Users | Yes | HR/Payroll | Yes | Emily | [5 empty] | Transaction-ZASR
Transaction-PA40 | 2010-09-01 | 30336 | Personnel Actions | No | HR/Payroll | Yes | Cindy | [5 empty] | To insure the 9003 post processing is working, test a non-exempt, an exempt RGE1 and MNT1 9month duration. SPOT too
Transaction-PU19 | 2010-09-01 | 30221 | Tax Reporter | No | HR/Payroll | Yes | Gregg | [5 empty] | Test full cycle, W-2 and 1099R, W-2C and 1099RC
Transaction-PZ12 | 2010-09-01 | 27310 | Family/Related Person | No | HR/Payroll | Yes | Desiree
Transaction-PZ07 | 2010-09-01 | 24022 | Participation Overview | No | HR/Payroll | Yes | Desiree
Transaction-RPCTRPU0 | 2010-09-01 | 22082 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Part of PU19
Transaction-ZHRI_TS_HIST | 2010-09-01 | 21170 | HR ESS - View Timesheet History | Yes | HR/Payroll | Yes | Mark
Report-RSNAST00 | 2010-09-01 | 17542 | Selection Program for Issuing Output |  | Logistics/HR | Yes | Elda/Larissa
Transaction-ZASR0 | 2010-09-01 | 14764 | Annual Salary Review - Overview | Yes | HR/Payroll | No | Emily | [5 empty] | Covered under Transaction-ZASR
Transaction-ZHRI_OE_CONTACT | 2010-09-01 | 14435 | Open Enrollment Contact Info | Yes | HR/Payroll | Yes | Mark
Transaction-PZ14 | 2010-09-01 | 12818 | Enrollment | No | HR/Payroll | Yes | Desiree
Transaction-ZHRPZ40 | 2010-09-01 | 11695 | FSA Claims (Clone from PZ40) | Yes | HR/Payroll | Yes | Desiree
Transaction-PCP0 | 2010-09-01 | 11534 | Edit posting runs | No | HR/Payroll | Yes | Gregg | [5 empty] | Test end to end - display, create, release, post to FI, deleting, reversing
Transaction-RPCALCU0 | 2010-09-01 | 10069 |  | No | HR/Payroll | Yes | Mary | [5 empty] | Payroll Driver program
Transaction-ZASR2 | 2010-09-01 | 9130 | Annual Salary Review - Change | Yes | HR/Payroll | No | Emily | [5 empty] | Transaction-ZASR
Transaction-ZHRI_DIR_HME | 2010-09-01 | 8109 | HR ITS - Home Address | Yes | HR/Payroll | Yes | Mary
Transaction-ZPYDEDUCT | 2010-09-01 | 7909 | Deductions - Internal Provider | Yes | HR/Payroll | Yes | Gregg
Transaction-HRBEN0001 | 2010-09-01 | 6997 | Enrollment | No | HR/Payroll | Yes | Desiree
Transaction-ZHRI_DIR_WIZ | 2010-09-01 | 6412 | HR ITS - Start pt of Dir Info Wizard | Yes | HR/Payroll | Yes | Mark
Transaction-ZOMC | 2010-09-01 | 6312 | HR - process OM transactions | Yes | HR/Payroll | Yes | Cindy
Transaction-ZHRI_DIR_WRK | 2010-09-01 | 6291 | HR ITS - Work Contact Info | Yes | HR/Payroll | Yes | Mark
Report-ZHR_9003_POST_COLLECTIVE | 2010-09-01 | 5792 | HR: Collective run of appointment post-processing | Yes | HR/Payroll | Yes | Cindy
Transaction-PT60 | 2010-09-01 | 5749 | Time Evaluation | No | HR/Payroll | Yes | Karon
Transaction-ZHRPAYROLL_INTERFACE | 2010-09-01 | 5076 | Run HR Payroll Interface Report | Yes | HR/Payroll | Yes | Cindy
Transaction-ZHRI_WIZ_ETH | 2010-09-01 | 5048 | HR ITS - Ethnic/Gender/Military Info | Yes | HR/Payroll | Yes | Mark
Transaction-ZHRI_TS_HISTADMIN | 2010-09-01 | 4886 | HR ITS - Timesheet History for Admin | Yes | HR/Payroll | Yes | Mark
Transaction-PC00_M10_CALC_SIMU | 2010-09-01 | 4844 | Simulation payroll accounting 10 | No | HR/Payroll | Yes | Frank
Transaction-RFFOUS_C | 2010-09-01 | 4817 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Print check proram
Transaction-ZHRALELOG | 2010-09-01 | 4809 | Log display for HR master data feed | Yes | HR/Payroll | Yes | Alan
Transaction-ZHRI_WIZ_WRK | 2010-09-01 | 4802 | HR ITS - Work Contact Info | Yes | HR/Payroll | Yes | Mark
Transaction-ZOMCHST | 2010-09-01 | 4478 | HR - process OM transactions | Yes | HR/Payroll | Yes | Cindy
Transaction-ZHRI_UPI | 2010-09-01 | 4465 | HR ITS - Update Personal Info | Yes | HR/Payroll | Yes | Mark
Transaction-ZHRI_WIZ_EMG | 2010-09-01 | 4456 | HR ITS - Emergency Contact Info | Yes | HR/Payroll | Yes | Mark
Transaction-CAT2 | 2010-09-01 | 4412 | Time Sheet: Maintain Times | No | HR/Payroll | Yes | Karon
Transaction-ZHRI_WIZ_NTF | 2010-09-01 | 4271 | HR ITS - Campus Emergency Notificatn | Yes | HR/Payroll | Yes | Mark
Report-H99_RFF_FRAME | 2010-09-01 | 4254 | Main Program for Calling RFFO*_C | n | HR/Payroll | No | [6 empty] | Tested as part of Off cycle workbench
Transaction-RPCTRSU0 | 2010-09-01 | 4198 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Tax Reporter Scheduler
Transaction-PO13 | 2010-09-01 | 4027 | Maintain Position | No | HR/Payroll | Yes | Cindy
Transaction-ZHRI_WIZ_EDU | 2010-09-01 | 4019 | HR ITS - Education Attainment | Yes | HR/Payroll | Yes | Mark
Transaction-ZASR | 2010-09-01 | 4004 | Annual Salary Review | Yes | HR/Payroll | Yes | Emily | [5 empty] | Master transaction for ASR - go thru whole cycle.
Transaction-RPCIPA00 | 2010-09-01 | 3992 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Posting Document Overview
Transaction-ZHRI_DIR_EMG | 2010-09-01 | 3890 | HR ITS - Emergency Contact Info | Yes | HR/Payroll | Yes | Mark
Transaction-ZHRI_DIR_EDU | 2010-09-01 | 3833 | HR ITS - Education Attainment | Yes | HR/Payroll | Yes | Mark
Transaction-PUOCBA | 2010-09-01 | 3624 | Off-Cycle-Batch: Subsequent Activity | No | HR/Payroll | Yes | Gregg
Transaction-ZHRI_DIR_NTF | 2010-09-01 | 3455 | HR ITS - Campus Emergency Notificatn | Yes | HR/Payroll | Yes | Mark
Transaction-PC00_M10_REC | 2010-09-01 | 2883 | Payroll reconciliation report | No | HR/Payroll | Yes | Gregg
Transaction-Z_CREATE_FI_POSTING | 2010-09-01 | 2663 | MIT Create FI Posting - RPCIPE00_OLD | Yes | HR/Payroll | Yes | Gregg
Transaction-ZHRI_DIR_ETH | 2010-09-01 | 2607 | HR ITS - Ethnic/Gender/Military Info | Yes | HR/Payroll | Yes | Mark
Transaction-RPCIPS00 | 2010-09-01 | 2581 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Display Payroll Posting Doc
Transaction-PC_PAYRESULT | 2010-09-01 | 2487 | Display Payroll Results | No | HR/Payroll | Yes | Frank
Transaction-ZHRI_UPI_WRK | 2010-09-01 | 2363 | HR ITS - Work Contact Info | Yes | HR/Payroll | Yes | Mark
Transaction-ZHRI_UPI_HME | 2010-09-01 | 2299 | HR ITS - Home Address | Yes | HR/Payroll | Yes | Mark
Report-RPCALCU0 | 2010-09-01 | 2217 | Payroll Driver (USA) | n | HR/Payroll | Yes | Greg M.
Transaction-ZHRAP | 2010-09-01 | 2105 | APR backend processing | Yes | HR/Payroll | Yes | Amanda | [5 empty] | Covered in APR unit testing scripts
Transaction-PT50 | 2010-09-01 | 2095 | Quota Overview | No | HR/Payroll | Yes | Karon
Transaction-CATSSHOW | 2010-09-01 | 2060 |  | No | HR/Payroll | Yes | Karon | [5 empty] | Display Timesheet data
Transaction-ZPECLASS_ATTENDEES | 2010-09-01 | 2025 | Instructor Class Attendee Report | Yes | HR/Payroll | Yes | Emily
Transaction-ZPY_MITSIS_LOG | 2010-09-01 | 1977 | MITSIS error log report | Yes | HR/Payroll | Yes | Alan
Transaction-ZHR_APR_BACKEND_PROC | 2010-09-01 | 1975 |  | Yes | HR/Payroll | Yes | Cindy
Transaction-PC00_M10_CLAIMS | 2010-09-01 | 1928 | Claims processing | No | HR/Payroll | Yes | Gregg
Transaction-ZASR2H | 2010-09-01 | 1865 | Annual Salary Review - Hourly | Yes | HR/Payroll | Yes | Emily | [5 empty] | Transaction-ZASR
Transaction-ZHRAP_USER | 2010-09-01 | 1850 | APR backend processing: regular user | Yes | HR/Payroll | Yes | Amanda | [5 empty] | Covered in APR unit testing scripts
Transaction-RPUOCB00 | 2010-09-01 | 1812 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Subsequent processing for Off cycle
Transaction-PAUX | 2010-09-01 | 1795 | Adjustment Workbench | No | HR/Payroll | Yes | Gregg
Report-H99_SELECT_OFFCYCLE | 2010-09-01 | 1770 | Selection Report for Process Model for Off-Cycle Batch | n | HR/Payroll | No | [6 empty] | Test as part of off cycle workbench
Report-RPCIPE00_OLD | 2010-09-01 | 1701 | Posting to Accounting: Create Posting Run | n | HR/Payroll | Yes | Greg M.
Transaction-H99_DISPLAY_PAYRESUL | 2010-09-01 | 1590 |  | No | HR/Payroll | Yes | Frank
Transaction-RPTIME00 | 2010-09-01 | 1517 |  | No | HR/Payroll | No | Karon | [5 empty] | Copy of RPT_TIME_EVAL_START
Transaction-RPT_TIME_EVAL_START | 2010-09-01 | 1515 |  | No | HR/Payroll | Yes | Karon | [5 empty] | Time Eval
Report-RHAUTUPD_NEW | 2010-09-01 | 1482 | User Master Data Reconciliation | n | HR/Payroll | Yes | Cindy
Report-RPURMU00 | 2010-09-01 | 1482 | Store Third-Party Remittance Evaluation Run (Update Remittance Tables) | No | HR/Payroll | Yes | Gregg
Report-ZPY_MITSIS_GRADAID_LOG | 2010-09-01 | 1468 | GRADUATE APPOINTMENT INTERFACE LOG | Yes | HR/Payroll | Yes | Alan
Transaction-HRBEN0014 | 2010-09-01 | 1458 | Termination of Participation | No | HR/Payroll | Yes | Desiree
Transaction-ZPEI_ATTENDEE_LIST | 2010-09-01 | 1441 | Web Version of Class Attendee List | Yes | HR/Payroll | Yes | Emily | [5 empty] | Test via Web - may have new transaction name for EL.
Transaction-PSV1 | 2010-09-01 | 1393 | Dynamic Attendance Menu | No | HR/Payroll | Yes | Emily | [5 empty] | New EL transaction LSO_PSV1 - new EL name is Participation Menu
Transaction-HRBEN0006 | 2010-09-01 | 1332 | Benefits Participation Overview | No | HR/Payroll | Yes | Desiree
Transaction-ZHR_HOURLY_GRAD | 2010-09-01 | 1326 | Hourly Paid Graduate Student Setup | Yes | HR/Payroll | Yes | Alan
Report-ZHRALE01 | 2010-09-01 | 1296 | HR: Lincoln Lab MD interface pre-processor | Yes | HR/Payroll | Yes | Alan
Transaction-ZHRCLAIMS | 2010-09-01 | 1270 | Tuition Assistance Course Monitor | Yes | HR/Payroll | Yes | Desiree
Transaction-PFCG | 2010-09-01 | 1261 | Role Maintenance | No | HR/Payroll | Yes | Cindy
Transaction-ZPY_GRADAID_LOG | 2010-09-01 | 1238 | Graduate Appointment Interface Log | Yes | HR/Payroll | Yes | Alan
Transaction-ZASRSUMRPT | 2010-09-01 | 1232 | Annual Salary Review - Summary Rpt | Yes | HR/Payroll | Yes | Emily
Transaction-PC00_M10_CLSTR | 2010-09-01 | 1170 | Tools - Payroll Results - 10 | No | HR/Payroll | Yes | Gregg
Transaction-PAUY | 2010-09-01 | 1168 | Adjustment Workbench (retro proc.) | No | HR/Payroll | Yes | Gregg
Transaction-RPCIPD00 | 2010-09-01 | 1164 |  | No | HR/Payroll | No | [6 empty] | Duplicate
Transaction-ZPYCDU2 | 2010-09-01 | 1133 | CDU version II | Yes | HR/Payroll | Yes | Mary
Transaction-PSV2 | 2010-09-01 | 1090 | Dynamic Business Event Menu | No | HR/Payroll | Yes | Emily | [5 empty] | New EL transaction LSO_PSV2 - new EL name is Course Menu
Transaction-RPUAUD00 | 2010-09-01 | 1087 |  | No | HR/Payroll | Yes | Cindy | [5 empty] | Log infotype changes
Transaction-S_AHR_61016380 | 2010-09-01 | 1065 | Logged Changes in Infotype Data | No | HR/Payroll | Yes | Cindy
Report-ZHRALELOG | 2010-09-01 | 1047 | HR ALE feed log report | Yes | HR/Payroll | Yes | Alan
Transaction-PSV3 | 2010-09-01 | 1044 | Dynamic Information Menu | No | HR/Payroll | Yes | Emily | [5 empty] | New EL transaction LSO_PSV3 - new EL name is Information Menu
Transaction-PC00_M10_CEDT | 2010-09-01 | 1038 | Payroll Remuneration Statement - 10 | No | HR/Payroll | Yes | Gregg
Transaction-PO03 | 2010-09-01 | 981 | Maintain Job | No | HR/Payroll | Yes | Cindy
Transaction-RPCPRRU0 | 2010-09-01 | 961 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Payroll Recon Rpt
Transaction-RPCIPE00_OLD | 2010-09-01 | 956 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Create Posting Doc
Report-RPCPRRU0 | 2010-09-01 | 933 | Payroll Reconciliation Report | No | HR/Payroll | Yes | Greg M.
Transaction-ZRPCDTCU0 | 2010-09-01 | 842 |  | Yes | HR/Payroll | Yes | Gregg | [5 empty] | ZPREDME
Transaction-ZHRALE | 2010-09-01 | 825 | HR LL master data feed | Yes | HR/Payroll | Yes | Alan
Transaction-PUOCLG | 2010-09-01 | 812 | OC-Batch: Batch Table List | No | HR/Payroll | Yes | Gregg
Transaction-ZPYRMISSING9004 | 2010-09-01 | 810 | HR/PY: Report on Missing IT9004s | Yes | HR/Payroll | Yes | Mary
Transaction-ZPYCDRPT2 | 2010-09-01 | 746 | CDU: Display EDACCA Entries | Yes | HR/Payroll | Yes | Mary
Report-RPTERL00 | 2010-09-01 | 732 | Time Evaluation Messages Display | n | HR/Payroll | Yes | Karon
Transaction-/1BCDWB/DBZHR_EDACCA | 2010-09-01 | 729 |  | No | HR/Payroll | No | [6 empty] | se16 on EDACCA table
Transaction-RPUBENTERM | 2010-09-01 | 729 |  | No | HR/Payroll | Yes | Desiree | [5 empty] | Term Benefits
Transaction-RPUBENOVIEW | 2010-09-01 | 718 |  | Yes | HR/Payroll | Yes | Desiree | [5 empty] | Benefits Overview
Transaction-ZPYCDDIS_S2 | 2010-09-01 | 708 | CDU: Analyze Distribution | Yes | HR/Payroll | Yes | Mary
Transaction-PP01 | 2010-09-01 | 678 | Maintain Plan Data (Menu-Guided) | No | HR/Payroll | Yes | Cindy
Transaction-PA03 | 2010-09-01 | 636 | Maintain Personnel Control Record | No | HR/Payroll | Yes | Frank
Transaction-ZPY_MITSIS_GRADAID_L | 2010-09-01 | 618 |  | Yes | HR/Payroll | Yes | Alan
Transaction-ZOMCGST | 2010-09-01 | 602 | HR - process OM transactions | Yes | HR/Payroll | Yes | Alan
Transaction-PC00_M99_CIPC_PNP | 2010-09-01 | 600 | Check Completeness of Posting | No | HR/Payroll | Yes | Frank
Transaction-RPCLMSU0 | 2010-09-01 | 574 |  | No | HR/Payroll | Yes | Frank | [5 empty] | Claims processing
Report-RPCTRPU0 | 2010-09-01 | 573 | Tax Form Generator | n | HR/Payroll | No | [6 empty] | see PU19 "tax reporter"
Transaction-ZHRRETIRE_ANNUITY | 2010-09-01 | 570 | Create Retiree in RDBP | Yes | HR/Payroll | Yes | Desiree
Transaction-/USE/DSM3 | 2010-09-01 | 565 | DSM Object Sync | No | HR/Payroll | Yes | Mary
Transaction-PC00_M10_CALC | 2010-09-01 | 541 | Payroll Driver USA | No | HR/Payroll | Yes | Frank
Transaction-RPCTRCU0 | 2010-09-01 | 535 |  | No | HR/Payroll | No | [6 empty] | Part of PU19
Transaction-PPOM | 2010-09-01 | 510 | Maintain Organizational Plan |  | HR/Payroll | Yes | Cindy
Transaction-CAT6 | 2010-09-01 | 506 | Transfer External -> Time Management | No | HR/Payroll | Yes | Karon
Transaction-ZHRASRSUM | 2010-09-01 | 505 |  | Yes | HR/Payroll | No | [6 empty] | Part of ASR
Report-ZPYRMISSING9004 | 2010-09-01 | 494 | HR/PY: Report Missing IT9004s | Yes | HR/Payroll | Yes | Mary
Transaction-HRBEN0012 | 2010-09-01 | 488 | Automatic Plan Enrollment | No | HR/Payroll | Yes | Desiree
Report-ZPYCDU01 | 2010-09-01 | 481 | Payroll: CDU version II | Yes | HR/Payroll | Yes | Mary
Report-RPTIME00 | 2010-09-01 | 466 | HR TIME: Time Evaluation | No | HR/Payroll | Yes | Karon
Report-RPCLJNU0 | 2010-09-01 | 465 | Payroll Journal | n | HR/Payroll | Yes | Greg M. | [5 empty] | Arrears, other variants
Transaction-ZHRI_UPI_EMG | 2010-09-01 | 424 | HR ITS - Emergency Contact Info | Yes | HR/Payroll | Yes | Mark
Transaction-PFOM | 2010-09-01 | 414 | Maintain Assignment to SAP Org.Objs |  | HR/Payroll | Yes | Cindy
Transaction-H99LT52OCG | 2010-09-01 | 406 |  | No | HR/Payroll | No |  |  | No |  |  |  | Tested thru OCWB
Transaction-ZPE_RHSEMI60 | 2010-09-01 | 405 | Business Information Report | Yes | HR/Payroll | Yes | Emily | [5 empty] | TEM/EL
Report-ZPE_CREATE_USER | 2010-09-01 | 404 | Create New Training & Events User | Yes | HR/Payroll | Yes | Emily | [5 empty] | Still used after EL implementation
Transaction-PC00_M10_FFOC | 2010-09-01 | 399 | Payroll Transfer - Check Printing 10 | Yes | HR/Payroll | Yes | Gregg
Transaction-ZASR2F | 2010-09-01 | 389 | Annual Salary Review - Faculty | Yes | HR/Payroll | Yes | Emily | [5 empty] | Transaction-ZASR
Transaction-PPOS_OLD | 2010-09-01 | 388 | Display Organizational Plan | No | HR/Payroll | Yes | Cindy
Transaction-ZPYCDPRN_O2 | 2010-09-01 | 378 | CDU:manual print of edacca(Override) | Yes | HR/Payroll | Yes | Mary
Transaction-ZPYCDU05 | 2010-09-01 | 373 |  | Yes | HR/Payroll | Yes | Mary | [5 empty] | Part of CDU2
Report-ZPY_LOAD_ZHR_EDACCA_PRN | 2010-09-01 | 372 | EDCCA: LOAD ROLES / SAP R/3 ZHR_EDACCA_PRN FEED | Yes | HR/Payroll | Yes | Mary | [5 empty] | DACCA Auth roles
Transaction-S_AHR_61018754 | 2010-09-01 | 369 | Display Cluster RU (USA Payroll Resu | No | HR/Payroll | Yes | Frank
Transaction-RPCLSTRU | 2010-09-01 | 369 |  | No | HR/Payroll | No | [6 empty] | Duplicate - display payroll results
Report-ZPY_DIST_CO_UPDATE | 2010-09-01 | 367 | Distribution Cost Object Update | Yes | HR/Payroll | Yes | Mary
Report-ZPT_LL_ACCRUALS_OUTBOUND | 2010-09-01 | 367 | Outbound leave accrual balances to Lincoln Lab | Yes | HR/Payroll | Yes | Karon
Report-ZPY_LOAD_MITSIS_GRADAID | 2010-09-01 | 367 | Load Appointments data about Graduate students | Yes | HR/Payroll | Yes | Alan
Report-ZHRDWLIMITACCESS | 2010-09-01 | 366 | Add entries to Data Warehouse access table ZHRDWLIMITACCESS | Yes | HR/Payroll | Yes | Cindy
Report-ZHRFIND_DUPLICATE_MITID | 2010-09-01 | 366 | HR: Finding Duplicate MIT-ID & PERNR without MIT-ID | Yes | HR/Payroll | Yes | Cindy
Report-ZEP_HR_EXTRACT | 2010-09-01 | 365 | Program ZEP_HR_EXTRACT | Yes | HR/Payroll | Yes | Cindy
Transaction-ZPYCDU01 | 2010-09-01 | 358 |  | Yes | HR/Payroll | Yes | Mary | [5 empty] | Part of CDU2
Transaction-RPCEDTU0 | 2010-09-01 | 346 |  | No | HR/Payroll | Yes | Mary | [5 empty] | Rem Stmt
Transaction-PC00_M10_FFOT | 2010-09-01 | 342 | Create Payroll Transfer DTA 10 | No | HR/Payroll | Yes | Gregg
Report-ZPY_LL_BANK_DETAIL | 2010-09-01 | 338 | Outbound Interface: Bank Details Data File to Lincoln | Yes | HR/Payroll | Yes | Alan
Transaction-ZHRBENTERM | 2010-09-01 | 326 | Terminate Ineligible Benefits | Yes | HR/Payroll | Yes | Desiree
Transaction-PC00_M99_PA03_RELEA | 2010-09-01 | 324 | Release payroll | No | HR/Payroll | Yes | Gregg
Transaction-ZPYR_UNAPPR_TIME | 2010-09-01 | 318 | Unapproved Time Entries Report | Yes | HR/Payroll | Yes | Karon
Transaction-ZHRPP_CHKREC | 2010-09-01 | 315 | Pension Payroll Check Reconciliation | Yes | HR/Payroll | Yes | Gregg
Transaction-ZPREDME | 2010-09-01 | 310 | HR: Pension Payroll Pre-Dme Trans | Yes | HR/Payroll | Yes | Gregg
Transaction-ZHR_CDAT | 2010-09-01 | 309 | HR: Convert pay date to/fm earn date | Yes | HR/Payroll | Yes | Cindy
Transaction-RPCIPC00_PNP | 2010-09-01 | 300 |  | No | HR/Payroll | Yes | Gregg
Transaction-ZPYR_APPT_MESSAGES | 2010-09-01 | 294 | Appointments Messages Report | Yes | HR/Payroll | Yes | Cindy
Transaction-RPCIPDEL | 2010-09-01 | 283 |  | Yes | HR/Payroll | Yes | Gregg
Transaction-RPCTRTU0_ALV | 2010-09-01 | 275 |  | No | HR/Payroll | No | [6 empty] | Part of PU19
Report-RPCTRCU0 | 2010-09-01 | 269 | Tax Reporter | n | HR/Payroll | No | [6 empty] | PU19 in 2010 list
Transaction-ZHRALF | 2010-09-01 | 268 | HR: Audit Lincoln Labs feed | Yes | HR/Payroll | Yes | Alan
Report-ZPY_LOAD_MITSIS_BIO_DATA | 2010-09-01 | 265 | Load Student's Biographic data from MITSIS feed | Yes | HR/Payroll | Yes | Alan
Transaction-ZPYII_DED | 2010-09-01 | 262 | Deductions | Yes | HR/Payroll | Yes | Frank
Transaction-ZHRI_UPI_EDU | 2010-09-01 | 257 | HR ITS - Education Attainment | Yes | HR/Payroll | Yes | Mark
Transaction-PC00_M10_RFFOAVIS | 2010-09-01 | 255 | Print zero net advices | No | HR/Payroll | Yes | Gregg
Transaction-ZHR_INBOUND_TIME | 2010-09-01 | 254 | Kronos inbound time load (Test Mode) | Yes | HR/Payroll | Yes | Karon
Transaction-RPTEXTPT | 2010-09-01 | 252 |  | No | HR/Payroll | Yes | Karon | [5 empty] | Time transfer
Report-H99_RFF_FRAME_REP | 2010-09-01 | 241 | Program for Calling RFFO*_C for Check Replacement | No | HR/Payroll | No |  |  | No |  |  |  | Duplicate
Transaction-PC00_M10_U500 | 2010-09-01 | 240 | 3PR Prepare evaluation run (US) | No | HR/Payroll | Yes | Gregg
Transaction-ZPTKRONOS_TIME_INBOU | 2010-09-01 | 235 |  | Yes | HR/Payroll | Yes | Karon
Transaction-ZHR_JOB+POS_DESC | 2010-09-01 | 232 | Complete Job/Position Description | Yes | HR/Payroll | Yes | Cindy
Transaction-ZHRI_UPI_ETH | 2010-09-01 | 227 | HR ITS - Ethnic/Military Info | Yes | HR/Payroll | Yes | Mark
Transaction-ZPYU008_CDU_LOG | 2010-09-01 | 224 |  | Yes | HR/Payroll | Yes | Mary | [5 empty] | Part of CDU2
Transaction-ZPYU002_CDU_PRN | 2010-09-01 | 221 |  | Yes | HR/Payroll | No | [6 empty] | Obsolete
Transaction-/USE/DSM3_MON | 2010-09-01 | 220 | DSM Object Sync: Monitor Desk | No | HR/Payroll | Yes | Mary
Report-ZHR_BENEFIT_IDOC_CLEANUP | 2010-09-01 | 218 | HR Benefit IDoc cleanup program | Yes | HR/Payroll | Yes | Desiree
Transaction-ZHR_IT9033_AUDIT_RPT | 2010-09-01 | 210 | HR/PY: IT9033 AUDIT REPORT | Yes | HR/Payroll | Yes | Cindy
Report-RPCIPC00 | 2010-09-01 | 205 | Posting to Accounting: Search for payroll results not posted | No | HR/Payroll | Yes | Greg M.
Transaction-ZHRPP_FLTACH | 2010-09-01 | 205 | ACH Data Transfer To FLEET | Yes | HR/Payroll | Yes | Gregg
Transaction-ZPYNRA0210 | 2010-09-01 | 204 | HR: Updating HR InfoTypes 0210 | Yes | HR/Payroll | Yes | Mary
Transaction-ZPTKRONOS_TIME_IN | 2010-09-01 | 202 | Kronos inbound time load (Update) | Yes | HR/Payroll | Yes | Karon
Transaction-PC00_M99_PA03_END | 2010-09-01 | 194 | Exit payroll | No | HR/Payroll | Yes | Gregg
Transaction-ZPYCDLOG_DIS2 | 2010-09-01 | 192 | Application log for distribution | Yes | HR/Payroll | Yes | Mary
Transaction-ZHRI_WIZ_HME | 2010-09-01 | 188 | HR ITS - Home Address | Yes | HR/Payroll | Yes | Mark
Transaction-ZPE_QUAL_RPT | 2010-09-01 | 185 | Qualification Data Report | Yes | HR/Payroll | Yes | Emily
Transaction-PA41 | 2010-09-01 | 183 | Change Entry/Leaving Date | No | HR/Payroll | Yes | Cindy
Transaction-HRBEN0015 | 2010-09-01 | 176 | Confirmation Form | Yes | HR/Payroll | Yes | Desiree
Transaction-ZPY_UPLD_SUMMER_SESS | 2010-09-01 | 172 | Upload Summer Session File | Yes | HR/Payroll | Yes | Alan
Transaction-ZPT_DIST_RELIEF | 2010-09-01 | 171 | SRS Distribution Relief | Yes | HR/Payroll | Yes | Frank
Transaction-PC00_M10_CLJN | 2010-09-01 | 170 | Payroll Journal | No | HR/Payroll | Yes | Gregg
Transaction-PC00_M99_URMP | 2010-09-01 | 170 | 3PR Create posting run (US) | No | HR/Payroll | Yes | Gregg
Transaction-ZPY_UNAPPR_TIME | 2010-09-01 | 165 |  | Yes | HR/Payroll | Yes | Karon
Transaction-ZPYCDMGR2 | 2010-09-01 | 162 | CDU Distribution Thread Manager V.2 | Yes | HR/Payroll | Yes | Mary
Transaction-ZHRRPUBENPARTM | 2010-09-01 | 162 |  | Yes | HR/Payroll | Yes | Desiree | [5 empty] | Term Inelig Benefits
Transaction-ZPY_ACH | 2010-09-01 | 161 | Send Payroll ACH Files to the Bank | Yes | HR/Payroll | Yes | Frank
Transaction-ZPY_APPT_MESSAGES | 2010-09-01 | 156 | Unapproved Time Entries Report | Yes | HR/Payroll | Yes | Karon
Transaction-RPCLJNU0 | 2010-09-01 | 155 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | Payroll Journal
Transaction-PC00_M99_PA03_CORR | 2010-09-01 | 154 | Corrections | No | HR/Payroll | Yes | Gregg
Transaction-CAT3 | 2010-09-01 | 151 | Time Sheet: Display Times | No | HR/Payroll | Yes | Karon
Report-ZHRCHECK_LINCOLN_FEED | 2010-09-01 | 147 | HR: Check Lincoln feed | Yes | HR/Payroll | Yes | Alan
Transaction-PC00_M99_URMU | 2010-09-01 | 140 | 3PR Store evaluation run | No | HR/Payroll | Yes | Gregg
Transaction-ZASRREJECTS | 2010-09-01 | 140 | HR: ASR Rejects Report | Yes | HR/Payroll | Yes | Emily
Transaction-ZPYCDJVP2 | 2010-09-01 | 138 | CDU:post journal voucher2 | Yes | HR/Payroll | Yes | Mary
Transaction-ZHRALF02 | 2010-09-01 | 136 |  | Yes | HR/Payroll | Yes | Alan
Transaction-ZPY_SUMMER_SESSIONS | 2010-09-01 | 136 | Loads Academic Summer Sessions | Yes | HR/Payroll | Yes | Alan
Transaction-ZPYLIFEINSRPT | 2010-09-01 | 136 | HR/PY:ZHRPY_ACTIVE_LIFE_INS_PREM_RPT | Yes | HR/Payroll | Yes | Desiree
Transaction-ZPYI001_I_DEDUCTIONS | 2010-09-01 | 135 |  | Yes | HR/Payroll | Yes | Frank
Transaction-S_AHR_61015611 | 2010-09-01 | 132 | Wage Type Statement | No | HR/Payroll | Yes | Gregg
Transaction-ZPYCDEXT2 | 2010-09-01 | 132 | CDU: Exit | Yes | HR/Payroll | Yes | Mary
Transaction-RPCLGA00 | 2010-09-01 | 132 |  | No | HR/Payroll | No | Gregg | [5 empty] | Duplicate
Transaction-PC00_M99_CLGA09 | 2010-09-01 | 130 | Wage type statement (US stand.) Int. | No | HR/Payroll | No | Gregg | [5 empty] | Duplicate
Transaction-ZPTKRONOS_ACCRUL_OUT | 2010-09-01 | 130 | Kronos outbound accruals (Prod) | Yes | HR/Payroll | Yes | Karon
Transaction-ZPYCDLOG_JVP | 2010-09-01 | 128 | Application log for jv post | Yes | HR/Payroll | No | [6 empty] | Obsolete
Transaction-PO10 | 2010-09-01 | 126 | Maintain Organizational Unit | No | HR/Payroll | Yes | Cindy
Transaction-ZPY_PAY_VAL_RPT | 2010-09-01 | 126 | Payroll Validation Report | Yes | HR/Payroll | Yes | Gregg
Transaction-ZPYIO_MITSIS_TIM | 2010-09-01 | 126 | Stident Gross Pay File to MITSIS | Yes | HR/Payroll | Yes | Cindy
Transaction-ZPYCDLOG_JVP | 2010-09-01 | 126 | Non-exempt vacation distribution | Yes | HR/Payroll | No | [6 empty] | Obsolete
Transaction-ZPYCDLOG_EXT | 2010-09-01 | 122 | Application log for payroll exit | Yes | HR/Payroll | No | [6 empty] | Obsolete
Transaction-ZPE_RHXTHIST | 2010-09-01 | 120 | Attendee's Training History | Yes | HR/Payroll | Yes | Emily | [5 empty] | TEM/EL
Report-ZHRCSB02 | 2010-09-01 | 118 | Send outbound COBRA data file to Crosby | Yes | HR/Payroll | No
Report-ZPYI001_I_DEDUCTIONS | 2010-09-01 | 118 | Interface: Inbound Deductions | Yes | HR/Payroll | No
Transaction-RFFOUS_T | 2010-09-01 | 117 |  | Yes | HR/Payroll | Yes | Gregg
Transaction-ZPY_SUMMERSESS_LOG | 2010-09-01 | 114 | Summer Session Log for MAPs | Yes | HR/Payroll | Yes | Alan
Report-RPTEXTPT | 2010-09-01 | 112 | Transfer Time Data to HR Time Management | No | HR/Payroll | Yes | Karon
Transaction-PT66 | 2010-09-01 | 112 | Display Cluster B2 | No | HR/Payroll | Yes | Karon
Transaction-H99CWTR0 | 2010-09-01 | 112 |  | No | HR/Payroll | No
Transaction-ZHR_AUDIT_LINCOLN_TI | 2010-09-01 | 110 |  | Yes | HR/Payroll | Yes | Karon
Transaction-RPCSC000 | 2010-09-01 | 109 |  | Yes | HR/Payroll | Yes | Gregg
Transaction-ZHRI_UPI_NTF | 2010-09-01 | 102 | HR ITS - Campus Emergency Notificatn | Yes | HR/Payroll | Yes | Mark
Transaction-ZPPLIFEINSRPT | 2010-09-01 | 102 | HR/PP: ZHRPP_LIFE_INS_PREM_RPT | Yes | HR/Payroll | No
Transaction-ZPY_NRA_0210_UPDATE | 2010-09-01 | 102 |  | Yes | HR/Payroll | Yes | Mary
Transaction-ZHRPT_UPDT_PDC | 2010-09-01 | 96 | HR/PT: Update PA0003 PDC Recalc Date | Yes | HR/Payroll | Yes | Karon
Transaction-PC00_M99_CIPC | 2010-09-01 | 90 | Check Completeness of Posting | No | HR/Payroll | Yes | Frank
Transaction-ZHRLTD_ASSIGN | 2010-09-01 | 90 | Transfer an Active Employee to LTD | Yes | HR/Payroll | Yes | Cindy
Transaction-ZTSO | 2010-09-01 | 86 | Time Approval Scheduled Outage | Yes | HR/Payroll | Yes | Karon
Transaction-ZPY_UPLOAD_SUMMER_SE | 2010-09-01 | 86 |  | Yes | HR/Payroll | No
Transaction-RPURMP00 | 2010-09-01 | 85 |  | No | HR/Payroll | Yes | g | [5 empty] | 3rd party posting
Transaction-RPCPL1U0 | 2010-09-01 | 84 |  | No | HR/Payroll | No | [6 empty] | Garnishment history rpt
Transaction-RPUBEN15 | 2010-09-01 | 83 |  | No | HR/Payroll | No
Transaction-ZPYU009_CDU_MGR | 2010-09-01 | 81 |  | Yes | HR/Payroll | No
Report-RPURMP00 | 2010-09-01 | 78 | Create Third-Party Remittance Posting Run | Yes | HR/Payroll | Yes | Gregg
Report-RPCSC000 | 2010-09-01 | 75 | Scheduler for parallel accounting | n | HR/Payroll | Yes | Greg M.
Transaction-ZHR_SM30_VLOG2 | 2010-09-01 | 72 | maintain the view of APR LOG2 | Yes | HR/Payroll | No
Transaction-RPURMU00 | 2010-09-01 | 70 |  | No | HR/Payroll | Yes | Gregg | [5 empty] | 3rd party
Transaction-ZHRASR_REJECTLOG_RPT | 2010-09-01 | 70 |  | Yes | HR/Payroll | No
Transaction-ZHRPY_ACTIVE_LIFE_IN | 2010-09-01 | 70 | Run HR Payroll Interface Report | Yes | HR/Payroll | Yes | Desiree
Transaction-PU01 | 2010-09-01 | 69 | Delete current payroll result | No | HR/Payroll | Yes | Frank
Transaction-ZASRTBL | 2010-09-01 | 69 | ASR: Table Maintenance | Yes | HR/Payroll | Yes | Emily
Transaction-S_ALR_87014259 | 2010-09-01 | 69 | Payroll Journal | No | HR/Payroll | No | [6 empty] | Duplicate
Transaction-ZPYU004_CDU_JVP2 | 2010-09-01 | 69 |  | Yes | HR/Payroll | Yes | Mary
Transaction-ZPY_LOAD_SUMMER_SESS | 2010-09-01 | 68 |  | Yes | HR/Payroll | No | [6 empty] | Duplicate
Report-ZPYU004_CDU_JVP2 | 2010-09-01 | 67 | CDU: Post journal vouchers | Yes | HR/Payroll | Yes | Mary | [5 empty] | Test as part of ZPYCDU2
Transaction-RPCLSTB2 | 2010-09-01 | 67 |  | No | HR/Payroll | No
Report-ZPY_CDU_MONITOR | 2010-09-01 | 66 | CDU Job Monitor | Yes | HR/Payroll | Yes | Mary
Report-ZPYU006_CDU_EXT | 2010-09-01 | 66 | Payroll control record exit | Yes | HR/Payroll | Yes | Mary | [5 empty] | Test as part of ZPYCDU2
Transaction-ZHRMITID | 2010-09-01 | 66 | Search Assign MITIDs | Yes | HR/Payroll | Yes | Alan
Report-ZHR_IT9033_AUDIT_RPT | 2010-09-01 | 66 | HR/PY: IT9033 Audit Report | Yes | HR/Payroll | No
Transaction-Text | 2010-09-01 | 66 | Wage Type Reporter | No | HR/Payroll | No
Transaction-ZPTKRONOS_ACCRUALS_O | 2010-09-01 | 66 |  | Yes | HR/Payroll | No
Transaction-ZPYU006_CDU_EXT | 2010-09-01 | 66 |  | Yes | HR/Payroll | Yes | Mary
Report-ZHR_FIDELITY | 2010-09-01 | 65 | HR: Fidelity feed | Yes | HR/Payroll | No | Desiree
Report-ZPY_LL_SALARY_DISTRIBUTIONS | 2010-09-01 | 65 | Lincoln Lab salary distribution | Yes | HR/Payroll | No
Report-ZPY_METPAY_CONTRIB | 2010-09-01 | 65 | Home Auto Outbound Interface: Contribution Data File to MetLife | Yes | HR/Payroll | No
Report-ZPYI003_O_FID_CONTRIB | 2010-09-01 | 65 | Interface: Fidelity Outbound Contributions | Yes | HR/Payroll | No
Report-ZPYI0170_FSA_CONTRIB | 2010-09-01 | 65 | FSA Outbound Interface: Contribution Data File to Crosby | Yes | HR/Payroll | No
Transaction-RPCLGA09 | 2010-09-01 | 65 |  | No | HR/Payroll | No
Transaction-ZHRPP_LIFE_INS_PREM_ | 2010-09-01 | 63 | Run HR Payroll Interface Report | Yes | HR/Payroll | No
Transaction-ZPY_PAYROLL_COMPARE_ | 2010-09-01 | 63 |  | Yes | HR/Payroll | Yes | Frank
Transaction-ZPY_STUDENT_GROSS_PA | 2010-09-01 | 63 |  | Yes | HR/Payroll | No
Transaction-ZHRPT_UPDT_PDC_RECAL | 2010-09-01 | 62 |  | Yes | HR/Payroll | Yes | k
Transaction-RPTERR00 | 2010-09-01 | 59 |  | No | HR/Payroll | No
Transaction-ZHRASRPL | 2010-09-01 | 59 |  | Yes | HR/Payroll | No
Transaction-ZPYCDPRN2 | 2010-09-01 | 58 | CDU:manual print of edacca ver. II | Yes | HR/Payroll | Yes | Mary
Transaction-ZPYDEPLIFERPT | 2010-09-01 | 58 | Dependent Life Report | Yes | HR/Payroll | Yes | Desiree
Transaction-ZPY_SUMMER_SESSION_L | 2010-09-01 | 57 |  | Yes | HR/Payroll | No
Report-ZPTKRONOS_ACCRUALS_OUTBOUND | 2010-09-01 | 56 | Outbound leave accrual balances to KRONOS | Yes | HR/Payroll | No
Transaction-HRBEN0041 | 2010-09-01 | 56 | Jump from IMG into Maintenance Views | Yes | HR/Payroll | No
Report-ZHRPT_UPDT_PDC_RECALC_DATE | 2010-09-01 | 55 | HR/PT: Update PA0003 PDC Recalculation Date | Yes | HR/Payroll | No
Report-RPTERR00 | 2010-09-01 | 54 | Time Management: Error Handling | No | HR/Payroll | Yes | Karon
Report-ZPTKRONOS_TIME_INBOUND | 2010-09-01 | 54 | Kronos inbound time interface | Yes | HR/Payroll | Yes | Karon
Report-ZPYU002_CDU_PRN | 2010-09-01 | 53 | CDU: Print Edacca | Yes | HR/Payroll | Yes | Mary | [5 empty] | Test as part of ZPYCDU2
Report-ZHR_ESI_FEED | 2010-09-01 | 53 | HR: Express Scripts feed | Yes | HR/Payroll | No
Report-ZPY_METPAY_CENSUS_DATA | 2010-09-01 | 53 | MetPay Outbound Interface: Census Data File to MetLife | Yes | HR/Payroll | No
Report-ZPY_METPAY_IN_BILLDED | 2010-09-01 | 53 | Interface: Metpay Inbound Premium Deductions | Yes | HR/Payroll | No
Report-ZPY_STUDENT_GROSS_PAY | 2010-09-01 | 53 | Student Gross Pay | Yes | HR/Payroll | No
Report-ZPYI002_I_FID_PERLOAD | 2010-09-01 | 53 | Interface: Inbound Percent Load | Yes | HR/Payroll | No
Report-ZPYI0170_FSA_CENSUS_DATA | 2010-09-01 | 53 | FSA Outbound Interface: Census Data File to Crosby | Yes | HR/Payroll | No
Report-ZPYI0170_FSA_ENROLLMENT_DATA | 2010-09-01 | 53 | FSA Outbound Interface: Enrollment Data File to Crosby | Yes | HR/Payroll | No
Report-ZHR_COPY_PCP | 2010-09-01 | 52 | HR: the program copies PCP data from IT0106-0 to IT0376(used by feeds) |  | HR/Payroll | Yes | Desiree
Transaction-ZCOBRA | 2010-09-01 | 52 | HR/BEN: ZHRCSB02 (Crosby Interface) | Yes | HR/Payroll | No
Transaction-ZHRCSB02 | 2010-09-01 | 52 |  | Yes | HR/Payroll | No
Transaction-ZASR_UPLOAD | 2010-09-01 | 51 | Obsolete: ASR- Upload Excel | Yes | HR/Payroll | Yes | Emily
Transaction-RE_RHBEGDA0 | 2010-09-01 | 50 | Change start date | No | HR/Payroll | Yes | Cindy
Report-/USE/PDS3_OPTIMIZE | 2010-09-01 | 50 | EPI-USE: Optimization per Object Types | Yes | HR/Payroll | No
Report-ZHR_IT0655 | 2010-09-01 | 50 | HR: Create or delete the infotype 0655 | Yes | HR/Payroll | No
Transaction-RPCIPC00 | 2010-09-01 | 50 |  | No | HR/Payroll | No
Transaction-RPCTRHU0 | 2010-09-01 | 49 |  | No | HR/Payroll | No
Transaction-ZHR_9003_POST_COLLEC | 2010-09-01 | 46 |  | Yes | HR/Payroll | No
Transaction-PO13D | 2010-09-01 | 42 | Display Position | No | HR/Payroll | Yes | Cindy
Transaction-ZHRTP_PENS_PAYROLL | 2010-09-01 | 40 |  | Yes | HR/Payroll | yes | Frank
Transaction-HRBEN0073 | 2010-09-01 | 36 | Health Plan Costs | No | HR/Payroll | No
Transaction-HRBEN0074 | 2010-09-01 | 36 | Insurance Plan Costs | No | HR/Payroll | No
Transaction-/USE/DSM3_CREATE | 2010-09-01 | 34 | DSM Object Sync: Create Sync | No | HR/Payroll | yes | Mary
Transaction-ZHR_BENEFIT_IDOC_CLE | 2010-09-01 | 34 |  | Yes | HR/Payroll | No
Transaction-ZHR_LIST_JOBS | 2010-09-01 | 34 | List Jobs with/without Descriptions | Yes | HR/Payroll | No
Transaction-ZHR_LIST_POSITION | 2010-09-01 | 34 | List Positions with/without Descript | Yes | HR/Payroll | No
Transaction-ZPYII_HANCOCK | 2010-09-01 | 34 | John Hancock Inbound File | Yes | HR/Payroll | No
Transaction-ZPYR_MIETAX | 2010-09-01 | 30 | Marshall Islands Tax Report | Yes | HR/Payroll | No
Transaction-PP01_DISP | 2010-09-01 | 29 | Display Plan Data (Menu Guided) | No | HR/Payroll | Yes | Cindy
Transaction-ZOMCHSTL | 2010-09-01 | 28 | HR - process Lincoln OM transactions | Yes | HR/Payroll | Yes | Alan
Transaction-ZPYR_MASS_HEALTH | 2010-09-01 | 26 | Mass Health Ins Quartely Report | Yes | HR/Payroll | No
Transaction-ZASR_FAC_SUPPL_LOAD | 2010-09-01 | 24 | ASR: Load Faculty Supplements Table | Yes | HR/Payroll | Yes | Emily
Transaction-ZHRPP_CREDIT_UNION | 2010-09-01 | 23 |  | Yes | HR/Payroll | No
Report-ZHR_STAFF_OUT_OF_BALANCE_RPT | 2010-09-01 | 22 | Staff out of balance report | Yes | HR/Payroll | No
Transaction-ZASRD | 2010-09-01 | 22 | HR/ASR: Distribution Report | Yes | HR/Payroll | No
Transaction-ZPYR_STAFF_OUTBAL | 2010-09-01 | 22 | Staff out of balance report | Yes | HR/Payroll | No
Transaction-ZHRASRUL | 2010-09-01 | 21 |  | Yes | HR/Payroll | No
Transaction-ZPY_LL_BANK_DETAIL | 2010-09-01 | 21 |  | Yes | HR/Payroll | No
Transaction-ZHRCHAIROV | 2010-09-01 | 20 |  | Yes | HR/Payroll | No
Transaction-ZPY_LOAD_MITSIS_GRAD | 2010-09-01 | 19 | Load MITSIS Grad appts file | Yes | HR/Payroll | Yes | Alan
Transaction-ZPYI005_I_JHK_LTCDED | 2010-09-01 | 18 |  | Yes | HR/Payroll | No
Transaction-ZPYRMISSING9003 | 2010-09-01 | 18 | HR/PY Missing 9003 Audit | Yes | HR/Payroll | No
Transaction-ZPY_MASS_HEALTH | 2010-09-01 | 16 | Graduate Appointment Interface Log | Yes | HR/Payroll | No
Transaction-ZPYR_OSTATE_TAX | 2010-09-01 | 16 | Other state tax report | Yes | HR/Payroll | No
Transaction-ZPYR_VAC_COST_OUT | 2010-09-01 | 16 | Vacation cost out report | Yes | HR/Payroll | No
Transaction-PC00_M99_CWTR | 2010-09-01 | 15 | Wage type reporter | No | HR/Payroll | Yes | Gregg
Transaction-PUST | 2010-09-01 | 15 | HR Process Workbench | No | HR/Payroll | Yes | Gregg
Transaction-ZPY_MIETAX | 2010-09-01 | 15 |  | Yes | HR/Payroll | No
Transaction-ZHRENDLIFE | 2010-09-01 | 14 | HR/BEN: End-Date IT0168 Life Ins. | Yes | HR/Payroll | No
Transaction-ZHROM_AUDIT3 | 2010-09-01 | 14 | Search Assign MITIDs | Yes | HR/Payroll | No
Transaction-ZHRSCHOOLS | 2010-09-01 | 14 | Maintain Ed Assistance Schools Table | Yes | HR/Payroll | No
Transaction-ZPYCDU | 2010-09-01 | 14 | CDU: Display EDACCA Entries | Yes | HR/Payroll | No
Report-ZPYU009_CDU_MGR | 2010-09-01 | 13 | CDU: Distribution Manager | Yes | HR/Payroll | Yes | Mary | [5 empty] | Test as part of ZPYCDU2
Report-ZHRCSB03 | 2010-09-01 | 13 | Send outbound COBRA dependent (aged-out) file to Crosby | Yes | HR/Payroll | No
Transaction-ZHRTABALANCE | 2010-09-01 | 13 | TA: Account Balance Administration | Yes | HR/Payroll | No
Report-H99CWTR0 | 2010-09-01 | 12 | Wage Type Reporter | n | HR/Payroll | Yes | Greg M.
Report-ZHRPY_CREDIT_UNION | 2010-09-01 | 12 | HR Payroll - Credit Union extract file | Yes | HR/Payroll | No
Report-ZPY_457B_CONTRIB_OUT | 2010-09-01 | 12 | TIAA CREF Outbound Interface | Yes | HR/Payroll | No
Report-ZPY_MASS_HEALTH | 2010-09-01 | 12 | Mass Health Insurance Contributions Quarterly Report | Yes | HR/Payroll | No
Report-ZPY_PAYROLL_COMPARE_AUDIT | 2010-09-01 | 12 | Payroll Validation Report | Yes | HR/Payroll | Yes | Mary
Report-ZPYI004_O_TOW_CONTRIB | 2010-09-01 | 12 | Interface: Towers Outbound Contributions | Yes | HR/Payroll | No
Report-ZPYI005_I_JHK_LTCDED | 2010-09-01 | 12 | Interface: John Hancock LTC Inbound Premium Deductions | Yes | HR/Payroll | No
Report-ZPYI006_O_JHK_LTCPRE | 2010-09-01 | 12 | Interface:John Hancock Outbound for Payroll deductions | Yes | HR/Payroll | No
Transaction-RPURMA00 | 2010-09-01 | 12 |  | No | HR/Payroll | Yes | g
Transaction-ZHR_IT0655 | 2010-09-01 | 12 | HR: Create/delete Infotype 0655 | Yes | HR/Payroll | Yes | Alan
Transaction-ZHRASR_FACULTY_SUPPL | 2010-09-01 | 12 |  | Yes | HR/Payroll | No
Transaction-ZHRBENSIM | 2010-09-01 | 12 | Obsolete:SimulateBenefitsCalculation | Yes | HR/Payroll | No
Transaction-ZPYLOADUNION0 | 2010-09-01 | 12 | HR/PY: Load Union IT0000 | Yes | HR/Payroll | No
Report-/USE/DSM3_EXTRACT | 2010-09-01 | 11 | Extract program for DSM3 | n | HR/Payroll | Yes | Mary
Transaction-ZHR_FSA_DELIMIT | 2010-09-01 | 11 | HR: Convert pay date to/fm earn date | Yes | HR/Payroll | Yes | Desiree
Transaction-ZHR_STAFF_OUT_OF_BAL | 2010-09-01 | 11 |  | Yes | HR/Payroll | No
Transaction-ZHRASRDISTRPT | 2010-09-01 | 11 | APR backend processing: regular user | Yes | HR/Payroll | No
Transaction-RE_RHGRENZ4 | 2010-09-01 | 10 | Set new end date for infotypes | No | HR/Payroll | Yes | Cindy
Report-ZPY_UNAPPR_TIME | 2010-09-01 | 10 | Unapproved Time Entries Report | Yes | HR/Payroll | No
Transaction-HRBEN0004 | 2010-09-01 | 10 | EOI Monitor | No | HR/Payroll | No
Transaction-RPLPAY00 | 2010-09-01 | 10 |  | No | HR/Payroll | No
Transaction-ZHRCONVERTHEALTH167 | 2010-09-01 | 10 | Convert Health Re-enrollment | Yes | HR/Payroll | Yes | Desiree
Transaction-ZPYCDDIS_S | 2010-09-01 | 10 | Obsolete-CDU:distribution(Selection) | Yes | HR/Payroll | No
Transaction-ZPYLOADUNION9003 | 2010-09-01 | 10 | HR/PY: Load Union IT9003 | Yes | HR/Payroll | No
Transaction-ZPYR_STATE_QTR | 2010-09-01 | 10 | State Quarterly Earnings Report | Yes | HR/Payroll | Yes | Frank
Transaction-PA10 | 2010-09-01 | 9 | Personnel File | No | HR/Payroll | No
Transaction-ZHR_ESI_FEED | 2010-09-01 | 9 |  | Yes | HR/Payroll | No
Transaction-PUOCLL | 2010-09-01 | 8 | OC: List of Replacements/Reversals | No | HR/Payroll | Yes | Gregg
Transaction-RPUBTCU0 | 2010-09-01 | 8 |  | No | HR/Payroll | No
Transaction-RPURMR00 | 2010-09-01 | 8 |  | No | HR/Payroll | No
Transaction-ZHR_VACATION_COST_OU | 2010-09-01 | 8 |  | Yes | HR/Payroll | No
Transaction-ZHRPY_CREDIT_UNION | 2010-09-01 | 8 |  | Yes | HR/Payroll | No
Transaction-ZPT_LL_ACCRUALS_OUTB | 2010-09-01 | 8 |  | Yes | HR/Payroll | No
Transaction-ZPYII_LL_AUDT_TM | 2010-09-01 | 8 | Lincoln Time Audit | Yes | HR/Payroll | No
Transaction-ZPYR003_OTHERSTATE_T | 2010-09-01 | 8 | HR: Updating HR InfoTypes 0210 | Yes | HR/Payroll | No
Report-ZPY_NRA_0210_UPDATE | 2010-09-01 | 7 | Updating HR InfoTypes 0210 Using the BDC Approach | Yes | HR/Payroll | Yes | Mary
Transaction-ZQADTAXREP | 2010-09-01 | 7 | W2 Comparison Report | Yes | HR/Payroll | Yes | Gregg
Transaction-PE01 | 2010-09-01 | 7 | HR: Maintain Payroll Schemas | No | HR/Payroll | No
Transaction-ZHRBEN_END_DATE_LIFE | 2010-09-01 | 7 | Terminate Ineligible Benefits | Yes | HR/Payroll | No
Transaction-ZPYI0170_FSA_CENSUS_ | 2010-09-01 | 7 |  | Yes | HR/Payroll | No
Report-ZHR_VACATION_COST_OUT_RPT | 2010-09-01 | 6 | Vacation cost out report | Yes | HR/Payroll | Yes | Frank
Report-ZPY_SICK_COST_OUT_RPT | 2010-09-01 | 6 | Sick/Personal Leave Cost Out Report | Yes | HR/Payroll | No
Transaction-HRBEN0072 | 2010-09-01 | 6 | Participation | No | HR/Payroll | No
Transaction-HRBEN0075 | 2010-09-01 | 6 | Savings Plan Contributions | No | HR/Payroll | No
Transaction-HRWTT00MAIN | 2010-09-01 | 6 | Wage type tool | No | HR/Payroll | No
Transaction-PA04 | 2010-09-01 | 6 | Maintain PA Number Ranges | No | HR/Payroll | No
Transaction-PC00_M10_CDTC | 2010-09-01 | 6 | Payroll Transfer Prelim. Prog DTA-10 | No | HR/Payroll | No
Transaction-PC00_M99_DLGA20 | 2010-09-01 | 6 | Wage type use - International | No | HR/Payroll | No
Transaction-PE03 | 2010-09-01 | 6 | HR: Features | No | HR/Payroll | No
Transaction-PPOSW | 2010-09-01 | 6 | Display Org. and Staffing (WF) | No | HR/Payroll | No
Transaction-RPLBEN02 | 2010-09-01 | 6 |  | No | HR/Payroll | No
Transaction-RPTBPC10 | 2010-09-01 | 6 |  | No | HR/Payroll | No
Transaction-RPUP2D00 | 2010-09-01 | 6 |  | No | HR/Payroll | No
Transaction-ZHRRPUFSA01 | 2010-09-01 | 6 |  | Yes | HR/Payroll | No
Transaction-ZHRSIMULATEBENEFITS | 2010-09-01 | 6 |  | Yes | HR/Payroll | No
Transaction-ZPYI0170_FSA_ENROLLM | 2010-09-01 | 6 |  | Yes | HR/Payroll | No
Transaction-ZPYIO_HIRD | 2010-09-01 | 6 | Outbound HIRD Monthly Interface | Yes | HR/Payroll | No
Transaction-ZPYLOAD_UNIONS_IT000 | 2010-09-01 | 6 | HR/PY:ZHRPY_ACTIVE_LIFE_INS_PREM_RPT | Yes | HR/Payroll | No
Report-RPCIPE00 | 2010-09-01 | 5 | Posting to Accounting: Create Posting Run | No | HR/Payroll | No
Report-ZPY_STATE_QTR | 2010-09-01 | 5 | State Quarterly Earnings Report | Yes | HR/Payroll | No
Transaction-RPUBENEOIM | 2010-09-01 | 5 |  | No | HR/Payroll | No
Transaction-ZHR_FIDELITY | 2010-09-01 | 5 |  | No | HR/Payroll | No
Transaction-ZHR_OUTBOUND_HIRD_DA | 2010-09-01 | 5 | Complete Job/Position Description | No | HR/Payroll | No
Transaction-ZHRAUDIT | 2010-09-01 | 5 | Maintain HR Actions & Audit | No | HR/Payroll | No
Transaction-ZHRBEN_IT167_CONVERT | 2010-09-01 | 5 |  | No | HR/Payroll | No
Transaction-ZPY_METPAY_CENSUS_DA | 2010-09-01 | 5 | Load MITSIS Grad appts file | No | HR/Payroll | No
Transaction-ZPY_STATE_QTR | 2010-09-01 | 5 | Payroll Validation Report | No | HR/Payroll | No
Transaction-ZPYLOAD_UNIONS_IT900 | 2010-09-01 | 5 | HR/PY:ZHRPY_ACTIVE_LIFE_INS_PREM_RPT | No | HR/Payroll | No
Transaction-ZPYU001_CDU_DIS | 2010-09-01 | 5 | Unapproved Time Entries Report | No | HR/Payroll | No
Transaction-ZPYU005_CDU_RPT | 2010-09-01 | 5 |  | No | HR/Payroll | No
Transaction-HRBEN0005 | 2010-09-01 | 4 | Enrollment Form | No | HR/Payroll | No
Transaction-HRBEN0055 | 2010-09-01 | 4 | Overview Adjustment Permissions | No | HR/Payroll | No
Transaction-HRBEN0076 | 2010-09-01 | 4 | Vesting Percentage | No | HR/Payroll | No
Transaction-HRBEN0078 | 2010-09-01 | 4 | FSA Contributions | No | HR/Payroll | No
Transaction-PC00_M99_PA03_CHECK | 2010-09-01 | 4 | Check results | No | HR/Payroll | No
Transaction-ZHR_IT0128 | 2010-09-01 | 4 | HR: Create/Delete Infotype 0128 | Yes | HR/Payroll | Yes | Alan
Transaction-ZHR_MARK_OE_PCP | 2010-09-01 | 4 | HR/PY: IT9033 AUDIT REPORT | Yes | HR/Payroll | No
Transaction-ZHRP_OM_UTIL | 2010-09-01 | 4 | FSA Claims (Clone from PZ40) | Yes | HR/Payroll | No
Transaction-ZPP_CREDIT_UNION | 2010-09-01 | 4 | HR: Pens Payroll Cred Union Extract | Yes | HR/Payroll | No
Transaction-ZPY_METPAY_IN | 2010-09-01 | 4 | zpy_metpay_in_billded | Yes | HR/Payroll | No
Transaction-ZPY_SICK_COST_OUT_RP | 2010-09-01 | 4 | Payroll Validation Report | Yes | HR/Payroll | No
Transaction-ZPYCDCTL | 2010-09-01 | 4 | Set edaca periods | Yes | HR/Payroll | No
Transaction-PE02 | 2010-09-01 | 3 | HR: Maintain Calculation Rules | No | HR/Payroll | Yes | Mary
Transaction-PC00_M10_CPRS | 2010-09-01 | 3 | Payroll Reconciliation (Scheduler) | No | HR/Payroll | No
Transaction-ZHRGETPERNR2_SELECTI | 2010-09-01 | 3 | Convert Health Re-enrollment | Yes | HR/Payroll | No
Transaction-ZHROMINTCHK | 2010-09-01 | 3 | Data integrity check report | Yes | HR/Payroll | No
Transaction-PC00_MNA_CC_MAN | 2010-09-01 | 2 | Cost Center Report - Manager | No | HR/Payroll | No
Transaction-PU03 | 2010-09-01 | 2 | Change Payroll Status | No | HR/Payroll | Yes | Frank
Transaction-HRBEN0003 | 2010-09-01 | 2 | Participation Monitor | No | HR/Payroll | No
Transaction-PA51 | 2010-09-01 | 2 | Display Time Data | No | HR/Payroll | No
Transaction-RPCDTCU0 | 2010-09-01 | 2 |  | No | HR/Payroll | No
Transaction-RPCPL5U0 | 2010-09-01 | 2 |  | No | HR/Payroll | No
Transaction-RPCTRDU0 | 2010-09-01 | 2 |  | No | HR/Payroll | No
Transaction-RPCTRTU0 | 2010-09-01 | 2 |  | No | HR/Payroll | No
Transaction-ZASRPAYRPT | 2010-09-01 | 2 | Obsolete: ASReview - Payroll Rpt | Yes | HR/Payroll | No
Transaction-ZHR_OE_STATS | 2010-09-01 | 2 | Open Enrollment PDF Statistics | Yes | HR/Payroll | No
Transaction-ZHRASRRPT_MINORITY | 2010-09-01 | 2 |  | Yes | HR/Payroll | No
Transaction-ZHRBEN_COPY0167CSTSH | 2010-09-01 | 2 | Terminate Ineligible Benefits | Yes | HR/Payroll | No
Transaction-ZHRSPECIAL_DATES | 2010-09-01 | 2 | Special dates table | Yes | HR/Payroll | No
Transaction-ZPY_METPAY_CONTRIB | 2010-09-01 | 2 | Home Auto Deposits | Yes | HR/Payroll | No
Transaction-ZPY_METPAY_IN_BILLDE | 2010-09-01 | 2 | Graduate Appointment Interface Log | Yes | HR/Payroll | No
Transaction-ZPYI003_O_FID_CONTRI | 2010-09-01 | 2 |  | Yes | HR/Payroll | No
Transaction-ZPYPOPEDACCA | 2010-09-01 | 2 |  | Yes | HR/Payroll | No
Transaction-ZPYR_F1_VISA | 2010-09-01 | 2 | F-1 Visa Report | Yes | HR/Payroll | No
Transaction-ZPYR_J1_VISA | 2010-09-01 | 2 | J-1 Visa Report | Yes | HR/Payroll | No
Transaction-ZPYR_MAP_RECONCILE | 2010-09-01 | 2 | MAP Reconcilliation Report | Yes | HR/Payroll | No
Transaction-PE04 | 2010-09-01 | 1 | Creates Functions and Operations | No | HR/Payroll | Yes | Mary
Transaction-PPO1 | 2010-09-01 | 1 | Change Cost Center Assignment | No | HR/Payroll | No
Report-RPFORMU0PBS | 2010-09-01 | 1 | Form 1042-S Printing | No | HR/Payroll | Yes | Mary | [5 empty] | Print 1042-S
Report-RPU470ADJUST_T52C5 | 2010-09-01 | 1 | HR TIME: Time Evaluation | No | HR/Payroll | No
Report-ZHRPP_FLTACH | 2010-09-01 | 1 | HR Pension Payroll ACH Data Transfer To FLEET | Yes | HR/Payroll | No
Report-ZPY_F1_VISA_REPORT | 2010-09-01 | 1 | F-1 Visa Report | Yes | HR/Payroll | No
Report-ZPY_J1_VISA_REPORT | 2010-09-01 | 1 | J-1 Visa Report | Yes | HR/Payroll | No
Transaction-PU00 | 2010-09-01 | 1 | Delete Personnel Data | No | HR/Payroll | Yes | Cindy
Transaction-S_ALR_87014137 | 2010-09-01 | 1 | Payday Calendar | No | HR/Payroll | No
Transaction-ZHR_COPY_PCP | 2010-09-01 | 1 | HR: Convert pay date to/fm earn date | Yes | HR/Payroll | No
Transaction-ZHRI_HOME_ADDR | 2010-09-01 | 1 | HR ITS - Home Address | Yes | HR/Payroll | No
Transaction-ZHRPAYUSR_V | 2010-09-01 | 1 | View HR Payroll Users with Phone No | Yes | HR/Payroll | No
Transaction-ZHRSCHOOLGLACC | 2010-09-01 | 1 | Maintain Journal Voucher Info for TA | Yes | HR/Payroll | No
Transaction-ZPY_457B_CONTRIB_OUT | 2010-09-01 | 1 |  | Yes | HR/Payroll | No
Transaction-ZPY_F1_VISA_REPORT | 2010-09-01 | 1 | Unapproved Time Entries Report | Yes | HR/Payroll | No
Transaction-ZPY_FI_LIABILITY_REV | 2010-09-01 | 1 | Unapproved Time Entries Report | Yes | HR/Payroll | No
Transaction-ZPY_J1_VISA_REPORT | 2010-09-01 | 1 | Graduate Appointment Interface Log | Yes | HR/Payroll | No
Transaction-ZPY_MAP_RECONCILIATI | 2010-09-01 | 1 | Graduate Appointment Interface Log | Yes | HR/Payroll | No
Transaction-ZPY_PAREA_CHANGES | 2010-09-01 | 1 |  | Yes | HR/Payroll | No
Transaction-ZPYCALC | 2010-09-01 | 1 | CDU:calculator | Yes | HR/Payroll | No
Transaction-ZPYI006_O_JHK_LTCPRE | 2010-09-01 | 1 |  | Yes | HR/Payroll | No
Transaction-ZPYI0170_FSA_CONTRIB | 2010-09-01 | 1 |  | Yes | HR/Payroll | No
Hires_E2E_Exempt |  |  | Hire Exempt | Yes | HR/Payroll | Yes | Amanda
Termination_E2E_Voluntary_wo_Vacation |  |  | w/o Vacation | Yes | HR/Payroll | Yes | Amanda
Position/directory title chng_E2E_90 |  |  | Change position title for an academic employee in org unit | Yes | HR/Payroll | Yes | Amanda
Position/directory title chng_E2E_91 |  |  | Change position title of non-academic exempt with multiple appts <=40 char | Yes | HR/Payroll | Yes | Amanda
Setup concurrent_E2E_66 |  |  | Setup concurrent appointment - additional appointment in same department | Yes | HR/Payroll | Yes | Amanda
Change time _E2E_133 |  |  | Change in time:Change in work hours and work schedule (CI) | Yes | HR/Payroll | Yes | Amanda
Salary Change_E2E_50 |  |  | Salary Increase (Academic) - DL, employee with an end date | Yes | HR/Payroll | Yes | Amanda
Salary Change_E2E_49 |  |  | Salary Change - DA - Adj to minimum contract rate | Yes | HR/Payroll | Yes | Amanda
Reclassification_E2E_122 |  |  | Exempt employee reclass with salary increase. Employee is on LOA w pay. | Yes | HR/Payroll | Yes | Amanda
Reclassification_E2E_107 |  |  | Non-exempt employee reclassification with no salary increase | Yes | HR/Payroll | Yes | Amanda
Change in position_E2E_27 |  |  | academic exempt employee with salary decrease. Same dept - MNT to unpaid FEL, ben elig to ineligible (PD associate to PD fellow) - vaca payout, end date earlier than current end date, 9003 segment 6/1 - 6/14 should be deleted | Yes | HR/Payroll | Yes | Amanda
Change in Time Group_E2E_93 |  |  | Change time group from 30000417 to 30000403 for a non-exempt (service staff) | Yes | HR/Payroll | Yes | Amanda
Extend Appt_E2E_71 |  |  | Change appointment end date for an academic (CFEL) | Yes | HR/Payroll | Yes | Amanda
Delimit Appt_E2E_126 |  |  | Delimit MNT appt in Biology for a person with two MNT appts | Yes | HR/Payroll | Yes | Amanda
End Temp increase_E2E_62 |  |  | Retroactive End Temp Increase for non-exempt STN employee | Yes | HR/Payroll | Yes | Amanda
Transfer_E2E_7 |  |  | Retro Diff Dept - Transfer from one exempt non-acad job to another exempt non-acad job, RGE, multiple cost objects with diff end dates, suspense accounts updated | Yes | HR/Payroll | Yes | Amanda
Transfer_E2E_4 |  |  | Transfer from one Support (STN/TEMP appt) to Support RGN | Yes | HR/Payroll | Yes | Amanda