## Sheet1
ReportTansactionName | TransactionReportName | tblTransactionChild.SP_YEAR | Counts | Title | MIT custom? Y/N | Team Responsible (HR/PY; Fin; EHS; Logistics; ABAP; Basis) | Test during Unit test? Y/N/TBD | Unit test person responsible | Unit Test Result Pass/Fail | Test during System Integration Test? Y/N/TBD | Included in System Integration Test End-to-end Scenario? Y/N | System Integration Test End-to-end scenario name | System Integration Test Person responsible | Notes | Field0
Report-RFFOUS_T | Report-RFFOUS_T | 2010-09-01 | 1538 | Payment Medium USA - Transfers/Bank Direct Debits in ACH Format |  | Logistics | Yes | Ken |  | No
Report-RM08RELEASE | Report-RM08RELEASE | 2010-09-01 | 53 | Release Blocked Invoices | No | Logistics | Yes | Ken |  | Yes
Report-SAPF110S | Report-SAPF110S | 2010-09-01 | 1366 | Payment Program | No | Logistics | Yes | Ken |  | Yes
Report-ZAPCHKN0 | Report-ZAPCHKN0 | 2010-09-01 | 471 | Check Register |  | Logistics | Yes | Ken |  | Yes
Report-ZAPCHKR1 | Report-ZAPCHKR1 | 2010-09-01 | 637 | Check Extract |  | Logistics | Yes | Ken |  | Yes
Report-ZAPUATP_HTTPS_BOA | Report-ZAPUATP_HTTPS_BOA | 2010-09-01 | 503 | Travel: HTTPS protocal to retrieve BoA files | Yes | Logistics | Yes | Ken |  | Yes
Report-ZFCCFE01_HTTPS_BOA | Report-ZFCCFE01_HTTPS_BOA | 2010-09-01 | 802 | Credit Card: HTTPS protocal to retrieve BoA files | Yes | Logistics | Yes | Ken |  | Yes
Report-ZFFOUS_C | Report-ZFFOUS_C | 2010-09-01 | 546 | International Payment Medium - Check (with check management) | Yes | Logistics | Yes | Ken |  | Yes
Report-ZMMLIQPO_A | Report-ZMMLIQPO_A | 2010-09-01 | 149 | PO Close Program | Yes | logidtics | Yes | Rita |  | Yes
Report-ZMMR002 | Report-ZMMR002 | 2010-09-01 | 2066 | Review/Print Requisition | Yes | logidtics | Yes | Rita |  | Yes
Report-ZMMR003 | Report-ZMMR003 | 2010-09-01 | 365 | Automatic ISP Requisition Printing | Yes | logidtics | Yes | Rita |  | Yes
Report-ZPMAFR | Report-ZPMAFR | 2010-09-01 | 53 | PM Material Requirements | Yes | logidtics | Yes | Rita |  | Yes
Report-ZRQTOPO | Report-ZRQTOPO | 2010-09-01 | 17546 | From Totally Released Reqs (SapWeb,NECX) Create PO (ME21) | Yes | Logistics | Yes | Elda |  | Yes
Transaction-F110 | Transaction-F110 | 2010-09-01 | 1110 | Parameters for Automatic Payment | No | Logistics | Yes | Ken |  | Yes
Transaction-F-44 | Transaction-F-44 | 2010-09-01 | 2186 | Clear Vendor | No | Logistics | Yes | Ken |  | No
Transaction-F-53 | Transaction-F-53 | 2010-09-01 | 3187 | Post Outgoing Payments | No | Logistics | Yes | Ken |  | No
Transaction-FB10 | Transaction-FB10 | 2010-09-01 | 68059 | Invoice/Credit Fast Entry | No | Logistics | Yes | Ken |  | Yes
Transaction-FB60 | Transaction-FB60 | 2010-09-01 | 4914 | Enter Incoming Invoices | No | Logistics | Yes | Ken |  | Yes
Transaction-FBL1N | Transaction-FBL1N | 2010-09-01 | 10803 | Vendor Line Items | No | Logistics | Yes | Ken |  | No
Transaction-FBRA | Transaction-FBRA | 2010-09-01 | 12194 | Reset Cleared Items | No | Logistics | Yes | Ken |  | No
Transaction-FCH1 | Transaction-FCH1 | 2010-09-01 | 10925 | Display Check Information | No | Logistics | Yes | Ken |  | Yes
Transaction-FCH2 | Transaction-FCH2 | 2010-09-01 | 28087 | Display Payment Document Checks | No | Logistics | Yes | Ken |  | Yes
Transaction-FCH3 | Transaction-FCH3 | 2010-09-01 | 16 | Void Checks | No | Logistics | Yes | Ken |  | Yes
Transaction-FCH6 | Transaction-FCH6 | 2010-09-01 | 51 | Change Check Information/Cash Check | No | Logistics | Yes | Ken |  | Yes
Transaction-FCH8 | Transaction-FCH8 | 2010-09-01 | 1065 | Reverse Check Payment | No | Logistics | Yes | Ken |  | No
Transaction-FCH9 | Transaction-FCH9 | 2010-09-01 | 80 | Void Issued Check | No | Logistics | Yes | Ken |  | No
Transaction-FCHI | Transaction-FCHI | 2010-09-01 | 672 | Check Lots | No | Logistics | Yes | Ken |  | No
Transaction-FCHN | Transaction-FCHN | 2010-09-01 | 342 | Check Register |  | Logistics | Yes | Ken |  | Yes
Transaction-FK01 | Transaction-FK01 | 2010-09-01 | 3333 | Create Vendor (Accounting) | No | Logistics | Yes | Ken |  | No
Transaction-FK02 | Transaction-FK02 | 2010-09-01 | 3865 | Change Vendor (Accounting) | No | Logistics | Yes | Ken |  | No
Transaction-FK03 | Transaction-FK03 | 2010-09-01 | 1616 | Display Vendor (Accounting) | No | Logistics | Yes | Ken |  | No
Transaction-FK04 | Transaction-FK04 | 2010-09-01 | 47 | Vendor Changes (Accounting) | No | Logistics | Yes | Ken |  | No
Transaction-FK05 | Transaction-FK05 | 2010-09-01 | 5 | Block Vendor (Accounting) | No | Logistics | Yes | Ken |  | No
Transaction-FV60 | Transaction-FV60 | 2010-09-01 | 24323 | Park Incoming Invoices | Yes | Logistics | Yes | Ken |  | Yes
Transaction-IA01 | Transaction-IA01 | 2010-09-01 | 539 | Create Equipment Task List | No | logidtics | Yes | Rita |  | Yes
Transaction-IA02 | Transaction-IA02 | 2010-09-01 | 7187 | Change Equipment Task List | No | y | Yes | Rita
Transaction-IE01 | Transaction-IE01 | 2010-09-01 | 1058 | Create Equipment | No | logidtics | Yes | Rita |  | Yes
Transaction-IE02 | Transaction-IE02 | 2010-09-01 | 20773 | Change Equipment | No | logidtics | Yes | Rita |  | Yes
Transaction-MIR4 | Transaction-MIR4 | 2010-09-01 | 29941 | Call MIRO - Change Status | No | Logistics | Yes | Ken |  | Yes
Transaction-MIR6 | Transaction-MIR6 | 2010-09-01 | 2 | Invoice Overview | No | Logistics | Yes | Ken |  | No
Transaction-MR03 | Transaction-MR03 | 2010-09-01 | 12 | Display Inv. Verification Document | No | Logistics | Yes | Ken |  | No
Transaction-MR8M | Transaction-MR8M | 2010-09-01 | 1790 | Cancel Invoice Document | No | Logistics | Yes | Ken |  | Yes
Transaction-MRBR | Transaction-MRBR | 2010-09-01 | 3196 | Release Blocked Invoices | No | Logistics | Yes | Ken |  | Yes
Transaction-S_P99_41000101 | Transaction-S_P99_41000101 | 2010-09-01 | 813 | Check Register | No | Logistics | Yes | Ken |  | Yes
Transaction-XK01 | Transaction-XK01 | 2010-09-01 | 49106 | Create Vendor (Centrally) | No | Logistics | Yes | Ken |  | Yes
Transaction-XK02 | Transaction-XK02 | 2010-09-01 | 2488756 | Change vendor (centrally) | No | Logistics | Yes | Ken |  | Yes
Transaction-XK03 | Transaction-XK03 | 2010-09-01 | 41695 | Display vendor (centrally) | No | Logistics | Yes | Ken |  | Yes
Transaction-XK04 | Transaction-XK04 | 2010-09-01 | 38 | Vendor Changes (Centrally) | No | Logistics | Yes | Ken |  | Yes
Transaction-XK05 | Transaction-XK05 | 2010-09-01 | 569391 | Block Vendor (Centrally) | No | Logistics | Yes | Ken |  | Yes
Transaction-ZAP1042FILE | Transaction-ZAP1042FILE | 2010-09-01 | 28 | Create reporting & data merge files | Yes | Logistics | Yes | Ken |  | Yes |  |  |  | test obsolete
Transaction-ZAP1042RTRV | Transaction-ZAP1042RTRV | 2010-09-01 | 12 | Retrieve the 1042S file for the IRS | Yes | Logistics | Yes | Ken |  | Yes |  |  |  | test obsolete
Transaction-ZAP1042VNDR | Transaction-ZAP1042VNDR | 2010-09-01 | 10 | Validate 1042-S vendor master data | Yes | Logistics | Yes | Ken |  | Yes |  |  |  | test obsolete
Transaction-ZAP1099M | Transaction-ZAP1099M | 2010-09-01 | 485 | Maintain 1099M IRS Output File | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZAP3 | Transaction-ZAP3 | 2010-09-01 | 70 | Display Alternate Payee Addresses | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZAPFEEDS | Transaction-ZAPFEEDS | 2010-09-01 | 1277 | AP Feeds | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZBP0 | Transaction-ZBP0 | 2010-09-01 | 18920 | Review/Printe Requisition | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZBP5 | Transaction-ZBP5 | 2010-09-01 | 1400 | PO Commitment Report | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZC01 | Transaction-ZC01 | 2010-09-01 | 482 | Credit Card: Create master data | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZC02 | Transaction-ZC02 | 2010-09-01 | 2386 | Credit Card: Change master data | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZC03 | Transaction-ZC03 | 2010-09-01 | 2356 | Credit Card: Display master data | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZC04 | Transaction-ZC04 | 2010-09-01 | 1031 | Credit Card: Create Acct.Assign.Rule | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZC05 | Transaction-ZC05 | 2010-09-01 | 1036 | Credit Card: Change Acct.Assign.Rule |  | Logistics | Yes | Ken |  | Yes
Transaction-ZC06 | Transaction-ZC06 | 2010-09-01 | 729 | Credit Card: Display Acct.Assgn.Rule | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZC60 | Transaction-ZC60 | 2010-09-01 | 2117 | List of checks | Yes | Logistics | Yes | Ken |  | No
Transaction-ZFCC02 | Transaction-ZFCC02 | 2010-09-01 | 684 | ProCard: Download Daily Run File | Yes | Logistics | Yes | Ken |  | No
Transaction-ZIW38 | Transaction-ZIW38 | 2010-09-01 | 167373 | Change PM orders | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZMM_MB51 | Transaction-ZMM_MB51 | 2010-09-01 | 14 | Material Movement Summary Report | Yes | logidtics | Yes | Rita |  | No
Transaction-ZMM_ME1M | Transaction-ZMM_ME1M | 2010-09-01 | 8 | Material Vendor Report | Yes | logidtics | Yes | Rita |  | No
Transaction-ZMM6 | Transaction-ZMM6 | 2010-09-01 | 602 | Physical Plant - Stock Issues | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZMMLIQPO | Transaction-ZMMLIQPO | 2010-09-01 | 119 | PO Close Program | Yes | logidtics | Yes | Rita |  | No
Transaction-ZMMVCEXTRACT | Transaction-ZMMVCEXTRACT | 2010-09-01 | 4 | eCustoms Vendor Master File Extract | Yes | Logistics | Yes | Ken |  | No
Transaction-ZMRP | Transaction-ZMRP | 2010-09-01 | 1226 | Reorder Report for PPLT | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZP04 | Transaction-ZP04 | 2010-09-01 | 1196 | List Of Outstanding Qheques | Yes | Logistics | Yes | Ken |  | No
Transaction-ZP07 | Transaction-ZP07 | 2010-09-01 | 512 | 1099 Listing | Yes | logidtics | Yes | Ken |  | No
Transaction-ZPARTS | Transaction-ZPARTS | 2010-09-01 | 268 | Transaction code | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZPAY | Transaction-ZPAY | 2010-09-01 | 1429 | Outsourcing chks for printing/wiring | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZPIBINCHECK | Transaction-ZPIBINCHECK | 2010-09-01 | 258 | Inventory Count Bin Check | Yes | logidtics | Yes |  |  | Yes
Transaction-ZPIINVCOUNT | Transaction-ZPIINVCOUNT | 2010-09-01 | 1157 | Physical Inv. --> upload inv. count | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZPMAFR | Transaction-ZPMAFR | 2010-09-01 | 190 | PM Air Filter Requirements Report | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZPMORD1 | Transaction-ZPMORD1 | 2010-09-01 | 346 | PMATS: Create Work Order | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZPMORD2 | Transaction-ZPMORD2 | 2010-09-01 | 352 | PMATS: Change Work Order | Yes | Logistics | Yes | Ken |  | No
Transaction-ZPMORD3 | Transaction-ZPMORD3 | 2010-09-01 | 48 | PMATS: Display Work Order | Yes | Logistics | Yes | Ken |  | No
Transaction-ZPMWORPT | Transaction-ZPMWORPT | 2010-09-01 | 51 | Work Order Report for PMATS | Yes | Logistics | Yes | Ken |  | No
Transaction-ZPP1 | Transaction-ZPP1 | 2010-09-01 | 300 | Physical plant - Barcode Generator | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZPP2 | Transaction-ZPP2 | 2010-09-01 | 26833 | Goods issue | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZPPINV | Transaction-ZPPINV | 2010-09-01 | 8984 | DoF: Register DoF Invoice | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZREQDISPLAY | Transaction-ZREQDISPLAY | 2010-09-01 | 145370 | Display requisition | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZREQINBXAPPR | Transaction-ZREQINBXAPPR | 2010-09-01 | 109469 | Requisition approver inbox | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZREQINBXCRE | Transaction-ZREQINBXCRE | 2010-09-01 | 4622 | Requisition creator inbox | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZREQSELECT | Transaction-ZREQSELECT | 2010-09-01 | 228839 | Select individual requisition | Yes | logidtics | Yes | Rita |  | Yes
Transaction-ZSIG | Transaction-ZSIG | 2010-09-01 | 8539 | Address for invoice authorization | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZTRACK1 | Transaction-ZTRACK1 | 2010-09-01 | 4766 | Create: Loaned Asset Tracking Entry | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZTRACK2 | Transaction-ZTRACK2 | 2010-09-01 | 5090 | Change: Loaned Asset Tracking Entry | Yes | Logistics | Yes | Ken |  | Yes
Transaction-ZTRACK4 | Transaction-ZTRACK4 | 2010-09-01 | 1826 | Report: Loaned Asset Tracking Entry | Yes | lLogistics | Yes | Ken |  | Yes
Transaction-ZVP_RESERVATIONS | Transaction-ZVP_RESERVATIONS | 2010-09-01 | 846 | Visitor Parking: Reservations | Yes | Logistics | Yes | Lee Collier |  | Yes
Transaction-ZWKCENTER_WORDER | Transaction-ZWKCENTER_WORDER | 2010-09-01 | 112 | Maintain wkcntr/wkordr mapping table | Yes | logidtics | Yes | Rita |  | Yes
Report-PP_PICK_LIST | Report-PP_PICK_LIST | 2009-09-01 | 801 | Pick List |  | logistics | Y | Rita |  | n |  |  |  |  | 2009-09-01
Report-RFCHIL00 | Report-RFCHIL00 | 2009-09-01 | 112 | Check lots | n | Logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Report-RFCHKD30 | Report-RFCHKD30 | 2009-09-01 | 28 | Reset Check Information Data | n | logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Report-RFCHKN00 | Report-RFCHKN00 | 2009-09-01 | 503 | Check Register | n | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-RFCHKN10 | Report-RFCHKN10 | 2009-09-01 | 891 | Check Register | N | Logistics | y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-RFITEMAP | Report-RFITEMAP | 2009-09-01 | 4371 | Vendor Line Item Display | N | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-RFKABL00 | Report-RFKABL00 | 2009-09-01 | 3 | Display Changes to Vendors | n | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-RFKEPL00 | Report-RFKEPL00 | 2009-09-01 | 372 | List of Vendor Line Items | n | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-RFKOPO00 | Report-RFKOPO00 | 2009-09-01 | 11 | List of Vendor Open Items | n | Logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Report-RFZALI20 | Report-RFZALI20 | 2009-09-01 | 13 | Payment List | n | Logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-RIAUFK10 | Report-RIAUFK10 | 2009-09-01 | 644 | Display Service and Maintenance Orders (Multi-Level) | n | Logistics | Y | Rita | pass | Y |  |  |  | IW40 | 2009-09-01
Report-RIMPLA00 | Report-RIMPLA00 | 2009-09-01 | 1572 | Maintenance Plan List | N | Logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-RM06BA00 | Report-RM06BA00 | 2009-09-01 | 2131 | List Display of Purchase Requisitions | N | Logistics | Y | Rita |  | Y |  |  |  | Transaction ME5A | 2009-09-01
Report-RM06BF00 | Report-RM06BF00 | 2009-09-01 | 1801 | Collective Release of Purchase Requisitions | N | Logistics | Y | Rita |  | Y |  |  |  | Transaction ME55 | 2009-09-01
Report-RM06EK00 | Report-RM06EK00 | 2009-09-01 | 879 | Purchasing Documents per Account Assignment |  | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-RM07IDIF | Report-RM07IDIF | 2009-09-01 | 3935 | List of Inventory Differences | n | logistics | Y | rita |  | Y |  |  |  |  | 2009-09-01
Report-RM07IDRU | Report-RM07IDRU | 2009-09-01 | 12 | Print Physical Inventory Document |  | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Report-RM07II31 | Report-RM07II31 | 2009-09-01 | 413 | Batch Input: Create Physical Inventory Documents for Normal Stock | n | logistics | Y | Rita |  | y |  |  |  |  | 2009-09-01
Report-RM08RELEASE | Report-RM08RELEASE | 2009-09-01 | 1829 | Release Blocked Invoices | n | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-RMMMBESTN | Report-RMMMBESTN | 2009-09-01 | 33818 | Stock Overview: Company Code/Plant/Storage Location/Batch | N | Logistics | Y | Rita |  | Y |  |  |  | Transaction MMBE | 2009-09-01
Report-RMMR1MRS | Report-RMMR1MRS | 2009-09-01 | 241 | Evaluated Receipt Settlement (ERS) with Logistics Invoice Verification | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Report-RSWIWORK | Report-RSWIWORK | 2009-09-01 | 961 | Formatting of Work Load | n | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-SAPF110S | Report-SAPF110S | 2009-09-01 | 1068 | Payment Program | n | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZAP_1042S_FILE_RETRIEV | Report-ZAP_1042S_FILE_RETRIEV | 2009-09-01 | 9 | #N/A | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZAP_1042S_FILE_VALIDAT | Report-ZAP_1042S_FILE_VALIDAT | 2009-09-01 | 11 | #N/A | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZAP_1042S_FILES_CREATE | Report-ZAP_1042S_FILES_CREATE | 2009-09-01 | 16 | Create 1042-S Reporting and Data-Merge files | Y | Logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZAPCHKN0 | Report-ZAPCHKN0 | 2009-09-01 | 530 | Check Register | Y | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZAPCHKR1 | Report-ZAPCHKR1 | 2009-09-01 | 550 | Check Extract | Y | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZAPCHKS1 | Report-ZAPCHKS1 | 2009-09-01 | 284 | AP: Send positive pay files to Fleet | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZAPI005A | Report-ZAPI005A | 2009-09-01 | 18 | Preferred Vendors - Load Non PO Invoices & Debit Notes | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZAPIFEED | Report-ZAPIFEED | 2009-09-01 | 711 | NON-PO Accounts Payable File Feed | Y | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZAPIFTPWIRE | Report-ZAPIFTPWIRE | 2009-09-01 | 5 | MIT Electronic Wire FTP Program | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZAPIOUTSRCPMT | Report-ZAPIOUTSRCPMT | 2009-09-01 | 555 | MIT Outsourcing of A/P Payments | Y | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZAPP004 | Report-ZAPP004 | 2009-09-01 | 113 | Vendor Remit To Addresses | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZAPUATP_HTTPS_BOA | Report-ZAPUATP_HTTPS_BOA | 2009-09-01 | 427 | Travel: HTTPS protocal to retrieve BoA files | Y | logistics | Y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZBP005 | Report-ZBP005 | 2009-09-01 | 951 | PO Commitment Report | Y | Logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-ZBPME52 | Report-ZBPME52 | 2009-09-01 | 104 | Modified Change Requisition for MIT | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Report-ZFCCFE01_HTTPS_BOA | Report-ZFCCFE01_HTTPS_BOA | 2009-09-01 | 415 | Credit Card: HTTPS protocal to retrieve BoA files | Y | logistics | Y | Ken |  | y |  |  |  |  | 2009-09-01
Report-ZFCCFE02 | Report-ZFCCFE02 | 2009-09-01 | 440 | ProCard: Download Daily Run Result to Local Drive | Y | Logistics | y | Ken | Pass | N |  |  |  |  | 2009-09-01
Report-ZFFOUS_C | Report-ZFFOUS_C | 2009-09-01 | 537 | International Payment Medium - Check (with check management) | Y | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZIAUFK20 | Report-ZIAUFK20 | 2009-09-01 | 89876 | Display and Change Service and Maintenance Orders | Y | Logistics | y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-ZM70AMEA_NEW | Report-ZM70AMEA_NEW | 2009-09-01 | 620 | Output from goods movements | Y | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-ZMMLIQPO_A | Report-ZMMLIQPO_A | 2009-09-01 | 57 | PO Close Program | Y | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Report-ZMMO001 | Report-ZMMO001 | 2009-09-01 | 87 | IM: Barcode ASCII File Generator | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Report-ZMMPARTS_LIST | Report-ZMMPARTS_LIST | 2009-09-01 | 79 | Program ZMMPARTS_LIST | Y | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Report-ZMMR001 | Report-ZMMR001 | 2009-09-01 | 235 | Physical Plant - Goods Issues | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Report-ZMMR002 | Report-ZMMR002 | 2009-09-01 | 15136 | Review/Print Requisition | Y | Logistics | y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-ZMMR003 | Report-ZMMR003 | 2009-09-01 | 392 | Automatic ISP Requisition Printing | Y | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Report-ZPMAFR | Report-ZPMAFR | 2009-09-01 | 89 | PM Material Requirements | Y | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Report-ZPMWORPT | Report-ZPMWORPT | 2009-09-01 | 12 | Work Order Report for PMATS | Y | Logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Report-ZPMZTRACK | Report-ZPMZTRACK | 2009-09-01 | 1079 | PMATS: Reporting | Y | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Report-ZPPIOREP | Report-ZPPIOREP | 2009-09-01 | 1083 | Department of Facilities - Internal Order Report | Y | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-ZREQ003 | Report-ZREQ003 | 2009-09-01 | 38178 | Requisition - Release Completely Effected | Y | Logistics | y | Rita |  | Y |  |  |  |  | 2009-09-01
Report-ZRQTOPO | Report-ZRQTOPO | 2009-09-01 | 18511 | From Totally Released Reqs (SapWeb,NECX) Create PO (ME21) | Y | Logistics | Y | Elda |  | Y |  |  |  |  | 2009-09-01
Report-ZSIGAUTH | Report-ZSIGAUTH | 2009-09-01 | 5501 | Mailing Address for Authorization of Incoming Invoices | Y | logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Transaction-COGI | Transaction-COGI | 2009-09-01 | 785 | Processing goods movemnts w. errors | n | logistics | y | Rita |  | N |  |  |  |  | 2009-09-01
Transaction-F110 | Transaction-F110 | 2009-09-01 | 656 | Parameters for Automatic Payment | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-F-44 | Transaction-F-44 | 2009-09-01 | 2337 | Clear Vendor | n | logistics | y | Ken |  | N |  |  |  |  | 2009-09-01
Transaction-F-53 | Transaction-F-53 | 2009-09-01 | 2293 | Post Outgoing Payments | n | Logistics | y | Ken |  | N |  |  |  |  | 2009-09-01
Transaction-FB10 | Transaction-FB10 | 2009-09-01 | 80231 | Invoice/Credit Fast Entry | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-FB60 | Transaction-FB60 | 2009-09-01 | 3702 | Enter Incoming Invoices | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-FBL1N | Transaction-FBL1N | 2009-09-01 | 4212 | Vendor Line Items | n | Logistics | y | Ken |  | N |  |  |  |  | 2009-09-01
Transaction-FBRA | Transaction-FBRA | 2009-09-01 | 6842 | Reset Cleared Items | n | Logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Transaction-FCH1 | Transaction-FCH1 | 2009-09-01 | 11715 | Display Check Information | n | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-FCH2 | Transaction-FCH2 | 2009-09-01 | 29864 | Display Payment Document Checks | n | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-FCH3 | Transaction-FCH3 | 2009-09-01 | 10 | Void Checks | n | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-FCH6 | Transaction-FCH6 | 2009-09-01 | 21 | Change Check Information/Cash Check | n | Logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Transaction-FCH7 | Transaction-FCH7 | 2009-09-01 | 16 | Reprint Check | n | Logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Transaction-FCH8 | Transaction-FCH8 | 2009-09-01 | 1378 | Reverse Check Payment | n | logistics | y | Ken |  | N |  |  |  |  | 2009-09-01
Transaction-FCH9 | Transaction-FCH9 | 2009-09-01 | 288 | Void Issued Check | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-FCHI | Transaction-FCHI | 2009-09-01 | 328 | Check Lots | n | Logistics | y | Ken |  | N |  |  |  |  | 2009-09-01
Transaction-FCHN | Transaction-FCHN | 2009-09-01 | 221 | Check Register | n | Logistics | y | Ken |  | N |  |  |  |  | 2009-09-01
Transaction-IA01 | Transaction-IA01 | 2009-09-01 | 2834 | Create Equipment Task List | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IA02 | Transaction-IA02 | 2009-09-01 | 892 | Change Equipment Task List | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IA05 | Transaction-IA05 | 2009-09-01 | 143 | Create general task list | n | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IA08 | Transaction-IA08 | 2009-09-01 | 72 | Change PM Task Lists | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IA17 | Transaction-IA17 | 2009-09-01 | 3 | Print Maintenance Task Lists | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IE01 | Transaction-IE01 | 2009-09-01 | 966 | Create Equipment | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IE02 | Transaction-IE02 | 2009-09-01 | 23965 | Change Equipment | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IE05 | Transaction-IE05 | 2009-09-01 | 41 | Change Equipment | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IL01 | Transaction-IL01 | 2009-09-01 | 3 | Create Functional Location | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IL02 | Transaction-IL02 | 2009-09-01 | 18 | Change Functional Location | n | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IP01 | Transaction-IP01 | 2009-09-01 | 2530 | Create Maintenance Plan | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IP02 | Transaction-IP02 | 2009-09-01 | 8857 | Change Maintenance Plan | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IP15 | Transaction-IP15 | 2009-09-01 | 42 | Change Maintenance Plan | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IP41 | Transaction-IP41 | 2009-09-01 | 987 | Add single plan | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IR01 | Transaction-IR01 | 2009-09-01 | 370 | Create Work Center | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IR02 | Transaction-IR02 | 2009-09-01 | 207 | Change Work Center | n | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IW31 | Transaction-IW31 | 2009-09-01 | 64265 | Create Order | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW32 | Transaction-IW32 | 2009-09-01 | 480640 | CHANGE ORDER | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW36 | Transaction-IW36 | 2009-09-01 | 2171 | Create PM Sub-Order | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW38 | Transaction-IW38 | 2009-09-01 | 190 | Change PM Orders | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW39 | Transaction-IW39 | 2009-09-01 | 859 | Display PM orders | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IW3D | Transaction-IW3D | 2009-09-01 | 48077 | Print Order | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW3K | Transaction-IW3K | 2009-09-01 | 56 | Change order component list | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IW41 | Transaction-IW41 | 2009-09-01 | 71 | Enter PM Order Confirmation | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW44 | Transaction-IW44 | 2009-09-01 | 35272 | PM Order Collective Confirmation | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW45 | Transaction-IW45 | 2009-09-01 | 2790 | Cancel PM Order Confirmation | n | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-IW48 | Transaction-IW48 | 2009-09-01 | 11 | Confirmation using operation list | n | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-IW62 | Transaction-IW62 | 2009-09-01 | 140 | Change Historical Order | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-MB01 | Transaction-MB01 | 2009-09-01 | 4545 | Post Goods Receipt for PO | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MB02 | Transaction-MB02 | 2009-09-01 | 29 | Change Material Document | n | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-MB1A | Transaction-MB1A | 2009-09-01 | 489 | Goods Withdrawal | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MB21 | Transaction-MB21 | 2009-09-01 | 3 | Create Reservation | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-MB26 | Transaction-MB26 | 2009-09-01 | 801 | Picking list | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MD01 | Transaction-MD01 | 2009-09-01 | 24 | MRP Run | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MD62 | Transaction-MD62 | 2009-09-01 | 140 | Change Planned Indep. Requirements | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME12 | Transaction-ME12 | 2009-09-01 | 62 | Change Purchasing Info Record | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ME21 | Transaction-ME21 | 2009-09-01 | 65735 | Create Purchase Order | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME21N | Transaction-ME21N | 2009-09-01 | 3517 | Create Purchase Order | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME22 | Transaction-ME22 | 2009-09-01 | 154293 | Change Purchase Order | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME22N | Transaction-ME22N | 2009-09-01 | 2279 | Change Purchase Order | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME23 | Transaction-ME23 | 2009-09-01 | 131803 | Display Purchase Order | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME23N | Transaction-ME23N | 2009-09-01 | 4239 | Display Purchase Order | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME2B | Transaction-ME2B | 2009-09-01 | 225 | POs by Requirement Tracking Number | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ME2K | Transaction-ME2K | 2009-09-01 | 879 | Purch. Orders by Account Assignment | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ME51 | Transaction-ME51 | 2009-09-01 | 404 | Create Purchase Requisition | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME51N | Transaction-ME51N | 2009-09-01 | 191 | Create Purchase Requisition | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME52 | Transaction-ME52 | 2009-09-01 | 98890 | Change Purchase Requisition | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME52N | Transaction-ME52N | 2009-09-01 | 1625 | Change Purchase Requisition | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME54 | Transaction-ME54 | 2009-09-01 | 8442 | Release Purchase Requisition | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME54N | Transaction-ME54N | 2009-09-01 | 2 | Release Purchase Requisition | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME55 | Transaction-ME55 | 2009-09-01 | 1801 | Collective Release of Purchase Reqs. | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ME56 | Transaction-ME56 | 2009-09-01 | 7 | Assign Source to Purch. Requisition | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ME80 | Transaction-ME80 | 2009-09-01 | 2 | Purchasing Reporting | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ME9F | Transaction-ME9F | 2009-09-01 | 98945 | Message Output: Purchase Orders | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MI01 | Transaction-MI01 | 2009-09-01 | 28 | Create Physical Inventory Document | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MI02 | Transaction-MI02 | 2009-09-01 | 183 | Change Physical Inventory Document | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MI04 | Transaction-MI04 | 2009-09-01 | 988 | Enter Inventory Count with Document | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-MI05 | Transaction-MI05 | 2009-09-01 | 1191 | Change Inventory Count | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MI07 | Transaction-MI07 | 2009-09-01 | 1303 | Process List of Differences | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MI09 | Transaction-MI09 | 2009-09-01 | 831 | Enter Inventory Count w/o Document | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MI10 | Transaction-MI10 | 2009-09-01 | 336 | Create List of Differences w/o Doc. | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-MI11 | Transaction-MI11 | 2009-09-01 | 190 | Recount Physical Inventory Document | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MIGO | Transaction-MIGO | 2009-09-01 | 17724 | Goods Movement | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MIR4 | Transaction-MIR4 | 2009-09-01 | 32348 | Call MIRO - Change Status | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-MIR6 | Transaction-MIR6 | 2009-09-01 | 7 | Invoice Overview | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-MIRO | Transaction-MIRO | 2009-09-01 | 169308 | Enter Incoming Invoice | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-MM01 | Transaction-MM01 | 2009-09-01 | 1599 | Create Material & | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MMSC | Transaction-MMSC | 2009-09-01 | 604 | Enter Storage Locations Collectively | n | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-MN05 | Transaction-MN05 | 2009-09-01 | 14 | Change Message: PO | n | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-MR03 | Transaction-MR03 | 2009-09-01 | 26 | Display Inv. Verification Document | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-MR8M | Transaction-MR8M | 2009-09-01 | 1686 | Cancel Invoice Document | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-MRBR | Transaction-MRBR | 2009-09-01 | 1772 | Release Blocked Invoices | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-PFTC | Transaction-PFTC | 2009-09-01 | 9 | General Task Maintenance | n | logistics | Y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-PT03 | Transaction-PT03 | 2009-09-01 | 29 | Display Work Schedule | n | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Transaction-S_P99_41000101 | Transaction-S_P99_41000101 | 2009-09-01 | 670 | Check Register | n | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-XK01 | Transaction-XK01 | 2009-09-01 | 11963 | Create vendor (centrally) | n | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-XK02 | Transaction-XK02 | 2009-09-01 | 43064 | Change vendor (centrally) | n | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-XK03 | Transaction-XK03 | 2009-09-01 | 25444 | Display vendor (centrally) | n | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-XK04 | Transaction-XK04 | 2009-09-01 | 40 | Vendor Changes (Centrally) | n | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-XK05 | Transaction-XK05 | 2009-09-01 | 3 | Block Vendor (Centrally) | n | logistics | Y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZAP1042FILE | Transaction-ZAP1042FILE | 2009-09-01 | 18 | Create reporting & data merge files | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZAP1042RTRV | Transaction-ZAP1042RTRV | 2009-09-01 | 9 | Retrieve the 1042S file for the IRS | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZAP1042VALD | Transaction-ZAP1042VALD | 2009-09-01 | 11 | Validate the 1042S withholdings file | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZAP1042VNDR | Transaction-ZAP1042VNDR | 2009-09-01 | 15 | Validate 1042-S vendor master data | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZAP1099M | Transaction-ZAP1099M | 2009-09-01 | 185 | Maintain 1099M IRS Output File | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZAP3 | Transaction-ZAP3 | 2009-09-01 | 112 | Display Alternate Payee Addresses | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZAPFEEDS | Transaction-ZAPFEEDS | 2009-09-01 | 713 | AP Feeds | Y | Logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZBP0 | Transaction-ZBP0 | 2009-09-01 | 11153 | Review/Print Requisition | Y | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZBP5 | Transaction-ZBP5 | 2009-09-01 | 951 | PO Commitment Report | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZC01 | Transaction-ZC01 | 2009-09-01 | 363 | Credit Card: Create master data | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZC02 | Transaction-ZC02 | 2009-09-01 | 2951 | Credit Card: Change master data | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZC03 | Transaction-ZC03 | 2009-09-01 | 2469 | Credit Card: Display master data | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZC04 | Transaction-ZC04 | 2009-09-01 | 1227 | Credit Card: Create Acct.Assign.Rule | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZC05 | Transaction-ZC05 | 2009-09-01 | 584 | Credit Card: Change Acct.Assign.Rule | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZC06 | Transaction-ZC06 | 2009-09-01 | 602 | Credit Card: Display Acct.Assgn.Rule | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZIW38 | Transaction-ZIW38 | 2009-09-01 | 89882 | Change PM orders | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZME52 | Transaction-ZME52 | 2009-09-01 | 104 | Change Requisition for MIT | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZMM_MB51 | Transaction-ZMM_MB51 | 2009-09-01 | 128 | Material Movement Summary Report | Y | Logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ZMM_ME1M | Transaction-ZMM_ME1M | 2009-09-01 | 67 | Material Vendor Report | Y | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ZMM6 | Transaction-ZMM6 | 2009-09-01 | 234 | Physical Plant - Stock Issues | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZMMD | Transaction-ZMMD | 2009-09-01 | 7 | Download Materials into Excel | Y | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ZMMLIQPO | Transaction-ZMMLIQPO | 2009-09-01 | 55 | PO Close Program | Y | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZMMVCEXTRACT | Transaction-ZMMVCEXTRACT | 2009-09-01 | 3 | eCustoms Vendor Master File Extract | Y | logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Transaction-ZMRP | Transaction-ZMRP | 2009-09-01 | 690 | Reorder Report for PPLT | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZP07 | Transaction-ZP07 | 2009-09-01 | 60 | 1099 Listing | Y | logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Transaction-ZPARTS | Transaction-ZPARTS | 2009-09-01 | 79 | Transaction code | Y | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ZPAY | Transaction-ZPAY | 2009-09-01 | 557 | Outsourcing chks for printing/wiring | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZPIBINCHECK | Transaction-ZPIBINCHECK | 2009-09-01 | 77 | Inventory Count Bin Check | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZPIINVCOUNT | Transaction-ZPIINVCOUNT | 2009-09-01 | 338 | Physical Inv. --> upload inv. count | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZPMAFR | Transaction-ZPMAFR | 2009-09-01 | 53 | PM Air Filter Requirements Report | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZPMORD1 | Transaction-ZPMORD1 | 2009-09-01 | 675 | PMATS: Create Work Order | Y | logistics | y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZPMORD2 | Transaction-ZPMORD2 | 2009-09-01 | 662 | PMATS: Change Work Order | Y | logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Transaction-ZPMORD3 | Transaction-ZPMORD3 | 2009-09-01 | 93 | PMATS: Display Work Order | Y | logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Transaction-ZPMWOCREATE | Transaction-ZPMWOCREATE | 2009-09-01 | 7291 | Create Work Order | Y | logistics | y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ZPMWORPT | Transaction-ZPMWORPT | 2009-09-01 | 12 | Work Order Report for PMATS | Y | logistics | y | Ken |  | n |  |  |  |  | 2009-09-01
Transaction-ZPP1 | Transaction-ZPP1 | 2009-09-01 | 87 | Physical plant - Barcode Generator | Y | logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZPP2 | Transaction-ZPP2 | 2009-09-01 | 26105 | Goods issue | Y | Logistics | y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZPPINV | Transaction-ZPPINV | 2009-09-01 | 9972 | DoF: Register DoF Invoice | Y | logistics | y | rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZREQDISPLAY | Transaction-ZREQDISPLAY | 2009-09-01 | 155205 | Display requisition | Y | Logistics | Y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ZREQINBXAPPR | Transaction-ZREQINBXAPPR | 2009-09-01 | 99776 | Requisition approver inbox | Y | Logistics | Y | Rita |  | n |  |  |  |  | 2009-09-01
Transaction-ZREQINBXCRE | Transaction-ZREQINBXCRE | 2009-09-01 | 3862 | Requisition creator inbox | Y | Logistics | Y | Elda |  | TBD |  |  |  |  | 2009-09-01
Transaction-ZREQSELECT | Transaction-ZREQSELECT | 2009-09-01 | 255517 | Select individual requisition | Y | logistics | Y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZRQA | Transaction-ZRQA | 2009-09-01 | 37958 | Display Totally Released Requisition | Y | logistics | Y | Rita |  | y |  |  |  |  | 2009-09-01
Transaction-ZSIG | Transaction-ZSIG | 2009-09-01 | 5501 | Address for invoice authorization | Y | logistics | Y | Ken |  | y |  |  |  |  | 2009-09-01
Transaction-ZTRACK1 | Transaction-ZTRACK1 | 2009-09-01 | 4614 | Create: Loaned Asset Tracking Entry | Y | Logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Transaction-ZTRACK2 | Transaction-ZTRACK2 | 2009-09-01 | 5082 | Change: Loaned Asset Tracking Entry | Y | Logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Transaction-ZTRACK4 | Transaction-ZTRACK4 | 2009-09-01 | 1079 | Report: Loaned Asset Tracking Entry | Y | Logistics | Y | Ken |  | Y |  |  |  |  | 2009-09-01
Transaction-ZVP_RESERVATIONS | Transaction-ZVP_RESERVATIONS | 2009-09-01 | 495 | Visitor Parking: Reservations | Y | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Transaction-ZVPBATCH | Transaction-ZVPBATCH | 2009-09-01 | 35 | Visitor Parking Batch Settlement | Y | Logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01
Transaction-ZWKCENTER_WORDER | Transaction-ZWKCENTER_WORDER | 2009-09-01 | 101 | Maintain wkcntr/wkordr mapping table | N | logistics | Y | Rita |  | Y |  |  |  |  | 2009-09-01