## ScreenResults(1)
# | Subject | Status | Queue | Owner | Priority | Requestors | Created | Last Contact | Last Updated | Time Left | Transport # Sequence
1393223 | SAP 2010: Resolving SPAU_ENH - BAdI / Enhancements | resolved | SAP::Test Issues | waiming | 1 | waiming@mit.edu | 2 weeks ago | 13 days ago | 6 days ago | 0 | Released & imported into SH3. SF2K949501 - SP10/RT#1393223: Enhancement ZIW31 SF2K949503 - Supp Pack 2010: SPAU_ENH for ZIBAPI_ALM_ORD_MOD2 SF2K949507 - Supp Pack 2010: SPAU_ENH for ZAP_RFP_TRANS_FV60_SETTING SF2K949505 - Supp Pack 2010 1393223 Adjust Z_ENH_LSO_PARTICIPATION_INSERT SF2K949511 - SP10/RT#1393223: Enhancements ZZ_ENH_...
1393315 | SAP 2010: FI Program Generations triggered from PA40 (IT0000) | open | SAP::Test Issues | Nobody | 2 | cindyo@mit.edu | 2 weeks ago |  | 9 days ago | 0
1394275 | SAP2010 HR: ZHRLTD_ASSIGN error | resolved | SAP::Test Issues | cindyo | 0 | cindyo@mit.edu | 13 days ago | 10 days ago | 6 days ago | 0 | Released & imported into SH3. SF3K903397 R3ADM* OSS 1514455 - Dump UNCAUGHT_EXCEPTION by hiring
1394285 | SAP2010 HR:IT9033 Audit Report | resolved | SAP::Test Issues | cindyo | 0 | cindyo@mit.edu | 13 days ago |  | 8 days ago | 0 | No transport required.
1394298 | SAP 2010 - HR Payroll - DSM errors | resolved | SAP::Test Issues | donovan | 0 | donovan@mit.edu | 13 days ago |  | 6 days ago | 0 | No transport required.
1394674 | SAPWeb Create/Change JV can't use WBS | resolved | SAP::Test Issues | rcasey | 0 | fuller@mit.edu | 13 days ago |  | 6 days ago | 0 | Released & imported into SH3. SF3K903395 R3ADM* OSS 1496055 - FBV1/FB01/fast entry: Message KI 235
1397279 | SAP 2010 - EHS - WWI fails to operate in Windows 7 | open | SAP::Test Issues | lcollier | 0 | lcollier@mit.edu | 10 days ago |  | 10 days ago | 0
1397513 | SAP 2010: EDI - Possible issue with inbound EDI invoices in SF2 | resolved | SAP::Test Issues | eprudden | 0 | eprudden@mit.edu | 10 days ago | 6 days ago | 6 days ago | 0 | No transport required.
1397757 | GuiXT Issue: Technically Completing Work Orders | resolved | SAP::Test Issues | mzhovnir | 0 | lstcroix@plant.mit.edu | 10 days ago |  | 24 hours ago | 0 | No transport required. Fix provided by GuiXT vendor.
1397770 | GuiXT: Action Log Button | resolved | SAP::Test Issues | mzhovnir | 0 | lstcroix@plant.mit.edu | 10 days ago |  | 24 hours ago | 0 | No transport required. Fix provided by GuiXT vendor.
1397775 | GuiXT: Put In Process | resolved | SAP::Test Issues | mzhovnir | 0 | lstcroix@plant.mit.edu | 10 days ago |  | 24 hours ago | 0 | No transport required. Fix provided by GuiXT vendor.
1398450 | SAP 2010 - HRP ZHR_HOURLY_GRAD | resolved | SAP::Test Issues | alanm | 0 | alanm@mit.edu | 9 days ago | 8 days ago | 6 days ago | 0 | Released & imported into SH3. SF3K903397 (see ticket 1394275)
1398904 | SAP 2010 - HR Payroll - Error in transaction ZHRRETIREE_ANNUITY | resolved | SAP::Test Issues | donovan | 0 | donovan@mit.edu, robertsd@mit.edu | 9 days ago | 3 days ago | 3 days ago | 0 | No transport required (at this time).
1399148 | SAP 2010 - HR Payroll - Registered Partner Dependent Type showing up in ESS and GUI on IT0021 | resolved | SAP::Test Issues | robertsd | 0 | robertsd@mit.edu | 9 days ago |  | 6 days ago | 0 | Released & imported into SH3. SF2K949522 - UPG: Hide Registered Partner Dependent Type in ESS
1399303 | Fi Line Item Validation errors cause call transaction error in JVSuite, RFP & JV Upload | resolved | SAP::Test Issues | rcasey | 0 | fuller@mit.edu | 9 days ago |  | 14 min ago | 0 | Released & imported into SH3. SF2K949517 SP10/RT#1399303: JV Upload, JVSuite & RFP FI LItem Val
1399891 | SAP 2010 - HR Payroll - Buttons missing from UPI Education search page | resolved | SAP::Test Issues | donovan | 0 | mprudden@mit.edu | 8 days ago |  | 6 days ago | 0 | Released & imported into SH3. SF2K949509 - UPG: Fixes to 2010 Support Pack Issues in ESS
1400177 | FI: Convert FI Validation/Substitution Mods to Enhancements | resolved | SAP::Test Issues | rcasey | 0 | fuller@mit.edu | 8 days ago |  | 17 min ago | 0 | Released & imported into SH3. SF2K949491 FI: RT#1400177 Convert Val/Subs Mods to Enhancements SF2K949513 SP10/RT#1400177: FI: Convert FI Validation/Substitution Mods
1400185 | AR: Support Package 3 mods converted to enhancements | resolved | SAP::Test Issues | rcasey | 0 | fuller@mit.edu | 8 days ago |  | 25 min ago | 0 | Released & imported into SH3. SF2K949489 AR: RT#1400185 Support Pack 3 mods converted to enhancements
1401511 | SAP 2010 - AP - 1042S form interface change | resolved | SAP::Test Issues | levie | 0 | levie@mit.edu | 6 days ago |  | 6 days ago | 0 | No transport required.
1404995 | SAP 2010: EL: Overview Link on Registar Tab in Portal does not work in Safari | open | SAP::Test Issues | ecunning | 0 | ecunning@mit.edu | 2 days ago | 32 hours ago | 32 hours ago | 0
1406401 | FW: Critical BEN/OE: Change zhr_mark_oe_pcp to look at DOCN2 | open | SAP::Test Issues | robertsd | 0 | robertsd@mit.edu | 30 hours ago |  | 9 hours ago | 0 | Critical Production Issue Requires dual testing See ticket 1399477 SF2K949541 - Benefits: unmark PCP for Open Enrollment
1406459 | SAP 2010 ZC92 - BDC screen missing | open | SAP::Test Issues | rcasey | 0 | rcasey@mit.edu | 28 hours ago |  | 24 hours ago | 0
1407157 | SAP2010 HR/PAY: Infotype numbers | resolved | SAP::Test Issues | cindyo | 0 | cindyo@mit.edu | 12 hours ago |  | 22 min ago | 0 | Released & imported into SH3. SF2K949547 HR/Pay: Infotype text (support Pk 2010)
1407292 | ZAR3 - line item text not copied into document line item | open | SAP::Test Issues | rcasey | 0 | rcasey@mit.edu | 11 hours ago |  | 9 hours ago | 0 | Critical Production Issue Requires dual testing See ticket #1404494 SF2K949535 - AR: RT#1404494 Line Item text incorrect Released and imported into SH3
1407632 | CO Validation - CO Item, Step 1 not working for KN, RP doc types | open | SAP::Test Issues | rcasey | 0 | rcasey@mit.edu | 7 hours ago |  | 7 hours ago | 0