## Action Log
SAP YE Support Pack FY11 - Consolidated Action Log
This document is used by IS&T and Business Process Owners as a guide to validate SAP systems after a database copy, infrastructure update and version upgrade. | [8 empty] | Performed in Environment? | [21 empty] | Dependencies or Timing Issues | Notes
Task # | User/Resp | Area | Dev/ Config / Trx. | DB Copy | Infra Update | Upgrade | R3 Auth | Description | SF3 Refresh |  | SF3 Post SP Application |  | SF2 |  | SH3 Refresh |  | SH3 Post SP Application |  | PS1 Post SP Application |  | SF5 |  | SH1 refresh |  | SH2 |  | SF7 |  | SF8 update
[9 empty] | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task refresh | Task Status | Required Task | Task Status | Required Task | Task Status | Required Task | Task Status
1 | Ron Parker | Email Notification | SE38 | Yes | Yes | Yes |  | Program ZBRSMAIL provides a mechanism to modify, replace, append, or write to tables Zemctrl and Zehcat. It is also possible to delete all of the rows of either of the two tables. These tables are used in the email redirection/distribution process. (Download values in ZEHCAT and ZEMCTRL tables) | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes | complete |  |  |  |  | No | n/a |  | Pre-refresh settings exported and then import after the refresh.
2 | Ron Parker | Email Notification |  | Yes | Yes | Yes |  | Reset table settings for Z_SENDMAIL : 1. delete all entries from ZEMCTRL. 2. replace the contents of ZEHCAT with two rows: HNCAT=<space><space>, CMODE=X, ACTION=X, All other fields=<space>; HNCAT=++, CMODE=X, ACTION=X, All other fields=<space> | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes | complete |  |  |  |  | No | n/a |  | Pre-refresh settings exported and then import after the refresh.
3 | Ron Parker | Email Notification | Config | Yes | Yes | Yes |  | Redirect e-mail notifications. Transaction SE30 Call View Maintenance. Table: ZEHCAT E-mail control table - handling categories. Action: Redirect Emailto: user@mit.edu or Action: Cancel. | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | No | n/a | Yes | complete | Yes | complete |  |  |  |  | No | n/a |  | Pre-refresh settings exported and then import after the refresh.
4 | Ron Parker | ITS | SICF |  |  |  |  | Activate /default_host/sap/public/bc/its/mimes | validate | complete | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate | complete | validate | complete |  |  |  |  | validate | complete
5 | Ron Parker | ITS | SICF |  |  |  |  | 1. SICF 2. /default_host/sap/public/bc/icons 3. Menu >> Service/Host 4. Activate Object S_ICF_ADM Object class AAAB Activity 07 ICF: Name of Virtual Host ' ' ICF: GUID of ICF Service/Alias 000000000000000000000000 ICF: Service/Host/Alias NODE | validate | complete | validate | complete | validate | complete | validate | complete | validate |  | validate | complete | validate | complete | validate | complete |  |  |  |  | validate | complete
6 | A. Miller | HR |  | Yes | N/A | N/A |  | Scramble HR data before system is open to others for validation | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | n/a | n/a | Yes | complete | No | [5 empty] | No | n/a
7 | Lucia Ma | MM | OMJ3 | Yes | Yes | Yes | Z_OMJ3 | Ensure Inventory printers are not directed to the production environment. Go to IMG: Materials management -> Inventory management and physical inventory -> Output determination -> Printer determination -> Printer determination by plant/storage location. (T_code: OMJ3) Change printers to MRP5. | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | No | complete
8 | Lucia Ma | MM | SPRO or SM30 (V_024_N) | Yes | Yes | Yes |  | Ensure Purchasing Group printers are not directed to the production environment. Go to IMG: Materials management -> Purchasing -> Messages ->Assign Output Devices to Purchasing Group. Change printers to MRP5. | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | No | complete
9 | Lucia Ma | MM | SM30 | Yes | Yes | Yes |  | Ensure ISP printouts are not directed to the production environment. Transaction SM30. Table: ZISPREQ Hit maintain and change printers to MRP5. (Also userid & password in table ZCAPARM) check view (ZV_MT*) | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | No | complete
10 | Lucia Ma | Classification | CT04 |  |  |  | Z#GL:CT04 | Change Facilities IO printer classification characteristic to print to MRP5, not a production printer. Looking for "DISTRIBUTION" | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | No | complete
11 | Lucia Ma | Cross App | SE38 | Yes | Yes | Yes |  | Run Program ZCOC020 | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | No | complete
12 | Lucia Ma | Workflow | SEWTYPV |  |  |  | Z#AA:WKFLADM | Reactivate all workflow event linkages. (Tcode: SWETYPV) | Yes | complete | validate | complete | validate | complete | Yes | complete | validate | complete | to check | complete | Yes | complete | Yes | complete |  |  |  |  | validate | complete
13 | Lucia Ma | Email Notification | SM30 |  |  |  | Z#EM:02_ZEM0 | Update ZEHCAT table to allow e-mail messages to be sent for commitment posting errors (first time entry into ZEHCAT) also make sure "FA" ~ "FZ" are redirected. | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | No | complete
14 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | DoF validation: Enter program GBT30FIF and search (do Find in program) for GLL. (There should be none, only GAL.) If GLL is found, then regenerate validation rules from step above. NOTE: the "30" in the program name is based on the client in which the program is run, i.e. change to "25" if the client is 025, etc. Also looking for TEMP_STRUCT-SGTXT in GBT30COJ. | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | to check | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
15 | Ron Parker | FI/CO | SE38 | Yes | Yes | Yes |  | Generate validations/substitutions and sets. Run program RGUGBR00 with params: *,*,xxxxxx NOTE: This step should be completed only after all transports have been applied to the system, because transports containing validation rules will overwrite and require regeneration. | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
16 | Lucia Ma | FI | SE38 | Yes | Yes | Yes |  | Regenerate FBV1 JV fast entry template: Run RFFAKP01 with parameters program = SAPLF040, application = PRPOS | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Y | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
17 | Lucia Ma | CO user exits | CMOD | Yes | Yes | Yes |  | Enter projects COOPA003, COOMKS01, WBSENHA, CATS0002 select "components" with "change" mode, make sure all exits are activated (green dots). If any component is not noted with a green dot, then return to CMOD screen, and deactivate, then reactivate the project, and confirm the project is activated./If deactivated, all users with CMOD need to check theirs as a follow up. | Yes | complete | validate | complete | validate | complete | Yes | complete | validate | complete | to check | complete | Yes | complete | Yes | complete |  |  |  |  | validate | complete
18 | Lucia Ma | CO | SE38 | Yes | Yes | Yes |  | Run programs RK811XST and RK811XUP to convert transaction groups for CO allocations (incl. Business cycles). No parameters necessary. | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Y | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
21 | Elda Prudden/Lucia | IXOS | OAC3 | Yes | Yes | Yes | Z_OAC3 | IXOS Archive Link Setting. Transaction OAC3 Change View "Links for Content Repositories": Overview. (ALSO NEED FOR SPONSORED BILL ARCHIVE KL-10/30/03) If Ron doesn't put a value in there, don't have to modify it (look at the Cont.Rep.ID field and using the pulldown, make sure that the production values are not being referenced). | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | yes | complete
22 | Elda Prudden/Lucia | LO-EDI & HR-EDI | WE20 | Yes | Yes | Yes |  | Change the Receiver Port for Outbound Parameters. Transaction WE20 (Partner Profiles). Double click on "Partner Number" then dobule click on "Outbound Parmtrs". New screen come up. Change the "Receiver Port" under "Outbound Options". To confirm, check table EDP13 (field RCVPOR). | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | yes | complete
23 | F. Quern | HR | SM30 |  |  |  |  | Validate entries in table ZHRRETIREE_PLANS | No | n/a | No | n/a | Yes | complete | No | complete | Yes | complete | to validate | complete | No | n/a | No | n/a |  |  |  |  | Yes | complete
24 | F. Quern / R3-Admin | Payroll | Dev |  |  |  |  | Update signature on check: "Void V Void" in all testing environments via transport. SHOULD NEVER GO TO PS1. Verify by transaction SE78, table Z_TTBT (SF2K927761 HRPP: Void Signiture File) | Yes | complete | validate | complete | validate | complete | Yes | complete | validate | complete | to validate | complete | Yes | complete | Yes | complete |  |  |  |  | validate | complete
25 | J. Tuttle | EHS / TEM | SM37 |  |  |  | IDs: ZZEHSBTCH001 ZZHRTEMBTC01 | Set up job to create users. Program, ZPE_CREATE_USER, under the ID, ZZHRTEMBTC01 , and is triggered by event, Z_TEM_SETUP (Check it first, if not exist, need to create one) NOTE: start after event "Z_TEM_SETUP" and it's a periodic job. Also create 2 additional batch jobs ZEHS_Daily_EHS_WEB_TRAINEE_FEED & ZEHS_ROLESDB_WA_RELATS under user ZZEHSBTCH01. | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | Y | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
26 | F. Quern | Payroll | Config |  |  |  |  | If refreshing a test environment determine if the control record should be checked during payrun processing if so comment out check from schema ZINO. This setting should never be commented out in a production environment. | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
27 | Bob Casey | FI | OB52 or ZFICLOSE |  |  |  | Z_CA_ZFICLOSE_POST_PER_OPN_CLO or Z#GL:OB52 or ID: ZZCAZFICLOSE | Open current FI posting period. | Yes | complete | No | n/a | No | n/a | Yes | complete | validate | complete | to validate | complete | Yes | complete | Yes | complete |  |  |  |  | validate | complete
28 | Wai-ming Li | All | [5 empty] | Dropbox pointed to new test environment | No | n/a | No | n/a | No | n/a | Yes | complete | No | n/a | No | n/a | Yes |  | Yes | [5 empty] | No | n/a
29 | F.Quern | Payroll | SE38 |  |  |  |  | Test BSI 8.0 connection. Execute program RPUBTCU0, select BSI Version 8.0 and execute. Test OC transaction (select a pernr) and verify BSI tax calculation is generated. | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | to validate | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
30 | F.Quern | Payroll | PU19 |  |  |  |  | Test ADS connection. Execute Test Run of Tax Forms for individual pernrs via transaction PU19. | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes | complete | to validate | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
31 | F.Quern | HR | SM30 |  |  |  |  | Compare Wage Type table: V_512W_O | No | n/a | Yes | complete | Yes | complete | No | n/a | Yes | complete | to validate | complete | No | n/a | No | n/a |  |  |  |  | Yes | complete
32 | Sharon DiLiberto | HR/Feed | [5 empty] | Check and verify/set HR Feed registry | Yes | complete | No | n/a | No | n/a | Yes | complete | No | n/a | n/a | n/a | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
33 | F.Quern | Payroll | SM30 |  |  |  |  | Check HR Payroll constant table: V_T511P, V_T511K | No | n/a | Yes | complete | Yes | complete | Yes | complete | Yes | complete | to validate | complete | No | n/a | No | n/a |  |  |  |  | Yes | complete
34 | F.Quern | Payroll | SPRO |  |  |  |  | Check PDF Validity Date for the tax form: V_T5UX7 Forms: HR_F_W2, HR_F_W2C, HR_F_1099R, HR_F_1099RC | No | n/a | Yes | complete | Yes | complete | Yes | complete | Yes | complete | to validate | complete | No | n/a | No | n/a |  |  |  |  | Yes | complete
35 | R3-ADMIN | Infra-structure | [5 empty] | Turn on the FAX Gateway | Yes | complete | validate | complete | validate | complete | Yes | complete | validate |  | validate | complete | Yes | complete | Yes | complete |  |  |  |  | validate | complete
36 | R3-ADMIN | Infra-structure | [5 empty] | Establish target systems Operation Mode (work process distributions) | Yes | complete | Yes | complete | Yes | complete | Yes | complete | Yes |  | Yes | complete | Yes | complete | Yes | complete |  |  |  |  | Yes | complete
37 | BASIS | HR | PA40 |  |  |  |  | The features generation program, RPUMKG00, to activate generated programs related to HR features. | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | [5 empty] | No | n/a
38 | Elda Prudden/Lucia | TLE EDI | SAP Instance Info |  |  |  |  | In TLE, change the "Application Server" name, the "Gateway Server Name" and the "Host Name" (this action log item is only required for the hardware renewal project) | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | No | n/a | n/a |  | n/a |  | No | n/a
39 | F. Quern | Portal | ESS/Training |  |  |  |  | Test Portal connectivity via ESS look up personal or assign Kerberos to an existing pernr training history. | Yes | complete | Yes | complete | Yes | pending | Yes | complete | Yes | complete | to validate | complete | Yes | pending | Yes | complete |  |  |  |  | Yes | complete
40 | B. Casey | FIN |  | Yes | Yes | Yes |  | Execute Trial Balance | No | n/a | No | n/a | No | n/a | Yes | complete | Yes | complete | No | n/a | No | n/a | No | n/a |  |  |  |  | No | n/a
Primary Coordinator:
Backup Coordinators:
.