## Results(1)
# | Subject | Status | QueueName | OwnerName | Requestors | CreatedRelative | CustomField.{Transport # Sequence }
1782625 | SAP 2011 - HR Benefits - OE TEXT CHANGES | resolved | SAP::Test Issues | robertsd | robertsd@mit.edu | 4 weeks ago | Associated transport moved to PS1 as Critical. Imported into SH1 prior to upgrade therefore no action required.
1785201 | SAP 2011 - Logistics - EDI issue in SF2 | resolved | SAP::Test Issues | levie | levie@mit.edu | 3 weeks ago | No transports required. Production settings need to take place by Elda and R3 at cut-over.
1785251 | SAP 2011 - EL - MIT Learning Center browser issues | resolved | SAP::Test Issues | ecunning | donovan@mit.edu | 3 weeks ago | (1) SF3K903597 R3ADM* OSS 1640534 - Correction for unified rendering 702/1 (2) SF3K903599 Upload & deploy Version 7.32 of ur_mimes_nw7.zip
1785261 | SAP 2011 - Tech Services - Problems running web dynpro applications in SF2 | resolved | SAP::Test Issues | waiming | donovan@mit.edu | 3 weeks ago | See RT# 1785251
1785347 | SAP 2011 - Sponsored Accounting - Issue running report ZSSB | resolved | SAP::Test Issues | nadendla | nadendla@mit.edu | 3 weeks ago | Required regeneration of function module Z_CO_COST_OBJECT_NAMES
1785565 | SAP 2011-Payroll-Transaction ZPYNRA0210 creating errors during execution | resolved | SAP::Test Issues | donovan | donovan@mit.edu | 3 weeks ago | SF2K951292 - PY: RT#1785565 ZPYNRA0210 creating errors during execution
1785651 | SAP 2011 - ESS Personal information and dependent screens | resolved | SAP::Test Issues | robertsd | robertsd@mit.edu | 3 weeks ago | Duplicate issue - see RT# 1786263.
1785658 | SAP 2011 Logistics Plant Maintenance GuiXT issue with IW31, IW32, IW33 & ZIW38 | open | SAP::Test Issues | lstcroix |  | 3 weeks ago
1786263 | SAP 2011 - SAPweb Self Service - Personal information - Name and Home Address - weird text appearing | resolved | SAP::Test Issues | robertsd | klyons@mit.edu | 3 weeks ago | Application of SAP Kernel 720 SupPkgLvl 112.
1786304 | SAP 2011 - SAPweb Self Service - Money Matters - Reimbursement Preferences - buttons don't work | resolved | SAP::Test Issues | levie | klyons@mit.edu | 3 weeks ago | See RT# 1785251
1786949 | SAP 2011 Logistics/Plant Maintenance transaction ZMRP error creating multiple line purchase order | resolved | SAP::Test Issues | ja17661 | ja17661@mit.edu | 3 weeks ago | SF2K951300 - SAPSP2011: RT1786949 - ZMRP fix
1787061 | RE: [tech-services] SAP 2011 - SAPweb Self Service - Personal information - Name and Home Address - weird text appearing | resolved | SAP::Test Issues | robertsd | mprudden@mit.edu | 3 weeks ago | Duplicate issue - see RT# 1786263.
1787968 | SAP 2011-Payroll- 457b deferrals stop prior to CY2011 standard plan contribution limit | resolved | SAP::Test Issues | gmcgrath | gmcgrath@mit.edu | 3 weeks ago | SF2K951296 PY:WT 449E to Tuition FSA as of 010106 to fix 457
1787992 | SAP 2011 - Benefits transaction ZHRBEN0012 - ABAP error | resolved | SAP::Test Issues | robertsd | robertsd@mit.edu | 3 weeks ago | SF2K951298 - HR-Ben RT#1787992 ZHRBEN0012 - ABAP error
1788564 | SAP 2011 - Authorization Profiles - # character issue | resolved | SAP::Test Issues | georgep | georgep@mit.edu | 3 weeks ago | SF3K903605 - R3ADM* RT1788564 Mod 4 # in Prof name CustMsg 903140/2011
1789792 | SP2011 FIN - Old SD user exits converted to implicit enhancement | open | SAP::Test Issues | rcasey |  | 3 weeks ago | SF2K951274 - SB: RT#1789792 Sponsored Billings Mod converted to ENH - 2
1789800 | SP2011 FIN - Medical Mods change to implicit enhancements | resolved | SAP::Test Issues | rcasey |  | 3 weeks ago | SF2K951257 - AR: RT#1789800 3 Med Txt Sup mods converted to enhancements
1790533 | SAP 2011: Error when generating Instructor Class Attendee Report on Portal | resolved | SAP::Test Issues | ecunning | ecunning@mit.edu | 2 weeks ago | SF2K951309 - EL: RT#1790533 - Attendee List - Add Req.d FPM GAF Interface
1790545 | SAP 2011-Payroll- 2011 on-line W2 forms generate an error when accessed | resolved | SAP::Test Issues | gmcgrath | gmcgrath@mit.edu | 2 weeks ago | SF2K951307 - PY:Add new 2011 EE W2 form to table ZPY_ESS_TAX_FORM
1790966 | SAP 2011 - Benefits ESS - Self record showing up on list of possible enrollees | resolved | SAP::Test Issues | robertsd | robertsd@mit.edu | 2 weeks ago | (1) SF2K951314 - HR-ESS: Hide ineligible dependents in benefits enrollment (2) SF3K903609 - R3ADM* OSS 1542155 - Incorrect Dependents appearing in ESS
1791017 | SAP 2011-Payroll- Employee name is misaligned on 2011 W2 form HR_F_W2_MULT_11 | resolved | SAP::Test Issues | gmcgrath | gmcgrath@mit.edu | 2 weeks ago | (1) SF3K903601 - R3ADM* OSS 1644528 - Alignment issues (2) SF3K903603 - R3ADM* OSS 1644528 - Alignment issues 2
1794012 | SAP 2011 - SAP-AP-IXOS images not accessible after Scanning/WF/Post is completed | resolved | SAP::Test Issues | levie | levie@mit.edu | 13 days ago | No transport or action required.
1794512 | SAP 2011 WF Workflow - over 12,000 items in everyone's SAP Inbox | waiting | SAP::Test Issues | rcasey | fuller@mit.edu | 13 days ago | Will address post SP go-live.
1795056 | SAP 2011 "Unable to process Formaldehyde" message with Hydrofluoric acid | resolved | SAP::Test Issues | lcollier | veal@mit.edu | 12 days ago | No transport or action required.
1795142 | SAP 2011: ASR - problem downloading the faculty spreadsheet | resolved | SAP::Test Issues | ecunning | ecunning@mit.edu | 12 days ago | SF2K951317 - HR ASR support packs: change FM to read binary file from srv
1795243 | SP 2011 - HRPayroll - Sick cost out report header | resolved | SAP::Test Issues | donovan | lesliem@mit.edu | 12 days ago | No transport or action required.
1795984 | SP2011- HRPayroll - ZOMCHST delimit not working | resolved | SAP::Test Issues | cindyo | lesliem@mit.edu | 12 days ago | SF2K951332 - HR tr.ZOMCHST support packs fix
1797740 | Transaction SE84 (i.e. the Repository Info System) is not returning the whole list of qualifying results | resolved | SAP::Test Issues | waiming | eprudden@mit.edu | 10 days ago | No transprot or action required.
1798524 | SAP 2011 - FW: SH1 Dumps for user ZZPYBATCH001 | resolved | SAP::Test Issues | donovan | fquern@mit.edu | 8 days ago | SF3K903607-R3ADM* OSS 1594347 -SAPSYS creates system log enqueue error + Application of SAP Kernel 720 SupPkgLvl 112.
1799213 | RE: [tech-services] Transaction SE84 (i.e. the Repository Info System) is not returning the whole list of qualifying results | resolved | SAP::Test Issues | Nobody | jrtuttle@mit.edu | 7 days ago | Duplicate issue - see RT# 1797740.
1799930 | SAP 2011 - Date Format Problem when Executing Function Modules in Test/Execute Mode | open | SAP::Test Issues | waiming | jrtuttle@mit.edu | 7 days ago
1800954 | SAP 2011 - VPIS - PDF not being generated in VPIS | resolved | SAP::Test Issues | mzhovnir | asaini@mit.edu | 6 days ago | SF2K951336 - SP2011/RT# 1800954: ZVPIS_PARKING_PERMIT PDF form
1802243 | SP 2011 - HR/Payroll - Delimit appointment via PA40 is generating error on payroll infotypes | open | SAP::Test Issues | cindyo | lesliem@mit.edu | 5 days ago
1802738 | SAP 2011 - Manual Funds Reservation Authorization issue | resolved | SAP::Test Issues | rcasey | rcasey@MIT.EDU | 5 days ago | (1) SF2K951340 - R3ADM* RT 1802738 Addt'l Auths Req'd in ZMIT Menu (2) SF2K951347 - R3ADM* RT 1802738 Fixed Company Code on F_FUNDSRES
1803201 | SAP2011 - HR Payroll - Unnecessary Characters in ESS Screen | resolved | SAP::Test Issues | robertsd | sspencer@mit.edu | 4 days ago | Duplicate issue - see RT# 1786263.
1803675 | SAP 2011: EL - Problem with canceling course via LSO_PV12 - SAP note available | resolved | SAP::Test Issues | robertsd | jfw@mit.edu | 4 days ago | SF3K903611 - R3ADM* OSS 1651756 -OM structure search: 'Planned' Objects
1804455 | SAP 2011 PM Problem with Printing Internal Comments (Op Line 20) | resolved | SAP::Test Issues | ja17661 | lstcroix@plant.mit.edu | 3 days ago | No transport or action required.
1804764 | SP 2011 - HR/Payroll - APR Interim Edit does not work | resolved | SAP::Test Issues | jkogera | lesliem@mit.edu | 3 days ago | No transport or action required.
1809644 | SAP 2011 FIN/TO - Remove Backup Attached indicator from ZTRSSB2 transaction | open | SAP::Test Issues | rcasey | rcasey@MIT.EDU | 2 days ago | SF2K951362 - SP11 (RT 1809644): ZTRI002 - Remove backup flag