## Overview and Assumptions
Timeframe for Test Execution
Comparison Test: 11/7/2011-11/28/2011 (3 holidays)
Integration Test: see comparision test
Assumptions:
Production snapshot as of midnight 11/17/2011
Test system will be available by start of day 11/7/2011
Comparison test consists of four payroll comparisons:
| Weekly Non-Exempt (payweek 42 (10/10/2011-10/16/2011)) | LL | 43/2011
| Monthly Exempt (October 2011) | MC | 44/2011 | Cycle 1 | Leslie will identify cost objects
Pension Payroll Lump Sum (October 31, 2011)
Pension Monthly Annuity Run (Nov 2011)
Overview of integration test strategy:
Generate payroll and run interfaces simulating the production payroll processes.
Compare test system SH1 results to PS1 Production results
Research discrepancies; resolve system issues
Execute select test scripts hiting key functionality not executed during pay run processes
Comparison Tools:
Create comparison reports using the EPIUSE variance monitor tool
Net pay comparisons in excel
Net pay comparison using EPIUSE variance monitor
Ultra Compare
Fox Pro
Overview of Script testing - majority of testing conducted by Business:
Test Scripts identified in Quality Center, both manual and automated:
in the HR domain space are 2 folders containing test scripts:
Support_Packs_Automated
Support_Packs_Manual

## Pre-test Prep
Non-Exempt Only
Exempt Only
Relevant to both exempt and non-exempt
MITSIS file* (contains non-exempt changes as well)
MITSIS gross pay file
Pension
Copy the following in-bound files:
3/24/2010 EDS In-bound Lump Sum File
3/24/2010 EDS In-bound Annuity File
HR-Payroll Team
Create Datafiles sub-folders for feedloads and comparisons (prod & test) | [6 empty] | complete | 2010-03-08
Copy production archived files to Datafiles folder area.
Student Bio Feed (MITSIS)
Keep LL Audit files
Parking file
TPASS file
Grad Appointment feed
LL Feeds - have Wai-ming copy files to test environment's sapin directory
| Archive Directory | Files Copied | # of Files | in/out | can be loaded locally? | task link
1 | hr/bcbs |  |  | out
2 | hr/crosby |  |  | out
3 | hr/crosby_dep |  |  | out
4 | hr/crosby_new |  |  | out
5 | hr/delta |  |  | out
6 | hr/eds_hr |  |  | out
7 | hr/fid_hr |  |  | out
8 | hr/hird |  |  | out
9 | hr/metpcensus |  |  | out
10 | hr/mitsis_dem |  |  | out
11 | hr/tufts |  |  | out
12 | hr/vision |  |  | out
13 | py/cu |  |  | out
14 | py/eds_cntrib |  |  | out
15 | py/facil_leav |  |  | out
16 | py/facil_time |  | 1 | in | Yes | 74
17 | py/fid_cntrib |  |  | out
18 | py/fid_cntrib |  |  | out
19 | py/fid_pct |  |  | in | No, | 48 | Set up job to load based on event. Wai-ming should ensure i_fcp event will trigger in SH1. Move file through drop box to test HW. File has been moved to server in prep for move through the dropbox
20 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
22 | py/fsa_dep |  |  | out
23 | py/fsa_dep |  |  | out
24 | py/fsa_enroll |  |  | out
25 | py/gradaid |  | 5/5/5 | in |  | 39
26 | py/hancock |  |  | in | Yes | 77
27 | py/hancock |  |  | out
28 | py/ll_audt_py
29 | py/ll_audt_tm
30 | py/ll_bank |  |  | out
31 | py/ll_leave |  |  | out
32 | py/ll_sal_dst |  |  | out
33 | py/ll_sal_dst |  |  | out
34 | py/mass_hlth |  |  | out
35 | py/mass_sqe |  |  | out
36 | py/metp-ded | dmetficw.094.20101021000000 | 1 | in | Yes | 50
37 | py/mitsis_tim |  |  | out
38 | py/parking |  | 1/1 | in | No | 75
39 | py/t_pass |  | 1 | in | No | 76
40 | py/tech_cash | dtcshded.325.20101022000000 | 1 | in | Yes | 49
41 | py/tiaa_cref |  |  | out
42 | py/metpcont | dmetficw.094.20101021000000
43 | hr/mitsis_dem [MITSIS Biographic/Demographic files] |  | 6/6 | in |  | 38
44 | Lincoln inbound |  | 22 | in |  | 40
45 | Lincoln appts audit |  | 1
46 | Lincoln supplements audit |  | 1
47 | Lincoln actions audit |  | 1
48 | Lincoln time audit |  | 1 |  |  | 71
49 | Pension Payroll EDS In-bound Annuity File |  | 1 | in | yes | 9
50 | Pension Payroll EDS In-bound Lump Sum File |  | 1 | in | yes | 8

## Comparision Run Schedule
Task # | Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Prep files ready? | Batch ID | Job Set # | Special Variant in PS1? | Update variant in sh1 | Notes | No. of files matched | PS1 | SH1 | Variances | Percent matched | Reasons for differences
P1 | Set up / Update SP Variants for all the feeds. |  |  | 2011-10-14 | 2011-10-14 | Mary D. Larissa Sharon | Complete |  |  |  | Yes - dates in variants will be changed 11/7.
P2 | Execute ZM Payroll simulation in PS1 |  |  | 2011-10-17 | 2011-10-17 | Gregg | Complete
P3 | Run HIRD report in PS1- do not send, retain file for comparison |  |  | 2011-10-17 | 2011-10-17 | SD | Complete |  | ZZHRBENBTC01 |  | Y- needs to be updated |  | So we have a comparison
P4 | Run ZPY_PENS_COMPENSATION - retain for comparison, Run in TEST mode |  |  | 2011-10-17 | 2011-10-17 |  | Complete
P5 | SF3 - After 10/4 snapshot applied and before support packs implemented, run ZM simulation for 10/2011 - use Gregg's rem stmt variant |  |  |  |  | Gregg | Complete | [5 empty] | Aliases in sf3?
P6 | SF3 - After support packs implemented, run ZM simulation for 10/2010 - use Greggs rem stmt variant |  |  | 2011-10-20 | 2011-10-20 | Gregg
P7 | Compare BEFORE and AFTER results of 10/2011 ZM, compare to the PS1 copy of well. |  |  | 2011-10-20 | 2011-10-20 | Gregg | [6 empty] | SF3 before v. after were identical. Each with 2 variances from PS1 due to IT0210 changes post simulation prior to copy.
P8 | SF3 - Execute Business Owner validation steps |  |  |  |  | HR Payroll Team
SIT Environment Ready - Prep for testing
1 | Verify Feed Registry Archive Control Tables are correct for the environment | SM30 | n/a | 2011-11-07 | 2011-11-07 | SD |  | n/a |  |  |  |  | Part of the action log. | n/a | n/a | n/a | n/a | n/a
2 | Re-configure EDI Test Environment to accept files from SH1 |  | n/a | 2011-11-07 | 2011-11-07 | Ron, Larisaa will remind him |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
3 | Confirm w/ R3 that Lincoln configuration for EDI is active |  | n/a | 2011-11-07 | 2011-11-07 | Ron Parker |  | n/a |  |  |  |  | Per Eric Ngo - The logical system is RC2CLNT400.(Ron should verify) | n/a | n/a | n/a | n/a | n/a
4 | Execute ZM Payroll simulation in sh1 |  |  | 2011-11-07 | 2011-11-07 | Gregg M. | Not done - is ok not to do | Yes |  |  |  |  | Compare to PS1 run. Use single line rem-statement. Log and report tie out. Don't need to wait for steps 1,,3 | 1
5 | Test ZOMCHST and IT0554 |  |  | 2011-11-07 | 2011-11-07 | Cindy | [6 empty] | Test for 2011 only-Hrly Student project will move changes to SH1during SP SIT = should not need this step for 2011.
6 | Validate EL web connections functional |  |  | 2011-11-07 | 2011-11-07 | Emily
7 | Validate APR web connections functional. |  |  | 2011-11-07 | 2011-11-07 | Jack
8 | Load ASR files uploaded from the archive server to the proper server for each environment so that the ASR Faculty spreadsheet works correctly. |  |  | 2011-11-07 | 2011-11-07 | Emily
9 | DW extract of HR/Pay data | Multiple | n/a | 2011-11-08 | 2011-11-08 | Elena |  | n/a |  |  |  |  | Payrolls and feeds may be running | 8
10 | Assign batch ids to testers - see sheet Batch IDs and aliases |  |  | 2011-11-07 | 2011-11-07 | George - reqyested by Mary
11 | Validate Laurie19 aliases established |  |  | 2011-11-07 | 2011-11-07 | Mary & Gregg
Weekly and Pension Payrolls
12 | Set up job for Job Set 1 - update variants with correct days. | Multiple |  | 2011-11-07 | 2011-11-07 | Sharon D |  |  | ZZHRBENBTC01
13 | Outbound Run FSA Census outbound interface using Ultracompare compare file to Sunday production run (10/16). | ZPYI0170_FSA_CENSUS_DATA | py/fsa_census | 2011-11-07 | 2011-11-08 | Desiree R. |  | -- | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution | 1
14 | Outbound Run FSA Enroll outbound interface (looks at the control record) using Ultracompare compare file to Sunday production run (10/16). | ZPYI0170_FSA_ENROLLMENT_DATA | py/fsa_enroll | 2011-11-07 | 2011-11-08 | Desiree R. |  | -- | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution | 1
15 | Outbound LL non-exempt leave accruals (this is a daily interface) using ultracompare compare files to Wed production runs (10/19) | Scheduled job ZHR_LL_ACCRUALS_OUT Check for errors on filezilla. | py/ll_leave | 2011-11-07 | 2011-11-07 | Alan |  | -- | ZZHRLLFEED01 | 1 | SP |  | This was moved up from Job Set 3 - needs to run before ZW payroll, | 1
16 | Weekly Payroll Processing (42/2011) | Script: Non-Exempt Payroll Test for Support Pack Update 2008.doc |  | 2011-11-07 | 2011-11-07 | MD |  | n/a |  |  |  |  | see comparisons results in step 22 below | - | - | - | - | -
17 | Pension Payroll - Lump Sum Run (10/31/2011) (includes loading PS1 copy of Pension Lump Sum file) |  |  | 2011-11-07 | 2011-11-07 | GM |  | Yes |  |  |  |  | Where do files come from? encrypted file dumps decrypted file processes correctly | 1
18 | Pension Payroll - Annuity Run (11/2011) (includes loading PS1 copy of Pension Annuity file) |  |  | 2011-11-07 | 2011-11-07 | GM |  | Yes |  |  |  |  | Where do files come from? see comparisons results in step 23 below | - | - | - | - | -
[14 empty] | n/a | n/a | n/a | n/a | n/a
19 | Set up job for Job Set 2 - update variants with correct days. | Run 11/7, do not need payroll results. |  | 2011-11-07 | 2011-11-07 | Sharon D | [6 empty] | Run 11/11, do not need payroll results.
20 | Outbound Run HR Fidelity outbound interface; using ultracompare compare file to Sunday production run (10/16). | zhr_fidelity | hr/fid_hr | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SPFID WKLY PS1 |  | can run w/ DW extracts, Orig run 3/14; chgs made 10/19 | 1
21 | Outbound Benefits outbound: BCBS using ultracompare compare file to Sunday production run (10/16). Run for dates 10/16 - 100 days thru 10/16 + 45. In IDOC Cleanup allow retro 10 days-variant all set. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/bcbs | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP BC OED/ SP BCBS PRD OE |  | can run w/ DW extracts; comparison will be made to the production run (EDI)
22 | Outbound Benefits outbound: Delta using ultracompare compare file to Sunday production run (10/16). Run for dates 10/16 - 100 days thru 10/16 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/delta | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP DELTA OE for both |  | can run w/ DW extracts; comparisons were made to production Differences were address changes, terminations, Campus Police (didn’t exclude them in SH1 run)
| Outbound Benefits outbound: Tufts using ultracompare compare file to Sunday production run (10/16). Run for dates 10/16 - 100 days thru 10/16 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/tufts | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP TUFTS OE for both |  | can run w/ DW extracts; comparison will be made to the production run (EDI) | 1
23 | Outbound Benefits outbound: Vision using ultracompare compare file to Sunday production run (10/16). Run for dates 10/16 - 100 days thru 10/16 + 45. There is currently no retro limit in IDOC Cleanup. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP VISION OE for both |  | can run w/ DW extracts comparison will be made to the production run (EDI) | 1
24 | Outbound Run Express Scripts outbound; using ultracompare compare file to Sunday production run (10/16). | ZHR_ESI_FEED | hr/esi | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP FULLFILE OE |  | can run w/ DW extracts | 1
25 | Outbound Run Crosby Outbound terminations; using ultracompare compare files to Sunday production runs (10/16). *** follow all the way through to vendor *** | ZHRCSB02 | hr/crosby; | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SPZHRCSB02_RPT |  | can run w/ DW extracts | 1
26 | Outbound Run Crosby Outbound new entrants for the prior month (Sept); using ultracompare compare files to Sunday production runs (9/1). | ZHRCSB02 | hr/crosby_new | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP_ZHRCSB02_NH |  | can run w/ DW extracts | 1
27 | Outbound Run Crosby Outbound dependents aging out; based on file created 10/1 for Nov ageoffs using ultracompare compare files to production runs (11/1). | ZHRCSB03 | hr/crosby_dep | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP_ZHRCSB03DEP |  | can run w/ DW extracts | 1
28 | Outbound Run Metpay Census outbound interface; using ultracompare compare file to Sunday production run (10/16). | ZPY_METPAY_CENSUS_DATA | hr/metpcensus | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | ZZHRBENBTC01 | 2 | SP PRODUCTION |  | can run w/ DW extracts | 1 |  |  |  |  | For retirees the program randomly selects which of the two pernrs the retiree has, resulting in sometimes the CUR record is picked, sometimes the RDBP. The variance is due to which reocrd was selected - so address might be the same but spelled differently between two records.
29 | Outbound Run Health Insurance Resposibility Disclosure (HIRD); outbound to Crosby | ZHR_OUTBOUND_HIRD_DATA | hr/hird | 2011-11-07 | 2011-11-08 | Desiree Emily |  | -- | Run Manually | 2 | No |  | Compare to file generated in PS1 on 10/17 (step 4). | 1 |  |  |  |  | One record with a character difference. Not Support pack related, due to special character conversion and whicj id and machine the extract was run.
30 | Payroll Results Comparison (ZW) |  |  | 2011-11-08 | 2011-11-10 | Gregg M. | [7 empty] | n/a
31 | Payroll Results Comparison (ZP) |  |  | 2011-11-08 | 2011-11-10 | Gregg M. | [7 empty] | n/a
31a | Payroll Results Comparison (ZP)Lump Sum |  |  | 2011-11-08 | 2011-11-10 | Gregg M. | [7 empty] | n/a
32 | FI POSTING COMPARISON (ZP) |  |  | 2011-11-08 | 2011-11-10 | Gregg M. | [6 empty] | accounts | n/a
32a | FI POSTING COMPARISON (ZP)Lump Sum |  |  | 2011-11-08 | 2011-11-10 | Gregg M. | [7 empty] | n/a
33 | EDACCA TABLE COMPARISON |  |  | 2011-11-10 | 2011-11-10 | Gregg M. | [7 empty] | n/a
34 | FI POSTING COMPARISON (ZW) |  |  | 2011-11-10 | 2011-11-10 | Gregg M. | [6 empty] | accounts | n/a
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| (After Payroll Execution) Weekly Outbound Interfaces | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
35 | Set up job for Job Set 3 - update variants with correct days. |  |  | 2011-11-07 | 2011-11-07 | Mary |  |  | ZZPYBATCH001
36 | Set up job for Job Set L3 - update variants with correct days. |  |  | 2011-11-07 | 2011-11-07 | Alan |  |  | ZZHRLLFEED01
37 | Outbound Timesheet file to MITSIS (combined w/ Grad Student Gross Pay) using ultracompare compare files to Wed production runs (10/19) | ZPYIO_MITSIS_TIM | py/mitsis_tim | 2011-11-07 | 2011-11-07 | Alan |  | Yes |  | 3 | ??? |  |  | 1
|  | Dates From Wednesday to Wednesday |  | 2011-11-07 | 2011-11-07 | Alan |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
38 | Outbound LL salary distribution weekly gross pay using ultracompare compare files to Wed production runs (10/19) File to be sent to Lincoln. | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2011-11-07 | 2011-11-07 | Alan |  | -- | ZZHRLLFEED01 | L3 | SP1ZW |  | Check for errors on filezilla | 1
[8 empty] | n/a | ZZHRLLFEED01 |  | SP2ZW |  |  | n/a | n/a | n/a | n/a | n/a
39 | Outbound Leave balance accruals for Facilities Service Staff (this is a daily interface) - should thi sbe run for Wed - after payroll? | ZPTKRONOS_ACCRUL_OUT | py/facil_leav | 2011-11-07 | 2011-11-07 | Run by Gregg, compares by Jack |  | -- | ZZPYBATCH001 | 3 | y |  | internal test performed; additionally subsequent test performed with facilities | 1
40 | Outbound FSA (Crosby). Compare results to production file using ultracompare compare files to Wed production runs (10/19) | ZPYIO_FSA_CONTRIB /ZPY0170_FSA_CONTRIB | py/fsa_dep | 2011-11-07 | 2011-11-07 | Run by Gregg, compares by Desiree |  | -- | ZZPYBATCH001 | 3 | SP_WEEKLY |  |  | 1
41 | Outbound Fidelity pension file (weekly 401 pension contributions) Use ZW Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS using ultracompare compare files to Wed production runs (10/19) | Scheduled Job ZPYIO_FID_CNTRIB/ ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2011-11-07 | 2011-11-07 | Gregg |  | -- | ZZPYBATCH001 | 3 | SP_ZWAUTOMATI |  |  | 1
42 | Outbound LL Bank details (this is a daily extract) | zpy_ll_bank_detail | py/ll_bank | 2011-11-07 | 2011-11-07 | Run by Gregg, compares by Alan |  | -- | ZZPYBATCH001 | L3 | No-run adhoc |  | Select a PS1 file which contains some changes and report test in sh1 | 1
43 | Inbound Student Bio Feed (MITSIS) (10/18-10/24) | ZMITSIS | hr/mitsis_dem | 2011-11-08 | 2011-11-08 | Alan M. |  | Yes | ZZHRMITSIS01 | IB1These 3 must run per day, one after the other | No |  | both old and new complete | 5
44 | Inbound Grad Appointment Inbound (this is a daily feed) (10/18-10/24) | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2011-11-08 | 2011-11-08 | Alan M. |  | Yes | ZZHRGRADAPT01 |  | No |  | both old and new complete | 7
45 | Inbound LL daily feed (10/18-10/24) run 5 feeds (one week) |  |  | 2011-11-08 | 2011-11-08 | Alan M. |  | Yes | ZZHRLLFEED01 |  | No |  | Check for errors on filezilla | 22
[14 empty] | n/a | n/a | n/a | n/a | n/a
| Additional Payroll Interface Activities (before planned monthly run) | Need to coordinate with Alan's run's |  |  |  |  | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
46 | Inbound Weekly Fidelity Percent Inbound; use Friday file (10/21); compare reports to prod reports; spot-check the loaded data | ZPYII_FID_PCT | py/fid_pct | 2011-11-08 | 2011-11-08 | Gregg |  | Yes | ZZPYBATCH001 | IB2 |  |  | Trigger through drop box in Linux version. | 1
47 | Inbound Weekly Tech Cash Inbound; use Friday file (10/21).; compare reports to prod reports; spot-check the loaded data | ZPYII_DED | py/tech_cash | 2011-11-08 | 2011-11-08 | Gregg |  | Yes | ZZPYBATCH001 | IB2 |  |  |  | 1
48 | Inbound Metpay Home/Auto inbound; compare reports to prod reports; spot-check the loaded data (10/20) | ZPY_METPAY_IN | py/metp-ded | 2011-11-08 | 2011-11-08 | Run by Gregg, compares by Jack |  | Yes | ZZPYBATCH001 | IB2 |  |  |  | 1
| Monthly Payroll Processing - ZM | Script: Exempt Payroll Test for Support Pack Update 2008.doc |  | 2011-11-08 | 2011-11-08 | MD |  | n/a |  |  |  |  | see results below | n/a | n/a | n/a | n/a | n/a
49 | Payroll Results Comparison (ZM) |  |  | 2011-11-10 | 2011-11-10 | Gregg M. |  | - | [5 empty] | n/a
50 | EDACCA TABLE COMPARISON |  |  | 2011-11-10 | 2011-11-10 | Gregg M. |  | - |  |  |  |  | see detail notes tab | n/a
51 | FI POSTING COMPARISON |  |  | 2011-11-10 | 2011-11-10 | Gregg M. |  | - |  |  |  |  | accounts compared | n/a
52 | After ZM 3-Party Processing - Test garnishments to A/P, have Ken execute his piece. |  |  | 2011-11-09 | 2011-11-09 | Gregg M, Ken LeVie |  | n/a |  |  |  |  | ZM 3PR pp 03.2010 new vs. old are a match - 33 vendor payment line items in each = 100% | n/a
| (After Monthly Payroll Payroll Execution) Outbound Interfaces (Comparisons to production files) | [5 empty] | - | [5 empty] | Set up jobs Friday. | n/a | n/a | n/a | n/a | n/a
53 | Set up job for Job Set 4 - update variants with correct days. |  |  | 2011-11-08 | 2011-11-08 | Mary |  |  | ZZPYBATCH001
54 | Set up job for Job Set L4 - update variants with correct days. |  |  | 2011-11-08 | 2011-11-08 | Alan |  |  | ZZHRLLFEED01
55 | Outbound Fidelity contributions outbound - monthly Use ZM Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS | ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2011-11-08 | 2011-11-08 | Gregg |  | -- | ZZPYBATCH001 | 4 | SP_ZM_AUTOMATI |  |  | 1
|  | Dates TBD |  | 2011-11-08 | 2011-11-08 |  | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
| Outbound EDS contributions outbound - monthly Include both weekly and monthly | ZPYIO_EDS_CNTRIB/ZPYI004_0_TOW_CONTRIB | py/eds_cntrib | 2011-11-10 | 2011-11-10 | Gregg |  | -- | ZZPYBATCH001 | 4 | SP_ZM_ZW |  | Obsolete as of 9/2011 | 1
|  | Check for errors on filezilla |  | 2011-11-10 | 2011-11-10 | LK/SD | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
56 | Outbound FSA contributions outbound - monthly Use monthly variant, change start date/time to before payroll run, check test, enter handliing rule 001 | ZPYIO_FSA_CONTRIB /ZPY0170_FSA_CONTRIB | py/fsa_dep | 2011-11-08 | 2011-11-08 | Mary |  | -- | ZZPYBATCH001 | 4 | SP_Monthly |  |  | 1
57 | Outbound Credit Union contributions Run for dates from PS1's last run email thru end of monthly payrun | ZPYIO_CU_UNION / ZHRPY_CREDIT_UNION | py/cu | 2011-11-08 | 2011-11-08 | Gregg |  | -- | ZZPYBATCH001 | 4 | SP_VAR_ZM_ZW |  |  | 1
58 | Outbound John Hancock (long term care) contributions | ZPYIO_HANCOCK /ZPYI006_0_JHK_LTCPRE | py/hancock | 2011-11-08 | 2011-11-08 | Mary |  | -- | ZZPYBATCH001 | 4 | SP_ZM_ZW |  |  | 1
59 | Outbound TIAA-CREF (457B) contributions (10/27File) | ZPYIO_TIAA_CREF/ZPY_457B_CONTRIB_OUT | py/tiaa_cref | 2011-11-08 | 2011-11-08 | Mary |  | -- | ZZPYBATCH001 | 4 | SP__ZMAUTOMATI |  |  | 1
| Outbound EDS HR Outbound 10/17 File Run from start date/time as ran in production from 10/28 | ZHR_FIDELITY | hr/eds_hr | 2011-11-10 | 2011-11-10 | Mary |  | -- | ZZPYBATCH001 | 4 | SP_EDS AUTOMAT |  | Obsolete as of 9/2011 | 1
60 | Outbound LL Salary distribution monthly gross pay | ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2011-11-08 | 2011-11-08 | Alan |  | -- | ZZHRLLFEED01 | L4 | SP-ZM |  |  | 1
61 | Outbound Pension outbound interface - Employment file | ZPY_PENSION_EMPL / ZPY_PENSION_EMPLOYMENT | py/pen_empl | 2011-11-08 | 2011-11-08 |  |  |  | ZZPYBATCH001 | 4 | no |  | Run Sept and Oct for comparisons for reasonability?
62 | Outbound Pension outbound interface -Personal file | ZPY_PENSION_PERS / ZPY_PENSION_PERSONAL | py/pen_pers | 2011-11-08 | 2011-11-08 |  |  |  | ZZPYBATCH001 | 4 | no |  | Run Sept and Oct for comparisons for reasonability?
63 | Outbound Pension outbound interface -Compensation file | ZPY_PENSION_COMP / ZPY_PENSION_COMPENSATION | py/pen_comp | 2011-11-08 | 2011-11-08 |  |  |  | ZZPYBATCH001 | 4 | no |  | Compare to PS1 extract run on 10/17 in step ???
64 | Outbound Pension outbound interface -Pay & Hours file | ZPY_PENSION_CONT / ZPY_PENSION_PAY_HOURS | py/pen_cont | 2011-11-08 | 2011-11-08 |  |  |  | ZZPYBATCH001 | 4 | no |  | Balance totals with recon report of 9C93
| Inbound Interface Comparisons | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
65 | Load LL Time Files (10/24/2010 upto 10 files) - weekly IDOC file - need to copy to test system's sapin directory This is a separate set of files than th lincoln feed in step 40. | ZHRALE | n/a | 2011-11-09 | 2011-11-09 | Alan/KM/EN |  | Yes |  | IB3 |  |  | TBD (may be that Eric will review) | 13
66 | Run LL time audit (10/24/2010) - weekly | ZPYII_LL_AUDT_TM | py/ll_audt_tm | 2011-11-09 | 2011-11-09 | Eric |  | Yes |  |  |  |  | TBD (may be that LL will review (ccassidy))
67 | Run LL HR/Payroll audit files (10/24/2010) - weekly | ZHRALF02 | py/ll_audt_py | 2011-11-09 | 2011-11-09 | Eric |  | -- |  |  |  |  | Validated by Collen in the past | n/a | n/a | n/a | n/a | n/a
66 | Inbound Run Kronos Feed and compare IT2001/2002 records with change date of (date file was executed, changed by whomever ran the file) or time eval results. (10/25/2010) - weekly | ZHR_INBOUND_TIME | py/facil_time | 2011-11-09 | 2011-11-09 | Run by Gregg, validation by Jack |  | Yes | ZZPYBATCH01 | IB4 |  |  |  | 1
67 | Inbound Parking Standard Internal deductions - monthly copy to test system's sapin directory (Use 10/25 file if available) | ZPYII_DED | py/parking | 2011-11-09 | 2011-11-09 | Run by Gregg, validation by Mary |  | Yes | ZZPYBATCH01 | IB4 |  |  | loaded encrypted through drop box | 1
68 | Inbound Tpass Standard Internal deductions - monthly; (use 11/16 file) (pre Nov payrun) 4 files, imputed income file is blank. Process 1 file - post tax TPAss. Will files be received by 11/16 - should we process Oct?? | ZPYII_DED | py/t_pass | 2011-11-09 | 2011-11-09 | Run by Gregg, validation by Mary |  | Yes | ZZPYBATCH01 | IB4 |  |  | loaded locally | 1
69 | Inbound Long Term Care (John Hancock) - monthly; (use 11/16 file) (pre Nov payrun) Will files be received by 11/16 - should we process Oct?? | zpyii _hancock | py/hancock | 2011-11-09 | 2011-11-09 | Run by Gregg, validation by Mary |  | Yes | ZZPYBATCH01 | IB4 |  |  |  | 1
70 | State Quarterly - outbound report - quarterly; Run Q3 2011 | pu19 sui wage reporting | ?- what should we do with this and next step - ask leslie? | 2011-11-10 | 2011-11-10 | SD/GM |  | -- | [5 empty] | 1
| Outbound MA Health - outbound report - quarterly; Reports 3rd qtr YTD MA /701, excludes RDBP, EL and includes only EmpStat = 3. Use mass health variant, chg to 1st qtr for current yr Run Q3 2011 | se38 ZPY_MASS_HEALTH | py/mass_hlth. | 2011-11-14 | 2011-11-15 | SD/GM |  | -- |  |  |  |  | Obolete for 2011 | 1
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
71 | Run weekly payroll - limited (43/2011). Mary Note: This run will be for only LL run. Test cases after this run will be for week 44/2011. |  |  | 2011-11-10 | 2011-11-10 | Gregg M. |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
72 | Run LL gross pay file for weekly outbound for payweek 43 Compare the output to pay week 43. File to be sent to Lincoln for comparison | Scheduled job ZPYIO_ LL_SAL_DST | py/ll_sal_dst | 2011-11-10 | 2011-11-10 | Alan |  | n/a | ZZHRLLFEED01 | L5 |  |  | Execute only if testing feed to LL. Campus compares and send to LL.
73 | Update SH1 will any PS1 updates conducted after 10/17: * eW-2 parameters *eW-2 false positives *Update Payroll control records for earliest retro date |  |  | 2011-11-10 | 2011-11-10 | Mary , Gregg,
| Open up testing for SIT test cases. | [12 empty] | n/a | n/a | n/a | n/a | n/a
74 | Validate access to sh1 |  |  | 2011-11-07 | 2011-11-07 | All testers
Tests to conduct WHILE Payroll comparisons are executing (no dates prior to Nov 1, 2011)
75 | E-Learning |  |  | 2011-11-07 | 2011-11-18 | Jane/Emily/et al
76 | Exempt (No retro) |  |  | 2011-11-07 | 2011-11-10 | Ana
77 | Non-Exempt (No retro) |  |  | 2011-11-07 | 2011-11-10 | Mae
78 | Students (No retro) |  |  | 2011-11-07 | 2011-11-10 | Mae
79 | ASR |  |  | 2011-11-07 | 2011-11-10 | Judy/Lisa/Adrienne/Emily
| Tests to conduct AFTER Payroll comparisons completed - can contain dates prior to Nov 1, 2011 |  |  | 2011-11-14 | 2011-11-23
80 | APR View a transaction |  |  |  |  | Scott/Amanda
81 | ESS - non Benefits |  |  |  |  | Leslie
82 | SAP Web - eDACCA, eSDS, time approvals |  |  |  |  | Leslie
83 | OM |  |  |  |  | Leslie & Cindy
84 | Exempt (Retros) |  |  | 2011-11-14 | 2011-11-14 | Ana
85 | Non-Exempt (Retros) |  |  | 2011-11-14 | 2011-11-14 | Mae
86 | Students (Retros) |  |  | 2011-11-14 | 2011-11-14 | Mae
87 | APR |  |  |  |  | Kristen/Amanda
88 | ESS-Benefits (Desiree help with Campus Police setup) |  |  |  |  | Diane/Anne/Shawn
89 | Benefits
90 | Faculty Chair |  |  |  |  | Jean D
91 | OM - org unit |  |  |  |  | Anne
92 | Pension |  |  |  |  | Diane
93 | Execute Cycle 1 Payrolls |  |  |  |  | Laurie19
94 | Miscellaneous (Gregg, support for garnishment tests) |  |  |  |  | Leslie/Scott/Tricia/Cindy/Mary/Desiree/Gregg
95 | Year End Reporting (Mary,Gregg for support) |  |  |  |  | Laurie19
96 | Validations of all above transactions to be completed by11/23/2011 |  |  |  |  | All
Legend:
Pay run execution
Section Heading
Lincoln Lab
Note on P33: robertsd: PS1 Comparison
Note on P35: robertsd: PS1 comparison
Note on P36: robertsd: PS1 Comparison

## Detail Notes
Detail Notes:
Step 4 | DW | Program ZWHPAYROLL_RESULTS_NEW; extracted for 2/22/2010; 6 files:
|  | wh-payruns.asc - 14084 | 14084
|  | wh-paydet.asc - 161194 | 161194
|  | wh-payarrs.asc - 652 | 652
|  | wh-pay_dd.asc - 2348 | 2348
|  | wh-paymnt.asc - 13443 | 13443
|  | wh-paypers.asc - 14084 | 14084
Program ZWHPAYROLL_FIN; extracted for 2/22/2010 -- 3/2/2010; 2 files:
|  | wh-pay_fi_docs.asc - 2082 | 2082
|  | wh-pay_fi_post.asc - 212717 | 212717
420604
Step 54 | PY | ZM eDACCA Comparison
ZM edacca compare of 26963 rows in each system had 6 rows with small differences on a single pernr.
Mary checked the pernr (35400) and found the differences were due from a calculation difference in tuition (RTD1) resulting after termination by feeds that were run on different days - where term date was set as interface run date (term date in new is 04/22/10 & term date in old is 04/23/10).
- gm
Since the daily rate for tuition is calculated based on the total number of days in the appt, the daily rate in the new sh1 is higher since it term’d one day earlier.
-md

## Batch IDs and aliases
Batch ID assignments | PS1 Owners | SIT Tester
ZZHRBENBTC01 | Sharon | Desiree
ZZPYBATCH001 | Laurie | Gregg
ZZHRGRDAPT01 | Scott | Alan
ZZHRMITSIS01 | Scott | Alan
ZZHRLLFEED | Tricia Sullivan-Mullen | Alan
Aliases
Laurie19 | Laurie | Mary & Gregg

## Suggestions from last Year
| Suggestions for next year (2011) | 2011 Action
1 | Hi Mary, One of the zutarchivecrtl or zhr_feed registry tables is messed up on the monthly metpay contributions. I don’t see the issue so I ran the weekly outbound one instead and ran the comparison. All 179 records matched except for the header line which has a run date imbedded. I think comparing just the weekly should be good enough for this feed, but let me know if you think otherwise. This SH3 environment was missing some of the set up needed to run the feeds that we ran a few times. I talked with Frank about getting these tables copied from either SH1 or SH2 so we don’t have to struggle to run them. I will ask the development team if that will affect their testing since their business analysts test in SF5. For our testing Zehcat was missing all hr/payroll feeds. I entered them manually. 3 Cobra feeds and the LL Bank feed were not set up to run in SH3. We can’t use the production version because they send out to different locations. This is my recommendation for next time. Sharon Sharon DiLiberto | Larissa and Sharon will validate - Step 1 in Comparison run schedule.
2 | Hi Mary, Alan’s LL leave accruals ran too late in the schedule. We should run the LL leave accruals with 10/18/2010 before running the non-exempt time eval/payroll on the next year’s list. LK has been working with Alan. I wonder if this affected the Kronos Leave Accruals too? Sharon | This step has been moved up from Job set L3 to Job set 1. For Facilities leave acccruals - should we leave as is, should we be comparing the Wed morning run?
3 | Make sure Lincoln has accesss to test system. They use Citrix and had issue in 2010 - sh3 needed to be added. | Will verify with Eric that Lincoln has access to SH1.
4 | Make sure web links, communications are established for test system - EL, APR. | Added step for EL and APR to comparison test schedule - any other?
5 | Sharon: . I will recommend that we get a copy of the zehcat, zutarchivecrtl and zhr_feed_registry from a better environment next time to reduce the problems that we incurred.
6 | Sharon: I will also recommend the Larissa be allowed in to test the EDI connection as part of the action log items. I also had to set up every vendor’s login credential in a view that can’t be exported and imported to this new environment.
7 | Emilly: we need to have the ASR files uploaded from the archive server to the proper server for each environment so that the ASR Faculty spreadsheet works correctly. This would need to be done before we can do ASR testing. We completely missed this in SH3 as we haven't used this environment yet. Is this something we could add to your list? | Added step - check with Emily if stated correctly.

## For Next Year
Suggestions for next year (2012)