## HR-Payroll
Task | Transaction tested | Tester | Backup | Complete* | Comments/Issues
Employee transactions | PA30 & PA40 |  |  |  |  | *S=Sunday & M=Monday
New hire |  | Leslie | Scott/Tricia
Termination |  | Leslie | Scott/Tricia
Supplement |  | Leslie | Scott/Tricia
Salary change |  | Leslie | Scott/Tricia
Promotion |  | Leslie | Scott/Tricia
Hourly Student transactions | ZOMCHST
Create position |  | Leslie | Scott/Tricia
Delimit position |  | Leslie | Scott/Tricia
Change hourly rate |  | Leslie | Scott/Tricia
Change end date |  | Leslie | Scott/Tricia
Grad Student transactions | PA30 & PA40
New appointment |  | Leslie | Scott/Tricia
Change appointment |  | Leslie | Scott/Tricia
Cancel appointment |  | Leslie | Scott/Tricia
Delimit appointment |  | Leslie | Scott/Tricia
APR - Appt Process Redesign | ZHRAP
Hire |  | Leslie | Scott/Tricia
Termination |  | Leslie | Scott/Tricia
Supplement |  | Leslie | Scott/Tricia
Leave |  | Leslie | Scott/Tricia
Change |  | Leslie | Scott/Tricia
ePaystub | ESS | Leslie | Scott/Tricia
eW-2 | ESS | Leslie | Scott/Tricia
direct deposit | PA30 & ESS | Leslie | Scott/Tricia
tax withholding | PA30 & ESS | Leslie | Scott/Tricia
deductions | ZPYDEDUCT | Leslie | Scott/Tricia
eSDS | SAPweb
exempt |  | Leslie | Scott/Tricia
non-exempt; reg & premium |  | Leslie | Scott/Tricia
grad student RA; stipend & tuition |  | Leslie | Scott/Tricia
eDACCA | SAPweb
Search by each criteria |  | Leslie | Scott/Tricia
Certify Q1 2010 DACCA |  | Leslie | Scott/Tricia
Approve/Distribute Time Sheets | SAPweb
Approve SC time sheets |  | Leslie | Scott/Tricia
SRS Vacation Tracker | SAPweb | Leslie | Scott/Tricia
Appt Process Redesign | ZHRAP | Leslie | Scott/Tricia
Gross to Net | Off-cycle work bench
Exempt |  | Leslie | Scott/Tricia
Non-exempt |  | Leslie | Scott/Tricia
Additional Tax amounts-federal |  | Leslie | Scott/Tricia
Additional Tax amounts -state |  | Leslie | Scott/Tricia
401K max & catchup in Dec |  | Leslie | Scott/Tricia
CDU - exempt | ZPYCDU2
MAP |  | Leslie | Scott/Tricia
RA tuition |  | Leslie | Scott/Tricia
vacation credits |  | Leslie | Scott/Tricia
off campus |  | Leslie | Scott/Tricia
reduced EB |  | Leslie | Scott/Tricia
Tax Reporter | PU19
Print W2 form |  | Leslie | Scott/Tricia
Print 1099R form |  | Leslie | Scott/Tricia
Print W2C form |  | Leslie | Scott/Tricia
Reports
Missing IT9004 report | ZPYRMISSING9004 | Leslie | Scott/Tricia
Vaca/Sick payout for ZW | S_AHR_61015611 | Leslie | Scott/Tricia
Sick cost out report | ZPYSCOR | Leslie | Scott/Tricia
Appointment error messages | ZPYR_APPT_MESSAGES | Leslie | Scott/Tricia
Feeds
Lincoln Daily feed - manual | ZHRALE | Tricia |  |  | see tab Lincoln feed for details
Contacts/Location
Leslie - on site NE49 3-7715
Tricia - home
Scott - home

## HR
Type | Transaction | Assigned to | Backup
SAPGUI | Benefits Enrollment | Diane | Riley
ESS | Benefits Enrollment | Diane
ESS Personal Info | Home address | Diane
| Ethnicity | Diane
| Work Address | Diane
| Emergency Contact | Diane
| MITAlert (check links only) | Diane
| Eduction History | Diane
Learning Center | Register for training | Diane | Riley
| Cancel registration | Diane
Contacts/Location
Diane - at home 781-325-6591
Riley - at home 781-799-2945 (cell)
Kathleen - at home ????

## EL
Type | Transaction | Assigned to | Backup
Learner | Access the portal, both by certificate and username/password login | Jane White
| Register for a course (verify auto email) | Jane White
| Cancel a course (verify auto email) | Jane White
| Prebook a course (verify auto email) | Jane White
Registrar | Create a course type (in ARCHIVE category) | Jane White
| Create a course (in ARCHIVE category) | Jane White
| Book someone/book list into a course (in ARCHIVE category) | Jane White
| Cancel someone from a course (in ARCHIVE category) | Jane White
Learner | Validate elearning course progress carried forward | Jane White
| Relaunch elearning course to see that it starts where I left off | Jane White
TNI Admin | Unassign myself from a learning group & validate that requirements disappear | Jane White
| Reassign myself to a training group and validate that requirements reappear | Jane White
Contacts/Location
Jane - at home 978-475-5843

## Lincoln feed
Lincoln File Steps
Sunday December 4, 2011
Lincoln Files
1. Campus Service Center shuts down Lincoln job on Friday, December 2, any time before 5pm
2. Lincoln files are generated on a regular schedule, at 6pm, but are not loaded because the job is not active.
3. Wai-Ming shuts down SAP Dropbox on Friday, December 2 at 6pm
4. Wai-Ming manually copies Lincoln files from the SAP Dropbox to SAP sapin directory on Friday - Saturday, and sends an e-mail message with sequence numbers of the files.
5. Tricia will load the files on Sunday, as part of Sunday validation. Files should be available in SAP sapin directory early Sunday morning.
a. Cannot be loaded until 3 pm (or whenever validation go ahead is given from IS&T) and Tricia’s user id has been unlocked
6. If successful, Tricia will email list that file was successful, and will start up Lincoln job (in preparation to Monday time files).
7. If not successful, Tricia will email list that file was unsuccessful with details of the errors
a. Larissa is IS&T point person for issues
Note:
Larissa talked with Eric, and he does not anticipate a big volume of changes to come on Friday; he also said that he will ask Lincoln Workforce center “to keep the volume light”, i.e. key only essential data on Friday. So hopefully we’ll have only one file on Friday, with not much data; just to make the validation easier/quicker
Email List
1. Larissa Kushkuley
2. Eric Ngo
3. Wai-ming Li
4. Leslie Wright
5. Tricia Sullivan-Mullen
6. Scott Ball
7. Frank Quern
8. Mary Donovan

## copy of 2009 validations
HR – Payroll Transactions to Validate
SAPGui Tests | PA30, PA40, ZPYDEDUCT, PT60, ZPYCDU, ZPYR_APPT_MESSAGES, ZPY_MITSIS_LOG, ZPY_PAY_VAL_RPT, and PT50 | Leslie Wright
SAPWeb Tests | eDACCA, eSDS, SRS vacation tracker in SAPweb and tax withholding and direct deposit via ESS. | Leslie Wright
HR Transactions to Validate
| Benefits enrollments ESS | Riley Hart, Kathleen Flynn
| Benefits enrollments GUI | Riley Hart / Kathleen Flynn
| All HR ESS functionality (Address, 3Es etc) | Riley Hart / Kathleen Flynn