Core Team Meeting

10/9/2012

Status:

SF2 DB/OS Upgrades complete

SH2 Refresh complete

SH1/SH2 DB/OS Upgrades complete

SH2 DB/OS Impact Testing – in process

SF3 Refresh complete

SAP YE Support Pack Release scheduled for 10/11 on track

PS1 DB/OS Upgrade Scheduled 10/20-21

Updates:

DB/OS Testing (SH2/SH1/SF2) – look to complete by 10/17

Unit Test Planning (Google doc) – look to complete by 10/24

SIT Test Planning – look to complete by 10/31

Ancillary Systems

- SM

- ADS

  - J01 – NW 7.3 SPS8 - SF8 Testing (in process)

  - J11 – SF2, SF3, SH1, SH2, SE1, SH3, SF6

  - J31 – PS1 (db upgrade on 10/20)

- Portal

  - J02 – removed from SF8, will be used for SH2

  - JP2 – SF3 (in process – includes NW 7.3 sps7 -> sps8 & db)

  - JP3 – SF2

  - JP4 – SH1 (production support)

  - JP5 – SH3 (prototyping environment)

  - JP6 – PS1 (db only upgrade 10/20; NW with production cut-over)

10/20-21 Outage:

Timeline (wiki)

Batch job rescheduling

Notifications

- SAPbiz

- 3-down

- Key Business Users

- Gateway Page (scheduled maintenance)

- GUI logon

Admin Systems Validations

- ABAP developer contact list

- BSA validation (who & what) – by 10/17

Other:

GUIxt testing in SF3 week of 10/22?

Issues (RT)

AP 1099 Merge Program

TM Vacation Tracker authorization change (# character elimination)

Basis GUI user exit

FIN Production Flag

Review timeline … (wiki)

Next Steps:

Continue Test Preparation

Continue System Preparation

Obtain YE Support Pack

Prepare 10/20-21 Cut-over Plan