## Slide 1: Trivial Pursuits
G
What's the world's southernmost national capital?
E
Which witch is flattened by a house in The Wizard of Oz?
H
What explorer was nicknamed Iberia's Pilot?
AL
What phenomenon appeared the day Mark Twain was born and the day he died?
SN
What do dates grow on?
SL
What are the Golden Nugget, Horseshoe, Lucky Stride and Jackpot?

## Slide 2: And the answers are …
G
What's the world's southernmost national capital?
Wellington, New Zealand
E
Which witch is flattened by a house in The Wizard of Oz?
The Wicked Witch of the East
H
What explorer was nicknamed Iberia's Pilot?
Christopher Columbus
AL
What phenomenon appeared the day Mark Twain was born and the day he died?
Halley's comet
SN
What do dates grow on?
Palm trees
SL
What are the Golden Nugget, Horseshoe, Lucky Stride and Jackpot?
Las Vegas casinos

## Slide 3
October 24, 2012
2012 Year End Support Pack Project
SAPbiz
Update

## Slide 4: Agenda
Quick Review of the Project Scope
Update on Project Risks
High Level Time Line (& where are we now?)
Testing
Important Dates Revisited
Next Steps

## Slide 5: Project Scope Update
What are we updating?
  Let’s jump to the project wiki
    https://2012 SP

## Slide 6: Project Risks
Identified Risks
  QA Resource Turnover
    Unfamiliarity with QC
    Unfamiliarity with QTP Scripts (Automated test cases) – getting up to speed
  Two Phase Testing Approach
    Requires tight coordination and resource availability between the Business & IS&T
    But … we have two years experience with this approach
  Resource availability for the project (both Business & IS&T)
  Delay of implementation of pre-Support Pack Projects
    OE (on schedule; transports went in last week; pilot this week)
  Pre-Support Pack Oracle & Operating System Upgrades

## Slide 7: Other Non-SP Projects
Other non-support pack project work (during SP project timeline)
  APR 3.0/HR Transactions (SE1 development environment)
  Facilities Discovery (SE1)
    Other activities
    AP YE Tax Report Changes (w/ SPs)
    SAP logon user exit enhancement

## Slide 8: High Level Timeline
Now -> 10/31/2012 - Plan, convert/create/update test scripts in QC, move pending support & project work into production
10/11/2012 – SAP release of year end base level support pack
10/20-21/2012 – Production outage; upgrade to DB & OS
10/22/2012 - End of day production snapshot to be used to refresh test environments
10/22/2012 - Development Freeze begins
11/01/2012 - Last date to implement support & enhancement changes until freeze ends on 12/5/2012
10/26/2012 - 11/2/2012 Unit test
11/5/2012 - 11/27/2012 System Integration Test
12/1/2012 - 12/2/2012 Go-live weekend!
12/5/2012 - Development Freeze ends

## Slide 9: Testing Timeline Details
  Let’s look at the Plans and Schedule on the wiki …
  2012 SP Project Wiki

## Slide 10: Testing Recap
  Two Phase Approach
    Unit Test - performed in SF2 by IS&T
    System Integration – performed in SH2 by IS&T and Business Testers as a combined pool
  Planning
    Quality Center (Central test case repository & tracking tool)
    Work with IS&T Testing Coordinators & QA
  Automated Testing
    New Automating testing tool introduced last year
    Approximately 35% of last year’s test cases have been automated

## Slide 11: Testing Recap (continued)
  So what am I testing?
  - let’s take a look on the wiki …
  2012+Year+End+SAP+Support+Pack+Project
  - let’s take a quick look at QC …
  https://qualitycenter.mit.edu:8443/qcbin/start_a.htm

## Slide 12: Testing Recap (continued)
  If I find an issue during testing how do I report it?
  - let’s go back to the wiki …
  2012+Year+End+SAP+Support+Pack+Project

## Slide 13: Transport Management
  So what if we have an issue in production during the freeze period that needs immediate attention?
  Let’s jump back to the wiki …
  https://wikis.mit.edu/confluence/display/sapscripts/2012+Year+End+SAP+Support+Pack+Project

## Slide 14: Where are we now? Project Landscape

## Slide 15: Where are we now? (continued)
  Any issues so far?
  Yup!
  - let’s go to RT …
  Request Tracker

## Slide 16: Recap of Important Dates
Now -> 10/31/2012 - Plan, convert/create/update test scripts in QC, move pending support & project work into production
10/11/2012 – SAP release of year end base level support pack
10/20-21/2012 – Production outage; upgrade to DB & OS
10/22/2012 - End of day production snapshot to be used to refresh test environments
10/22/2012 - Development Freeze begins
11/01/2012 - Last date to implement support & enhancement changes until freeze ends on 12/5/2012
10/26/2012 - 11/2/2012 Unit test
11/5/2012 - 11/27/2012 System Integration Test
12/1/2012 - 12/2/2012 Go-live weekend!
12/5/2012 - Development Freeze ends

## Slide 17: Next Steps
  Review your test cases (Business)
  Finish testing current development work in progress (Business & IS&T)
  Completion of application of support packs to the Development and Test Systems (IS&T)
  Test Execution (Business & IS&T)
  Prepare for go-live (All)

## Slide 18: Not-soTrivial Pursuits
G
What environment will we be testing in?
E
What is QC?
H
When will the last transports be moved to production before the freeze?
AL
Where can I find project related information?
SN
What are we updating?
SL
When is go-live weekend?

## Slide 19: Questions?
Any additional questions? Please contact:
Frank Quern Bart Dahlstrom
X2-4512 x3-9605
fquern@mit.edu bartd@mit.edu
OR
Your SAP testing team coordinator:
HR-Payroll (HRP): Mary Donovan
Financial-Logistics-EHS (FLE): Kristen Hann

## Slide 20: the wicked witch of the west
Happy Halloween!