## Slide 1: Trivial Pursuits
G
Where's the Sears Tower?
E
What city was the setting for Gunsmoke?
H
What did the B&O Railroad's initials stand for?
AL
Who was Lancelot's son in Arthurian legend?
SN
How many dimensions does a solid have?
SL
What's the site of the annual All-American Soap Box Derby?

## Slide 2: And the answers are …
G
Where's the Sears Tower?
Chicago
E
What city was the setting for Gunsmoke?
Dodge City, Kansas
H
What did the B&O Railroad's initials stand for?
Baltimore and Ohio
AL
Who was Lancelot's son in Arthurian legend?
Galahad
SN
How many dimensions does a solid have?
Three
SL
What's the site of the annual All-American Soap Box Derby?
Akron, Ohio

## Slide 3
November 28, 2012
2012 Year End Support Pack Project
SAPbiz
Update

## Slide 4: Agenda
Review of Scope
Testing Status
Issues
Cutover Plan

## Slide 5: Project Scope Update
What are we updating?
  Let’s jump to the project wiki
    2012 SP Wiki

## Slide 6: Other Non-SP Projects
Other non-support pack project work (during SP project timeline)
  APR 3.0/HR Transactions (SE1 development environment)
  Facilities Discovery (SE1)
    Other activities
    AP YE Tax Report Changes (w/ SPs)
    SAP logon user exit enhancement

## Slide 7: Where are we now? Test execution
Test Status
  Unit – complete
    FLE: 459 transactions
    HRP: 277 transactions (includes EL)

## Slide 8: Where are we now? Test execution
Test Status
  SIT – complete:
    Some testing details …
  Quality Center (QC)
Area | Total
E_Learning (Automated) | 3
E_Learning (Manual) | 69
HR_Payroll - Automated | 41
HR_Payroll - Manual | 160
EHS - Automated | 25
EHS-Manual | 32
Finance - Automated | 144
Finance - Manual | 280
IST Automated | 1
Logistics - Automated | 120
Logistics - Manual | 188
 | 1063

## Slide 9: Issues
Is it worth it?
Well, yes …
  We can jump to RT for details: https://help.mit.edu/
Phases Issues were identified in … |  |  |  | 
(as of 11/27/12) |  |  |  | 
Issue type | Unit | SIT |  | Open
Required an SAP fix | 5 | 4 |  | 2
Required an MIT fix | 7 | 10 |  | 
Infrastructure Related | 6 | 8 |  | 
User/Data Error | 3 | 4 |  | 
Duplicate | 1 | 3 |  | 
Production Issue - to be addressed after SP | 1 | 2 |  | 
Totals | 23 | 31 | 54 | 2

## Slide 10: Issues (cont.)
How does it compare to prior years?
 | 2010 | 2011 | 2012
Issues | 64 | 41 | 54
SAP fix required | 3 | 8 | 9
MIT fix required | 23 | 17 | 17
Total fixes required | 26 | 25 | 26

## Slide 11: Next Steps
11/28/2012 - 11/30/2012 System Preparation
11/30/2012 - 12/3/2012 Go-live weekend!
Meaning … we’ll have to execute a cutover plan!!
  Let’s jump to the project wiki’s Cutover Plan page and take a look at the plan …
  2012 SAP SP Wiki

## Slide 12: Not-soTrivial Pursuits
G
How can I find out the status of the cutover?
Call this number 617-324-7468
E
Who performs the validations?
Assigned business personnel as defined in the cutover plan.
H
When will the SAP system be brought down?
5:00 PM Friday 11/30/2012
AL
Where can I find the cutover plan?
On the project wiki
SN
What are we updating?
The SAP ERP System
SL
When is go-live weekend?
11/30-12/3/2012

## Slide 13: Questions?
Any additional questions? Please contact:
Frank Quern Bart Dahlstrom
X2-4512 x3-9605
fquern@mit.edu bartd@mit.edu
OR
Your SAP testing coordinator:
HR-Payroll: Mary Donovan
Financial-Logistics-EHS : Kristen Hann
Technical Services: Wai-ming Li
R3-Administration: Ron Parker

## Slide 14: Soapbox derby …
Support Packs are Coming!
Support Packs are Coming!