## Slide 1: Trivial Pursuits
G
What’s the world’s northernmost national capital?
Reykjavik, Iceland
E
Who was the first non-human to win an Oscar?
Mickey Mouse
H
Who succeeded Pope Paul VI?
John Paul I
AL
What novel opens with: “The great fish moved silently through the night water”?
Jaws
SN
What’s a row of crows called?
A murder
SL
What sport did George Plimpton write about in The Bogey Man?
Golf

## Slide 2
February 13, 2013
2012 Year End Support Pack Project
SAPbiz
Lessons Learned

## Slide 3: Agenda
The Purpose of Lessons Learned
Recap of the Project
Lessons Learned

## Slide 4: Purpose of Lessons Learned
An opportunity to obtain feedback on:
  the project as a whole
  its organization
  its management
  its execution
… with the purpose of improving the process.

## Slide 5: Recap: Project Scope
What did we update?
  ERP System (application of support packs)
    Applied ERP 6.0 Enhancement Pack 6
    Applied Support Packs 604 SP53 / 606 SP04/EA SP15
  Oracle Database Patch (11.2.0.3)
  Other Updates
    Operating System
    GUI logon
    Authorization Enhancement
  Please refer to the project wiki for further details
    2012 Year End SAP Support Pack Project

## Slide 6: Recap: Important Dates
October - Plan, convert/create/update test scripts in QC, move pending support & project work into production
10/11/2012 – SAP release of year end base level support pack
10/20-21/2012 – Production outage; DB & OS upgrade
10/22/2012 - End of day production snapshot to be used to refresh test environments
10/22/2012 - Development Freeze begins
11/01/2012 - Last date to implement support & enhancement changes until freeze ends on 12/5/2012
10/26/2012 - 11/2/2012 Unit test
11/5/2012 - 11/27/2012 System Integration Test
12/1/2012 - 12/2/2012 Go-live weekend!
12/5/2012 - Development Freeze ends

## Slide 7: Recap: System Integration Testing
Expanded QC as the central repository for test cases and test tracking execution.
Successfully used automated testing (32% of all testing (last year was 25%)).
Testing Status:
  Please refer to QC for details
Area | Total Executed 2011 | Total Executed 2012
HR_Payroll_Automated | 15 | 41
HR_Payroll -Manual | 147 | 160
E-Learning - Automated | 3 | 3
E-Learning | 46 | 69
Authorizations | 1 | 0
EHS – Automated | 5 | 25
EHS-Manual | 45 | 32
Finance - Automated | 115 | 144
Finance - Manual | 263 | 280
IST Automated | 1 | 1
IST Manual | 1 | 0
Logistics - Automated | 91 | 120
Logistics - Manual | 157 | 185
 | 887 | 1060

## Slide 8: Recap: Issues
Was it worth it?
Well yes …
Did it catch everything?
Nope
    Post Go-live Issues – 2 (FM Parked Doc, Performance)
    Authorization - 2
Issue type | Unit | SIT | 2012 | 2011
Required an SAP fix | 5 | 4 | 9 | 8
Required an MIT fix | 7 | 10 | 17 | 17
Infrastructure Related | 6 | 8 | 14 | 2
User/Data Error | 3 | 4 | 7 | 7
Duplicate | 1 | 3 | 4 | 6
Production Issue - to be addressed after SP | 1 | 2 | 3 | 1
 | 23 | 31 | 54 | 41

## Slide 9: Lessons Learned
  Let’s jump to the project wiki …
    2012 SP Lessons Learned

## Slide 10: Next Steps
Compile your feedback, IS&T’s feedback and the Steering Committee’s feedback
Prioritize feedback
Review w/ IS&T & BPO Management & Implement

## Slide 11: Not-soTrivial Pursuits
G
Who do I contact if I have a script that I would like automated?
QA email address istqa@mit.edu
E
H
AL
Where can I find project information for reference?
On the project wiki
SN
What did we update?
The SAP ERP, as well as the underlining Oracle dbs and Operating System
SL
Who will be the 2013 Support Pack Project Manager?
When should we begin preparing for this year’s YE Support Pack application process?
Now
Which issue type in testing required the most fixes?
Issues requiring an MIT fix

## Slide 12: Questions?
Any additional questions? Please contact:
Frank Quern Bart Dahlstrom
X2-4512 x3-9605
fquern@mit.edu bartd@mit.edu
OR
Your SAP team lead:
HR-Payroll(HRP): Frank Quern
Financial-Logistics-EHS (FLE): Siobhan Cunningham
Technical Services: Wai-ming Li