## test tasks
Environment | Test case | Assigned to | Pass/Fail | Comments
SF2 | ITS application - Open enrollment | Desiree | Pass | Testing 9/25/2012 - 9/28/2012
| Print W-2 | Gregg | Pass
| Download W-2 file & procss thru Accuwage | Gregg | Pass
| Download 1042-S file. Printed one tax form | Mary | Pass
| Upload Pension Payroll Lump Sum file DTOWRLMP.012.20120717042344.TXT | Mary | Pass
| MIT Training access - enroll in class (Portal test) | Mary | Pass
| SHA transaction | Cindy | Pass
| Process payroll for BSI pernrs | Gregg | Pass
SH2 PS1 Snapshot 23:50 9/19/2012 | Run ZM 9.2012 - save results for SF3 testing | Gregg | Pass | Testing 10/2/2012 - 10/5/2012
| Post ZM payroll period 09.2012 | Gregg | Pass
| Process CDU ZM 09.2012 | Mary | Pass
| Process ZW payroll period 38.2012 9/10/2012-9/16/2012 | Gregg | Pass
| Post ZW payroll period 38.2012 | Gregg | Pass
| Process CDU ZW 38.2012 | Mary | Pass
| Notify Kristen posting is complete. | Mary | Pass
| ITS application - Open enrollment | Desiree
| Test ESS eW-2 and ePaystub | Mary | Pass
| APR web functions | Emily
| Test upload/download of ASR spreadsheet (test in sh1 with new transports) | CIndy | Pass
| Process outbound Lincoln gross pay file via dropbox - see if Eric can receive file. | Gregg
| Process inbound 9/20 Lincoln feed from dropbox (after payroll) | Gregg
| Print copy of W-2 | Gregg | Pass
| Download 1042-S file from Gui to local drive | Mary | Pass
| Reload Kronos feed - for next period 9/24 or 25 | Gregg
| MIT Training access - enroll in class (Portal test in sh1) (includes triggering email) | Mary
| Execute a WBT course | Mary/Desiree | Pass
| EHS Training Reports in sh1 | Mary | Pass
| SHA transactions (includes triggering email) (Web abd GUI) | Cindy | Pass

## SH2 userids
User ids for SH2 testing
robertsd
donovan
ecunning
cindyo
gmcgrath
ljonesbr