## Overview and Assumptions
Timeframe for Test Execution
Comparison Test: 11/7/2011-11/28/2011 (3 holidays)
Integration Test: see comparision test
Assumptions:
Production snapshot as of midnight 10/22/2012
Test system will be available by start of day 11/5/2012
Comparison test consists of four payroll comparisons:
| Weekly Non-Exempt (payweek 43 (10/15/2012-10/21/2012)) | LL | 44/2012
| Monthly Exempt (October 2012) | MC | 45/2012 | Cycle 1 | Leslie will identify cost objects
Pension Payroll Lump Sum (October 31, 2012)
Pension Monthly Annuity Run (Nov 2012)
Overview of integration test strategy:
Generate payroll and run interfaces simulating the production payroll processes.
Compare test system SH1 results to PS1 Production results
Research discrepancies; resolve system issues
Execute select test scripts hiting key functionality not executed during pay run processes
Comparison Tools:
Create comparison reports using the EPIUSE variance monitor tool
Net pay comparisons in excel
Net pay comparison using EPIUSE variance monitor
Ultra Compare
Fox Pro
Overview of Script testing - majority of testing conducted by Business:
Test Scripts identified in Quality Center, both manual and automated:
in the HR domain space are the folder containing test scripts:
HR-Payroll/Manual_test_Suite
HR-Payroll/Automated_Test_Suite
Test lab folder: 2012_SupportPacks

## Pre-test Prep
Non-Exempt Only
Exempt Only
Relevant to both exempt and non-exempt
MITSIS file* (contains non-exempt changes as well)
MITSIS gross pay file
Pension
Copy the following in-bound files:
3/24/2010 EDS In-bound Lump Sum File
3/24/2010 EDS In-bound Annuity File
HR-Payroll Team
Create Datafiles sub-folders for feedloads and comparisons (prod & test) | [6 empty] | complete | 2010-03-08
Copy production archived files to Datafiles folder area.
Student Bio Feed (MITSIS)
Keep LL Audit files
Parking file
TPASS file
Grad Appointment feed
LL Feeds - have Wai-ming copy files to test environment's sapin directory
| Archive Directory | Files Copied | # of Files | in/out | can be loaded locally? | task link
1 | hr/bcbs |  |  | out
2 | hr/crosby |  |  | out
3 | hr/crosby_dep |  |  | out
4 | hr/crosby_new |  |  | out
5 | hr/delta |  |  | out
6 | hr/eds_hr |  |  | out
7 | hr/fid_hr |  |  | out
8 | hr/hird |  |  | out
9 | hr/metpcensus |  |  | out
10 | hr/mitsis_dem |  |  | out
11 | hr/tufts |  |  | out
12 | hr/vision |  |  | out
13 | py/cu |  |  | out
14 | py/eds_cntrib |  |  | out
15 | py/facil_leav |  |  | out
16 | py/facil_time |  | 1 | in | Yes | 74
17 | py/fid_cntrib |  |  | out
18 | py/fid_cntrib |  |  | out
19 | py/fid_pct |  |  | in | No, | 48 | Set up job to load based on event. Wai-ming should ensure i_fcp event will trigger in SH1. Move file through drop box to test HW. File has been moved to server in prep for move through the dropbox
20 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
21 | py/fsa_census |  |  | out
22 | py/fsa_dep |  |  | out
23 | py/fsa_dep |  |  | out
24 | py/fsa_enroll |  |  | out
25 | py/gradaid |  | 5/5/5 | in |  | 39
26 | py/hancock |  |  | in | Yes | 77
27 | py/hancock |  |  | out
28 | py/ll_audt_py
29 | py/ll_audt_tm
30 | py/ll_bank |  |  | out
31 | py/ll_leave |  |  | out
32 | py/ll_sal_dst |  |  | out
33 | py/ll_sal_dst |  |  | out
34 | py/mass_hlth |  |  | out
35 | py/mass_sqe |  |  | out
36 | py/metp-ded | dmetficw.094.20101021000000 | 1 | in | Yes | 50
37 | py/mitsis_tim |  |  | out
38 | py/parking |  | 1/1 | in | No | 75
39 | py/t_pass |  | 1 | in | No | 76
40 | py/tech_cash | dtcshded.325.20101022000000 | 1 | in | Yes | 49
41 | py/tiaa_cref |  |  | out
42 | py/metpcont | dmetficw.094.20101021000000
43 | hr/mitsis_dem [MITSIS Biographic/Demographic files] |  | 6/6 | in |  | 38
44 | Lincoln inbound |  | 22 | in |  | 40
45 | Lincoln appts audit |  | 1
46 | Lincoln supplements audit |  | 1
47 | Lincoln actions audit |  | 1
48 | Lincoln time audit |  | 1 |  |  | 71
49 | Pension Payroll EDS In-bound Annuity File |  | 1 | in | yes | 9
50 | Pension Payroll EDS In-bound Lump Sum File |  | 1 | in | yes | 8

## Comparision Run Schedule
Task # | Activity | Transction /Program | SAP Archive Server Directory (for feeds) | Start | End | Resp | Status | Prep files ready? | Batch ID | Job Set # | Special Variant in PS1? | Update variant in sh2 | Notes | No. of files matched | PS1 | SH2 | Variances | Percent matched | Reasons for differences
P1 | Set up / Update SP Variants for all the feeds. |  |  | 2012-10-19 | 2012-10-19 | Mary D. Larissa Sharon | Complete |  |  |  | Yes - dates in variants will be changed 11/5.
P2 | Execute ZM Payroll simulation in PS1 for 10.2012 |  |  | 2012-10-22 | 2012-10-22 | Gregg | Complete
P3 | Run HIRD report in PS1- do not send, retain file for comparison |  |  | 2012-10-22 | 2012-10-22 | Mary | Complete |  | ZZHRBENBTC01 |  | Y- needs to be updated |  | So we have a comparison
P4 | Run ZPY_PENS_COMPENSATION - retain for comparison, Run in TEST mode |  |  | 2012-10-22 | 2012-10-22 | Mary | Complete
P5 | SH2 - After 9/17 snapshot applied and before support packs implemented, run ZM simulation for 09.2012 - use Gregg's rem stmt variant |  |  | 2012-10-01 | 2012-10-01 | Gregg | Complete | [5 empty] | Aliases in sf3?
P6 | SF3 - After support packs implemented, run ZM & ZW actual for 38.2012 & 09.2012 - use Greggs rem stmt variant |  |  | 2012-10-22 | 2012-10-22 | Gregg | Complete
P7 | SF3 - process ZM and ZW postings and CDU postings, let FI group know when finished. |  |  | 2012-10-19 | 2012-10-19 | Gregg /Mary | Complete
P8 | Compare BEFORE and AFTER results of 09.2012 ZM, compare to the PS1 copy of well. |  |  | 2012-10-19 | 2012-10-19 | Gregg | Complete | [5 empty] | SF3 before v. after were identical. Each with 2 variances from PS1 due to IT0210 changes post simulation prior to copy. |  | 13181 | 13182 | 2 | 100 | IL tax change, & 1 pernr transferred ZW to ZM paid in ZM first in SH2 & ZW first in SF3
P9 | SF3 - Execute Business Owner validation steps |  |  |  |  | HR Payroll Team | Did not do in 2012
P10 | Capture production logs for the EL incoming feeds for 10/23/2012 - to be used for test comparisons. - see list of jobs in doc EL Feeds and EMAIL notifications.xls |  |  | 2012-10-23 | 2012-10-23 | Mary | Complete |  | Run under batch id ZZHRELBTCH01
SIT Environment Ready - Prep for testing
1 | Verify Feed Registry Archive Control Tables are correct for the environment - Need to change encryption flag for those files which are copied into test sapin directory. | SM30 | n/a | 2012-11-05 | 2012-11-05 | SD | Complete | n/a |  |  |  |  | Part of the action log. | n/a | n/a | n/a | n/a | n/a
2 | Re-configure EDI Test Environment to accept files from SH2 |  | n/a | 2012-11-05 | 2012-11-05 | Ron, Larisaa will remind him | Complete | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
3 | Confirm w/ R3 that Lincoln configuration for EDI is active |  | n/a | 2012-11-05 | 2012-11-05 | Ron Parker | Complete | n/a |  |  |  |  | Per Eric Ngo - The logical system is RC2CLNT400.(Ron should verify) | n/a | n/a | n/a | n/a | n/a
4 | Execute ZM Payroll simulation in sh2 for period 10.2012. Compare to PS1 simulation run on 10/22. |  |  | 2012-11-05 | 2012-11-05 | Gregg M. | Complete | Yes |  |  |  |  | Compare to PS1 run. Use single line rem-statement. Log and report tie out. Don't need to wait for steps 1,,3 |  | 21120 pernrs (includes zeros) | 21120 pernrs | 2 | 100 | IL tax change, & IT0210 change timing
5 | Test ZOMCHST and IT0554/9018 - did we do this last year because of SHA project |  |  | 2012-11-05 | 2012-11-05 | Cindy | Complete | [5 empty] | Test for 2011 only-Hrly Student project will move changes to SH1during SP SIT = should not need this step for 2011.
6 | Validate EL web connections functional |  |  | 2012-11-05 | 2012-11-05 | Desiree | Complete
7 | Validate APR web connections functional. |  |  | 2012-11-05 | 2012-11-05 | Emily | Complete
8 | Load ASR files uploaded from the archive server to the proper server for each environment so that the ASR Faculty spreadsheet works correctly. |  |  | 2012-11-05 | 2012-11-05 | Emily | Complete
9 | DW extract of HR/Pay data | Multiple | n/a | 2012-11-05 | 2012-11-05 | Elena | Complete | n/a |  |  |  |  | Payrolls and feeds may be running | 8
10 | Assign batch ids to testers - see sheet Batch IDs and aliases |  |  | 2012-11-05 | 2012-11-05 | George - requested by Mary | Complete
11 | Validate Laurie19 aliases established |  |  | 2012-11-05 | 2012-11-05 | Mary & Gregg | Complete
Weekly and Pension Payrolls
| Set up job for Job Set 1 - update variants with correct days. | Multiple |  | 2012-11-05 | 2012-11-05 | Sharon D | Ran jobs one by one |  | ZZHRBENBTC01
12 | Outbound Run FSA Census outbound interface using Ultracompare compare file to Sunday production run (10/21). | ZPYI0170_FSA_CENSUS_DATA | py/fsa_census | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution |  | 2674 | 2675 | 1 | 100% | add'l record added after snapshot
13 | Outbound Run FSA Enroll outbound interface (looks at the control record) using Ultracompare compare file to Sunday production run (10/21). | ZPYI0170_FSA_ENROLLMENT_DATA | py/fsa_enroll | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 1 | No |  | run before payroll (checks the control record so we want the right period executed) minor discrepancy due to timing of execution |  | 2979 | 2980 | 1 | 100% | add'l record added after snapshot
14 | Outbound LL non-exempt leave accruals (this is a daily interface) using ultracompare compare files to Wed production runs (10/24) | Scheduled job ZHR_LL_ACCRUALS_OUT Check for errors on filezilla. | py/ll_leave | 2012-11-05 | 2012-11-05 | Gregg | Complete | Yes | ZZHRLLFEED01 | 1 | SP |  | This was moved up from Job Set 3 - needs to run before ZW payroll, | 2 | 3437 pernrs | 3430 pernrs | 76 | 98 | Accruals for 24th & pernrs with status changes
15 | Weekly Payroll Processing (43/2012) Work week 10/15/2012-10/21/2012 | Script: Non-Exempt Payroll Test for Support Pack Update 2008.doc |  | 2012-11-05 | 2012-11-05 | MD | Complete | n/a |  |  |  |  | see comparisons results in step 22 below | - | - | - | - | -
16 | Pension Payroll - Lump Sum Run (10/31/2012) (includes loading PS1 copy of Pension Lump Sum file) |  |  | 2012-11-05 | 2012-11-05 | GM | Complete | [5 empty] | Where do files come from? encrypted file dumps decrypted file processes correctly
17 | Pension Payroll - Annuity Run (11/2012) (includes loading PS1 copy of Pension Annuity file) |  |  | 2012-11-05 | 2012-11-05 | GM | Complete | [5 empty] | Where do files come from? see comparisons results in step 23 below | - | - | - | - | -
[14 empty] | n/a | n/a | n/a | n/a | n/a
| Set up job for Job Set 2 - update variants with correct days. | Run 11/5, do not need payroll results. |  | 2012-11-05 | 2012-11-05 | Sharon D | Ran jobs one by one | [5 empty] | Run 11/11, do not need payroll results.
18 | Outbound Run HR Fidelity outbound interface; using ultracompare compare file to Monday production run (10/22). Set parameter to process week before snapshot Mon-Sun | zhr_fidelity | hr/fid_hr | 2012-11-05 | 2012-11-06 | Lisa |  | Yes | ZZHRBENBTC01 | 2 | SPFID WKLY PS1 |  | can run w/ DW extracts, Orig run 3/14; chgs made 10/19
19 | Outbound Benefits outbound: BCBS using ultracompare compare file to Sunday production run (10/21). Run for dates 10/21 - 100 days thru 10/21 + 45. In IDOC Cleanup allow retro 10 days-variant all set. | Two steps: rpuben52 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/bcbs | 2012-11-05 | 2012-11-06 | Lisa |  | Yes | ZZHRBENBTC01 | 2 | Use BCBS PROD when not in OE cycle, else use SP BC OED/ SP BCBS PRD OE |  | can run w/ DW extracts; comparison will be made to the production run (EDI)
20 | Outbound Benefits outbound: Delta using ultracompare compare file to Sunday production run (10/21). Run for dates 10/21 - 100 days thru 10/21 + 45. In IDOC Cleanup allow retro 10 days. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/delta | 2012-11-05 | 2012-11-06 | Lisa |  | Yes | ZZHRBENBTC01 | 2 | Use DELTA when not in OE cycle, else SP DELTA OE for both |  | can run w/ DW extracts; comparisons were made to production Differences were address changes, terminations, Campus Police (didn’t exclude them in SH1 run)
21 | Outbound Benefits outbound: Vision using ultracompare compare file to Sunday production run (10/21). Run for dates 10/21 - 100 days thru 10/21 + 45. There is currently no retro limit in IDOC Cleanup. | Two steps: HRBEN0052 & program ZHR_BENEFIT_IDOC_CLEANUP | hr/vision | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 2 | Use VISION when not in OE cycle, else SP VISION OE for both |  | can run w/ DW extracts comparison will be made to the production run (EDI) |  | 69925 | 69981 | 103 | 99.9% | Date selection
22 | Outbound Run Express Scripts outbound; using ultracompare compare file to Sunday production run (10/21). | ZHR_ESI_FEED | hr/esi | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 2 | SP FULLFILE SP FULLFILE OE |  | can run w/ DW extracts |  | 14238 | 14208 | 55 |  | Date selection, master data changes
23 | Outbound Run Crosby Outbound terminations; using ultracompare compare files to Sunday production runs (10/21). *** follow all the way through to vendor *** | ZHRCSB02 | hr/crosby; | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 2 | SPZHRCSB02_RPT |  | can run w/ DW extracts |  | 68 | 68 | 0
24 | Outbound Run Crosby Outbound new entrants for the prior month (Sept); using ultracompare compare files to Sunday production runs (9/1). | ZHRCSB02 | hr/crosby_new | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 2 | SP_ZHRCSB02_NH |  | can run w/ DW extracts |  | 342 | 339 | 53 | 84.6% | Master data changes
25 | Outbound Run Crosby Outbound dependents aging out; based on file created 10/1 for Nov ageoffs using ultracompare compare files to production runs (10/1). | ZHRCSB03 | hr/crosby_dep | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 2 | SP_ZHRCSB03DEP |  | can run w/ DW extracts |  | 30 | 30 | 0 | 100%
26 | Outbound Run Metpay Census outbound interface; using ultracompare compare file to Sunday production run (10/22). | ZPY_METPAY_CENSUS_DATA | hr/metpcensus | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | ZZHRBENBTC01 | 2 | SP PRODUCTION |  | can run w/ DW extracts |  | 14644 | 14664 | 2434 | 93.4% | Capitals and trailing zeroes
27 | Outbound Run Health Insurance Resposibility Disclosure (HIRD); outbound to Crosby | ZHR_OUTBOUND_HIRD_DATA | hr/hird | 2012-11-05 | 2012-11-06 | Lisa | Complete | Yes | Run Manually | 2 | SP HIRD Test |  | Compare to file generated in PS1 on 1022 (step 4). |  | 39 | 34 | 10 | 74.4% | Master data changes - and there was a PS issue
28 | Payroll Results Comparison (ZW) |  |  | 2012-11-06 | 2012-11-08 | Gregg M. | Complete | [5 empty] | pernrs | n/a | 4182 | 4182 | 3 | 100 | 1 summoms chng in PS1, 1 time load error in SH2, 1 manual add of PHol time in PS1
29 | Payroll Results Comparison (ZP) |  |  | 2012-11-06 | 2012-11-08 | Gregg M. | Complete | [5 empty] | pernrs | n/a | 5726 | 5725 | 11 | 100 | 8 payment voids in PS1, 3 PS1 manual data changes
30 | Payroll Results Comparison (ZP)Lump Sum |  |  | 2012-11-06 | 2012-11-08 | Gregg M. | Complete | [5 empty] | pernrs | n/a | 32 | 33 | 1 | 97 | 1 pernr LS deleted manual & set-up as annuity
31 | FI POSTING COMPARISON (ZP) |  |  | 2012-11-06 | 2012-11-08 | Gregg M. | Complete | [5 empty] | lines in document | n/a | 25 accts | 25 accts | 5 | 80 | expected due to pernr from LS & data changhes
32 | FI POSTING COMPARISON (ZP)Lump Sum |  |  | 2012-11-06 | 2012-11-08 | Gregg M. | Complete | [5 empty] | accounts | n/a | 4 accts | 4 accts | 2 | 50 | diff due to pernr switched to annuity
33 | EDACCA TABLE COMPARISON |  |  | 2012-11-08 | 2012-11-08 | Gregg M. | Complete | [6 empty] | n/a | 6118 totaled rows | 6114 | 7 | 100 | 3 pernrs had differences: 1 was locked in PS1 CDU run, 1 had time/pay error in SH2 only, 1 had PHOL added manually to PS1 only
34 | FI POSTING COMPARISON (ZW) |  |  | 2012-11-08 | 2012-11-08 | Gregg M. | Complete | [5 empty] | lines in document | n/a | 1695 GL/CO posts | 1695 GL/CO posts | 8 | 99 | Expected due to 3 perrns with pay differences
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| (After Payroll Execution) Weekly Outbound Interfaces | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
| Set up job for Job Set 3 - update variants with correct days. |  |  | 2011-11-05 | 2011-11-05 | Mary | Ran jobs one by one |  | ZZPYBATCH001
| Set up job for Job Set L3 - update variants with correct days. |  |  | 2011-11-05 | 2011-11-05 | Gregg |  |  | ZZHRLLFEED01
35 | Outbound Timesheet file to MITSIS (combined w/ Grad Student Gross Pay) using ultracompare compare files to Tuesday's production runs (10/23) | ZPYIO_MITSIS_TIM | py/mitsis_tim | 2011-11-05 | 2011-11-05 | Gregg | Complete * | Yes |  | 3 | ??? |  |  |  | 2920 | 2875 | 45 | 98% | 4 pernrs different: 1 had time eval error, 2 has data changes in PS1 after snapshot, one had adj not picked up in test feed b/c of paramters used to run extract.
|  | Dates From Wednesday to Wednesday |  | 2011-11-05 | 2011-11-05 | Gregg |  | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
36 | Outbound LL salary distribution weekly gross pay using ultracompare compare files to Wed production runs (10/24) File to be sent to Lincoln, coordinate with Eric. | Program: ZPY_LL_SALARY_DISTRIBUTIONS | py/ll_sal_dst | 2011-11-05 | 2011-11-05 | Gregg | Complete | Yes | ZZPYBATCH001 | L3 | SP1ZW |  | Check for errors on filezilla |  | 6484 | 6484 | 0 | 100%
[8 empty] | n/a | ZZHRLLFEED01 |  | SP2ZW |  |  | n/a | n/a | n/a | n/a | n/a
37 | Outbound Leave balance accruals for Facilities Service Staff (this is a daily interface) | ZPTKRONOS_ACCRUL_OUT | py/facil_leav | 2011-11-05 | 2011-11-05 | Run by Gregg, compares by Cindy | Complete | Yes | ZZPYBATCH001 | 3 | y |  | internal test performed; additionally subsequent test performed with facilities |  | 2460 | 2454 | 6 | 99.8 | 3 pernrs - 1 found retired, 2 others had data difference between systems.
38 | Outbound FSA (Crosby). Compare results to production file using ultracompare compare files to Wed production runs (10/24) | ZPYIO_FSA_CONTRIB /ZPYI0170_FSA_CONTRIB | py/fsa_dep | 2011-11-05 | 2011-11-05 | Run by Gregg, compares by Lisa | Complete | Yes | ZZPYBATCH001 | 3 | SP_WEEKLY |  |  |  | 385 | 385 | 0 | 100
39 | Outbound Fidelity pension file (weekly 401 pension contributions) Use ZW Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS using ultracompare compare files to Wed production runs (10/24) | Scheduled Job ZPYIO_FID_CNTRIB/ ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2011-11-05 | 2011-11-05 | Run by Gregg, compares by Mary | Complete | Yes | ZZPYBATCH001 | 3 | SP_ZWAUTOMATI |  |  |  | 2388 | 2388 | 0 | 100
40 | Outbound LL Bank details (this is a daily extract) - compare feed from 10/23 | zpy_ll_bank_detail | py/ll_bank | 2011-11-05 | 2011-11-05 | Run by Gregg, compares by Gregg | Complete | Yes | ZZPYBATCH001 | L3 | No-run adhoc |  | Select a PS1 file which contains some changes and repeat test in sh2 |  | 7 | 7 | 0 | 100
| Inbound feeds to prep ZM payroll and next ZW payorll (before planned monthly run) | For 2012, change to include SHA feeds. Run 1 set of feeds for day after snapshot, then run Bio and Grad feeds up to exempt payroll process date. Execute LL daily feed up to date of next ZW payroll run.
41 | Inbound Student Bio Feed (MITSIS) (10/23) | ZMITSIS/ZPY_LOAD_MITSIS_BIO_DATA | hr/mitsis_dem | 2011-11-05 | 2011-11-05 | Gregg | Complete | Yes | ZZHRMITSIS01 | Execute these 5 feeds in order listed. | No |  | both old and new complete
42 | Inbound SHA Student Feed (10/23) Pre-req is the Student Bio feed above. Also need the previuos day's filr for comparison (10/22), Need to copy unencrypted file to sh2/sapin directory. | ZHR_HSA_UPLOAD | py/sha_stdt Provider ccode=stud Feed code= has | 2012-11-06 | 2012-11-06 | Process by Lucia, compares by Cindy | Complete |  | ZZPHSABTC01 | [5 empty] | 104 | 104 | 0 | 100%
43 | Inbound SHA UROP Feed (10/23) Need to copy unencrypted file to sh2/sapin directory. | ZHR_UROP_UPLOAD | py/sha_urop Provider ccode=stud Feed code= uro | 2012-11-06 | 2012-11-06 | Process by Lucia, compares by Cindy | Complete |  | ZZPHSABTC01 | [5 empty] | 41 | 41 | 0 | 100%
44 | Inbound Grad Appointment Inbound (this is a daily feed) (10/23) Copy PS1 file to local directory. | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2012-11-06 | 2012-11-06 | Gregg | Complete | Yes | ZZHRGRADAPT01 |  | No |  | both old and new complete
45 | Inbound LL daily feed (processed on 10/23). Feed files can be identified by running ZHRALELOG Need to copy unencrypted file to sh2/sapin directory. | ZHRALE01 | hr/ll_hr_time Provider ccode=mith Feed code= hrm | 2012-11-06 | 2012-11-06 | Gregg | Complete |  | ZZHRLLFEED01 |  | No |  | Check for errors on filezilla Validate using transaction ZHRALELOG TBD (may be that Eric will review)
46 | Inbound ZTN_MITSIS_ACADEMIC_TERMS (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_MITSIS_ACADEMIC_TERMS_IN | none - Provider ccode=dstud Feed code= trm | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 | Execute these 9 feeds in order | SP ACAD_TERMS |  | both old and new complete |  |  | 12 |  |  | Verified against copy of production log
47 | Inbound ZTN_MITSIS_ACADEMIC_SUBJECTS (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_MITSIS_ACAD_SUBJECTS_IN | none - Provider ccode=dstud Feed code= sub | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 |  | SP ACAD_SUBJ |  | In PS1 program runs about 6AM - file may not be received until the afternoon, so the program is running the previous day's file. |  |  | 4706 |  |  | Verified against copy of production log
48 | Inbound ZTN_MITSIS_SUBJECT_ENROLLMENT (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_MITSIS_ENROLLMENT_IN | none - Provider ccode=dstud Feed code= erl | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 |  | SP ENROLLMENT |  |  |  |  | 215 |  |  | Verified against copy of production log
49 | Inbound ZTN_LINCOLN_PI_RECONCILER_FEED (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_LINCOLN_PI_RECONCILER_IN | none - Provider ccode=dllte Feed code=pir | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 |  | SP PI_RECON |  |  |  |  | 126 |  |  | Verified against copy of production log
50 | Inbound ZTN_LINCOLN_PI_TRAINEE_FEED (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_LINCOLN_PI_TRAINEE_FEED | none - Provider ccode=dllte Feed code=pit | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 |  | SP PI_TRAINEE |  |  |  |  | 3499 | 1 |  | Verified against copy of production log - one person updated, pernr added to PS1 after snapshot.
51 | Inbound ZTN_LINCOLN_COURSE_COMPLETIONS (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_LINCOLN_COURSE_COMPLETIONS | none - Provider ccode=dllte Feed code=crc | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 |  | SP LL_COMPLS |  |  |  |  | 22828 |  |  | Verified against copy of production log
52 | Inbound ZTN_REMEDY_INTERACTIVE_CONNECTOR (this is a daily feed) (10/23) Not yet running in PS1 need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_LINCOLN_COURSE_COMPLETIONS | none - Provider ccode=dehsw Feed code=ecc | 2012-11-06 | 2012-11-06 | Mary | N/A - not running in PS1 |  | ZZHRELBTCH01 |  | SP EHS_ERGO
53 | Inbound LSO TNI DW ORG DLC MAPPING IN (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZTN_DW_ORG_DLC_MAPPING_IN | none - Provider ccode=dinfr Feed code=org | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 |  | SP DLC_ORG_LD |  |  |  |  | 1636 |  |  | Verified against copy of production log
54 | Inbound RCR QUALIFICATION LOAD (this is a daily feed) (10/23) need to have Waiming decrypt file from sapin folder and store on local drive | ZHRRCR_UPLOAD | none - Provider ccode=dciti Feed code=qlf | 2012-11-06 | 2012-11-06 | Mary | Complete |  | ZZHRELBTCH01 |  | Seelct local file and add testers email address |  | Check for errors on filezilla |  |  | 2417 |  |  | Verified against copy of production log
55 | Inbound Student Bio Feed (MITSIS) (10/23-10/25) (Run just up to the date of the exempt payroll execution, which is 10/25/2012). | ZMITSIS | hr/mitsis_dem | 2012-11-06 | 2012-11-06 | Gregg | Complete | Yes | ZZHRMITSIS01 | IB1These 3 must run per day, one after the other | No |  | both old and new complete
56 | Inbound Grad Appointment Inbound (this is a daily feed) (10/23-10/25) (Run just up to thedate of the exempt payroll execution, which is 10/25/2012). | ZPY_LOAD_MITSIS_GRAD | py/gradaid | 2012-11-06 | 2012-11-06 | Gregg | Complete | Yes | ZZHRGRADAPT01 |  | No |  | both old and new complete
57 | Inbound LL daily feed (10/24) run thru Wed (before ZM processing) Will run Monday's files after the LL audit files are processed. |  |  | 2012-11-06 | 2012-11-06 | Gregg | Complete |  | ZZHRLLFEED01 |  | No |  | Check for errors on filezilla Validate using transaction ZHRALELOG TBD (may be that Eric will review)
58 | Email: EL training reminder | ZTN_ACTSEL_NOTIF_TRAINING | N/A | 2012-11-06 | 2012-11-06 | Mary | Complete | Captured 10/23 log | ZZHRELBTCH01 |  | No
59 | Email: EL Expiring quals | ZTN_EMAIL_LRNR_EXPIRING_QUALS | N/A | 2012-11-06 | 2012-11-06 | Mary | Complete | n/a | ZZHRELBTCH01 |  | No
| Additional Payroll Interface Activities (before planned monthly run) | Need to coordinate with above inbound run's |  |  |  |  | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
60 | Inbound Weekly Fidelity Percent Inbound; use Friday file (10/26); compare reports to prod reports; spot-check the loaded data Copy PS1 file to local directory. | ZPYII_FID_PCT | py/fid_pct | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Cindy | Complete | Yes | ZZPYBATCH001 | IB2 |  |  | Trigger through drop box in Linux version. |  |  | 20 |  | 100 | Spot checked updates
61 | Inbound Weekly Tech Cash Inbound; use Friday file (10/26).; compare reports to prod reports; spot-check the loaded data Copy PS1 file to local directory. | ZPYII_DED | py/tech_cash | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Cindy | Complete | Yes | ZZPYBATCH001 | IB2 | [5 empty] | 511 |  | 100 | Spot checked updates
62 | Inbound Metpay Home/Auto inbound; compare reports to prod reports; spot-check the loaded data (10/25) Copy PS1 file to local directory. | ZPY_METPAY_IN | py/metp-ded | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Cindy | Complete | Yes | ZZPYBATCH001 | IB2 | [5 empty] | 15 |  | 100 | Spot checked updates
63 | Monthly Payroll Processing - ZM | Script: Exempt Payroll Test for Support Pack Update 2008.doc |  | 2012-11-06 | 2012-11-06 | MD |  | n/a |  |  |  |  | see results below | n/a | n/a | n/a | n/a | n/a
64 | Payroll Results Comparison (ZM) |  |  | 2012-11-07 | 2012-11-07 | Gregg M. | Complete | - |  |  |  |  | pernrs | n/a | 13900 pernrs | 13877 pernrs | 528 | 96 | Tech cash load timing caused 416 variances,
65 | EDACCA TABLE COMPARISON |  |  | 2012-11-07 | 2012-11-07 | Gregg M. | Complete | - |  |  |  |  | see detail notes tab | n/a | 28125 totaled rows | 25769 | 4148 | 99 | Timing
66 | FI POSTING COMPARISON |  |  | 2012-11-07 | 2012-11-07 | Gregg M. | Complete | - |  |  |  |  | lines in document | n/a | 69 | 68 | 32 | 53 | Expected due to GTN differences. Difference in posted net pay was about one-tenth percent
67 | After ZM 3-Party Processing - Test garnishments to A/P: Run F110 payment process; verify check format and Mass ACH file format. |  |  | 2012-11-07 | 2012-11-07 | Gregg M, Ken LeVie | Complete | n/a |  |  |  |  | ZM 3PR pp 03.2010 new vs. old are a match - 33 vendor payment line items in each = 100% | n/a
| (After Monthly Payroll Payroll Execution) Outbound Interfaces (Comparisons to production files) | [5 empty] | - | [5 empty] | Set up jobs Friday. | n/a | n/a | n/a | n/a | n/a
| Set up job for Job Set 4 - update variants with correct days. |  |  | 2012-11-06 | 2012-11-06 | Mary | Ran jobs one by one |  | ZZPYBATCH001
| Set up job for Job Set L4 - update variants with correct days. |  |  | 2012-11-06 | 2012-11-06 | Alan |  |  | ZZHRLLFEED01
68 | Outbound Fidelity contributions outbound - monthly Use ZM Automatic variant, change start date/time to when PR ran, uncheck test for file to go to AS | ZPYI003_O_FID_CONTRIB | py/fid_cntrib | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Mary | Complete | Yes | ZZPYBATCH001 | 4 | SP_ZM_AUTOMATI |  |  | 1 | 6966 | 6964 | 18 | 99.8% | Master data changes between environments
|  | Dates TBD |  | 2012-11-06 | 2012-11-06 |  | n/a | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
69 | Outbound FSA contributions outbound - monthly Use monthly variant, change start date/time to before payroll run, check test, enter handliing rule 001 | ZPYIO_FSA_CONTRIB /ZPYI0170_FSA_CONTRIB | py/fsa_dep | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Emily | Complete | Yes | ZZPYBATCH001 | 4 | SP_Monthly |  |  | 1 | 2168 | 2167 | 1 | 99.995 | pernr 95311 - change in PS1, not in SH2
70 | Outbound Credit Union contributions Run for dates from PS1's last run email thru end of monthly payrun | ZPYIO_CU_UNION / ZHRPY_CREDIT_UNION | py/cu | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Emily | Complete | Yes | ZZPYBATCH001 | 4 | SP_VAR_ZM_ZW |  |  | 1 | 2953 | 2952 | 1 | 99.97 | pernr 26016 - vacation payout in PS1 with credit union, not in SH2
71 | Outbound John Hancock (long term care) contributions | ZPYIO_HANCOCK /ZPYI006_0_JHK_LTCPRE | py/hancock | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Emily | Complete | Yes | ZZPYBATCH001 | 4 | SP_ZM_ZW |  |  | 1 | 539 | 539 | 0 | 100
72 | Outbound TIAA-CREF (457B) contributions (10/27File) | ZPYIO_TIAA_CREF/ZPY_457B_CONTRIB_OUT | py/tiaa_cref | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Emily | Complete | Yes | ZZPYBATCH001 | 4 | SP__ZMAUTOMATI |  |  | 1 | 221 | 221 | 0 | 100
73 | Outbound LL Salary distribution monthly gross pay - send copy to Lincoln, coordinate with Eric. | ZPY_LL_SALARY_DISTRIBUTIONS_DST | py/ll_sal_dst | 2012-11-06 | 2012-11-06 | Gregg | Complete | Yes | ZZPYBATCH001 | L4 | SP-ZM |  |  | 1
74 | Outbound Pension outbound interface - Employment file (run before | ZPY_PENSION_EMPL / ZPY_PENSION_EMPLOYMENT | py/pen_empl | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Cindy | Complete |  | ZZPYBATCH001 | 4 | no |  | Run Sept and Oct for comparisons for reasonability? |  | 1421 | 1247 | 174 | 87.8% | Master Data differences between environments
75 | Outbound Pension outbound interface -Personal file | ZPY_PENSION_PERS / ZPY_PENSION_PERSONAL | py/pen_pers | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Cindy | Complete |  | ZZPYBATCH001 | 4 | no |  | Run Sept and Oct for comparisons for reasonability? |  | 1212 | 950 | 262 | 78.4% | Master Data differences between environments
76 | Outbound Pension outbound interface -Compensation file | ZPY_PENSION_COMP / ZPY_PENSION_COMPENSATION | py/pen_comp | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Cindy | Complete |  | ZZPYBATCH001 | 4 | SP Test (for SP2012, ran in PS1 on 10/22 for Sept. |  | Compare to PS1 extract run on 10/17 in step ??? |  | 1159 | 1159 | 0 | 100%
77 | Outbound Pension outbound interface -Pay & Hours file | ZPY_PENSION_CONT / ZPY_PENSION_PAY_HOURS | py/pen_cont | 2012-11-06 | 2012-11-06 | Run by Gregg, compares by Mary | Complete | Yes | ZZPYBATCH001 | 4 | Run for ZM and one week of ZW - use dates 11/5/2012-11/08/2012 |  | Balance totals with recon report of 9C93 |  | 11898 | 11902 | 50 | 99.6% | All Master data changes.
| Inbound Interface Comparisons | [5 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
78 | Load LL Daily feed (10/25-10/26) catchup on files after ZM run. - weekly IDOC file - need to copy to test system's sapin directory This is a separate set of files than th lincoln feed in step 40. | ZHRALE | n/a | 2012-11-07 | 2012-11-07 | Gregg | Complete |  |  | IB3 |  |  | Validate using transaction ZHRALELOG TBD (may be that Eric will review) | 13
79 | Run LL HR/Payroll audit files (10/29/2011) - weekly need to copy to test system's sapin directory - 3 separate files. Once files are in sapin and above step is processed, Lincoln person can execute audit report. | ZHRALF02 | py/ll_audt_py | 2012-11-07 | 2012-11-07 | Eric | Complete | -- |  |  |  |  | Validated by Collen in the past | n/a | n/a | n/a | n/a | n/a
80 | Load LL Daily feed (10/29/2011 upto 10 files) - weekly IDOC file - need to copy to test system's sapin directory This is a separate set of files than th lincoln feed in step 40. | ZHRALE | n/a | 2012-11-07 | 2012-11-07 | Gregg | Complete |  |  | IB3 |  |  | TBD (may be that Eric will review) | 13
81 | Run LL time audit (10/29/2011) - weekly need to copy to test system's sapin directory - 1 file. Once file is in sapin and above step is processed, Lincoln person can execute audit report. | ZPYII_LL_AUDT_TM | py/ll_audt_tm | 2012-11-07 | 2012-11-07 | Eric | Complete | [5 empty] | TBD (may be that LL will review (ccassidy))
82 | Inbound Run Kronos Feed and compare IT2001/2002 records with change date of (date file was executed, changed by whomever ran the file) or time eval results. (10/30/2012) - weekly need to copy to test system's sapin directory. Warning - cannot repeat run unless first delete first update - will double data if run repeated. | ZHR_INBOUND_TIME | py/facil_time | 2012-11-07 | 2012-11-07 | Run by Gregg, validation by Lisa | Complete |  | ZZPYBATCH01 | IB4 |  |  | Can run by chosing decrypted file from local server. Make sure file is consistent with week to be processed - dates must line up! | 1 | 2124 | 2058 |  |  | Standard errors
83 | Inbound Parking Standard Internal deductions - monthly copy to test system's sapin directory (Use 10/19 file if available, change date in file to Nov) need to copy to test system's sapin directory | ZPYII_DED | py/parking Provider code=park Feed code = ded | 2012-11-07 | 2012-11-07 | Run by Gregg, validation by Mary | Complete |  | ZZPYBATCH01 | IB4 |  |  | loaded encrypted through drop box | 1 | 4544 | 4542 | 2 | 99.99% | Master data changes.
84 | Inbound Tpass Standard Internal deductions - monthly; (use 10/17 file and change dates to 11/17) (pre Nov payrun) 4 files, imputed income file is blank. Process 1 file - post tax TPAss-wage type 554D. Will files be received by 11/16 - should we process Oct?? Can copy to local directory - need to change date in file to Nov. | ZPYII_DED | py/t_pass Provider code=tark Feed code = ded | 2012-11-07 | 2012-11-07 | Run by Gregg, validation by Mary | Complete | Yes | ZZPYBATCH01 | IB4 |  |  | loaded locally | 1 | 602 | 601 | 1 | 99.99% | Master data change
85 | Inbound Long Term Care (John Hancock) - monthly; (use 11/16 file) (pre Nov payrun) Will files be received by 11/16 - should we process Oct?? Can copy to local directory - need to change date in file to Dec. | zpyii _hancock | py/hancock Provider code=jhan Feed code = ltb | 2012-11-07 | 2012-11-07 | Run by Gregg, validation by Mary | Complete | Yes | ZZPYBATCH01 | IB4 |  |  |  | 1 | 16 | 15 | 1 | 94% | Master data change
86 | State Quarterly - outbound report - quarterly; Run Q3 2011 | pu19 sui wage reporting | ?- what should we do with this and next step - ask leslie? | 2012-11-09 | 2012-11-09 | Gregg | Complete | -- |  |  |  |  | count = lines in file | 1 | 18281 | 18281 | 0 | 100%
[7 empty] | - | [6 empty] | n/a | n/a | n/a | n/a | n/a
87 | Run weekly payroll - limited (44/2012). Mary Note: This run will be for only LL run. Test cases after this run will be for week 45/2012. |  |  | 2012-11-08 | 2012-11-08 | Gregg M. | Complete | n/a | [5 empty] | n/a | n/a | n/a | n/a | n/a
88 | Run LL gross pay file for weekly outbound for payweek 44 Compare the output to pay week 44. File to be sent to Lincoln for comparison | Scheduled job ZPY_LL_SALARY_DISTRIBUTIONS | py/ll_sal_dst | 2012-11-08 | 2012-11-08 | Gregg | Complete | n/a | ZZPYBATCH01 | L5 |  |  | Execute only if testing feed to LL. Campus compares and send to LL.
89 | Update SH2 will any PS1 updates conducted after 10/17: * eW-2 parameters *eW-2 false positives *Update Payroll control records for earliest retro date |  |  | 2012-11-08 | 2012-11-08 | Mary , Gregg, | Complete
90 | Create and download 1042-S file Validate ACH File Testing printing: Payroll check DACCA W-2 1099R 1042-S |  |  | 2012-11-09 | 2012-11-09 | Mary , Gregg, | Complete
| Test LL files created in their Support Pack QA Environment | [12 empty] | n/a | n/a | n/a | n/a | n/a
91 | Run LL HR/Payroll audit files (11/5/2012) - weekly | ZHRALF02 | py/ll_audt_py | 2011-11-14 | 2011-11-14 | Eric |  | -- |  |  |  |  | Start date dependent on progress of previous steps and if LL is ready to generate files. | n/a | n/a | n/a | n/a | n/a
92 | Load LL daily feed (11/5/2012) - these files will be generated by LL in their QA environment, to test their Support Packs upgrade. (This was not conducted fo SP2010, as LL did not upgrade Support Packs in 2010). | ZHRALE | n/a | 2011-11-14 | 2011-11-14 | Gregg | [6 empty] | Start date dependent on progress of previous steps and if LL is ready to generate files. | 13
93 | Run LL time audit (11/5/2012) - weekly | ZPYII_LL_AUDT_TM | py/ll_audt_tm | 2011-11-14 | 2011-11-14 | Eric | [6 empty] | Start date dependent on progress of previous steps and if LL is ready to generate files.
| Open up testing for SIT test cases. | [12 empty] | n/a | n/a | n/a | n/a | n/a
94 | Validate access to sh2 |  |  | 2012-11-06 | 2012-11-06 | All testers | Complete
Tests to conduct WHILE Payroll comparisons are executing (no dates prior to Nov 1, 2012)
95 | E-Learning |  |  | 2012-11-06 | 2011-11-21 | Melissa/et al
96 | Exempt (No retro) |  |  |  | 2011-11-10 | Leslie | Complete
97 | Non-Exempt (No retro) |  |  | 2012-11-06 | 2011-11-10 | Leslie | Complete
98 | Students (No retro) |  |  | 2012-11-06 | 2011-11-10 | Leslie
99 | ASR |  |  | 2012-11-06 | 2011-11-10 | Adrienne/Emily/Lisa | Complete
100 | APR View a transaction |  |  | 2012-11-06 | 2012-11-09 | Leslie
101 | ESS - non Benefits |  |  | 2012-11-06 | 2012-11-09 | Leslie | Complete
102 | OM |  |  | 2012-11-06 | 2012-11-09 | Leslie & Cindy
103 | APR - Front end data entry (no SAP processing) |  |  | 2012-11-06 | 2012-11-09 | Leslie
104 | ESS-Benefits (Desiree help with Campus Police setup) |  |  | 2012-11-06 | 2012-11-09 | Diane
105 | Benefits - Pendion EOI |  |  | 2012-11-06 | 2012-11-06 | Mike
106 | Faculty Chair |  |  | 2012-11-06 | 2012-11-09 | Jean D | Complete
107 | Pension - date 12/1/2012 or later to execute week of 11/7. |  |  | 2012-11-06 | 2012-11-09 | Diane
108 | Year End Reporting (Mary,Gregg for support) |  |  | 2012-11-06 | 2012-11-09 | Leslie | Complete
| Tests to conduct AFTER Payroll comparisons completed - can contain dates prior to Nov 1, 2012 |  |  | 2012-11-09 | 2012-11-21
109 | SAP Web - eDACCA, eSDS, time approvals |  |  | 2012-11-13 | 2012-11-21 | Leslie | Complete
110 | Exempt (Retros) |  |  | 2012-11-13 | 2012-11-21 | Leslie | Complete
111 | Non-Exempt (Retros) |  |  | 2012-11-13 | 2012-11-21 | Leslie | Complete
112 | Students (Retros) |  |  | 2012-11-13 | 2012-11-21 | Leslie
113 | APR - SAP backend processing |  |  | 2012-11-13 | 2012-11-21 | Leslie
| OM - org unit |  |  | this might be automated |  | Anne
115 | Execute Cycle 1 Payrolls |  |  | 2012-11-13 | 2012-11-21 | Leslie
116 | Miscellaneous (Gregg, support for garnishment tests) |  |  | 2012-11-13 | 2012-11-21 | Leslie Mary (NRA cases) | Complete
| Validations of all above transactions to be completed by 11/21/2012 |  |  |  |  | All
Legend:
Pay run execution
Section Heading
Lincoln Lab
Note on P35: robertsd: PS1 Comparison
Note on P37: robertsd: PS1 Comparison

## Detail Notes
Detail Notes:
Step 4 | DW | Program ZWHPAYROLL_RESULTS_NEW; extracted for 2/22/2010; 6 files:
|  | wh-payruns.asc - 14084 | 14084
|  | wh-paydet.asc - 161194 | 161194
|  | wh-payarrs.asc - 652 | 652
|  | wh-pay_dd.asc - 2348 | 2348
|  | wh-paymnt.asc - 13443 | 13443
|  | wh-paypers.asc - 14084 | 14084
Program ZWHPAYROLL_FIN; extracted for 2/22/2010 -- 3/2/2010; 2 files:
|  | wh-pay_fi_docs.asc - 2082 | 2082
|  | wh-pay_fi_post.asc - 212717 | 212717
420604
Step 54 | PY | ZM eDACCA Comparison
ZM edacca compare of 26963 rows in each system had 6 rows with small differences on a single pernr.
Mary checked the pernr (35400) and found the differences were due from a calculation difference in tuition (RTD1) resulting after termination by feeds that were run on different days - where term date was set as interface run date (term date in new is 04/22/10 & term date in old is 04/23/10).
- gm
Since the daily rate for tuition is calculated based on the total number of days in the appt, the daily rate in the new sh1 is higher since it term’d one day earlier.
-md

## Batch IDs and aliases
Batch ID assignments | PS1 Owners | SIT Tester
ZZHRBENBTC01 | Sharon | Lisa
ZZPYBATCH001 | Laurie | Gregg
ZZHRGRDAPT01 | Scott | Gregg
ZZHRMITSIS01 | Scott | Gregg
ZZHRLLFEED | Tricia Sullivan-Mullen | Gregg
ZZHRELBTCH01 | John Tuttle | Mary
ZZPYHSABTC01 | Lucia Ma | Lucia Ma
Aliases
Laurie19 | Laurie | Mary & Gregg

## Suggestions from last Year
Suggestions for next year (2012)
Change SIT authorization for users like Shwn Spencer so they can update IT0105 themselves for ESS testing

## For Next Year
Suggestions for next year (2012)
Change SIT authorization for users like Shwn Spencer so they can update IT0105 themselves for ESS testing