This document contains the following items for use during go live weekend:

- SAP Support Pack Application Task List and Schedule

- Communication and Contact Information

  - VOICEMAIL WITH STATUS: 617-324-7468

  - CONFERENCE CALL LINE: Webex

Call-in toll-free number (US/Canada): 1-877-668-4490 
Call-in toll number (US/Canada): 1-408-792-6300

Saturday Access code: 641 997 485

Sunday Access code: 643 690 991

  - At the conclusion of each task in section 1 below send email to sap-upgrade-core@mit.edu indicating completion of task

- Validation Information

- Escalation Plan

- SAP Support Pack Update Task List

|  | Date | Time | Action / Task | Person(s) Responsible |
| --- | --- | --- | --- | --- |
| Pre-Update Schedule and Processes |  |  |  |  |
|  | Monday 11/26/12 complete | By 9 AM (5 Minutes) | Post messages on insideMIT, SAPweb and ESS (Employee Self Service) web sites about upcoming SAP outage. (message can be found at end of this document) | Web-Tech (JAD) |
|  | complete | By 10:00 AM | Post message on ECAT web site about upcoming SAP outage. | VPF - John Doyle VPF - Jeff Rosa |
|  | In process | 10:00 AM | Begin online upgrade piece of the application of Enhancement Pack(s). Run time 2 days (complete by EOD 11/27). PS1 is locked during this window (no transports can be imported – critical transports would have to wait). | R3-Admin (R. Parker) |
|  | complete | 12 PM | Post message on SAPgui indicating upcoming SAP outage | R3-Admin (R. Parker) |
|  | complete | By 12 PM | Confirm that there are no GuiXT Changes | PM – Frank Quern DOF – M. Sherman |
|  | complete | By 5:00 PM | Send message to MIT-SAP community about upcoming SAP outage. (message at end of this document) | Project Manager (Frank Quern) |
|  | Tuesday 11/27/12 complete | 10:30 AM | Cutover weekend planning meeting IS&T. | IS&T-SAP |
|  | complete | 12:00 PM | Steering Committee Meeting – review cut-over plan/ Go/No-go decision – W92 | Steering Committee |
|  | complete | By 5:00 PM | Email Steering Committee Go/No-go decision | Project Manager ( Frank Quern) |
|  | Wednesday 11/28/2012 complete | 10:30 AM- 12 PM (noon) | SAPbiz meeting to review the Production Cutover schedule and details, including action log and user support | Project Manager ( Frank Quern) |
|  | complete | 2:00 – 3:00PM | Final review all issues in RT project queue, transport list, and web components. | R3-Admin /Core Team/ABAP Team/Web-Tech/BAs |
|  | complete | 3 – 4 PM | SAP Action log team meeting to review the Production Cutover action log. | Support Pack Action log Team |
|  |  | By EOD | R3-Admin email message about system down time | R3-Admin (R. Parker) |
|  |  | By EOD | Final Copy of the Production Update Schedule published and emailed. | Project Manager (Frank Quern) |
|  | Thursday 11/29/2012 | By 4 PM | Schedule Pre & Post Trial Balance reports to be used by R3-Admin for controlled data comparisons. (Schedule date should be 12/3/2012). Notify R3-Admin (R. Parker) and PM (Frank Quern) when jobs have been scheduled. | VPF Finance (Jo Lyn Whitlock) (C. Auguste) |
|  |  | By 4 PM | Final Copy of the Production Update Schedule published and emailed. | Project Manager (Frank Quern) |
|  | Friday 11/30/12 | By 2 PM | Facility supervisors print out work lists as back up for Monday Morning | Facilities (L. St. Croix) |
|  |  | By 12 PM (noon) (3 Hours) | Reschedule (shift) DW batch jobs to Sunday night (10PM & 12AM). | DW (E. Zhitnikov) |
|  |  | By 4:20 PM | Shift Concur outbound execution from 5:00 pm to 4:20pm | Tech Services (Wai-ming Li) |
|  |  | By 4:30 PM | Suspend weekend MITSIS Grad Appointment Feed - On sky-app-1 under userid as_cron comment out weekend rprgapxt_new job | Enterprise Appl. Admin (K. Mullins) |
|  |  | By 5:00 PM | Workflow and JV Validation Reports - Workflow inbox report (Yan Jiang) - JV Parked Documents Report (Yan Jiang) - RFPs (Cathy Cherico) | VPF (Yan Jiang) (Cathy Cherico) |
|  | Friday 11/30/12 | 4:35 PM (5 Minutes) | Stop EDI Production Jobs (5 Minutes) Will need access to logistics batch id ZZLOGISBAT01. - email sap-upgrade-core@mit.edu when complete | Tech Services (E. Prudden) R3-Admin (G. Petrowsky) |
|  | Friday 11/30/12 | 5 PM (15 Minutes) | Shut down EDI application server (note: email sent to EDI partners earlier in the week notifying them of the shutdown window). - Run the push POs job - Shutdown the web server - Shutdown the application server - email sap-upgrade-core@mit.edu when complete | Enterprise Appl. Admin (O. Wang) |
|  |  | 5 PM | Voice message update when system goes down (617-324-7468) - email sap-upgrade-core@mit.edu when complete | Project Manager (F. Quern) |
|  |  | 5 PM | System Downtime Message (3 Down) - email sap-upgrade-core@mit.edu when complete | R3-Admin |
|  |  | 5 PM | Bring down application servers. Production Environment becomes unavailable to users (including SAPWeb, Self Service and ECAT). - email sap-upgrade-core@mit.edu when complete | R3-Admin |
|  |  | 5 PM (5 Minutes) | Disable Gateways: Enable “PS1 System Unavailable” redirect on SAPweb & Self Service/insideMIT web sites (including EHS specific message activating their manual reporting of injuries) After Gateway is disabled Remove Port References (this will be a permanent setting) - email sap-upgrade-core@mit.edu when complete | Web-Tech (JAD) |
|  |  | 5 PM (5 Minutes) | Suspend Drop-box processing. - email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li) |
|  |  | 5 – 9 PM | Validation Reports (Trial Balance) executed in SAP. - Ron notifies Jo Lyn Whitlock, Clarel Auguste via email cc fquern@mit.edu, rcasey@mit.edu, keyurpb@mit.edu that the reports are complete & downloaded. - VPF confirms the receipt of the Trial Balance Report. - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) VPF (Clarel Auguste) (Jo Lyn Whitlock) |
|  | Friday 11/30/12 | 5 – 9 PM | Limited activity in PS1. - With the exception of the Data warehouse jobs (and the trial balances) shift the remaining time-scheduled non-infrastructure jobs to execute after the weekend cutover activities (after 6am on Monday - Users locked - Save WT info to internal SAP table - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) (G. Petrowsky) |
| Support Pack Application and Processes |  |  |  |  |
|  | Friday 11/30/12 | 9 – 12AM | Backup PS1. - Bring down the SAP systems - Perform SRDF mirroring split back-up - email sap-upgrade-core@mit.edu when complete | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Matt Anctil) |
|  | Saturday (morning) 12/1/12 | 12 - 9AM | SAP ERP: Execute support pack application; includes BSI upgrade. - Email Notification to sap-upgrade-core@mit.edu from Ron Parker at the start of the support pack application - Email notifications to sap-upgrade-core@mit.edu by 12:00 midnight on Friday (11/30) with status and by 7 am on Saturday (12/2) from Ron Parker upon completion. | R3-Admin (R. Parker) |
|  | Saturday 12/1/2012 | 9 AM – 1 PM | Backup System (R-MAN) - email sap-upgrade-core@mit.edu when complete | R3-Admin OIS/Enterprise Storage & Backup (Matt Anctil) |
|  |  | 1 PM – 9 PM | Execute concurrently: Generate DB Statistics (6 – 8 hours) Complete ABAP Loads (5 hours) - email sap-upgrade-core@mit.edu when complete | R3-Admin |
|  |  | 4 PM | Conference Call Check-in Core Team Check in at 4pm on Saturday (use conference call webex line) | Project Manager (Frank Quern) Project Sponsor (Bart Dahlstrom) Core Team |
|  |  | 9 PM (15 mins) | Restore WT Table (once loads are done) - email sap-upgrade-core@mit.edu when complete | R3-Admin |
|  |  | 9:00 PM – 10:00 PM | Transports Application – after the completion of the ABAP Loads - Email before transport application - Email after transport application is done | R3-Admin |
|  |  | 10 PM | Set Production Flag for Finance | R3-Admin (R. Parker) Admin Systems (K. Patel) (F. Quern) |
|  |  | 10:30 PM | Validation reports executed (trial balance reports) - R3-ADMIN notifies Clarel Auguste and Jo Lyn Whitlock via email, cc to Frank Quern as soon as the trial balance is available for review - R3-ADMIN unlock CAUGUSTE id in PS1 | R3-Admin (R. Parker) VPF Finance (Clarel Auguste) |
| Post Upgrade Schedule and Processes |  |  |  |  |
|  | Sunday 12/2/12 | 1:30am – 7:00am | On Line back up of PS1 (reestablishment of SRDF mirroring). | R3-Admin OIS/Enterprise Storage & Backup (Matt Anctil) |
|  | Sunday 12/2/12 | 8 – 9 am | TB Validation reports validated - Clarel notifies Frank Quern when validation of the trial balance report is complete. | VPF Finance (Clarel Auguste) |
|  |  | 8 – 10 am | R3-Admin Action Log - LSO SMARTFORM Validation Verify/correct the status of the function group /1BCDWB/SF00000029. If necessary, correct the PS1 function group by performing the following: (1) re-activate SMARTFORM ZLSO_PWB_COMPL_CONFIRMATION (via SMARTFORMS) (2) rebuild the function group /1BCDWB/SF00000029 navigation index and object list (via SE80) (3) regenerate the function group /1BCDWB/SF00000029 master program (via SE80) 2. +++ | R3-Admin (All) |
|  |  | 8 AM | Unlock web-services ids in Production JAD (Jim Dobrovic). | R3-Admin (G. Petrowsky) |
|  |  | 8 AM | Enable Gateways (SAPWeb/ESS); after verifying application connections. | Web-tech (JAD) |
|  |  | By 10 AM | Execute SAP report SEGREP to update segment length in the table EDISDEF | Tech Services (L. Kushkuley) |
|  |  | By 10 AM | EDI Step 1 Turn on the EDI “gourmet-1” server (start EDI) | Enterprise Appl. Admin (Olivia Wang) |
|  |  | By 10 AM | EDI (TLE) Step 2a Update SAP EDI Version number | Tech Services (E. Prudden) |
|  |  | 10 AM | EDI (TLE) Step 2b Load new BEN mappings (TLE) | Tech Services (L. Kushkuley) |
|  |  | 10:30 AM | EDI Step 3 Start EDI Jobs | Enterprise Appl. Admin (Olivia Wang) |
|  |  | By 11 AM (5 Minutes) | EDI Step 4 (last step) Schedule EDI Job - Unlock ids - Schedule EDI Job - Monitor first job released (on the ½ hr) | R3-Admin (G. Petrowsky) Tech Services (E. Prudden) (ZZLOGISBAT01) |
|  |  | By 10 AM | Email to ist-sap@mit.edu - List of transports applied and any related issues. - List of jobs shifted in PS1 during cutover | R3-Admin (R. Parker) |
|  |  | 10 AM – 12 PM | - ADMIN SYS Action Log users unlocked - ADMIN SYS executes the PS1 Action Log / Validations and email steps completed to rest of the team (sap-action-log-team@mit.edu) - ADMIN SYS Extended Team reviews transport logs | R3-Admin (G. Petrowsky) Action Log (Frank Quern) |
|  |  | By 12 PM | Unlock validators (testers) - email sap-upgrade-core@mit.edu when complete | R3-Admin (G. Petrowsky) |
|  |  | By 12 PM | Update voice message whether or not Data Validation is on schedule. Email to SAP-Validation-team@mit.edu that the validation is to start on schedule | Project Manager (Frank Quern) |
|  |  | 12 PM – 2 PM | PS1 Data Validations & Transaction processing listed in section 3 below performed by designated users; SAPWeb and Self Service will be available for validation; All servers will be available. | BPOs Admin Sys BAs |
|  |  | By 2 PM | Coordinators for each area should send email to sap-validation-team@mit.edu at the completion of validations indicating any issues encountered. | BPOs Admin Sys BAs R3-Admin |
|  |  | 2:30 PM | Conference Call Check-in Go/No Go conference call Sunday webex Line (Process owners, B. Dahlstrom, R. Parker, Wai-ming Li Admin Sys Team Leads) | Business Owners/ Test Coordinators Sponsor (B. Dahlstrom) Tech Services (W. Li) Admin Sys Team Leads IS&T Test Coordinators (K. Hann), (M. Donovan) |
|  |  | After conf call | Send e-mail to (sapbiz, sap-upgrade-core, ist-sap@mit.edu,warehouse@mit.edu, Elena@mit.edu,) indicating decisions/results. | Project Manager (Frank Quern) |
|  |  | 3PM – 5PM | Unlock users (Facilities, SMART) Unlock all users (R3-Admin notifies operations center at 3-1500). At end of unlock send message to web-tech@mit.edu, with a copy to ist-sap@mit.edu, update gateway messages. | R3-Admin (G. Petrowsky) |
|  |  | 5 PM Sunday (5 Minutes) | Enable Drop box - email sap-upgrade-core@mit.edu when complete | Tech Services (Wai-ming Li) |
|  |  | 8PM – 12AM | Data Warehouse Job Validation - Elena confirm job validation completion via email to sap-upgrade-core@mit.edu - Run extracts (10PM & 12AM) | DW (E. Zhitnikov) |
|  |  | 10 PM | Execute ProCard from Bank of America Feed - email sap-upgrade-core@mit.edu when complete | Tech Services (Eping Wei) |
|  | Monday 12/3/12 | 1:30 AM | On Line back up of PS1 (reestablishment of SRDF mirroring). | R3-Admin (R. Parker) OIS/Enterprise Storage & Backup (Matt Anctil) |
|  |  | By 6 AM | Update the 3-down web page & SAPgui message. | R3-Admin (R. Parker) Project Manager (Frank Quern) |
|  |  | By 6 AM | Remove SAP outage message on ECAT webpage. | VPF – John Doyle VPF – Jeff Rosa |
|  |  | By 6 AM | Remove SAPweb, ESS and EHS messages | Web Services (JAD) |
|  |  | By 6 AM | Validate SAPweb, ESS and EHS messages have been removed (verify in IE, Firefox, Safari) | Admin Systems (Team) |
|  |  | 6 AM | Email notification to the MIT Community stating the update is completed and Production is available. | Project Manager (Frank Quern) |
|  |  | 9 AM | Reinstate weekend MITSIS Grad Appointment Feed | Enterprise Appl. Admin (K. Mullins) |

- Communication and Contact Information

An IS&T telephone number (617-324-7468) will carry a message as to the status of the update beginning at noon on Friday 11/30 through noon on Monday 12/3.  The Project Manager will update this message as needed.  A conference call number (webex) is available for check-ins during the weekend and for the Go/No Go call at 4:00pm on Sunday.

Coordinators for the weekend’s activities are listed below.

  - IS&T is responsible for:

    - System update

    - Action log execution and coordination

    - User support during production validation

    - Communication via voice message, email and conference call as to whether the update is proceeding as scheduled

    - Resolve and escalate issues where needed

  - Business area validation coordinators are responsible for

    - Coordination of production validation

    - Notify PM immediately if any issues are found

    - Update PM when production validation is completed

Weekend Coordinators / Validation List / Escalation Team contact information:

| Area | Name – Location | Contact Telephone # | Email |
| --- | --- | --- | --- |
| A/P | John Larkin – NE49 | 617-253-2729 | jlarkin@mit.edu |
| VPF | Jo Lyn Whitlock – NE49 | 617-253-2771 | jolyn@mit.edu |
| VPF | Clarel Auguste – NE49 | 617-253-8488 | cauguste@mit.edu |
| VPF | Yan Jiang – NE49 | 617-253-2764 | yanjiang@mit.edu |
| VPF – Travel | Kara Sechrist – Off Campus | Contact PM | sechrist@mit.edu |
| Dept. of Facilities | Lisa St. Croix – Off Campus | Contact PM | lstcroix@plant.mit.edu |
| Dept. of Facilities | Steve Fosher – Off Campus | Contact PM | snfosh22@mit.edu |
| EHS | Laurie Veal – Off Campus | Contact PM | veal@mit.edu |
| EHS | Lee Collier – W92 | 617-324-5957 | lcollier@mit.edu |
| HR/Benefits | Michael Peretti – Off Campus | Contact PM | mperetti@mit.edu |
| HR/Benefits | Diane Johnston – Off Campus | Contact PM | djohnsto@mit.edu |
| HR/Benefits | Riley Hart – Off Campus | Contact PM | rileyh@mit.edu |
| EL | Melissa Kavlakli – Off Campus | Contact PM | mjpotter@mit.edu |
| EL | Jane White – Off Campus | Contact PM | jwc@mit.edu |
| Procurement | Scott Ball – Off Campus | Contact PM | sc16196@mit.edu |
| Procurement | David Petricone – Off Campus | Contact PM | petricon@mit.edu |
| Procurement | Kimberly Harmon – Off Campus | Contact PM | kharmon@mit.edu |
| VPF – HR/Payroll | Leslie Wright – NE49 | 617-253-7715 | lesliem@mit.edu |
| VPF – HR/Payroll | Tricia Sullivan-Mullen – NE49 | 617-253-4809 | tsmullen@mit.edu (will user batch id ZZHRLLFEED01 as part of validations) |
| IS&T – QA | Don Flanders – W92 | Refer to online directory |  |
| IS&T - QA | Jack Kelliher | Contact PM | jackkell@mit.edu |
| IS&T - R3-Admin | George Petrowsky – W92 | Refer to online directory | georgep@mit.edu |
| IS&T - R3-Admin | Ron Parker – W92 | Refer to online directory | rep@mit.edu |
| IS&T - ERP System Manager | Bart Dahlstrom – W92 | Refer to online directory | bartd@mit.edu |
| IS&T - FI / EHS team lead | Siobhan Cunningham – W92 | Refer to online directory | snc@mit.edu |
| IS&T – Logistics | Ken LeVie – W92 | Refer to online directory | levie@mit.edu |
| IS&T - FI Team | Bob Casey – NE49 | Refer to online directory | rcasey@mit.edu |
| IS&T - FI Team | Keyur Patel | Refer to online directory | keyurpb@mit.edu |
| IS&T – EHS/Parking | Lee Collier – W92 | Refer to online directory | lcollier@mit.edu |
| IS&T – PM/VPIS Parking | Rita Zhovnirovsky | Refer to online directory | mzhovnir@mit.edu |
| IS&T – PM | Jim Fragala | Refer to online directory |  |
| IS&T – Log/FIN/EHS Team Coordinator | Kristen Hann – W92 | Refer to online directory | khann@mit.edu |
| IS&T – Web Services (IDD) | James Dobrovic – W92 | Refer to online directory | jad@mit.edu |
| IS&T – Tech Services | Wai-ming Li – N42 | Refer to online directory | waiming@mit.eu |
| IS&T – OIS | Olivia Wang – W91 | Refer to online directory | owing@mit.edu |
| IS&T - Data warehouse | Elena Zhitnikov – W92 | Refer to online directory | elena@mit.edu |
| IS&T - Data warehouse | Svetlana Lemeshov – W92 | Refer to online directory | lemeshov@mit.edu |
| IS&T - HR team lead | Frank Quern – W92 | Refer to online directory | fquern@mit.edu |
| IS&T – HR/Payroll Coordinator | Mary Donovan – W92 | Refer to online directory | donovan@mit.edu |
| IS&T – OIS | Matt Anctil | 617-909-7889 | manctil@mit.edu |
| IS&T – OIS | Dave Kalenderian | 617-549-6991 | davek@mit.edu |
| IS&T – OIS | Garry Zacheiss | 617-216-1541 | zacheiss@mit.edu |
| IS&T - OIS | Server Operations | 617-775-3302 | Team Line |
| Project Manager | Frank Quern | 617-452-4512 | fquern@mit.edu |

Business process owners / weekend coordinators are highlighted in the above list.

Monday Morning Coverage (12/3/2012)

| Area | Name | Location | Time | Email |
| --- | --- | --- | --- | --- |
| FLE | Lee Collier | W92 | 7:30am | lcollier@mit.edu |
| FLE |  | Off Campus | 7:30am |  |
| HRP | Lisa Jones-Brinkley | W92 | 7:30am | ljonesbr@mit.edu |
| HRP | Cindy DeSimone | W92 | 7:30am | cindyo@mit.edu |
| HRP | Desiree Roberts | Off Campus | 7:30am | robertsd@mit.edu |
| R3-Admin | R3 Team | W92 | 7:30am | r3-admin@mit.edu |
| Tech Services | Elda Prudden | W92 | 7:30am | eprudden@mit.edu |
| Tech Services | Mark Prudden | W92 | 7:30am | mprudden@mit.edu |
| Tech Services | Carolyn Fuller | Off Campus | 7:30am | fuller@mit.edu |
| SP Project | Frank Quern | W92 | 7:30am | fquern@mit.edu |
| FLE | Admin Systems Team | W92 | 8:00am + | administrative-systems@mit.edu |
| HRP | Admin Systems Team | W92 | 8:00am + | hrpay-sppt@mit.edu |

Production Validation Information

Production Validation will occur in NE49, W92, NE125, N52 and remotely.  Validation is scheduled to start at 2:00 PM, however, please check the message line (617-324-7468) before coming into the office or starting to test remotely.  The message will be updated by 11:30 AM if there are potential delays and by 12:00 PM if testing can start.  Please forward all validation test results, positive or negative, to the email list sap-validation-team@mit.edu as soon as your validation steps are complete.

Frank Quern will coordinate between IS&T and Business Process Owners (VPF, HR, Facilities, Payroll, EHS), on Sunday December 2nd.  Frank will be responsible for the following activities:

  - Coordinating telephone message, emails with changes / updates

  - Escalating issues

  - Communicating validation results

  - Contacting R3-Admin at the conclusion of the validation to continue the system preparation for Monday

| Transaction Information | Description | Person(s) Responsible |
| --- | --- | --- |
| Trial Balance Report validation occurs first. Ron Parker will email Clarel Auguste, Jo Lyn Whitlock, and Frank Quern when the reports have finished processing. Clarel will notify Frank via telephone/email when validation is complete. Frank will follow up with an email to the following: Sap-action-log-team@mit.edu, sap-upgrade-core@mit.edu |  |  |
| Report Testing | Run a trial balance | R3-Admin/Clarel Auguste |
| IS&T executes the PS1 section of the action log second. Each IS&T team member will notify the action log team when his/her steps are complete. Frank will follow up with an email to the following lists when action log is complete. Sap-validation-team@mit.edu, sap-upgrade-core@mit.edu |  |  |
| IS&T Action Log |  | Admin Systems/Tech Services |

| Transaction | Description | Tester name/ID |
| --- | --- | --- |
| The noted individuals will test/validate the following transactions. Frank will be notified by test coordinator for each area when testing for the area is complete. Frank will follow up with an email to the following lists: sap-upgrade-core@mit.edu, sap-action-log-team@mit.edu, sap-validation-team@mit.edu; ist-sap@mit.edu |  |  |
| Transaction | Description | Tester name/ID |
| ME21N | Create PO from Req | Procurement Testing Team |
| ME22N | Change order | Procurement Testing Team David Petricone |
| ME52N | Change Req | Procurement Testing Team |
| SAPWeb | Enter Req | Procurement Testing Team |
| SAPWeb | View Req | Procurement Testing Team Procurement Testing Team |
| SAPWeb | View PO | Procurement Testing Team |
| ME22N | Add Attachment | Procurement Testing Team |
| ME23N | Display Attachment | Procurement Testing Team |
| ME21N/ME22N | User Exits (example: Block Misc. Material Group 2150) | Procurement Testing Team |
| SAPWeb | Create Ecat Order | Procurement Testing Team |
| OAWD | IXOS Workflow | John Larkin |
|  | Credit card transactions | Kim Harmon |
| MIRO | PO Invoice Post | John Larkin |
| F-58 | Create Fast Check | John Larkin |
| F-65 | Park Document | Yan Jiang |
| FBV2 | Change Parked Document | Yan Jiang |
| FBV3 | Display Parked Document | Yan Jiang |
| ZJVV | Execute JV Parked, Documents Report (Compare with Friday version) | Yan Jiang |
| ZJVP | Execute JV Posted, Documents Report | Yan Jiang |
| SO01 | JV Inbox (Compare with Friday version) | Yan Jiang |
| F-65 | Create JV via SAPWeb (Park Document) | Yan Jiang |
| SO01 | Reject Parked Document | Yan Jiang |
| FBV2 | Resubmit JV via SAPWeb (Change Parked Document) | Yan Jiang |
| NA | Confirm email notifications | Yan Jiang |
| ZJVA | Spreadsheet Upload | Yan Jiang |
| ZSTM | Summary Statement | Clarel Auguste |
| ZDTR | Detail Transaction Report | Clarel Auguste |
| IW31 | (PM) Work queues | Lisa St. Croix |
| IW32 | (PM) Work queues | Lisa St. Croix |
| ZIW38 | (PM) Work queues | Lisa St. Croix |
| Web Forms | (PM) Work queues | Lisa St. Croix |
|  | Inventory Management | Steve Fosher |
| EHS SAP Web PI Space Registration Roomset Create | Create a roomset (header) | Laurie Veal (PC/Mac) |
| EHS SAP Web PI Space Registration Roomset Change | Edit, display a roomset (header) | Laurie Veal (PC/Mac) |
| EHS SAP Web PI Space Registration Room | Assign a room to a roomset. Maintain room status, inspection status, and de-commission status of a room. Add / maintain contact information for a room. Identify hazards and safety equipment in a room. Print a green card. | Laurie Veal (PC/Mac) |
| EHS SAP Web PI Space Registration SARA | Add, delete substance list per room Maintain substance quantity per room | Laurie Veal (PC/Mac) |
| EHS SAP Web Supervisor’s Injury Report | Supervisor’s Injury Report | Laurie Veal (PC) Lee Collier (Mac) |
| Travel | Concur | Kara Sechrist |
| HR – Payroll Transactions to Validate |  |  |
| SAPGui Tests | PA30, PA40, ZPYDEDUCT, PT60, ZPYCDU, ZPYR_APPT_MESSAGES, ZPY_MITSIS_LOG, ZPY_PAY_VAL_RPT, and PT50 (refer to HRP plan on the project wiki), validate LL feed | Leslie Wright |
| SAPWeb Tests | eDACCA, eSDS, SRS vacation tracker in SAPweb and tax withholding and direct deposit via ESS. | Leslie Wright |
| HR Transactions to Validate |  |  |
| SAP GUI/ESS/EL | Refer to HRP plan on the project wiki | Diane Johnston; Riley Hart for issues. |
| Sunday 2:30 PM Check-in | If go, coordinate steps to continue. If no-go, meet to discuss next steps – roll back options with escalation team | BPO, IS&T |

- Escalation Plan

If an issue is found, please contact Frank Quern AND the Escalation Support Team person for your area immediately.  The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall.  If the problem can not be resolved quickly, the Business Owners will provide details related to the impact of the issue on the process and users. Bart will consider impacts for all areas as a whole and determine whether to go ahead with the update or roll back the system.

All people listed below must ensure that they can be reached on Sunday December 2nd.

Functional Malfunction(s)

Jo Lyn Whitlock	Business Process Owner (VPF GL Operations)

Mike Peretti	Business Process Owner (HR) / Weekend Coordinator

Melissa Kavlakli 		Business Process Owner (EL) / Weekend Coordinator

Leslie Wright	Business Process Owner (Payroll) / Weekend Coordinator

Lisa St. Croix	Business Process Owner (Facilities) / Weekend Coordinator

Laurie Veal	Business Process Owner (EH&S) / Weekend Coordinator

Scott Ball	Business Process Owner (Procurement) / Weekend Coordinator

John Larkin	Business Process Owner (Accounts Payable) / Weekend Coordinator

Catastrophic Malfunction

Bart Dahlstrom	Project Sponsor IS&T / ADMIN SYS ERP Systems Manager

Steering Committee (+)

- Bill VanSchalkwyk 	Managing Director, EHS Programs

- Gerry O'Toole 		VPF Director of Financial Operations

- Tricia Sullivan-Mullen	VPF Director of Financial Systems and Data

- Basil Stewart 		Controller

- Marty Dugal 		Assistant Director, Facilities Operations

- Mary Weisse 		Associate Director, IS&T Data Management

- Steve Buckley 		Associate Director, IS&T Sys Engineering

- Kathleen Flynn 		HR Manager of Operations

- Frank Quern		SP Project Manager

Escalation Support Team

Ron Parker	Basis / Technical Support

George Petrowsky	R3 Authorizations

Elena Zhitnikov		Data Warehouse Team

Frank Quern	Support Pack PM

Siobhan Cunningham	FIN/LOG/EH&S Team Lead

Jim Dobrovic	Web Services

Wai-ming Li	Tech Services

Kristen Hann	FI/LOG/EHS Team Coordinator

Mary Donovan	HR/Payroll/EL Team Coordinator

Mailing Lists

The following email lists have been maintained for this project.

| sap-action-log-team@mit.edu | All persons having a task on the ADMIN SYS action log plus Support Pack Core Team members |
| --- | --- |
| sap-validation-team@mit.edu | All members of validation team plus all members of escalation team |
| sap-upgrade-core@mit.edu | Support Pack Core Team members |
| sap-upgrade-steering-committee@mit.edu | Steering Committee members |
| ist-sap@mit.edu | All members of the IS&T Support Pack Extended Team |

COMMUNITY MESSAGES TO BE SENT OR POSTED

To: sap-prd-notice@mit.edu; aos@mit.edu; itpartners@mit.edu; warehouse@mit.edu

Cc: sapbiz@mit.edu; is&t@mit.edu

Subject: Planned SAP Maintenance Outage this Weekend (12/1-12/2)

To: All SAP USERS,

The SAP production environment will be unavailable this weekend beginning at 5:00pm Friday, November 30th, 2012 and ending by 6:00am Monday, December 3rd, 2012 for scheduled system maintenance. During this outage SAP’s Year End Support and Enhancement Packs will be installed bringing MIT’s SAP implementation up to the most current support pack level required for 2012 AP and HR/Payroll system compliance.

SAP, ECAT, and all SAPweb activity, including Employee Self Service (ESS), EL, time sheet entry/approval, requisitioning, journal vouchers, and credit card verification will be inaccessible during this maintenance period.

The Data Warehouse will be available throughout the weekend with the data from SAP as of the end of day, Thursday, November 29th. On Monday, December 3rd, the Data Warehouse will include the data entered between Friday, November 30th and Sunday, December 2nd.

In addition to this communication, reminder notices will be posted as banner messages for related Web services as well as log-on messages on SAPGUI. Visit   http://3down.mit.edu/ for updated information during the outage. If you have any questions about this system outage or the maintenance being performed, feel free to contact me, Frank Quern at my email address, fquern@mit.edu.

Thank you for your patience and understanding during this scheduled system maintenance period.

Kind regards,

Frank Quern
Senior IT Manager – SP Project Manager
Information Services & Technology (IS&T)
Massachusetts Institute of Technology
77 Massachusetts Ave., W92-210
Cambridge, MA 02139-4307
Phone: 617-452-4512

SAPWeb and SAPWebSS page message:

Important Notice:
All SAPweb and SAPweb Self Service applications will be unavailable from 5:00pm Friday, November 30, 2012 until 6:00am Monday, December 3, 2012 while planned year-end SAP system maintenance is performed. Please visit http://3down.mit.edu/ for more frequently updated information during the outage.

Here is the message we plan to append to SAPweb/ss banners during the SAP support pack outage. (with the links spelled out) :

The Supervisor Injury Report application on the EHS SAPWeb gateway page is offline. 
If an injury occurs during this time, please follow the instructions on the

http://ehs.mit.edu/site/content/sap-system-outage-injury-reporting page
for filling out an electronic copy of the Supervisor's Injury Report  
and e-mail a copy to the OSHA recordkeeper, <a href="mailto:sma@mit.edu">sma@mit.edu</a>.