This document contains the following items for use during go live weekend:

- SAP Portal Upgrade Task List

- Communication and Contact information

  - At the conclusion of each task in section 1 below send email to sap-upgrade-core@mit.edu indicating completion of task

  - Conference Call Line (if needed): Webex

    - Call-in number: 1-617-324-0000

    - Saturday Access code: 644 183 460

  - Contacts

- Validation Information

- Escalation Plan

- SAP Portal Upgrade Task List:

| Task ID | Date | Time | Task | Assigned to | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | 4/1/2013 | by noon | Request Outage Message | Frank Quern | complete |
| 2 | 4/1/2013 | by EOD | Post Outage Message on SAPweb/SAPwebSS | ops | complete |
| 3 | 4/3/2013 | by EOD | Setup Webex Audio Meeting | Frank Quern | complete |
| 4 | 4/3/2013 | 1:00pm | Cut-over meeting | Team | complete |
| 5 | 4/3/2013 | by EOD | Notify EH&S & Help Desk about outage | Melissa Kavlakli | complete |
| 6 | 4/4/2013 | by EOD | Distribute cut-over plan | Frank Quern | complete |
| 7 | 4/5/2013 | by EOD | Move all support pack files to EPS/in directory | Qian Kang | complete |
| 8 | 4/6/2013 | 7:00am | Add MIT Learning Center Gateway access redirection & validate | Kevin Mullins | complete |
| 9 | 4/6/2013 | 7:15am | Import OSS note via transport: SF3K903890 - R3ADM* OSS 1808171 - Corrections to unified rendering to SAP | Rich Katkowski | complete |
| 10 | 4/6/2013 | 8:00am | Confirm successful backup from the night before | Qian Kang | complete |
| 11 | 4/6/2013 | 8:15am | Restart SAP Portal to cleanup resources (15 min) | Qian Kang | complete |
| 12 | 4/6/2013 | 8:30am | Run upgrade program JSPM (3 hours) | Qian Kang | complete |
| 13 | 4/6/2013 | 11:30am | Restart SAP Portal to clear resources | Qian Kang | complete |
| 14 | 4/6/2013 | 12:00pm | Manually change EHS Report page to include “Chrome” as “supported agent” | Qian Kang | complete |
| 15 | 4/6/2013 | 12:00pm | R3-admin validations (system related) | Qian Kang | complete |
| 16 | 4/6/2013 | 12:30pm | Web-based course validation (1/2 hour) | Qian Kang | complete |
| 17 | 4/6/2013 | 1:00pm | IS&T Validation | Mary Donovan Desiree Roberts | complete |
| 18 | 4/6/2013 | 1:00pm | Business Validation | Melissa Kavlakli Jane White | complete |
| 19 | 4/6/2013 | 2:00pm | Check in call | Team | complete |
| 20 | 4/6/2013 | 2:00pm | Remove MIT Learning Center Gateway access redirection & validate | Kevin Mullins | complete |
| 21 | 4/6/2013 | 2:00pm | Remove Outage Message on SAPweb/SAPwebSS | Kevin Mullins | complete |

- Communication and Contact Information

The sap-upgrade-core@mit.edu email address will be used to communicate the completion of tasks throughout the cut-over. A conference call number (webex – see top of this document) is available for check-ins or issue conversation should the need arise during the weekend.

Contact information for the weekend’s activities are listed below.

  - IS&T is responsible for:

    - System update

    - Action log execution and coordination

    - Limited production validation

    - Communication via email and conference call (if needed) as to whether the update is proceeding as scheduled

    - Resolve and escalate issues where needed

  - Business is responsible for:

    - Production validation

    - Notifying Support team of any issues encountered

    - Confirmation that it is ok to open the system to the community

Weekend Team contact information:

| Name | Department | email | business | mobile | on/off campus | alt email |
| --- | --- | --- | --- | --- | --- | --- |
| Frank Quern | Admin Systems | fquern@mit.edu | 617-452-4512 | 617-694-7957 | on |  |
| Ron Parker | R3-Administration | rep@mit.edu | (617) 253-1339 | Contact PM | off | r3-admin@mit.edu |
| Qian Kang | R3-Administration | qiankang@mit.edu | (617) 324-9001 | Contact PM | on | r3-admin@mit.edu |
| Rich Katkowski | R3-Administration | rkatkows@mit.edu | (617) 253-8597 | n/a | on | r3-admin@mit.edu |
| Elda Prudden | Technical Services | eprudden@mit.edu | 617-253-5153 | Contact PM | off |  |
| John Tuttle | Technical Services | jrtuttle@mit.edu | (617) 324-0097 | Contact PM | off |  |
| Mary Donovan | Admin Systems | donovan@mit.edu | (617) 258-0453 | Contact PM | on |  |
| Desiree Roberts | Admin Systems | robertsd@mit.edu | (617) 324-5961 | Contact PM | on |  |
| Jane White | MIT Learning | jfw@mit.edu | 617-258-0456 | Contact PM | off |  |
| Melissa Kavlaki | MIT Learning | mjpotter@mit.edu | 617-253-4279 | Contact PM | off |  |
| Kevin Mullins | OPS | kmullins@mit.edu | 617-324-8311 | Contact PM | off | ops@mit.edu |

- Production Validation Information

Production Validation will occur remotely and on site by Admin Systems personnel and Business personnel.  Validation is scheduled to start at 1:00pm on Saturday 4/6/2013 but validators should be available and online by 11:00am should the update progress sooner than expected. The Project Manager (Frank Quern) will send out an email notification indicating that validations can begin.  Please forward all validation test results, positive or negative, to the email list as soon as your validation steps are complete.

The following direct link to the production portal should be used during the validation window:

https://idp.mit.edu/idp/profile/Shibboleth/SSO?shire=https://sbsjp601.mit.edu:56801/saml/receiver&target=https://sbsjp601.mit.edu:56801/irj/portal&providerId=https://sbsjp601.mit.edu:56801/irj/portal

- Escalation Plan

If an issue is found, please contact the email list immediately.  The support team will try to identify the cause of the problem, work on a resolution as well as analyze the impact of the issue overall.  If the problem cannot be resolved quickly, the escalation team will consider impacts for all areas as a whole and determine whether to go ahead with the update or seek approval for a roll back of the system.

All escalation team members listed below must ensure that they can be reached on Saturday 4/6.

Escalation Support Team

Ron Parker	Basis/Technical Support

Frank Quern	Support Pack PM

Qian Kang	Basis/Technical Support

Mary Donovan	Sr. Business Systems Analyst

Desiree Roberts	Sr. Business Systems Analyst

John Tuttle	Sr. ABAP Developer

Catastrophic Malfunction

Bart Dahlstrom		Associate Director, Admin Systems

Mary Weisse		Associate Director, Data Management

Mark Silis		Associate Director, Operations & Infrastructure