## Slide 1
September 24, 2012
2013 Year End Support Pack Project
Steering Committee
Kickoff

## Slide 2: Agenda
Background
Project Organization
Project wiki
Project Risks
Important Dates
Next Steps

## Slide 3: Background
Support Packs
  We all know what they are, periodic releases of system changes and corrections by SAP.
  Rather than apply these support packs when released we collect the Support Packs for a single installation at year end in an effort to minimize business interruption.
  The timing of our process is driven by SAP’s release of its year end support pack, typically in mid-October, which contains the base level necessary for the successful execution of SAP’s delivered year end tax reporting functionality (AP and Payroll) and stages the system for regulatory changes for the upcoming calendar year.

## Slide 4: Background
What are the benefits of applying Support Packs and the process itself?
  MIT will be able to successfully file its year end tax returns (W2s, 1099s, 1042s).
  MIT will be able to apply future regulatory changes with minimal interruption.
  It is an opportunity to keep all functional areas current.
  It adheres to SAP’s support recommendations.
  It provides a solid organizational exercise in testing.
  Ensures up to date test scripts for chosen transaction.

## Slide 5: Project Organization
Planning
Communication
Support Pack Technical Application
Testing
Go-live

## Slide 6: Project Organization
Communication
  Project Kickoff Meetings
    Steering Committee – 9/13/2013
    IS&T – Core Team & Extended Team – week of 09/16/2013
    SAPbiz – 09/25/2013
  Monthly Meetings
    Steering Committee
    SAPbiz
  Weekly Meetings
    Core Team
    Test Coordinators - Business & IS&T
  Email lists
  Project wiki
    https://wikis.mit.edu/confluence/display/sapscripts/2013+Year+End+SAP+Support+Pack+Project
    Contains project plans, test plans, general information, etc …; great source – use it!
    Don’t have access please contact Frank Quern (fquern@mit.edu)

## Slide 7: Roles & Responsibilities
Lets jump to the project wiki …
to look at the Project Scope
to look at the Team Roles & Responsibilities
to look at the Technical Landscape
to look at the Project Transport Management Process
to look at the Project Testing Plan
to look at the Schedule
    https://wikis.mit.edu/confluence/display/sapscripts/2013+Year+End+SAP+Support+Pack+Project

## Slide 8: Other Non-SP Projects
Other non-support pack project work (during SP project timeline)
  Facilities System Modernization
  Atlas – JAVA application theme changes
  SAPweb Help Migration to KB
    Other activities
    …
    …

## Slide 9: Project Risks
Identified Risks
  QA Upgrade
    Tentatively scheduled for next week
  Two Phase Testing Approach
    Requires tight coordination and resource availability between the Business & IS&T
    But … we have three years experience with this approach
  Resource availability for the project (both Business & IS&T)
  Delay of implementation of pre-Support Pack Projects
    OE (scheduled for October)
  Impacts from other requested updates
    Atlas Java Application
    PM Modernization Project
    SAPweb Migration to KB

## Slide 10: Important Dates
Now - October - Plan, convert/create/update test scripts in QC, move pending support & project work into production
10/10/2013 – SAP release of year end base level support pack
10/21/2013 - End of day production snapshot to be used to refresh test environments
10/19/2013 - Development Freeze begins
10/31/2013 - Last date to implement support & enhancement changes until freeze ends on 12/5/2012
10/25/2013 - 11/1/2013 Unit test
11/4/2013 - 12/1/2013 System Integration Test
12/7/2013 - 12/8/2013 Go-live weekend!
12/11/2013 - Development Freeze ends

## Slide 11: Next Steps
  Finish System changes currently in the pipeline
  Unit test Spreadsheet (google docs)
  Test Planning
  System preparation

## Slide 12: Questions?
Any additional questions? Please contact:
Frank Quern Bart Dahlstrom
X2-4512 x3-9605
fquern@mit.edu bartd@mit.edu
OR
Your SAP testing team coordinator:
HR-Payroll: Desiree Roberts
Financial-Logistics-EHS: Ken Le Vie